## Material Master AJ
NO. OF PROJECTS | BOM Received date | TASK | PROJECT# | PROJECT DESCRIPTION | WO# | CATALOG | Item # | PR # | PR REQUESTED DATE | PR APPROVED DATE | PR Cur. Status | PR Line # | Unit of Issue | Order Qty. | Unit Cost | Ext. Cost (Line Cost) | RFQ # | RFQ Status | RFQ Status Date | RFQ Due Date | PO # | PO Line # | PO Award Date | PO Status | PO Status Date | Buyer | Vendor | Vendor Date (EDD) | Delivery Status | Delivery Date | Recv. Qty | Remarks | Color Code list | table | month | year
1 | 2022-09-10 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0097 | TUBE, METALLIC, REFRIGERATION, COPPER, 3/8 INCH X 50 FEET | 17049 | 2022-09-10 | 2022-09-21 |  | 14 | RO | 20 | [6 empty] | KW1-5620 | 13 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 20 |  | AJ | AJ table | September | 2022
1 | 2022-09-10 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0110 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 17049 | 2022-09-10 | 2022-09-21 |  | 11 | EA | 16 | [6 empty] | KW1-5620 | 11 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 16 |  | AJ | AJ table | September | 2022
1 | 2022-09-10 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 17049 | 2022-09-10 | 2022-09-21 |  | 10 | BX | 5 | [6 empty] | KW1-5620 | 10 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 5 |  | AJ | AJ table | September | 2022
1 | 2022-09-10 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5305-60-V00-0148 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 17049 | 2022-09-10 | 2022-09-21 |  | 17 | BX | 80 | [6 empty] | KW1-5620 | 17 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 80 |  | AJ | AJ table | September | 2022
1 | 2022-09-10 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5530-00-618-8073 | PLYWOOD, MAPLE, PUREBOND, 3/4 IN x 4 FT x 8 FT | 17049 | 2022-09-10 | 2022-09-21 |  | 13 | SH | 30 | [6 empty] | KW1-5620 | 13 | [5 empty] | 2022-11-17 | COMP | 2022-10-22 | 30 |  | AJ | AJ table | September | 2022
1 | 2022-09-10 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0048 | DRYWALL SHEET, (GYPSUM BOARD), 4 X 8 FEET X 1/2 INCH | 17044 | 2022-09-10 | 2022-09-15 |  | 2 | EA | 50 | [6 empty] | KW1-5212 | 5 | [5 empty] | 2022-10-05 | comp | 2022-09-27 | 50 |  | AJ | AJ table | September | 2022
1 | 2022-09-10 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 7210-60-V00-0059 | FLOOR COVERING, VINYL RESIN, 3 MM X 40 FEET | 17049 | 2022-09-10 | 2022-09-21 |  | 19 | RO | 5 | [6 empty] | KW1-5620 | 19 | [5 empty] | 2022-11-17 |  |  |  |  | AJ | AJ table | September | 2022
1 | 2022-09-11 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5940-60-V00-0083 | LUG, TERMINAL, FORK, INSULATED, YELLOW, 12-10 AWG | 17052 | 2022-09-11 | 2022-09-17 |  | 2 | PG | 25 | [6 empty] | KW1-5267 | 3 | [5 empty] | 2022-10-24 | COMP | 2022-10-03 | 25 |  | AJ | AJ table | September | 2022
1 | 2022-09-12 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4130-60-V00-0137 | MOUNTING BASE, AIR-CONDITIONER, POLYPROPYLENE, IVORY, 17 X 3 X 5.12 INCHES | 17045 | 2022-09-12 | 2022-09-19 |  | 1 | PG | 16 | [6 empty] | KW1-5181 | 1 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 16 |  | AJ | AJ table | September | 2022
1 | 2022-09-12 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8030-60-V00-0053 | FOAM, CONSTRUCTION, CREAM, 700ML | 17042 | 2022-09-12 | 2022-09-20 |  | 24 | EA | 4 | [6 empty] | KWA-5530 | 24 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0098 | TUBE, METALLIC, REFRIGERATION, COPPER, 5/8 INCH X 50 FEET | 17046 | 2022-09-19 | 2022-09-24 |  | 1 | RO | 20 | [6 empty] | KW1-5212 | 1 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 20 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0288 | COUPLING, DRAINAGE PIPE, POLYPROPYLENE, ORANGE, 4.33 INCHES | 17046 | 2022-09-19 | 2022-09-24 |  | 2 | EA | 8 | [6 empty] | KW1-5212 | 8 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 8 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0288 | COUPLING, DRAINAGE PIPE, POLYPROPYLENE, ORANGE, 4.33 INCHES | 17046 | 2022-09-19 | 2022-09-24 |  | 3 | EA | 8 | [6 empty] | KW1-5212 | 13 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 8 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0304 | COUPLING, DRAINAGE PIPE, (PAN CONNECTOR), POLYPROPYLENE, WHITE, 4 INCHES X 110 MM | 17046 | 2022-09-19 | 2022-09-24 |  | 5 | EA | 2 | [6 empty] | KW1-5212 | 5 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0304 | COUPLING, DRAINAGE PIPE, (PAN CONNECTOR), POLYPROPYLENE, WHITE, 4 INCHES X 110 MM | 17046 | 2022-09-19 | 2022-09-24 |  | 4 | EA | 4 | [6 empty] | KW1-5212 | 4 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0390 | TEE-Y, DRAINAGE PIPE, PVC-U, 45 DEGREE, TERRACOTTA, 110 MILLIMETER | 17046 | 2022-09-19 | 2022-09-24 |  | 6 | EA | 4 | [6 empty] | KW1-5212 | 3 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 5 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0390 | TEE-Y, DRAINAGE PIPE, PVC-U, 45 DEGREE, TERRACOTTA, 110 MILLIMETER | 17046 | 2022-09-19 | 2022-09-24 |  | 8 | EA | 5 | [6 empty] | KW1-5212 | 9 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 5 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0390 | TEE-Y, DRAINAGE PIPE, PVC-U, 45 DEGREE, TERRACOTTA, 110 MILLIMETER | 17046 | 2022-09-19 | 2022-09-24 |  | 7 | EA | 5 | [6 empty] | KW1-5212 | 14 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 5 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0830 | COUPLING, UPVC, SCH-40, GRAY, 2 INCHES | 17046 | 2022-09-19 | 2022-09-24 |  | 9 | EA | 4 | [6 empty] | KW1-5212 | 9 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0830 | COUPLING, UPVC, SCH-40, GRAY, 2 INCHES | 17046 | 2022-09-19 | 2022-09-24 |  | 10 | EA | 4 | [6 empty] | KW1-5212 | 10 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0834 | COUPLING, CPVC, SCH-40, TAN, 25 MM | 17046 | 2022-09-19 | 2022-09-24 |  | 11 | EA | 4 | [6 empty] | KW1-5212 | 11 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0834 | COUPLING, CPVC, SCH-40, TAN, 25 MM | 17046 | 2022-09-19 | 2022-09-24 |  | 13 | EA | 8 | [6 empty] | KW1-5212 | 12 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 8 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0834 | COUPLING, CPVC, SCH-40, TAN, 25 MM | 17046 | 2022-09-19 | 2022-09-24 |  | 12 | EA | 8 | [6 empty] | KW1-5212 | 13 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 8 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0927 | TEE, PIPE, SOCKET X SOCKET X FIPT, SCH-80, CPVC, OFF-WHITE, 25 MM X 1/2 INCH | 17046 | 2022-09-19 | 2022-09-24 |  | 14 | EA | 10 | [6 empty] | KW1-5212 | 14 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 10 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0927 | TEE, PIPE, SOCKET X SOCKET X FIPT, SCH-80, CPVC, OFF-WHITE, 25 MM X 1/2 INCH | 17046 | 2022-09-19 | 2022-09-24 |  | 15 | EA | 10 | [6 empty] | KW1-5212 | 15 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 10 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0973 | TEE, PIPE, SEWER AND DRAIN FITTINGS, PVC, SCH-80, ORANGE, 110 MM | 17046 | 2022-09-19 | 2022-09-24 |  | 16 | EA | 2 | [6 empty] | KW1-5212 | 16 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4820-60-V00-0234 | VALVE, BALL, BRASS, 1 INCH | 17046 | 2022-09-19 | 2022-09-24 |  | 17 | EA | 1 | [6 empty] | KW1-5212 | 17 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5340-60-V00-0449 | ANCHOR, KIT, CONICAL, PLASTIC, #10 X 1 X 1/4 INCH | 17046 | 2022-09-19 | 2022-09-24 |  | 18 | KT | 5 | [6 empty] | KW1-5212 | 18 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 5 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0042 | TILE, CEILING, PVC, WHITE, 2 X 2 FEET | 17046 | 2022-09-19 | 2022-09-24 |  | 19 | BX | 1 | [6 empty] | KW1-5212 | 19 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 17046 | 2022-09-19 | 2022-09-24 |  | 20 | EA | 20 | [6 empty] | KW1-5212 | 20 | [5 empty] | 2022-09-24 | COMP | 2022-10-01 | 20 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5930-60-V00-0243 | LIGHT-SWITCH, METAL, 2 WAY, 1 GANG, 250V, 10A | 17041 | 2022-09-21 | 2022-09-30 |  | 10 | EA | 19 | [6 empty] | KW1-5358 | 10 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 19 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4130-60-V00-0288 | TAPE, WRAP, INSULATION, 3 INCHES X 150 FEET | 17041 | 2022-09-21 | 2022-09-30 |  | 1 | RO | 31 | [6 empty] | KW1-5358 | 1 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 31 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4320-60-V00-0078 | PUMP, CENTRIFUGAL, WATER, 2740 RPM, 50 HZ | 17041 | 2022-09-21 | 2022-09-24 |  | 2 | EA | 1 | [6 empty] | KW1-5358 | 2 | [5 empty] | 2022-11-25 | COMP | 2022-10-11 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4510-60-V00-0049 | TRAP, BOTTLE, ADJUSTABLE INLET, WHITE, 1-1/2 INCHES | 17051 | 2022-09-21 | 2022-09-24 |  | 1 | EA | 1 | [6 empty] | KW1-5212 | 6 | [5 empty] | 2022-10-22 | COMP | 2022-10-01 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4510-60-V00-0102 | COVER, DRAIN, w/HOLE, SQUARE, METAL, 6 X 6 INCHES | 17049 | 2022-09-21 | 2022-09-24 |  | 6 | EA | 2 | [6 empty] | KW1-5620 | 6 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4510-60-V00-0102 | COVER, DRAIN, w/HOLE, SQUARE, METAL, 6 X 6 INCHES | 17049 | 2022-09-21 | 2022-09-24 |  | 5 | EA | 2 | [6 empty] | KW1-5620 | 5 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 5 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4510-60-V00-0124 | FAUCET, LEVER, SINGLE, CHROME, BRASS, WASH BASIN MIXER | 17044 | 2022-09-21 | 2022-09-24 |  | 1 | EA | 1 | [6 empty] | KW1-5212 | 4 | [5 empty] | 2022-10-05 | COMP | 2022-09-29 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0054 | PIPE, UPVC, SCH40, NON-PRESSURE, GREY, 50 MM X 2.2MM X 6 METER | 17053 | 2022-09-21 | 2022-09-21 |  | 1 | EA | 1 | [6 empty] | KW1-5679 | 1 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0054 | PIPE, UPVC, SCH40, NON-PRESSURE, GREY, 50 MM X 2.2MM X 6 METER | 17053 | 2022-09-21 | 2022-09-21 |  | 3 | EA | 1 | [6 empty] | KW1-5679 | 3 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0054 | PIPE, UPVC, SCH40, NON-PRESSURE, GREY, 50 MM X 2.2MM X 6 METER | 17053 | 2022-09-21 | 2022-09-21 |  | 2 | EA | 2 | [6 empty] | KW1-5679 | 2 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0054 | PIPE, UPVC, SCH40, NON-PRESSURE, GREY, 50 MM X 2.2MM X 6 METER | 17053 | 2022-09-21 | 2022-09-21 |  | 4 | EA | 2 | [6 empty] | KW1-5679 | 4 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0101 | PIPE, PLASTIC, PVC, ORANGE, 4 INCHES X 13 FEET | 17048 | 2022-09-21 | 2022-09-24 |  | 4 | EA | 1 | [6 empty] | KW1-5212 | 24 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0101 | PIPE, PLASTIC, PVC, ORANGE, 4 INCHES X 13 FEET | 17048 | 2022-09-21 | 2022-09-19 |  | 1 | EA | 4 | [6 empty] | KW1-5212 | 21 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0101 | PIPE, PLASTIC, PVC, ORANGE, 4 INCHES X 13 FEET | 17048 | 2022-09-21 | 2022-09-24 |  | 3 | EA | 4 | [6 empty] | KW1-5212 | 23 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0101 | PIPE, PLASTIC, PVC, ORANGE, 4 INCHES X 13 FEET | 17048 | 2022-09-21 | 2022-09-24 |  | 2 | EA | 4 | [6 empty] | KW1-5212 | 22 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0103 | PIPE, PLASTIC, SCH-40, UPVC, GRAY, 2 INCHES | 17053 | 2022-09-21 | 2022-09-21 |  | 5 | EA | 4 | [6 empty] | KW1-5679 | 5 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0103 | PIPE, PLASTIC, SCH-40, UPVC, GRAY, 2 INCHES | 17053 | 2022-09-21 | 2022-09-21 |  | 6 | EA | 4 | [6 empty] | KW1-5679 | 6 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0107 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 2 INCHES | 17045 | 2022-09-21 | 2022-09-24 |  | 2 | EA | 2 | [6 empty] | KW1-5181 | 2 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0108 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 17048 | 2022-09-21 | 2022-09-24 |  | 8 | EA | 2 | [6 empty] | KW1-5212 | 28 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0108 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 17048 | 2022-09-21 | 2022-09-24 |  | 5 | EA | 8 | [6 empty] | KW1-5212 | 25 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 8 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0108 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 17048 | 2022-09-21 | 2022-09-24 |  | 7 | EA | 10 | [6 empty] | KW1-5212 | 27 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 10 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0108 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 17048 | 2022-09-21 | 2022-09-24 |  | 6 | EA | 10 | [6 empty] | KW1-5212 | 26 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 10 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0111 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 1 INCH | 17045 | 2022-09-21 | 2022-09-24 |  | 3 | EA | 3 | [6 empty] | KW1-5181 | 3 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 3 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4720-60-V00-0262 | HOSE, METALLIC, FLEXIBLE, SINGLE NUT, STAINLESS STEEL BRAIDED, 1/2-INCH X 1 FEET | 17042 | 2022-09-21 | 2022-09-24 |  | 1 | EA | 1 | [6 empty] | KWA-5530 | 1 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0251 | COUPLING, POLYPROPYLENE, GREEN, 20 MM | 17048 | 2022-09-21 | 2022-09-19 |  | 9 | EA | 4 | [6 empty] | KW1-5212 | 29 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0458 | ELBOW, PIPE, SOCKET X SPIGOT, 45°, PVC, ORANGE, 110MM | 17048 | 2022-09-21 | 2022-09-19 |  | 10 | EA | 5 | [6 empty] | KW1-5212 | 30 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 5 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0458 | ELBOW, PIPE, SOCKET X SPIGOT, 45°, PVC, ORANGE, 110MM | 17048 | 2022-09-21 | 2022-09-24 |  | 12 | EA | 8 | [6 empty] | KW1-5212 | 32 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 8 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0458 | ELBOW, PIPE, SOCKET X SPIGOT, 45°, PVC, ORANGE, 110MM | 17048 | 2022-09-21 | 2022-09-24 |  | 11 | EA | 8 | [6 empty] | KW1-5212 | 31 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 8 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0501 | FLANGE, PVC-U, GRAY, 160MM | 17053 | 2022-09-21 | 2022-09-21 |  | 7 | EA | 1 | [6 empty] | KW1-5679 | 7 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0594 | C-CLAMP W/ RUBBER, GALVANIZED STEEL, 2 INCHES | 17041 | 2022-09-21 | 2022-09-30 |  | 3 | EA | 69 | [6 empty] | KW1-5358 | 3 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 69 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0705 | TEE, PIPE, SOCKET X SOCKET X SPIGOT, 87 °, PVC, ORANGE, 110MM | 17053 | 2022-09-21 | 2022-09-21 |  | 8 | EA | 4 | [6 empty] | KW1-5679 | 8 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0705 | TEE, PIPE, SOCKET X SOCKET X SPIGOT, 87 °, PVC, ORANGE, 110MM | 17053 | 2022-09-21 | 2022-09-21 |  | 9 | EA | 4 | [6 empty] | KW1-5679 | 9 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0706 | TEE, PIPE, SOCKET X SOCKET X SPIGOT, 87.5 °, UPVC, GRAY, 50MM | 17050 | 2022-09-21 | 2022-09-21 |  | 1 | EA | 3 | [6 empty] | KW1-5212 | 4 | [5 empty] | 2022-10-22 | COMP | 2022-10-01 | 3 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0708 | TRAP, DRAINAGE PIPE, UNDERGROUND, 45°, PVC-U, TERRACOTTA, 110 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 10 | EA | 2 | [6 empty] | KW1-5679 | 10 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0708 | TRAP, DRAINAGE PIPE, UNDERGROUND, 45°, PVC-U, TERRACOTTA, 110 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 12 | EA | 3 | [6 empty] | KW1-5679 | 12 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 3 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0708 | TRAP, DRAINAGE PIPE, UNDERGROUND, 45°, PVC-U, TERRACOTTA, 110 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 11 | EA | 3 | [6 empty] | KW1-5679 | 11 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 3 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0754 | ADAPTER, PRESSURE FITTINGS, MALE, CPVC, STANDARD, SOCKET X MIPT, PN16, OFF-WHITE, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 2 | EA | 6 | [6 empty] | KWA-5530 | 2 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 6 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0754 | ADAPTER, PRESSURE FITTINGS, MALE, CPVC, STANDARD, SOCKET X MIPT, PN16, OFF-WHITE, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 3 | EA | 6 | [6 empty] | KWA-5530 | 3 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 6 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0755 | ADAPTER, PIPE, SCH 40, MIPT X SOCKET, CPVC, OFF-WHITE, 32 MM X 1 INCH | 17049 | 2022-09-21 | 2022-09-24 |  | 2 | EA | 2 | [6 empty] | KW1-5620 | 2 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0755 | ADAPTER, PIPE, SCH 40, MIPT X SOCKET, CPVC, OFF-WHITE, 32 MM X 1 INCH | 17049 | 2022-09-21 | 2022-09-21 |  | 3 | EA | 4 | [6 empty] | KW1-5620 | 3 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0757 | ADAPTER, MALE, CPVC, STRAIGHT, SOCKET X MIPT, SCH-40, OFF-WHITE, 63 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 4 | EA | 4 | [6 empty] | KWA-5530 | 4 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0761 | ADAPTER, PRESSURE FITTINGS, FEMALE, CPVC, STANDARD, SOCKET X SR FIPT, SCH- 40, OFF-WHITE, 50 MM | 17049 | 2022-09-21 | 2022-09-19 |  | 7 | EA | 4 | [6 empty] | KW1-5620 | 7 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0763 | ADAPTER, PRESSURE FITTINGS, FEMALE, CPVC, REDUCTION, SOCKET X FIPT, SCH- 40, OFF-WHITE, 3/4 X 1/2 INCH | 17041 | 2022-09-21 | 2022-09-24 |  | 5 | EA | 3 | [6 empty] | KW1-5358 | 5 | [5 empty] | 2022-10-30 | COMP | 2022-10-12 | 3 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0763 | ADAPTER, PRESSURE FITTINGS, FEMALE, CPVC, REDUCTION, SOCKET X FIPT, SCH- 40, OFF-WHITE, 3/4 X 1/2 INCH | 17041 | 2022-09-21 | 2022-09-24 |  | 4 | EA | 4 | [6 empty] | KW1-5358 | 4 | [5 empty] | 2022-10-30 | COMP | 2022-10-12 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0770 | ADAPTER, PRESSURE FITTINGS, FEMALE, CPVC, STANDARD, SOCKET X SR FIPT, SCH- 40, OFF-WHITE, 63 MM | 17041 | 2022-09-21 | 2022-09-24 |  | 6 | EA | 3 | [6 empty] | KW1-5358 | 6 | [5 empty] | 2022-10-30 | COMP | 2022-10-12 | 3 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0773 | ADAPTER, PRESSURE FITTINGS, MALE, CPVC, REDUCTION, SOCKET X MIPT, SCH- 40, OFF-WHITE, 3 X 2 INCHES | 17049 | 2022-09-21 | 2022-09-24 |  | 8 | EA | 4 | [6 empty] | KW1-5620 | 8 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0795 | CAP, PIPE, UPVC, SPIGOT, SCH-80, ORANGE, 4 INCHES | 17049 | 2022-09-21 | 2022-09-24 |  | 1 | EA | 2 | [6 empty] | KW1-5620 | 1 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0798 | CAP, PIPE, UPVC, SCH-40, GRAY, 2 INCHES | 17045 | 2022-09-21 | 2022-09-24 |  | 4 | EA | 2 | [6 empty] | KW1-5181 | 4 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0798 | CAP, PIPE, UPVC, SCH-40, GRAY, 2 INCHES | 17045 | 2022-09-21 | 2022-09-24 |  | 5 | EA | 2 | [6 empty] | KW1-5181 | 5 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0817 | COUPLING, WASTE, SHOWER, BRASS, 1-1/2 INCHES | 17042 | 2022-09-21 | 2022-09-19 |  | 5 | EA | 2 | [6 empty] | KWA-5530 | 5 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0829 | COUPLING, UPVC, SCH-40, GRAY, 50 MM | 17045 | 2022-09-21 | 2022-09-19 |  | 6 | EA | 4 | [6 empty] | KW1-5181 | 6 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0845 | WYE, TRUE, PIPE, SCH 40, UPVC, GRAY, 45 °, 50MM | 17048 | 2022-09-21 | 2022-09-19 |  | 13 | EA | 2 | [6 empty] | KW1-5212 | 33 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0847 | WYE, PIPE, SEWAGE, 45 °, UPVC, ORANGE, 110MM | 17053 | 2022-09-21 | 2022-09-21 |  | 13 | EA | 1 | [6 empty] | KW1-5679 | 13 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0850 | ELBOW, CPVC, SOCKET X SOCKET, SCH 40, OFF-WHITE, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 9 | EA | 4 | [6 empty] | KWA-5530 | [6 empty] | 2022-09-24 | COMP | 2022-10-17 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0850 | ELBOW, CPVC, SOCKET X SOCKET, SCH 40, OFF-WHITE, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 6 | EA | 10 | [6 empty] | KWA-5530 | 6 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 10 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0850 | ELBOW, CPVC, SOCKET X SOCKET, SCH 40, OFF-WHITE, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 8 | EA | 10 | [6 empty] | KWA-5530 | 8 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 10 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0850 | ELBOW, CPVC, SOCKET X SOCKET, SCH 40, OFF-WHITE, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 7 | EA | 10 | [6 empty] | KWA-5530 | 10 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 10 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0851 | ELBOW, CPVC, 90 DEGREE, SCH- 40, OFF-WHITE, 1 INCH | 17045 | 2022-09-21 | 2022-09-24 |  | 7 | EA | 5 | [6 empty] | KW1-5181 | 7 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 5 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0854 | ELBOW, CPVC, 90 DEGREE, SCH- 40, OFF-WHITE, 2 INCHES | 17049 | 2022-09-21 | 2022-09-24 |  | 4 | EA | 4 | [6 empty] | KW1-5620 | 4 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0856 | ELBOW, PRESSURE FITTINGS, CPVC, STANDARD, 45 °, SOCKET X SOCKET, SCH- 40, OFF-WHITE, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 10 | EA | 6 | [6 empty] | KWA-5530 | 10 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 6 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0861 | ELBOW, CPVC, 45 DEGREE, SCH- 40, OFF-WHITE, 2 INCHES | 17048 | 2022-09-21 | 2022-09-24 |  | 14 | EA | 2 | [6 empty] | KW1-5212 | 34 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0863 | ELBOW, PRESSURE FITTINGS, CPVC, BRASS, REDUCTION, 90 °, SOCKET X FIPT, SCH- 40, OFF-WHITE, 25 x 20 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 11 | EA | 2 | [6 empty] | KWA-5530 | 11 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0863 | ELBOW, PRESSURE FITTINGS, CPVC, BRASS, REDUCTION, 90 °, SOCKET X FIPT, SCH- 40, OFF-WHITE, 25 x 20 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 13 | EA | 6 | [6 empty] | KWA-5530 | 13 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 6 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0863 | ELBOW, PRESSURE FITTINGS, CPVC, BRASS, REDUCTION, 90 °, SOCKET X FIPT, SCH- 40, OFF-WHITE, 25 x 20 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 12 | EA | 6 | [6 empty] | KWA-5530 | 12 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 6 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0869 | ELBOW, PIPE, SCH-40, SOCKET X SOCKET, 90°, PVC, GRAY, 63 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 14 | EA | 2 | [6 empty] | KW1-5679 | 14 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0869 | ELBOW, PIPE, SCH-40, SOCKET X SOCKET, 90°, PVC, GRAY, 63 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 16 | EA | 8 | [6 empty] | KW1-5679 | 16 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 8 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0869 | ELBOW, PIPE, SCH-40, SOCKET X SOCKET, 90°, PVC, GRAY, 63 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 15 | EA | 8 | [6 empty] | KW1-5679 | 15 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 8 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0874 | ELBOW, PIPE, UPVC, STANDARD, 90 °, SOCKET X SOCKET, SCH- 40, GRAY, 50 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 17 | EA | 6 | [6 empty] | KW1-5679 | 17 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 6 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0876 | ELBOW, PIPE, SOCKET X SOCKET, 45 °, UPVC, GRAY, 50MM | 17053 | 2022-09-21 | 2022-09-21 |  | 18 | EA | 6 | [6 empty] | KW1-5679 | 18 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 6 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0877 | ELBOW, PIPE, UPVC, 45 °, SOCKET X SOCKET, PN16, GRAY, 63 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 19 | EA | 10 | [6 empty] | KW1-5679 | 19 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 10 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0877 | ELBOW, PIPE, UPVC, 45 °, SOCKET X SOCKET, PN16, GRAY, 63 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 20 | EA | 10 | [6 empty] | KW1-5679 | 20 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 10 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0880 | ELBOW, UPVC, SCH-80, ORANGE, 4 INCHES | 17045 | 2022-09-21 | 2022-09-19 |  | 8 | EA | 6 | [6 empty] | KW1-5181 | 8 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 6 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0897 | BUSHING, PIPE, REDUCER, SCH-40, CPVC, OFF-WHITE, 2 X 1 INCHES | 17048 | 2022-09-21 | 2022-09-24 |  | 15 | EA | 2 | [6 empty] | KW1-5212 | 35 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0899 | BUSHING, PIPE, REDUCTION, SCH- 40, CPVC, OFF-WHITE, 2 X 1-1/2 INCHES | 17041 | 2022-09-21 | 2022-09-24 |  | 7 | EA | 1 | [6 empty] | KW1-5358 | 7 | [5 empty] | 2022-09-24 | COMP | 2022-10-30 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0900 | BUSHING, PIPE, REDUCER, SCH-40, CPVC, OFF-WHITE, 4 X 2 INCHES | 17053 | 2022-09-21 | 2022-09-21 |  | 21 | EA | 1 | [6 empty] | KW1-5679 | 21 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0900 | BUSHING, PIPE, REDUCER, SCH-40, CPVC, OFF-WHITE, 4 X 2 INCHES | 17053 | 2022-09-21 | 2022-09-21 |  | 23 | EA | 3 | [6 empty] | KW1-5679 | 23 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 3 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0900 | BUSHING, PIPE, REDUCER, SCH-40, CPVC, OFF-WHITE, 4 X 2 INCHES | 17053 | 2022-09-21 | 2022-09-21 |  | 22 | EA | 3 | [6 empty] | KW1-5679 | 22 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 3 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0908 | BUSHING, PIPE, SEWAGE, REDUCTION, SCH-40, PVC, ORANGE, 4 X 1-1/2 INCHES | 17053 | 2022-09-21 | 2022-09-21 |  | 24 | EA | 1 | [6 empty] | KW1-5679 | 24 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0923 | TEE, PIPE, CPVC, SCH-40, OFF-WHITE, 63 MM | 17048 | 2022-09-21 | 2022-09-24 |  | 16 | EA | 1 | [6 empty] | KW1-5212 | 36 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0940 | TEE, PIPE, SOCKET X SOCKET X SOCKET, CPVC, OFF-WHITE, SCH 40, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 14 | EA | 4 | [6 empty] | KWA-5530 | 14 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0940 | TEE, PIPE, SOCKET X SOCKET X SOCKET, CPVC, OFF-WHITE, SCH 40, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 16 | EA | 6 | [6 empty] | KWA-5530 | 16 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 6 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0940 | TEE, PIPE, SOCKET X SOCKET X SOCKET, CPVC, OFF-WHITE, SCH 40, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 15 | EA | 6 | [6 empty] | KWA-5530 | 15 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 6 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0949 | UNION, PIPE, SOCKET X SOCKET, SCH- 40, CPVC, OFF-WHITE, 32 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 17 | EA | 2 | [6 empty] | KWA-5530 | 17 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0970 | ELBOW, PRESSURE FITTINGS, PVC, STANDARD, 90 °, SPIGOT X SOCKET, ORANGE, 110 MM | 17042 | 2022-09-21 | 2022-09-19 |  | 18 | EA | 5 | [6 empty] | KWA-5530 | 18 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 5 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0970 | ELBOW, PRESSURE FITTINGS, PVC, STANDARD, 90 °, SPIGOT X SOCKET, ORANGE, 110 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 20 | EA | 6 | [6 empty] | KWA-5530 | 20 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 6 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0970 | ELBOW, PRESSURE FITTINGS, PVC, STANDARD, 90 °, SPIGOT X SOCKET, ORANGE, 110 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 19 | EA | 6 | [6 empty] | KWA-5530 | 19 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 6 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4820-60-V00-0227 | VALVE, ANGLE, 1/2 X 1/2 INCHES | 17047 | 2022-09-21 | 2022-09-24 |  | 1 | EA | 2 | [6 empty] | KW1-5212 | 2 | [5 empty] | 2022-10-22 | COMP | 2022-10-01 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4820-60-V00-0227 | VALVE, ANGLE, 1/2 X 1/2 INCHES | 17047 | 2022-09-21 | 2022-09-24 |  | 2 | EA | 16 | [6 empty] | KW1-5212 | 3 | [5 empty] | 2022-10-22 | COMP | 2022-10-01 | 16 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4820-60-V00-0229 | VALVE, BALL, BRASS, PN25, RED, 3/4 INCH | 17042 | 2022-09-21 | 2022-09-24 |  | 21 | EA | 2 | [6 empty] | KWA-5530 | 21 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4820-60-V00-0229 | VALVE, BALL, BRASS, PN25, RED, 3/4 INCH | 17042 | 2022-09-21 | 2022-09-24 |  | 22 | EA | 2 | [6 empty] | KWA-5530 | 22 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4820-60-V00-0235 | VALVE, BALL, BRASS, 2 INCHES | 17048 | 2022-09-21 | 2022-09-24 |  | 17 | EA | 1 | [6 empty] | KW1-5212 | 37 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 17049 | 2022-09-21 | 2022-09-21 |  | 15 | BX | 52 | [6 empty] | KW1-5620 | 15 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 52 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5305-60-V00-0175 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 3-1/2 INCHES | 17053 | 2022-09-21 | 2022-09-21 |  | 25 | BX | 10 | [6 empty] | KW1-5679 | 25 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 10 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 17042 | 2022-09-21 | 2022-09-24 |  | 23 | BX | 1 | [6 empty] | KWA-5530 | 23 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5340-60-V00-0497 | LATCH, DOOR, STAINLESS STEEL, 3 INCHES | 17045 | 2022-09-21 | 2022-09-24 |  | 9 | EA | 6 | [6 empty] | KW1-5181 | 9 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 6 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5530-00-129-7721 | PLYWOOD, CONSTRUCTION, 1/4 X 48 X 96 INCHES | 17040 | 2022-09-21 | 2022-09-24 |  | 1 | SH | 3 | [6 empty] | KW1-5212 | 7 | [5 empty] | 2022-09-24 | COMP | 2022-09-29 | 3 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0030 | INSULATION SLEEVING, THERMAL, 3/8 X 72 INCHES | 17041 | 2022-09-21 | 2022-09-30 |  | 8 | EA | 166 | [6 empty] | KW1-5358 | 8 | [5 empty] | 2022-10-30 | COMP | 2022-10-06 | 166 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0031 | INSULATION SLEEVING, THERMAL, 5/8 X 72 INCHES | 17041 | 2022-09-21 | 2022-09-30 |  | 9 | EA | 166 | [6 empty] | KW1-5358 | 9 | [5 empty] | 2022-10-30 | COMP | 2022-10-06 | 166 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0044 | TAPE, SELF ADHESIVE, DRYWALL JOINT, FIBERGLASS, 2 INCHES X 300 FEET | 17045 | 2022-09-21 | 2022-09-24 |  | 10 | EA | 20 | [6 empty] | KW1-5181 | 10 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 20 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5650-60-V00-0004 | CHANNEL, STRUCTURAL, C-SHAPE, STEEL, 1-5/8 X 3-5/8 INCHES X 10 FEET | 17049 | 2022-09-21 | 2022-09-24 |  | 12 | EA | 76 | [6 empty] | KW1-5620 | 12 | [5 empty] | 2022-11-17 | COMP | 2022-10-22 | 76 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5670-60-V00-0026 | WALL ANGLE / GRID, CEILING, TEE, GALVANIZED STEEL, WHITE, 12 FEET | 17049 | 2022-09-21 | 2022-09-24 |  | 16 | EA | 90 | [6 empty] | KW1-5620 | 16 | [5 empty] | 2022-11-17 | COMP | 2022-10-22 | 90 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5680-60-V00-0006 | GRID, CEILING, TEE, WHITE, 24 INCHES | 17049 | 2022-09-21 | 2022-09-24 |  | 21 | EA | 1400 | [6 empty] | KW1-5620 | 21 | [5 empty] | 2022-11-17 | COMP | 2022-10-22 | 300 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5680-60-V00-0007 | GRID, CEILING, T-RUNNER, WHITE, 12 FEET | 17049 | 2022-09-21 | 2022-09-24 |  | 20 | EA | 300 | [6 empty] | KW1-5620 | 20 | [5 empty] | 2022-11-17 | COMP | 2022-10-22 | 300 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 17041 | 2022-09-21 | 2022-09-30 |  | 11 | EA | 62 | [6 empty] | KW1-5358 | 11 | [5 empty] | 2022-11-25 | COMP | 2022-10-11 | 62 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 17041 | 2022-09-21 | 2022-09-30 |  | 12 | EA | 47 | [6 empty] | KW1-5358 | 12 | [5 empty] | 2022-11-25 | COMP | 2022-10-11 | 47 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5935-60-V00-0160 | SOCKET, OUTLET, WEATHERPROOF, 2 GANG, 2 POLES, 13 AMPS | 17052 | 2022-09-21 | 2022-09-17 |  | 1 | EA | 4 | [6 empty] | KW1-5267 | 2 | [5 empty] | 2022-09-24 | COMP | 2022-10-03 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5935-60-V00-0167 | CONNECTOR, WIRE, RED, 18 -10 AWG | 17041 | 2022-09-21 | 2022-09-30 |  | 13 | PG | 20 | [6 empty] | KW1-5358 | 13 | [5 empty] | 2022-10-30 | COMP | 2022-10-15 | 20 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 17041 | 2022-09-21 | 2022-09-30 |  | 14 | PG | 20 | [6 empty] | KW1-5358 | 14 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 20 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-00-156-3253 | STRAP, TIE DOWN, ELECTRICAL COMPONE, 13-7/20 INCHES | 17041 | 2022-09-21 | 2022-09-30 |  | 15 | HD | 6 | [6 empty] | KW1-5358 | 15 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 6 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0235 | RACEWAY, NONMETALLIC (CABLE TRUNKING), PVC, WHITE, 100 X 100 MM, 3 METERS | 17041 | 2022-09-21 | 2022-09-30 |  | 16 | EA | 25 | [6 empty] | KW1-5358 | 16 | [5 empty] | 2022-11-25 | COMP | 2022-10-11 | 25 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0235 | RACEWAY, NONMETALLIC (CABLE TRUNKING), PVC, WHITE, 100 X 100 MM, 3 METERS | 17041 | 2022-09-21 | 2022-09-30 |  | 17 | EA | 35 | [6 empty] | KW1-5358 | 17 | [5 empty] | 2022-11-25 | COMP | 2022-10-11 | 35 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0373 | COUPLING, ELECTRICAL CONDUIT, PVC, BLACK, 20 MM | 17041 | 2022-09-21 | 2022-09-30 |  | 18 | EA | 300 | [6 empty] | KW1-5358 | 18 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 300 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0436 | ADAPTER, CONDUIT, w/ BUSH, MALE, PVC, WHITE, 20MM | 17041 | 2022-09-21 | 2022-09-30 |  | 19 | EA | 400 | [6 empty] | KW1-5358 | 19 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 400 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0480 | JUNCTION BOX, w/ BLANK SIDE, 100 X 100 X 50 MM | 17041 | 2022-09-21 | 2022-09-30 |  | 20 | EA | 10 | [6 empty] | KW1-5358 | 20 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 10 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0500 | CLAMP, ELECTRICAL, CONDUIT, PVC, BLACK, 20 MM | 17041 | 2022-09-21 | 2022-09-30 |  | 21 | EA | 62 | [6 empty] | KW1-5358 | 21 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 62 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0500 | CLAMP, ELECTRICAL, CONDUIT, PVC, BLACK, 20 MM | 17041 | 2022-09-21 | 2022-09-30 |  | 22 | EA | 1200 | [6 empty] | KW1-5358 | 22 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 1200 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0505 | STUFFING TUBE (CABLE GLAND), PG16, POLYAMIDE, GRAY, 9 -14 MM | 17041 | 2022-09-21 | 2022-09-30 |  | 23 | EA | 140 | [6 empty] | KW1-5358 | 23 | [5 empty] | 2002-11-13 | COMP | 2022-10-11 | 140 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0526 | CONDUIT, NONMETALLIC, RIGID, PVC, BLACK, 3/4 INCH X 10 FEET | 17041 | 2022-09-21 | 2022-09-30 |  | 24 | EA | 365 | [6 empty] | KW1-5358 | 24 | [5 empty] | 2022-10-30 | COMP | 2022-10-15 | 365 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 17041 | 2022-09-21 | 2022-09-30 |  | 25 | RO | 2 | [6 empty] | KW1-5358 | 25 | [5 empty] | 2022-10-30 | COMP | 2022-10-15 | 2 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 17041 | 2022-09-21 | 2022-09-30 |  | 26 | RO | 5 | [6 empty] | KW1-5358 | 26 | [5 empty] | 2022-10-30 | COMP | 2022-10-15 | 5 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V01-0029 | JUNCTION BOX, PVC, BLACK, 2 WAY, 20MM | 17704 | 2022-09-21 | 2022-09-21 |  | 1 | EA | 100 | [6 empty] | KW1-5212 | 13 | [5 empty] | 2022-12-28 | COMP | 2022-10-08 | 100 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 17041 | 2022-09-21 | 2022-09-30 |  | 27 | RL | 1 | [6 empty] | KW1-5358 | 27 | [5 empty] | 2022-10-30 | COMP | 2022-10-10 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 17041 | 2022-09-21 | 2022-09-30 |  | 28 | RL | 58 | [6 empty] | KW1-5358 | 28 | [5 empty] | 2022-10-30 | COMP | 2022-10-10 | 58 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6145-60-V00-0143 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4 MM² | 17041 | 2022-09-21 | 2022-09-30 |  | 29 | RL | 7 | [6 empty] | KW1-5358 | 29 | [5 empty] | 2022-10-30 | COMP | 2022-10-10 | 7 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6145-60-V00-0151 | WIRE, ELECTRICAL, BLACK, 1 CORE, 2.5 mm² | 17041 | 2022-09-21 | 2022-09-30 |  | 30 | RO | 56 | [6 empty] | KW1-5358 | 30 | [5 empty] | 2022-10-30 | COMP | 2022-10-10 | 56 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6145-60-V00-0152 | WIRE, ELECTRICAL, RED, 1 CORE, 2.5 MM ² | 17041 | 2022-09-21 | 2022-09-30 |  | 31 | RL | 22 | [6 empty] | KW1-5358 | 31 | [5 empty] | 2022-10-30 | COMP | 2022-10-10 | 22 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6145-60-V00-0154 | WIRE, ELECTRICAL, BLACK, 1 CORE, 4 MM ² | 17041 | 2022-09-21 | 2022-09-30 |  | 32 | RO | 4 | [6 empty] | KW1-5358 | 32 | [5 empty] | 2022-10-30 | COMP | 2022-10-10 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6145-60-V00-0156 | WIRE, ELECTRICAL, BLUE, 1 CORE, 2.5 MM ² | 17041 | 2022-09-21 | 2022-09-30 |  | 33 | RO | 20 | [6 empty] | KW1-5358 | 33 | [5 empty] | 2022-10-30 | COMP | 2022-10-10 | 20 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 17041 | 2022-09-21 | 2022-09-30 |  | 34 | EA | 1 | [6 empty] | KW1-5358 | 34 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6210-60-V00-0136 | LIGHT UNIT, EMERGENCY, (EXIT LIGHT), LED, 120-277 V, 50/60 HZ, 2 W | 17041 | 2022-09-21 | 2022-09-30 |  | 35 | EA | 4 | [6 empty] | KW1-5358 | 35 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 4 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8010-60-V00-0006 | PAINT, LATEX, MATT, OFF-WHITE, 3.2 LITER | 17049 | 2022-09-21 | 2022-09-24 |  | 18 | CN | 60 | [6 empty] | KW1-5620 | 18 | [5 empty] | 2022-11-17 | COMP | 2022-10-30 | 60 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8020-00-260-1302 | BRUSH, PAINT, BRISTLES, CHISELED, 2 INCHES | 17050 | 2022-09-21 | 2022-09-24 |  | 2 | EA | 20 | [6 empty] | KW1-5212 | 5 | [5 empty] | 2022-10-22 | COMP | 2022-10-01 | 5 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8040-60-V00-0045 | ADHESIVE, CEMENT, PVC, CLEAR, 16 FL. OUNCES | 17041 | 2022-09-21 | 2022-09-30 |  | 36 | CN | 1 | [6 empty] | KW1-5358 | 36 | [5 empty] | 2022-10-30 | COMP | 2022-10-12 | 1 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5660-60-V00-0046 | FENCING, WIRE, PVC COATED, GREEN, 2.5 MM | 17049 | 2022-09-21 | 2022-09-21 |  | 9 | RO | 3 | [6 empty] | KW1-5620 | 9 | [5 empty] | 2022-11-17 | WINSP | 2022-10-31 | 3 |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 17043 | 2022-09-21 | 2022-09-21 |  | 1 | EA | 400 | [6 empty] | KW1-5212 | 3 | [5 empty] | 2022-09-24 |  |  |  |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-05-V00-0005 | PANEL, DRYWALL, WALL BOARD, REGULAR, MOLD-GUARD, 1/2 INCH X 4 X 8 FEET | 17053 | 2022-09-21 | 2022-09-21 |  | 26 | EA | 20 | [6 empty] | KW1-5679 | 26 | [5 empty] | 2022-11-14 |  |  |  |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5650-60-V00-0002 | ROOFING METAL, WHITE, 0.35 MM X 3 METER | 17045 | 2022-09-21 | 2022-09-24 |  | 11 | SH | 40 | [6 empty] | KW1-5212 | 11 | [5 empty] | 2022-10-30 |  |  |  |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5680-60-V00-0001 | CORNER BEAD, PAPER-FACED METAL, OFF-WHITE, 1 INCH X 10 FEET | 17053 | 2022-09-21 | 2022-09-21 |  | 27 | EA | 65 | [6 empty] | KW1-5679 | 27 | [5 empty] | 2022-11-14 |  |  |  |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5930-60-V00-0215 | SWITCH, BOX, POP-UP, FLOOR, 2-GANG, STAINLESS STEEL, SILVER, 110-220V, 10-20A | 17053 | 2022-09-21 | 2022-09-21 |  | 28 | EA | 60 | [6 empty] | KW1-5679 | 28 | [5 empty] | 2022-11-14 |  |  |  |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0103 | JUNCTION BOX, PVC, BLACK, 3 WAY, 20 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 29 | EA | 50 | [6 empty] | KW1-5679 | 29 | [5 empty] | 2022-11-14 |  |  |  |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0413 | ANCHOR, PLASTIC, BUTTERFLY, WHITE, 6MM | 17053 | 2022-09-21 | 2022-09-21 |  | 30 | BX | 5 | [6 empty] | KW1-5679 | 30 | [5 empty] | 2022-11-14 |  |  |  |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V01-0223 | BEND, ELECTRICAL CONDUIT, PVC, BLACK, 3/4 INCHES | 17704 | 2022-09-21 | 2022-09-21 |  | 1 | EA | 100 | [6 empty] | KW1-5212 | 3 | [5 empty] | 2022-09-24 |  |  |  |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6145-60-V00-0153 | WIRE, ELECTRICAL, YELLOW, 1 CORE, 2.5 MM² | 17053 | 2022-09-21 | 2022-09-21 |  | 31 | RL | 18 | [6 empty] | KW1-5679 | 31 | [5 empty] | 2022-11-14 |  |  |  |  | AJ | AJ table | September | 2022
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6210-60-V00-0011 | FIXTURE, LIGHTING, LED, 5000K, 100-277V, 20W, 2 FEET | 17053 | 2022-09-21 | 2022-09-21 |  | 32 | EA | 8 | [6 empty] | KW1-5679 | 32 | [5 empty] | 2022-11-14 |  |  |  |  | AJ | AJ table | September | 2022
2 | 2023-01-14 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6210-60-V00-0082 | LIGHT, PANEL, LED, COOL WHITE, 50/60 HZ, 40W, w/ EMERGENCY BATTERY | 25435 | 2023-01-14 | 2023-01-15 |  | 1 | EA | 5 | [6 empty] | KW1-7626 | 3 | [5 empty] | 2023-02-11 | COMP | 2023-01-29 | 5 |  | AJ | AJ table | January | 2023
2 | 2023-01-14 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6210-60-V00-0094 | FIXTURE, LIGHTING, LED, RETROFIT, POLYCARBONATE, PURE WHITE, 40W | 25435 | 2023-01-14 | 2023-01-15 |  | 2 | EA | 6 | [6 empty] | KW1-7626 | 4 | [5 empty] | 2023-02-11 | COMP | 2023-01-29 | 6 |  | AJ | AJ table | January | 2023
2 | 2023-01-14 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 25435 | 2023-01-14 | 2023-01-15 |  | 3 | EA | 3 | [6 empty] | KW1-7626 | 5 | [5 empty] | 2023-02-11 | COMP | 2023-01-29 | 3 |  | AJ | AJ table | January | 2023
2 | 2023-01-14 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6210-60-V00-0099 | FIXTURE, LIGHTING, LED, FLOOD, 5000K, 50/60HZ, 90W | 25436 | 2023-01-14 | 2023-01-15 |  | 1 | EA | 2 | [6 empty] | KW1-7626 | 7 | [5 empty] | 2023-02-11 | COMP | 2023-01-29 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 25492 | 2023-01-15 | 2023-01-16 |  | 9 | RO | 1 | [6 empty] | KW1-7510 | 9 | [5 empty] | 2023-01-25 | COMP | 2023-01-25 | 1 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 25492 | 2023-01-15 | 2023-01-16 |  | 2 | RO | 3 | [6 empty] | KW1-7510 | 2 | [5 empty] | 2023-01-25 | COMP | 2023-01-25 | 3 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0428 | LUG, TERMINAL, ROUND TYPE, ONE-HOLE, M12, 120MM² | 25492 | 2023-01-15 | 2023-01-16 |  | 6 | PG | 1 | [6 empty] | KW1-7510 | 6 | [5 empty] | 2023-01-25 | COMP | 2023-01-25 | 1 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0417 | LUG, TERMINAL, SINGLE-HOLE, 240MM² X M12 | 25492 | 2023-01-15 | 2023-01-16 |  | 5 | PG | 2 | [6 empty] | KW1-7510 | 4 | [5 empty] | 2023-01-25 | COMP | 2023-01-25 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0353 | STUFFING TUBE (CABLE GLAND), SINGLE WIRE ARMOR, BRASS, M63, 54.6-65.8 MM | 25492 | 2023-01-15 | 2023-01-16 |  | 4 | EA | 20 | [6 empty] | KW1-7510 | 4 | [5 empty] | 2023-03-31 | COMP | 2023-01-25 | 20 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5935-60-V00-0167 | CONNECTOR, WIRE, RED, 18 -10 AWG | 25496 | 2023-01-15 | 2023-01-16 |  | 1 | BX | 2 | [6 empty] | KW1-7508 | 7 | [5 empty] | 2023-01-25 | COMP | 2023-01-25 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0487 | COUPLING, ELECTRICAL CONDUIT, w/ SCREW, Â½ INCH | 25495 | 2023-01-15 | 2023-01-16 |  | 3 | EA | 50 | [6 empty] | KW1-7508 | 2 | [5 empty] | 2023-02-11 | COMP | 2023-03-20 | 50 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0483 | BOX CONNECTOR, ELECTRICAL, ZINC DIE CAST, 1/2 INCH | 25495 | 2023-01-15 | 2023-01-16 |  | 2 | EA | 50 | [6 empty] | KW1-7508 | 3 | [5 empty] | 2023-02-11 | COMP | 2023-03-20 | 50 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0381 | CLAMP, ELECTRICAL, CONDUIT, 2 HOLE, STEEL, 1/2 INCH | 25495 | 2023-01-15 | 2023-01-16 |  | 1 | EA | 25 | [6 empty] | KW1-7508 | 4 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 25 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0528 | CONDUIT, RIGID, EMT, GALVANIZED STEEL, 1/2 INCH X 10 FEET | 25495 | 2023-01-15 | 2023-01-16 |  | 4 | EA | 15 | [6 empty] | KW1-7508 | 5 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 15 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0335 | STRAP, TIE DOWN, ELECTRICAL, COMPON (CABLE TIE), BLACK, 50 LBS, 4.6 MM X 11.02 INCHES | 25492 | 2023-01-15 | 2023-01-16 |  | 3 | BX | 2 | [6 empty] | KW1-7508 | 3 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 25494 | 2023-01-15 | 2023-01-16 |  | 1 | BX | 2 | [6 empty] | KW1-7508 | [6 empty] | 2023-02-11 | COMP | 2023-01-25 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5970-01-013-9368 | TAPE, INSULATION, ELECTRICAL, GREEN, 3/4 X 792 INCHES | 25492 | 2023-01-15 | 2023-01-16 |  | 1 | RO | 1 | [6 empty] | KW1-7508 | 1 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 1 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6350-60-V00-0102 | ALARM, SMOKE, AUTOMATIC, PLASTIC | 25492 | 2023-01-15 | 2023-01-16 |  | 13 | EA | 8 | [6 empty] | KW1-7508 | 13 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 8 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5305-60-V00-0001 | SCREW, SELF DRILLING, HEX WASHER HEAD, STEEL, 5/16 X 1 INCH | 25493 | 2023-01-15 | 2023-01-16 |  | 1 | PG | 2 | [6 empty] | KW1-7508 | [6 empty] | 2023-02-11 | COMP | 2023-01-25 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0484 | BOX CONNECTOR, ELECTRICAL, METALLIC CONDUIT, ZINC, 3/4 INCH | 25492 | 2023-01-15 | 2023-01-16 |  | 7 | EA | 15 | [6 empty] | KW1-7508 | 7 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 15 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 25492 | 2023-01-15 | 2023-01-16 |  | 8 | RO | 2 | [6 empty] | KW1-7508 | 10 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0153 | WIRE, ELECTRICAL, YELLOW, 1 CORE, 2.5 MM² | 25492 | 2023-01-15 | 2023-01-16 |  | 10 | RO | 2 | [6 empty] | KW1-7508 | 11 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0157 | WIRE, ELECTRICAL, YELLOW, 1 CORE, 4MM ² | 25492 | 2023-01-15 | 2023-01-16 |  | 11 | RO | 4 | [6 empty] | KW1-7508 | 12 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 4 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0159 | WIRE, ELECTRICAL, BLUE, 1 CORE, 4 MM ² | 25492 | 2023-01-15 | 2023-01-16 |  | 12 | RO | 2 | [6 empty] | KW1-7508 | 12 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0136 | WIRE, ELECTRICAL, RED, 1 CORE, 4 MM ² | 25495 | 2023-01-15 |  |  | 5 | RO | 2 | [6 empty] | KW1-7508 | 6 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0458 | ELBOW, PIPE, SOCKET X SPIGOT, 45°, PVC, ORANGE, 110MM | 25577 | 2023-01-17 | 2023-01-19 |  | 7 | EA | 4 | [6 empty] | KW1-7799 | 1 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 4 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0390 | TEE-Y, DRAINAGE PIPE, PVC-U, 45 DEGREE, TERRACOTTA, 110 MILLIMETER | 25577 | 2023-01-17 | 2023-01-19 |  | 6 | EA | 1 | [6 empty] | KW1-7799 | 7 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 1 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0589 | PLUG, ACCESS, w/ THREADED CAP, UPVC, GRAY, 110MM | 25578 | 2023-01-17 | 2023-01-19 |  | 1 | EA | 2 | [6 empty] | KW1-8003 | 15 | [5 empty] | 2023-03-15 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0973 | TEE, PIPE, SEWER AND DRAIN FITTINGS, PVC, SCH-80, ORANGE, 110 MM | 25577 | 2023-01-17 | 2023-01-19 |  | 16 | EA | 2 | [6 empty] | KW1-7799 | 8 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0964 | COUPLING, SEWAGE, w/RUBBER GASKET, PVC, ORANGE, 4 INCHES | 25575 | 2023-01-17 | 2023-01-19 |  | 5 | EA | 8 | [6 empty] | KW1-8003 | 16 | [5 empty] | 2023-03-15 | COMP | 2023-03-15 | 8 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4710-60-V00-0101 | PIPE, PLASTIC, PVC, ORANGE, 4 INCHES X 13 FEET | 25577 | 2023-01-17 | 2023-01-19 |  | 3 | EA | 5 | [6 empty] | KW1-7799 | 9 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 5 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0132 | STRAP, METAL | 25577 | 2023-01-17 | 2023-01-19 |  | 1 | EA | 3 | [6 empty] | KW1-7799 | 2 | [5 empty] | 2023-03-05 | COMP | 2023-03-15 | 3 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 8040-60-V00-0051 | ADHESIVE, CEMENT, PVC, WET 'R DRY, MEDIUM BODY, AQUA BLUE, 32 OZ. | 25575 | 2023-01-17 | 2023-01-19 |  | 8 | EA | 2 | [6 empty] | KW1-8003 | 10 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0908 | BUSHING, PIPE, SEWAGE, REDUCTION, SCH-40, PVC, ORANGE, 4 X 1-1/2 INCHES | 25577 | 2023-01-17 | 2023-01-19 |  | 13 | EA | 4 | [6 empty] | KW1-7799 | 3 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 4 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 8030-60-V00-0051 | TAPE, ANTISEIZING, (TEFLON TAPE), 0.5 X 520 INCHES | 25577 | 2023-01-17 | 2023-01-19 |  | 17 | EA | 10 | [6 empty] | KW1-7799 | 10 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 10 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0708 | TRAP, DRAINAGE PIPE, UNDERGROUND, 45°, PVC-U, TERRACOTTA, 110 MM | 25577 | 2023-01-17 | 2023-01-19 |  | 8 | EA | 1 | [6 empty] | KW1-7799 | 4 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 1 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0795 | CAP, PIPE, UPVC, SPIGOT, SCH-80, ORANGE, 4 INCHES | 25574 | 2023-01-17 | 2023-01-19 |  | 1 | EA | 2 | [6 empty] | KW1-8003 | 1 | [5 empty] | 2023-03-15 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4820-60-V00-0235 | VALVE, BALL, BRASS, 2 INCHES | 25574 | 2023-01-17 | 2023-01-19 |  | 3 | EA | 2 | [6 empty] | KW1-8003 | 1 | [5 empty] | 2023-03-15 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0845 | WYE, TRUE, PIPE, SCH 40, UPVC, GRAY, 45 °, 50MM | 25576 | 2023-01-17 | 2023-01-19 |  | 1 | EA | 2 | [6 empty] | KW1-8003 | 1 | [5 empty] | 2023-03-15 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0632 | BUSHING, PIPE, REDUCER, SOCKET X SOCKET, CPVC, OFFWHITE, 32 X 25 MM | 25578 | 2023-01-17 | 2023-01-19 |  | 2 | EA | 2 | [6 empty] | KW1-8003 | 16 | [5 empty] | 2023-03-15 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0829 | COUPLING, UPVC, SCH-40, GRAY, 50 MM | 25574 | 2023-01-17 | 2023-01-19 |  | 2 | EA | 4 | [6 empty] | KW1-8003 | 1 | [5 empty] | 2023-03-15 | COMP | 2023-03-15 | 4 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0757 | ADAPTER, MALE, CPVC, STRAIGHT, SOCKET X MIPT, SCH-40, OFF-WHITE, 63 MM | 25575 | 2023-01-17 | 2023-01-19 |  | 2 | EA | 6 | [6 empty] | KW1-8003 | 5 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 6 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4710-60-V00-0054 | PIPE, UPVC, SCH40, NON-PRESSURE, GREY, 50 MM X 2.2MM X 6 METER | 25577 | 2023-01-17 | 2023-01-19 |  | 2 | EA | 6 | [6 empty] | KW1-7799 | 5 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 6 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0835 | COUPLING, CPVC, SCH-40, TAN, 32 MM | 25575 | 2023-01-17 | 2023-01-19 |  | 2 | EA | 4 | [6 empty] | KW1-8003 | 6 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 4 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0970 | ELBOW, PRESSURE FITTINGS, PVC, STANDARD, 90 °, SPIGOT X SOCKET, ORANGE, 110 MM | 25577 | 2023-01-17 | 2023-01-19 |  | 15 | EA | 8 | [6 empty] | KW1-7799 | 6 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 8 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0897 | BUSHING, PIPE, REDUCER, SCH-40, CPVC, OFF-WHITE, 2 X 1 INCHES | 25575 | 2023-01-17 | 2023-01-19 |  | 3 | EA | 2 | [6 empty] | KW1-8003 | 7 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0854 | ELBOW, CPVC, 90 DEGREE, SCH- 40, OFF-WHITE, 2 INCHES | 25577 | 2023-01-17 | 2023-01-19 |  | 12 | EA | 5 | [6 empty] | KW1-8003 | 11 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 5 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0940 | TEE, PIPE, SOCKET X SOCKET X SOCKET, CPVC, OFF-WHITE, SCH 40, 25 MM | 25577 | 2023-01-17 | 2023-01-19 |  | 14 | EA | 2 | [6 empty] | KW1-8003 | 12 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0850 | ELBOW, CPVC, SOCKET X SOCKET, SCH 40, OFF-WHITE, 25 MM | 25577 | 2023-01-17 | 2023-01-19 |  | 11 | EA | 6 | [6 empty] | KW1-8003 | 13 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 6 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4710-60-V00-0108 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 25577 | 2023-01-17 | 2023-01-19 |  | 5 | EA | 2 | [6 empty] | KW1-8003 | 14 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0949 | UNION, PIPE, SOCKET X SOCKET, SCH- 40, CPVC, OFF-WHITE, 32 MM | 25575 | 2023-01-17 | 2023-01-19 |  | 4 | EA | 2 | [6 empty] | KW1-8003 | 8 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4710-60-V00-0111 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 1 INCH | 25575 | 2023-01-17 | 2023-01-19 |  | 1 | EA | 10 | [6 empty] | KW1-8003 | 9 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 10 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4710-60-V00-0107 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 2 INCHES | 25577 | 2023-01-17 | 2023-01-19 |  | 4 | EA | 4 | [6 empty] | KW1-7799 | 15 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 4 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0770 | ADAPTER, PRESSURE FITTINGS, FEMALE, CPVC, STANDARD, SOCKET X SR FIPT, SCH- 40, OFF-WHITE, 63 MM | 25577 | 2023-01-17 | 2023-01-19 |  | 10 | EA | 2 | [6 empty] | KW1-7799 | 16 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 2 |  | AJ | AJ table | January | 2023
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0923 | TEE, PIPE, CPVC, SCH-40, OFF-WHITE, 63 MM | 25576 | 2023-01-17 | 2023-01-19 |  | 2 | EA | 1 | [6 empty] | KW1-8003 | 13 | [5 empty] | 2023-03-15 | COMP | 2023-03-12 | 1 |  | AJ | AJ table | January | 2023
2 | 2023-01-19 |  | AJ22-0135 | Replace 65 Street Light Heads | 238765 | PANEL | FABRICATION,LIGHT CONTROL PANEL (LC3) WITH LIGHT CONTROL PANEL MOUNTING STAND , APPROVED SUBMITTAL VIA TRANSMITTAL # AJ220044-LCV-ELE-DSN-0001 | 41575 | 2023-01-19 | 2023-01-21 |  | 1 | AY | 1 | [6 empty] | KW1-11546 | 10 | [5 empty] | 2023-03-08 | COMP | 2023-04-04 | 1 |  | AJ | AJ table | January | 2023
2 | 2023-01-23 | 70 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0584 | OUTLET, DRAIN, MALE, BRASS, 2 INCHES | 25945 | 2023-01-23 | 2023-01-26 |  | 2 | EA | 2 | [6 empty] | KW1-7727 | 3 | [5 empty] | 2023-02-18 | COMP | 2023-02-15 | 2 |  | AJ | AJ table | January | 2023
3 | 2023-02-11 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5975-60-V00-0036 | PROTECTOR, CABLE, SPIRAL WRAPPING BAND, w/ CLIP, POLYETHYLENE, BLACK, 15 MM X 1.5 METER | 27260 | 2023-02-11 | 2023-02-12 | CLOSE | 1 | RO | 100 | 8.25 | 825 | 11082 | CLOSE | 2023-03-05 | 2023-02-15 | KW1-8005 | 23 | 2023-03-05 | CLOSE | 2023-08-14 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-04-30 | COMP | 2023-04-27 | 100.00 |  | UCO | AJ table | February | 2023
3 | 2023-02-11 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5975-60-V00-0090 | COUPLING, ELECTRICAL CONDUIT, COMPRESSION, ZINC DIE CAST, 3/4 INCH | 27260 | 2023-02-11 | 2023-02-12 | CLOSE | 2 | EA | 30 | 9.49 | 284.7 | 11082 | CLOSE | 2023-03-05 | 2023-02-15 | KW1-8005 | 24 | 2023-03-05 | CLOSE | 2023-08-14 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-05-30 | COMP | 2023-04-30 | 30.00 |  | UCO | AJ table | February | 2023
3 | 2023-02-11 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5975-60-V00-0530 | CONDUIT, RIGID, GALVANIZED STEEL, THREADED, 3/4 INCH X 10 FEET | 27260 | 2023-02-11 | 2023-02-12 | CLOSE | 3 | EA | 60 | 55.13 | 3307.8 | 11082 | CLOSE | 2023-03-05 | 2023-02-15 | KW1-8005 | 25 | 2023-03-05 | CLOSE | 2023-08-14 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-04-30 | COMP | 2023-03-13 | 60.00 |  | UCO | AJ table | February | 2023
3 | 2023-02-11 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5995-60-V00-0132 | STRAP, TIE DOWN (CABLE TIE), NYLON 6/6, BLACK, 7 INCHES | 27260 | 2023-02-11 | 2023-02-12 | CLOSE | 4 | PG | 10 | 16.5 | 165 | 11082 | CLOSE | 2023-03-05 | 2023-02-15 | KW1-8005 | 26 | 2023-03-05 | CLOSE | 2023-08-14 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-04-30 | COMP | 2023-03-14 | 10.00 |  | UCO | AJ table | February | 2023
3 | 2023-02-11 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 27292 | 2023-02-11 | 2023-02-12 | CLOSE | 2 | RL | 6 | 57.75 | 346.5 | 11086 | CLOSE | 2023-02-21 | 2023-02-15 | KW1-7987 | 1 | 2023-02-21 | CLOSE | 2023-05-09 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-03-30 | COMP | 2023-02-27 | 6.00 |  | UCO | AJ table | February | 2023
3 | 2023-02-11 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 6145-60-V00-0151 | WIRE, ELECTRICAL, BLACK, 1 CORE, 2.5 mm² | 27292 | 2023-02-11 | 2023-02-12 | CLOSE | 3 | RO | 15 | 57.34 | 860.1 | 11086 | CLOSE | 2023-02-21 | 2023-02-15 | KW1-7987 | 2 | 2023-02-21 | CLOSE | 2023-05-09 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-03-30 | COMP | 2023-02-27 | 15.00 |  | UCO | AJ table | February | 2023
3 | 2023-02-11 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 6145-60-V00-0152 | WIRE, ELECTRICAL, RED, 1 CORE, 2.5 MM ² | 27292 | 2023-02-11 | 2023-02-12 | CLOSE | 4 | RO | 15 | 57.34 | 860.1 | 11086 | CLOSE | 2023-02-21 | 2023-02-15 | KW1-7987 | 3 | 2023-02-21 | CLOSE | 2023-05-09 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-03-30 | COMP | 2023-02-27 | 15.00 |  | UCO | AJ table | February | 2023
3 | 2023-02-11 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 6145-60-V00-0153 | WIRE, ELECTRICAL, YELLOW, 1 CORE, 2.5 MM² | 27292 | 2023-02-11 | 2023-02-12 | CLOSE | 5 | RL | 15 | 57.34 | 860.1 | 11086 | CLOSE | 2023-02-21 | 2023-02-15 | KW1-7987 | 4 | 2023-02-21 | CLOSE | 2023-05-09 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-03-30 | COMP | 2023-02-27 | 15.00 |  | UCO | AJ table | February | 2023
3 | 2023-02-11 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 6145-60-V00-0156 | WIRE, ELECTRICAL, BLUE, 1 CORE, 2.5 MM ² | 27292 | 2023-02-11 | 2023-02-12 | CLOSE | 6 | RO | 15 | 55.62 | 834.3 | 11086 | CLOSE | 2023-02-21 | 2023-02-15 | KW1-7987 | 5 | 2023-02-21 | CLOSE | 2023-05-09 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-03-30 | COMP | 2023-02-27 | 15.00 |  | UCO | AJ table | February | 2023
3 | 2023-02-15 | 30 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5306-60-V00-0118 | NUT AND BOLT, 1-1/2 X 3/8 INCHES | 27610 | 2023-02-15 | 2023-02-20 | CLOSE | 1 | EA | 300 | 0.85 | 255 | 11608 | CLOSE | 2023-03-23 | 2023-03-07 | KW1-8626 | 1 | 2023-03-27 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-14 | COMP | 2023-03-30 | 300.00 |  | UCO | AJ table | February | 2023
3 | 2023-02-15 | 30 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5940-01-619-8810 | TERMINAL, LUG, 4-16 AWG, BLUE, 0.19 X 0.33 INCHES | 27609 | 2023-02-15 | 2023-02-16 | CLOSE | 1 | EA | 300 | 1.18 | 354 | 11213 | CLOSE | 2023-02-23 | 2023-02-19 | KW1-8050 | 20 | 2023-03-07 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-05-07 | COMP | 2023-03-28 | 300.00 |  | UCO | AJ table | February | 2023
3 | 2023-02-15 | 30 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5975-60-V00-0741 | BOX CONNECTOR, ELECTRICAL (CONDUIT HUB), RIGID, ZINC, 3/4 INCH | 27611 | 2023-02-15 | 2023-05-28 | CLOSE | 1 | EA | 90 | 17.3 | 1557 | 13866 | CLOSE | 2023-05-31 | 2023-06-01 | KW1-9751 | 1 | 2023-05-31 | CLOSE | 2023-11-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-07-15 | COMP | 2023-06-20 | 90.00 |  | UCO | AJ table | February | 2023
3 | 2023-02-15 | 30 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5975-60-V00-0743 | BOX CONNECTOR, ELECTRICAL, CONDUIT, SET SCREW, STEEL, 3/4 INCH | 27611 | 2023-02-15 | 2023-05-28 | CLOSE | 3 | EA | 150 | 3.2 | 480 | 13866 | CLOSE | 2023-05-31 | 2023-06-01 | KW1-9751 | 2 | 2023-05-31 | CLOSE | 2023-11-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-08-15 | COMP | 2023-07-06 | 36.00 |  | UCO | AJ table | February | 2023
3 | 2023-02-15 | 30 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5975-60-V00-0744 | RACEWAY, NONMETALLIC, OPEN SLOT WIRING CABLE, DUCT w/COVER, PVC, 2 X 1 INCHES X 6 FEET | 27611 | 2023-02-15 | 2023-05-28 | CLOSE | 4 | EA | 60 | 11.25 | 675 | 13866 | CLOSE | 2023-05-31 | 2023-06-01 | KW1-9751 | 3 | 2023-05-31 | CLOSE | 2023-11-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-08-15 | COMP | 2023-07-13 | 10.00 |  | UCO | AJ table | February | 2023
3 | 2023-02-15 | 30 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 6145-60-V00-0009 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 10 MM ² | 27609 | 2023-02-15 | 2023-02-16 | CLOSE | 2 | RL | 10 | 206.64 | 2066.4 | 11213 | CLOSE | 2023-02-23 | 2023-02-19 | KW1-8050 | 21 | 2023-03-07 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-04-05 | COMP | 2023-03-11 | 9.00 |  | UCO | AJ table | February | 2023
3 | 2023-02-15 | 30 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5975-60-V00-0812 | CONDUIT, METAL, RIGID IMC, THREADED, STEEL, 3/4 INCH X 3 MTR | 55710 | 2024-02-29 | 2024-03-07 | APPR | 1 | EA | 40 | 25.68 | 1027.2 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | UCO | AJ table | February | 2023
4 | 2023-02-27 | 60 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5650-60-V00-0004 | CHANNEL, STRUCTURAL, C-SHAPE, STEEL, 1-5/8 X 3-5/8 INCHES X 10 FEET | 28446 | 2023-02-27 | 2023-02-27 | CLOSE | 1 | EA | 86 | 4.13 | 355.18 | 11608 | CLOSE | 2023-03-23 | 2023-03-07 | KW1-8626 | 5 | 2023-03-27 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-06 | COMP | 2023-05-02 | 86.00 |  | AJ | AJ table | February | 2023
5 | 2023-03-25 |  | AJ22-0136 | T353 Relocation | 2141524 | 4240-60-V00-0104 | MESH, SAFETY, FLUORESCENT ORANGE, 1 X 50 METER | 30405 | 2023-03-25 | 2023-03-26 | CLOSE | 1 | RO | 10 | 237.6 | 2376 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 1 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-07-03 | 10.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5940-60-V00-0090 | LUG, TERMINAL, ROUND TYPE, COPPER, ONE-HOLE, 25MM² X 10MM | 30462 | 2023-03-26 | 2023-03-26 | CLOSE | 2 | PK | 2 | 9.09 | 18.18 | 13217 | SENT | 2023-05-11 | 2023-05-06 | KW1-9447 | 1 | 2023-05-16 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-16 | COMP | 2023-05-16 | 2.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5975-60-V00-0521 | CLAMP, GROUNDING, BRONZE, 5/8 - 1/2 INCH | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 10 | EA | 4 | 24.98 | 99.92 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 12 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 4.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 9 | RO | 1 | 262.24 | 262.24 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 11 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 1.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 4130-60-V00-0137 | MOUNTING BASE, AIR-CONDITIONER, POLYPROPYLENE, IVORY, 17 X 3 X 5.12 INCHES | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 8 | EA | 2 | 62.94 | 125.88 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 10 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 2.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 4730-60-V00-0594 | C-CLAMP W/ RUBBER, GALVANIZED STEEL, 2 INCHES | 30460 | 2023-03-26 | 2023-03-26 | CLOSE | 5 | EA | 20 | 10.32 | 206.4 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 20 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 20.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 4130-60-V00-0288 | TAPE, WRAP, INSULATION, 3 INCHES X 150 FEET | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 7 | RO | 6 | 32.3 | 193.8 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 9 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 6.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 8030-60-V00-0053 | FOAM, CONSTRUCTION, CREAM, 700ML | 30459 | 2023-03-26 | 2023-03-26 | CLOSE | 1 | EA | 2 | 19.65 | 39.3 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 14 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 2.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5940-60-V00-0083 | LUG, TERMINAL, FORK, INSULATED, YELLOW, 12-10 AWG | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 6 | PG | 1 | 63.77 | 63.77 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 8 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 1.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 30461 | 2023-03-26 | 2023-03-26 | CLOSE | 1 | EA | 4 | 57.7 | 230.8 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 22 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 4.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 5 | RO | 1 | 65.6 | 65.6 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 7 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 1.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5975-00-156-3253 | STRAP, TIE DOWN, ELECTRICAL COMPONE, 13-7/20 INCHES | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 4 | HD | 2 | 18.98 | 37.96 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 6 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 2.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 3 | EA | 10 | 3.5 | 35 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 5 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 10.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5975-60-V00-0504 | UNION, ELECTRICAL CONDUIT, NYLON POLYAMIDE, LONG THREAD, 5-10 MM | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 2 | EA | 10 | 3.33 | 33.3 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 4 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 10.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 4710-60-V00-0110 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 1 | EA | 4 | 19.98 | 79.92 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 3 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-24 | 4.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 4730-60-V00-0833 | COUPLING, PIPE, SCH-40, SOCKET X SOCKET, CPVC, TAN, 20 MM | 30460 | 2023-03-26 | 2023-03-26 | CLOSE | 4 | EA | 10 | 4 | 40 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 19 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-24 | 10.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 30460 | 2023-03-26 | 2023-03-26 | CLOSE | 3 | BX | 2 | 29.94 | 59.88 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 18 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 2.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5305-60-V00-0173 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 30460 | 2023-03-26 | 2023-03-26 | CLOSE | 2 | BX | 2 | 33.8 | 67.6 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 17 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 2.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5305-60-V00-0196 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 3/8 INCHES | 30460 | 2023-03-26 | 2023-03-26 | CLOSE | 1 | BX | 2 | 32.63 | 65.26 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 16 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 2.00 |  | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 6145-60-V00-0119 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 25MM Â² | 30458 | 2023-03-26 |  |  | 1 | M | 100 | [17 empty] | CANCELLED AS PER JUNE | AJ | AJ table | March | 2023
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 6145-60-V00-0088 | CABLE, POWER, ELECTRICAL, WHITE, 7 CORE, 1.5 MM² | 30462 | 2023-03-26 | 2023-03-26 | CLOSE | 1 | RO | 2 | 165.26 | 330.52 | 13383 | CLOSE | 2023-05-09 | 2023-05-10 | KW1-9448 | 1 | 2023-05-09 | APPR | 2023-05-09 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL INC | 2023-05-10 |  |  |  |  | AJ | AJ table | March | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4710-60-V00-0073 | PIPE, PN16, UPVC, GREY, 110 X 8.1 MM X 6 METERS | 31564 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | EA | 1.00 | 184.1 | 184.1 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 1 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 1.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4730-60-V00-0935 | TEE, PIPE, PRESSURE FITTINGS, REDUCTION, SOCKET X SOCKET X SOCKET, PVC, GRAY, 8 X 6 INCHES | 31566 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | EA | 2.00 | 141.65 | 283.3 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 2 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 2.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4730-60-V00-0383 | ELBOW, PIPE, 45 DEGREE, UPVC PLASTIC, GREY, 110 X 131 MILLIMETER | 31568 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | EA | 4.00 | 48.72 | 194.88 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 3 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 4.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4730-60-V00-0978 | FLANGE, PIPE, RING TYPE, PN10, SCH-80, PVC, 200MM | 31568 | 2023-04-13 | 2023-04-15 | CLOSE | 2 | EA | 2.00 | 113.8 | 227.6 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 4 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 2.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4730-60-V00-0904 | BUSHING, PIPE, REDUCER, PVC, GRAY, 8 X 6 INCHES | 31568 | 2023-04-13 | 2023-04-15 | CLOSE | 3 | EA | 4.00 | 45.78 | 183.12 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 5 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 4.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4730-60-V00-0410 | ELBOW, PIPE, PVC, 45°, SOCKET X SOCKET, SCH-80, GRAY, 8 INCHES | 31568 | 2023-04-13 | 2023-04-15 | CLOSE | 4 | EA | 6.00 | 156.96 | 941.76 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 6 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 6.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4710-60-V00-0074 | PIPE, PN16, UPVC, GREY, 200 X 14.7 MM X 6 METERS | 31568 | 2023-04-13 | 2023-04-15 | CLOSE | 5 | EA | 3.00 | 391.09 | 1173.27 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 7 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 3.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4240-60-V00-0151 | TAPE, WARNING, ELECTRIC LINE BELOW, RED, POLYETHYLENE PLASTIC, 6 INCHES X 1000 FEET | 31570 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | CA | 1.00 | 474.8 | 474.8 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 8 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-31 07:00 | COMP | 2023-04-17 | 1.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4240-60-V00-0150 | TAPE, WARNING, UNDERGROUND, CAUTION BURIED WATER LINE BELOW, BLUE & BLACK, 6 INCHES X 1000 FEET | 31570 | 2023-04-13 | 2023-04-15 | CLOSE | 2 | RL | 1.00 | 196.55 | 196.55 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 9 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-31 07:00 | COMP | 2023-04-17 | 1.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4730-60-V00-0285 | COUPLING, PIPE, DOUBLE SOCKET, PLASTIC, UPVC, GREY, 110 X 131 MILLIMETER | 31570 | 2023-04-13 | 2023-04-15 | CLOSE | 3 | EA | 4.00 | 10 | 40 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 10 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 4.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4730-60-V00-0903 | BUSHING, PIPE, REDUCER, PVC, GRAY, 6 X 4 INCHES | 31570 | 2023-04-13 | 2023-04-15 | CLOSE | 4 | EA | 4.00 | 20.3 | 81.2 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 11 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 4.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4730-60-V00-0827 | COUPLING, PVC, PN10, 5-7/8 X 8 INCHES | 31570 | 2023-04-13 | 2023-04-15 | CLOSE | 5 | EA | 4.00 | 37.13 | 148.52 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 12 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 4.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4730-60-V00-1652 | CAP, PIPE, END, UPVC, GRAY, 200 MM | 31585 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | EA | 2.00 | 117.62 | 235.24 | 12768 | CLOSE | 2023-04-20 | 2023-04-17 | KW1-9125 | 1 | 2023-04-20 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-04 | COMP | 2023-04-25 | 2.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 8135-60-V00-0003 | PLASTIC SHEET, POLYETHYLENE, CLEAR, 6 MIL, 32 X 100 FEET | 31586 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | RO | 1.00 | 348.91 | 348.91 | 12768 | CLOSE | 2023-04-20 | 2023-04-17 | KW1-9125 | 3 | 2023-04-20 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-04 | COMP | 2023-04-25 | 1.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 5640-60-V00-0057 | BACKER ROD, GAPS, CLOSED-CELL POLYETHYLENE, GRAY, 5/8 INCH X 20 FEET | 31587 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | EA | 5.00 | 20.19 | 100.95 | 12768 | CLOSE | 2023-04-20 | 2023-04-17 | KW1-9125 | 5 | 2023-04-20 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-04 | COMP | 2023-04-25 | 5.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 5530-60-V00-0010 | PLYWOOD, CONSTRUCTION, MARINE GRADE, 3/4 INCH X 8 X 4 FEET | 31588 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | SH | 6.00 | 60.31 | 361.86 | 12927 | CLOSE | 2023-05-16 | 2023-04-26 | KW1-9235 | 14 | 2023-04-27 | CLOSE | 2023-08-26 | Kannoth, Shajee -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-07 | COMP | 2023-05-02 | 6.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 5660-60-V00-0015 | TIE WIRE, ANNEALED, STEEL, 9 GAGE, 100 LB | 31589 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | CL | 1.00 | 855.11 | 855.11 | 12768 | CLOSE | 2023-04-20 | 2023-04-17 | KW1-9125 | 7 | 2023-04-20 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-04 | COMP | 2023-04-29 | 1.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 5610-60-V00-0018 | CONCRETE MIX, GRAY, 4000 PSI, 80 LBS | 31590 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | EA | 80.00 | 15.66 | 1252.8 | 12768 | CLOSE | 2023-04-20 | 2023-04-17 | KW1-9125 | 9 | 2023-04-20 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-04 | COMP | 2023-04-25 | 20.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4240-60-V00-0104 | MESH, SAFETY, FLUORESCENT ORANGE, 1 X 50 METER | 31591 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | RO | 3.00 | 237.6 | 712.8 | 12768 | CLOSE | 2023-04-20 | 2023-04-17 | KW1-9125 | 11 | 2023-04-20 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-04 | COMP | 2023-04-25 | 3.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 8135-60-V00-0024 | FIBREBOARD, SOLID, BITUMEN, BLACK, 2400 X 100 X 9.5 MM | 31591 | 2023-04-13 | 2023-04-15 | CLOSE | 2 | EA | 21.00 | 8.97 | 188.37 | 12768 | CLOSE | 2023-04-20 | 2023-04-17 | KW1-9125 | 12 | 2023-04-20 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-04 | COMP | 2023-05-03 | 21.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 5620-60-V00-0012 | CONCRETE SPACER (COVER BLOCK), w/TIE-WIRE ATTACHMENT HOLE, 65/75 MM | 31591 | 2023-04-13 | 2023-04-15 | CLOSE | 3 | PG | 1.00 | 634.83 | 634.83 | 12768 | CLOSE | 2023-04-20 | 2023-04-17 | KW1-9125 | 13 | 2023-04-20 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-04 | COMP | 2023-04-25 | 1.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 8030-60-V00-0005 | SEALING COMPOUND, TWO PART POLYSULPHIDE, GREY, 2 LITRES | 31591 | 2023-04-13 | 2023-04-15 | CLOSE | 4 | PG | 4.00 | 121.08 | 484.32 | 12768 | CLOSE | 2023-04-20 | 2023-04-17 | KW1-9125 | 14 | 2023-04-20 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-06-20 | COMP | 2023-05-03 | 4.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-17 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 8030-60-V00-0062 | CLEANER, PIPE, PURLE, 16 OUNCES | 31822 | 2023-04-17 | 2023-04-19 | CLOSE | 1 | CN | 10 | 22.98 | 229.8 | 12883 | INPRG | 2023-04-26 | 2023-04-25 | KW1-9220 | 10 | 2023-04-26 | CLOSE | 2023-08-19 | Kannoth, Shajee -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-07 | COMP | 2023-05-01 | 10.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-17 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 7930-60-V00-0047 | CLEANER, CLEAR, 16 FL OZ | 31822 | 2023-04-17 | 2023-04-19 | CLOSE | 2 | CN | 15 | 26.31 | 394.65 | 12883 | INPRG | 2023-04-26 | 2023-04-25 | KW1-9220 | 11 | 2023-04-26 | CLOSE | 2023-08-19 | Kannoth, Shajee -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-07 | COMP | 2023-05-01 | 15.00 |  | AJ | AJ table | April | 2023
6 | 2023-04-17 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 8040-60-V00-0051 | ADHESIVE, CEMENT, PVC, WET 'R DRY, MEDIUM BODY, AQUA BLUE, 32 OZ. | 31822 | 2023-04-17 | 2023-04-19 | CLOSE | 3 | EA | 8 | 87.41 | 699.28 | 12883 | INPRG | 2023-04-26 | 2023-04-25 | KW1-9220 | 12 | 2023-04-26 | CLOSE | 2023-08-19 | Kannoth, Shajee -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-07 | COMP | 2023-05-01 | 8.00 |  | AJ | AJ table | April | 2023
7 | 2023-04-29 | 80 | AJ22-0044 | T357 Relocation | 2141526 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 32769 | 2023-04-29 | 2023-05-03 | CLOSE | 2 | BX | 2 | 51.5 | 103 | 13233 | CLOSE | 2023-05-07 | 2023-05-06 | KW1-9404 | 4 | 2023-05-07 | CLOSE | 2023-09-24 | Reghuraman, Karthik -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-14 07:00 | COMP | 2023-05-11 | 2.00 |  | AJ | AJ table | April | 2023
8 | 2023-04-29 | 80 | AJ22-0135 | T357 Relocation | 2141526 | 5640-60-V00-0041 | PANEL, CEILING (ACOUSTICAL TILE), MINERAL FIBER, WHITE, 24 X 24 X 3/4 INCHES | 32772 | 2023-04-29 | 2023-05-03 | CLOSE | 1 | EA | 70 | 9.4 | 658 | 13233 | CLOSE | 2023-05-07 | 2023-05-06 | KW1-9404 | 7 | 2023-05-07 | CLOSE | 2023-09-24 | Reghuraman, Karthik -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-14 07:00 | COMP | 2023-05-11 | 70.00 |  | AJ | AJ table | April | 2023
8 | 2023-04-29 | 80 | AJ22-0135 | T357 Relocation | 2141526 | 5305-60-V00-0009 | SCREW, SELF TAPPING, STEEL, 5/16 X 6 INCHES | 32771 | 2023-04-29 | 2023-05-03 | CLOSE | 1 | PG | 2 | 53.98 | 107.96 | 13233 | CLOSE | 2023-05-07 | 2023-05-06 | KW1-9404 | 6 | 2023-05-07 | CLOSE | 2023-09-24 | Reghuraman, Karthik -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-14 07:00 | COMP | 2023-05-11 | 2.00 |  | AJ | AJ table | April | 2023
8 | 2023-04-29 | 80 | AJ22-0135 | T357 Relocation | 2141526 | 5305-60-V00-0015 | SCREW, SELF DRILLING, HEX WASHER, STEEL, 1/4 -14 X 3/4 INCHES | 32773 | 2023-04-29 | 2023-05-03 | CLOSE | 1 | EA | 50 | 0.31 | 15.5 | 13233 | CLOSE | 2023-05-07 | 2023-05-06 | KW1-9404 | 10 | 2023-05-07 | CLOSE | 2023-09-24 | Reghuraman, Karthik -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-14 07:00 | COMP | 2023-05-11 | 50.00 |  | AJ | AJ table | April | 2023
8 | 2023-04-29 | 80 | AJ22-0135 | T357 Relocation | 2141526 | 5680-60-V00-0006 | GRID, CEILING, TEE, WHITE, 24 INCHES | 32772 | 2023-04-29 | 2023-05-03 |  | 1 | EA | 70 | [6 empty] | KW1-9404 | 7 | [6 empty] | COMP | 2023-05-11 | 70 |  | AJ | AJ table | April | 2023
8 | 2023-04-29 | 80 | AJ22-0135 | T357 Relocation | 2141526 | 5305-60-V00-0199 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 -1/2 INCHES | 32769 | 2023-04-29 | 2023-05-03 | CLOSE | 1 | BX | 10 | 27.03 | 270.3 | 13233 | CLOSE | 2023-05-07 | 2023-05-06 | KW1-9404 | 3 | 2023-05-07 | CLOSE | 2023-09-24 | Reghuraman, Karthik -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-14 07:00 | COMP | 2023-05-11 | 10.00 |  | AJ | AJ table | April | 2023
9 | 2023-04-29 | 80 | AJ22-0205 | T357 Relocation | 2141526 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 32772 | 2023-04-29 | 2023-05-03 | CLOSE | 3 | EA | 2 | 13.73 | 27.46 | 13233 | CLOSE | 2023-05-07 | 2023-05-06 | KW1-9404 | 9 | 2023-05-07 | CLOSE | 2023-09-24 | Reghuraman, Karthik -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-14 07:00 | COMP | 2023-05-11 | 2.00 |  | AJ | AJ table | April | 2023
10 | 2023-05-09 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 6625-60-V00-0094 | METER, w/NEMA, CUSTOM ENCLOSURE, 4X PM5560 | 33443 | 2023-05-09 |  | CAN | 1 | EA | 54 | 6817 | 368118 | [16 empty] | UCO | AJ table | May | 2023
11 | 2023-05-10 |  | AJ22-0417 | Z1 Pool Water Leak Assessment | 5171089 | 5975-60-V00-0530 | CONDUIT, RIGID, GALVANIZED STEEL, THREADED, 3/4 INCH X 10 FEET | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 3 | EA | 60 | 63.27 | 3796.2 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 3 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-10 | COMP | 2023-06-13 | 60.00 |  | AJ | AJ table | May | 2023
12 | 2023-05-10 |  | AJ22-0536 | T357 Relocation | 5171089 | 5995-60-V00-0132 | STRAP, TIE DOWN (CABLE TIE), NYLON 6/6, BLACK, 7 INCHES | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 5 | PG | 10 | 15.48 | 154.8 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 5 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-10 | COMP | 2023-06-08 | 10.00 |  | AJ | AJ table | May | 2023
13 | 2023-05-10 |  | AJ23-0193 | 43 Electrical Meter Installation | 5171089 | 5975-60-V00-0090 | COUPLING, ELECTRICAL CONDUIT, COMPRESSION, ZINC DIE CAST, 3/4 INCH | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 2 | EA | 30 | 19.98 | 599.4 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 2 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-07-25 | COMP | 2023-07-25 | 30.00 |  | AJ | AJ table | May | 2023
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 7 | RL | 6 | 65.6 | 393.6 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 7 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-10 | COMP | 2023-06-06 | 6.00 |  | UCO | AJ table | May | 2023
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 6145-60-V00-0153 | WIRE, ELECTRICAL, YELLOW, 1 CORE, 2.5 MM² | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 8 | RL | 15 | 59.44 | 891.6 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 8 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-10 | COMP | 2023-06-06 | 15.00 |  | UCO | AJ table | May | 2023
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 6145-60-V00-0156 | WIRE, ELECTRICAL, BLUE, 1 CORE, 2.5 MM ² | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 9 | RO | 15 | 64.42 | 966.3 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 9 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-10 | COMP | 2023-06-06 | 15.00 |  | UCO | AJ table | May | 2023
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 6145-60-V00-0151 | WIRE, ELECTRICAL, BLACK, 1 CORE, 2.5 mm² | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 10 | RO | 15 | 65.6 | 984 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 10 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-10 | COMP | 2023-06-06 | 15.00 |  | UCO | AJ table | May | 2023
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 6145-60-V00-0152 | WIRE, ELECTRICAL, RED, 1 CORE, 2.5 MM ² | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 11 | RL | 15 | 65.6 | 984 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 11 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-10 | COMP | 2023-06-06 | 15.00 |  | UCO | AJ table | May | 2023
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 5975-60-V00-0036 | PROTECTOR, CABLE, SPIRAL WRAPPING BAND, w/ CLIP, POLYETHYLENE, BLACK, 15 MM X 1.5 METER | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 12 | RO | 100 | 16.48 | 1648 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 12 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-07-25 | COMP | 2023-07-25 | 100.00 |  | UCO | AJ table | May | 2023
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 5975-60-V00-0741 | BOX CONNECTOR, ELECTRICAL (CONDUIT HUB), RIGID, ZINC, 3/4 INCH | 33484 | 2023-05-10 | 2023-05-28 | CLOSE | 1 | EA | 90 | 56.4 | 5076 | 13619 | CLOSE | 2023-05-29 | 2023-05-23 | KW1-9710 | 1 | 2023-05-29 | APPR | 2023-05-29 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-07-24 | COMP | 2023-06-14 | 90.00 |  | UCO | AJ table | May | 2023
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 5975-60-V00-0743 | BOX CONNECTOR, ELECTRICAL, CONDUIT, SET SCREW, STEEL, 3/4 INCH | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 1 | EA | 150 | 13.29 | 1993.5 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 1 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-26 | COMP | 2023-07-25 | 5.00 |  | UCO | AJ table | May | 2023
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 5940-01-619-8810 | TERMINAL, LUG, 4-16 AWG, BLUE, 0.19 X 0.33 INCHES | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 4 | EA | 25 | 1.5 | 37.5 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 4 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-07-25 | COMP | 2023-08-06 | 25.00 |  | UCO | AJ table | May | 2023
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 6145-60-V00-0009 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 10 MM ² | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 6 | RL | 10 | 231.6 | 2316 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 6 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-10 | COMP | 2023-06-07 | 10.00 |  | UCO | AJ table | May | 2023
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 6625-60-V00-0094 | METER, w/NEMA, CUSTOM ENCLOSURE, 4X PM5560 | 33442 | 2023-05-10 |  | CAN | 1 | EA | 60 | 6817 | 409020 | [16 empty] | UCO | AJ table | May | 2023
14 | 2023-05-10 | 40 | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 5975-60-V00-0812 | CONDUIT, METAL, RIGID IMC, THREADED, STEEL, 3/4 INCH X 3 MTR | 55709 | 2024-02-29 | 2024-03-09 | CLOSE | 1 | EA | 40 | 25.68 | 1027.2 | 22248 | CLOSE | 2024-03-10 |  | KW1-15518 | 1 | 2024-03-10 | APPR | 2024-03-10 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-04-30 |  |  |  |  | UCO | AJ table | May | 2023
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 5975-60-V00-0744 | RACEWAY, NONMETALLIC, OPEN SLOT WIRING CABLE, DUCT w/COVER, PVC, 2 X 1 INCHES X 6 FEET | 33484 | 2023-05-10 | 2023-05-28 | CLOSE | 2 | EA | 60 | 40.1 | 2406 | 13619 | CLOSE | 2023-05-29 | 2023-05-23 | KW1-9710 | 2 | 2023-05-29 | APPR | 2023-05-29 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-31 | COMP | 2023-12-22 | 40.00 |  | UCO | AJ table | May | 2023
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0521 | CLAMP, GROUNDING, BRONZE, 5/8 - 1/2 INCH | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 1 | EA | 10 | 24.98 | 249.8 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 1 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 10.00 |  | AJ | AJ table | May | 2023
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0349 | STRAP, TIE DOWN, ELECTRICAL COMPONENT, (CABLE TIE) NYLON, BLACK, 360.68 X 4.83 MM | 33620 | 2023-05-13 | 2023-05-13 | CLOSE | 1 | PG | 1 | 104.2 | 104.2 | 13490 | INPRG | 2023-05-19 | 2023-05-16 | KW1-9546 | 5 | 2023-05-17 | CLOSE | 2023-09-09 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-07-12 | COMP | 2023-05-30 | 1.00 |  | AJ | AJ table | May | 2023
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 2 | RO | 1 | 13.65 | 13.65 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 2 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 1.00 |  | AJ | AJ table | May | 2023
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-01-613-4740 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 3 | PG | 1 | 62.44 | 62.44 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 3 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 1.00 |  | AJ | AJ table | May | 2023
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-01-015-5060 | TAPE, INSULATION, ELECTRICAL, BLUE, 3/4 X 792 INCHES | 33620 | 2023-05-13 | 2023-05-13 | CLOSE | 2 | RO | 1 | 9.5 | 9.5 | 13490 | INPRG | 2023-05-19 | 2023-05-16 | KW1-9546 | 6 | 2023-05-17 | CLOSE | 2023-09-09 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-31 | COMP | 2023-05-21 | 1.00 |  | AJ | AJ table | May | 2023
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-01-174-5651 | TAPE, INSULATION, ELECTRICAL, YELLOW, 3/4 X 792 INCHES | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 4 | RO | 1 | 9.99 | 9.99 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 4 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-06-01 | 1.00 |  | AJ | AJ table | May | 2023
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-01-013-9369 | TAPE, INSULATION, ELECTRICAL, RED, 3/4 X 792 INCHES | 33621 | 2023-05-13 | 2023-05-13 | CLOSE | 1 | RO | 1 | 11 | 11 | 13582 | CLOSE | 2023-05-25 | 2023-05-21 | KW1-9671 | 23 | 2023-05-27 | CLOSE | 2023-09-24 | Bharadwajan, Sajan - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-31 | COMP | 2023-05-30 | 1.00 |  | AJ | AJ table | May | 2023
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 5 | EA | 3 | 351.32 | 1053.96 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 5 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 3.00 |  | AJ | AJ table | May | 2023
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0504 | UNION, ELECTRICAL CONDUIT, NYLON POLYAMIDE, LONG THREAD, 5-10 MM | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 6 | EA | 10 | 3.33 | 33.3 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 6 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 10.00 |  | AJ | AJ table | May | 2023
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0429 | LUG, TERMINAL, ROUND TYPE, ONE-HOLE, 16MM²-M6 | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 7 | PG | 1 | 64.1 | 64.1 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 7 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-15 | COMP | 2023-08-01 | 1.00 |  | AJ | AJ table | May | 2023
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5940-60-V00-0026 | TERMINAL, LUG, TUBULAR, TIN PLATED, 8.4 MM X 50 MM² | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 8 | EA | 20 | 3.16 | 63.2 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 8 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 20.00 |  | AJ | AJ table | May | 2023
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 9 | RL | 1 | 262.24 | 262.24 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 9 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-06-01 | 1.00 |  | AJ | AJ table | May | 2023
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0122 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 50 MM² | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 10 | MR | 120 | 45.29 | 5434.8 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 10 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-06-01 | 120.00 |  | AJ | AJ table | May | 2023
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0516 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, BRASS, CW, 50S | 33619 | 2023-05-13 | 2023-05-13 | CLOSE | 1 | EA | 5 | 43.29 | 216.45 | 13582 | CLOSE | 2023-05-25 | 2023-05-21 | KW1-9671 | 22 | 2023-05-27 | CLOSE | 2023-09-24 | Bharadwajan, Sajan - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-31 | COMP | 2023-05-30 | 5.00 |  | AJ | AJ table | May | 2023
15 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 5 | EA | 3 | 351.32 | 1053.96 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 5 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 3.00 |  | AJ | AJ table | August | 2023
15 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0504 | UNION, ELECTRICAL CONDUIT, NYLON POLYAMIDE, LONG THREAD, 5-10 MM | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 6 | EA | 10 | 3.33 | 33.3 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 6 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 10.00 |  | AJ | AJ table | August | 2023
15 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0429 | LUG, TERMINAL, ROUND TYPE, ONE-HOLE, 16MM²-M6 | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 7 | PG | 1 | 64.1 | 64.1 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 7 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-15 | COMP | 2023-08-01 | 1.00 |  | AJ | AJ table | August | 2023
15 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5940-60-V00-0026 | TERMINAL, LUG, TUBULAR, TIN PLATED, 8.4 MM X 50 MM² | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 8 | EA | 20 | 3.16 | 63.2 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 8 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 20.00 |  | AJ | AJ table | August | 2023
15 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 9 | RL | 1 | 262.24 | 262.24 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 9 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-06-01 | 1.00 |  | AJ | AJ table | August | 2023
15 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0122 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 50 MM² | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 10 | MR | 120 | 45.29 | 5434.8 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 10 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-06-01 | 120.00 |  | AJ | AJ table | August | 2023
16 | 2023-05-16 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 5306-60-V00-0118 | NUT AND BOLT, 1-1/2 X 3/8 INCHES | 33647 | 2023-05-16 | 2023-05-16 | CLOSE | 1 | EA | 300 | 0.85 | 255 | 13569 | CLOSE | 2023-05-23 | 2023-05-21 | KW1-9646 | 14 | 2023-05-23 | CLOSE | 2023-12-02 | Kannoth, Shajee -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-31 | COMP | 2023-05-28 | 300.00 |  | UCO | AJ table | May | 2023
17 | 2023-05-27 | 50 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5510-60-V00-0028 | PLYWOOD, CONSTRUCTION, MARINE GRADE, 1/2 INCH X 8 X 4 FEET | 34457 | 2023-05-27 | 2023-06-01 | CLOSE | 1 | SH | 15 | 30.7 | 460.5 | 13892 | SENT | 2023-06-08 | 2023-06-05 | KW1-9904 | 4 | 2023-06-08 | CLOSE | 2023-11-19 | Kannoth, Shajee -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-06-16 | COMP | 2023-06-11 | 15.00 |  | AJ | AJ table | May | 2023
17 | 2023-05-27 | 50 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8030-60-V00-0008 | SEALING COMPOUND, GUTTER & SEAM, WHITE, 10 OZ. | 34501 | 2023-05-27 | 2023-05-30 | CLOSE | 1 | CA | 2 | 23.1 | 46.2 | 13872 | CLOSE | 2023-06-08 | 2023-06-01 | KW1-9836 | 8 | 2023-06-06 | CLOSE | 2023-11-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-06-13 07:00 | COMP | 2023-06-10 | 2.00 |  | AJ | AJ table | May | 2023
17 | 2023-06-06 | 100 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8030-60-V00-0008 | SEALING COMPOUND, GUTTER & SEAM, WHITE, 10 OZ | 34501, 35130 | 2023-06-06 | 2023-06-07 |  | 1 | CQ | 26 | [6 empty] | KW1-10029 | 1 | [5 empty] | 2023-06-28 | COMP | 2023-06-27 | 26 |  | AJ | AJ table | June | 2023
17 | 2023-06-07 | 60 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0065 | INSULATION BOARD, THERMAL, XPS FOAM (STYROFOAM), BLUE, 1250 X 600 X 50 MM | 35132 | 2023-06-07 | 2023-06-20 | CLOSE | 1 | PK | 50 | 98.3 | 4915 | 14349 | CLOSE | 2023-06-22 | 2023-06-21 | KW1-10030 | 1 | 2023-06-22 | CLOSE | 2023-07-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | COMMERCIAL UNITED GINCO EST. | 2023-06-29 07:00 | COMP | 2023-07-03 | 50.00 |  | AJ | AJ table | June | 2023
17 | 2023-06-07 | 20,60,100 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5530-60-V00-0003 | PLYWOOD, CONSTRUCTION, MARINE GRADE, 3/4 INCH X 8 X 4 FEET | 35133, 35131, 35146 | 2023-06-07 | 2023-06-21 |  | 1 | EA | 210 | [6 empty] | KW1-10030 | 5 | [5 empty] | 2023-07-15 | COMP | 2023-07-06 | 210 |  | AJ | AJ table | June | 2023
17 | 2023-07-09 | 110 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 36925 | 2023-07-09 | 2023-07-13 | CLOSE | 1 | BX | 50 | 27.96 | 1398 | 15257 | CLOSE | 2023-08-02 | 2023-07-26 | KW1-10683 | 1 | 2023-08-03 | CLOSE | 2024-01-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-08-12 | COMP | 2023-08-07 | 50.00 |  | AJ | AJ table | July | 2023
18 | 2023-07-13 |  | AJ23-0467 | Z2 B506 Additional Power for AVIS System | 6185682 | PANEL | FABRICATION, PANEL MAIN BREAKER-100A 3 POLE MCCB (SUB BREAKERS 30MA 20A RCBO (8EA) 8 WAYS INDOOR DB PANEL | 48307 | 2023-07-13 | 2023-07-13 | [22 empty] | AJ | AJ table | July | 2023
19 | 2023-07-23 | 50 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-05-V00-0005 | PANEL, DRYWALL, WALL BOARD, REGULAR, MOLD-GUARD, 1/2 INCH X 4 X 8 FEET | 37969 | 2023-07-23 | 2023-07-24 | CLOSE | 1 | EA | 10 | 28.14 | 281.4 | 15285 | CLOSE | 2023-07-30 | 2023-07-27 | KW1-10628 | 8 | 2023-07-30 | CLOSE | 2023-11-05 | Kandankara, Thomas -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-08-12 | COMP | 2023-08-03 | 10.00 |  | AJ | AJ table | July | 2023
19 | 2023-07-23 | 50 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0048 | DRYWALL SHEET, (GYPSUM BOARD), 4 X 8 FEET X 1/2 INCH | 37970 | 2023-07-23 | 2023-07-23 | CLOSE | 1 | EA | 180 | 19.31 | 3475.8 | 15265 | CLOSE | 2023-07-27 | 2023-07-26 | KW1-10539 | 3 | 2023-07-27 | CLOSE | 2023-11-05 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-08-03 | COMP | 2023-07-29 | 180.00 |  | AJ | AJ table | July | 2023
20 | 2023-08-01 |  | AJ23-0467 | Z5 TI Repairs 5620T | 5857174 | PANEL | FABRICATION PANEL, DB PANEL INCOMER 63A 240V/415V-63A (SEE ATTACHED SUBMITTAL) | 49007 | 2023-08-01 | 2023-08-01 | [22 empty] | AJ | AJ table | August | 2023
20 | 2023-08-01 |  | AJ23-0467 | Replace The Senior Pods T6028 Electrical Panel | 6236594 | PANEL | FABRICATION PANEL, MSB (MAIN SWITCH BOARD ) 415/240V,3PH,4W,50HZ, 1600A (SEE ATTACHED SUBMITTAL | 49280 | 2023-08-01 | 2023-08-10 | [22 empty] | AJ | AJ table | August | 2023
21 | 2023-08-02 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0041 | PANEL, CEILING (ACOUSTICAL TILE), MINERAL FIBER, WHITE, 24 X 24 X 3/4 INCHES | 38834 | 2023-08-02 | 2023-08-07 | CLOSE | 1 | EA | 500 | 8.99 | 4495 | 15672 | CLOSE | 2023-08-12 | 2023-08-10 | KW1-10892 | 1 | 2023-08-12 | CLOSE | 2023-11-19 | Santhumayor, Santhosh - Vectrus - No Export | KASAR MARJAN CONTRACTING CO. | 2023-08-19 | COMP | 2023-08-16 | 500.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-02 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5670-60-V00-0026 | WALL ANGLE / GRID, CEILING, TEE, GALVANIZED STEEL, WHITE, 12 FEET | 38833 | 2023-08-02 | 2023-08-07 | CLOSE | 2 | EA | 30 | 18.48 | 554.4 | 15670 | CLOSE | 2023-08-12 | 2023-08-10 | KW1-10890 | 27 | 2023-08-12 | APPR | 2023-08-12 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-08-19 | COMP | 2023-08-16 | 30.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-02 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5680-60-V00-0006 | GRID, CEILING, TEE, WHITE, 24 INCHES | 38833 | 2023-08-02 | 2023-08-07 | CLOSE | 3 | EA | 500 | 4.33 | 2165 | 15670 | CLOSE | 2023-08-12 | 2023-08-10 | KW1-10890 | 28 | 2023-08-12 | APPR | 2023-08-12 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-08-19 | COMP | 2023-08-16 | 500.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-02 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5680-60-V00-0007 | GRID, CEILING, T-RUNNER, WHITE, 12 FEET | 38833 | 2023-08-02 | 2023-08-07 | CLOSE | 1 | EA | 50 | 19.15 | 957.5 | 15670 | CLOSE | 2023-08-12 | 2023-08-10 | KW1-10890 | 26 | 2023-08-12 | APPR | 2023-08-12 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-08-19 | COMP | 2023-08-16 | 50.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5305-60-V00-0196 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 3/8 INCHES | 38837 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | BX | 5 | 32.63 | 163.15 | 15618 | CLOSE | 2023-08-09 | 2023-08-08 | KW1-10826 | 2 | 2023-08-10 | CLOSE | 2023-11-25 | Santhumayor, Santhosh - Vectrus - No Export | KASAR MARJAN CONTRACTING CO. | 2023-08-16 | COMP | 2023-08-14 | 5.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5305-60-V00-0223 | SCREW, TAPPING, FLAT HEAD, PHILIPS, STEEL, #8 X 1-1/4 INCHES | 38844 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | BX | 4 | 53.61 | 214.44 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 6 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-17 | COMP | 2023-08-15 | 4.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5340-60-V00-0141 | DOORSTOP, FLOOR MOUNT, BRASS, 1-3/4 X 1-1/4 INCHES | 38847 | 2023-08-05 | 2023-08-06 | CLOSE | 4 | EA | 16 | 13.65 | 218.4 | 15621 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10866 | 7 | 2023-08-10 | APPR | 2023-08-10 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-09-07 | COMP | 2023-08-15 | 16.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5340-60-V00-0169 | LOCK SET, MORTISE, RIM EXIT DEVICE, KEY OUTSIDE UNLOCKS/LOCKS TRIM | 39068, 39071 | 2023-08-05 | 2023-08-06 |  | 1 | EA | 4 | [6 empty] | KW1-10818 | 1 | [5 empty] | 2023-08-22 | COMP | 2023-08-14 | 4 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5340-60-V00-0267 | COVER STRIP, DRIP, RAIN GUARD, ALUMINUM, 2-1/2 X 1-1/2 INCHES | 38842 | 2023-08-05 | 2023-08-06 | CLOSE | 2 | FT | 50 | 21.98 | 1099 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 3 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-09-21 | COMP | 2023-09-04 | 50.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5340-60-V00-0457 | LOCK SET, DOOR, CYLINDRICAL, w/ KNOB, 5-PIN, 1-3/8 X 3/4 INCHES | 38841 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | ST | 17 | 64.3 | 1093.1 | 15618 | CLOSE | 2023-08-09 | 2023-08-08 | KW1-10826 | 7 | 2023-08-10 | CLOSE | 2023-11-25 | Santhumayor, Santhosh - Vectrus - No Export | KASAR MARJAN CONTRACTING CO. | 2023-08-16 | COMP | 2023-08-14 | 17.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5340-60-V00-0476 | HINGE, DOOR, STAINLESS STEEL, 2.5 MM X 3-1/2 X 3 INCHES | 38844 | 2023-08-05 | 2023-08-06 | CLOSE | 2 | EA | 51 | 30.97 | 1579.47 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 7 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-17 | COMP | 2023-08-15 | 51.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5340-60-V00-0491 | STOPPER, DOOR, RUBBER, 2 INCHES | 38840 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | EA | 21 | 10.32 | 216.72 | 15618 | CLOSE | 2023-08-09 | 2023-08-08 | KW1-10826 | 6 | 2023-08-10 | CLOSE | 2023-11-25 | Santhumayor, Santhosh - Vectrus - No Export | KASAR MARJAN CONTRACTING CO. | 2023-08-16 | COMP | 2023-08-14 | 21.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0005 | WEATHER STRIP, THRESHOLD, ALUMINUM, 3.2 X 6.4 X 12.7 X 127.0 MM | 38846 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | EA | 4 | 42.6 | 170.4 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 10 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-09-28 | COMP | 2023-09-04 | 4.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0035 | WEATHER STRIP, DOOR, W/BRUSH, 2 X 36 INCHES | 38844 | 2023-08-05 | 2023-08-06 | CLOSE | 4 | EA | 4 | 30.47 | 121.88 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 9 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-17 | COMP | 2023-08-15 | 4.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0036 | WEATHER STRIP, FLUTE TOP, ALUMINIUM, 16 FEET X 1-1/2 INCHES | 38847 | 2023-08-05 | 2023-08-06 | CLOSE | 3 | EA | 5 | 23.39 | 116.95 | 15621 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10866 | 6 | 2023-08-10 | APPR | 2023-08-10 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-24 | COMP | 2023-08-15 | 5.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0066 | TAPE, ROOF SEAL, BLACK, 65MIL X 6 INCH X 25 FEET | 38847 | 2023-08-05 | 2023-08-06 | CLOSE | 2 | RL | 20 | 99.7 | 1994 | 15621 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10866 | 5 | 2023-08-10 | APPR | 2023-08-10 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-10-11 | COMP | 2023-10-11 | 20.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5660-60-V00-0045 | WIRE, STEEL, GALVANIZED, 28 GAGE, 100 FEET | 38844 | 2023-08-05 | 2023-08-06 | CLOSE | 3 | EA | 20 | 58.28 | 1165.6 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 8 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-17 | COMP | 2023-08-15 | 20.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 7230-60-V00-0009 | VENETIAN BLIND (WINDOW BLIND), VERTICAL, VINYL, CREAM/BEIGE, 50 X 50 INCHES | 39069 | 2023-08-05 | 2023-08-16 | CLOSE | 1 | EA | 10 | 49.5 | 495 | 15927 | CLOSE | 2023-08-22 | 2023-08-20 | KW1-11107 | 18 | 2023-08-23 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2023-09-10 | COMP | 2023-09-09 | 1.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GL | 38845 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | GL | 5 | 228.5 | 1142.5 | 15621 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10866 | 1 | 2023-08-10 | APPR | 2023-08-10 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-24 | COMP | 2023-08-17 | 3.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8010-60-V00-0006 | PAINT, LATEX, MATT, OFF-WHITE, 3.2 LITER | 38838 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | CN | 30 | 44.16 | 1324.8 | 15618 | CLOSE | 2023-08-09 | 2023-08-08 | KW1-10826 | 4 | 2023-08-10 | CLOSE | 2023-11-25 | Santhumayor, Santhosh - Vectrus - No Export | KASAR MARJAN CONTRACTING CO. | 2023-08-16 | COMP | 2023-08-19 | 30.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8010-60-V00-0028 | PAINT, ENAMEL, GLOSS, DESERT SAND, 3.6 LITER | 38842 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | CN | 26 | 39.96 | 1038.96 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 2 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-21 | COMP | 2023-08-19 | 26.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8010-60-V00-0053 | PAINT, LATEX, MATT, BROWN, 3.2 AND 3.6 LITERS | 38932 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | CN | 7 | 41.25 | 288.75 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 11 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-31 | COMP | 2023-08-27 | 7.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8010-60-V00-0089 | PRIMER, PAINT, LATEX, INTERIOR, WATERBASED, WHITE, 5 GALLON | 39066 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | CN | 6 | 41.63 | 249.78 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 12 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-21 | COMP | 2023-08-17 | 6.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8010-60-V00-0124 | PRIMER, RED OXIDE, OIL BASED, RED, 1 GL | 38843 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | CN | 5 | 27.64 | 138.2 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 4 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-21 | COMP | 2023-08-17 | 5.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8030-01-075-1156 | CAULKING COMPOUND, CARTRIDGE, WHITE, 10 OZ | 39067 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | EA | 72 | 3.27 | 235.44 | 15618 | CLOSE | 2023-08-09 | 2023-08-08 | KW1-10826 | 8 | 2023-08-10 | CLOSE | 2023-11-25 | Santhumayor, Santhosh - Vectrus - No Export | KASAR MARJAN CONTRACTING CO. | 2023-10-04 | COMP | 2023-08-22 | 72.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8030-60-V00-0052 | PUTTY, ALL PURPOSE, LIGHT GRAY, 3.43 KG | 38845 | 2023-08-05 | 2023-08-06 | CLOSE | 3 | CN | 3 | 125.2 | 375.6 | 15621 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10866 | 3 | 2023-08-10 | APPR | 2023-08-10 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-24 | COMP | 2023-08-17 | 3.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8030-60-V00-0053 | FOAM, CONSTRUCTION, CREAM, 700ML | 38837 | 2023-08-05 | 2023-08-06 | CLOSE | 2 | CN | 7 | 19.65 | 137.55 | 15618 | CLOSE | 2023-08-09 | 2023-08-08 | KW1-10826 | 3 | 2023-08-10 | CLOSE | 2023-11-25 | Santhumayor, Santhosh - Vectrus - No Export | KASAR MARJAN CONTRACTING CO. | 2023-08-16 | COMP | 2023-08-14 | 7.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8040-60-V00-0033 | ADHESIVE, RESIN, SYNTHETIC, WHITE, 5 KG | 38847 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | CN | 1 | 20.57 | 20.57 | 15621 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10866 | 4 | 2023-08-10 | APPR | 2023-08-10 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-24 | COMP | 2023-08-15 | 1.00 |  | AJ | AJ table | August | 2023
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 9540-60-V00-0009 | ANGLE, STRUCTURAL, ALUMINUM, CREAM, 2 X 2 INCH X 20 FEET | 38839 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | EA | 20 | 14.99 | 299.8 | 15618 | CLOSE | 2023-08-09 | 2023-08-08 | KW1-10826 | 5 | 2023-08-10 | CLOSE | 2023-11-25 | Santhumayor, Santhosh - Vectrus - No Export | KASAR MARJAN CONTRACTING CO. | 2023-08-16 | COMP | 2023-08-14 | 20.00 |  | AJ | AJ table | August | 2023
22 | 2023-08-05 |  | AJ23-0467 | Deficiency repairs | 6590045 | PANEL | FABRICATION PANEL, ( MAIN BREAKER-100/125 3 POLE MCCB (SUB BREAKERS 32A 3 POLE MCCB ( 1 EA), 20A 1 POLE MCCB (3 EA) , 63A 3 POLE MCCB (2EA) , | 49124 | 2023-08-05 | [23 empty] | AJ | AJ table | August | 2023
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5930-60-V00-0066 | LIGHT-SWITCH, 2 WAY, 2 GANG, WHITE, 230V, 10A | 39146 | 2023-08-06 | 2023-08-24 |  | 3 | EA | 4 | [6 empty] | KW1-11148 | 2 | [5 empty] | 2023-10-19 | COMP | 2023-09-30 | 4 |  | AJ | AJ table | August | 2023
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5930-60-V00-0243 | LIGHT-SWITCH, METAL, 2 WAY, 1 GANG, 250V, 10A | 39144 | 2023-08-06 | 2023-08-15 |  | 3 | EA | 4 | [6 empty] | KW1-11019 | 5 | [6 empty] | COMP | 2023-08-22 | 4 |  | AJ | AJ table | August | 2023
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5930-60-V00-0387 | SWITCH, TOGGLE, METALCLAD, W/MOUNTING BOX, 1-WAY, 1-GANG, 250V, 10 A | 39146 | 2023-08-06 | 2023-08-24 |  | 2 | EA | 14 | [6 empty] | KW1-11148 | 1 | [5 empty] | 2023-10-19 | COMP | 2023-10-18 | 14 |  | AJ | AJ table | August | 2023
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 39144 | 2023-08-06 | 2023-08-15 | CLOSE | 1 | EA | 65 | 10.32 | 670.8 | 15880 | CLOSE | 2023-08-18 | 2023-08-17 | KW1-11019 | 2 | 2023-08-18 | CLOSE | 2023-12-02 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 03:00 | COMP | 2023-09-02 | 65.00 |  | AJ | AJ table | August | 2023
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 39144 | 2023-08-06 | 2023-08-15 | CLOSE | 2 | RO | 5 | 13.65 | 68.25 | 15880 | CLOSE | 2023-08-18 | 2023-08-17 | KW1-11019 | 3 | 2023-08-18 | CLOSE | 2023-12-02 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-25 03:00 | COMP | 2023-08-22 | 5.00 |  | AJ | AJ table | August | 2023
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 39144 | 2023-08-06 | 2023-08-15 | CLOSE | 5 | EA | 4 | 351.32 | 1405.28 | 15880 | CLOSE | 2023-08-18 | 2023-08-17 | KW1-11019 | 6 | 2023-08-18 | CLOSE | 2023-12-02 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-25 03:00 | COMP | 2023-08-22 | 4.00 |  | AJ | AJ table | August | 2023
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0042 | BOX CONNECTOR, ELECTRICAL, STRAIGHT, LIQUID TIGHT CONDUIT, NICKEL PLATED BRASS, 1/2 INCH | 39144 | 2023-08-06 | 2023-08-15 |  | 8 | EA | 150 | [6 empty] | KW1-11019 | 7 | [6 empty] | COMP | 2023-08-22 | 150 |  | AJ | AJ table | August | 2023
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 39144 | 2023-08-06 | 2023-08-15 | CLOSE | 3 | RO | 5 | 92.57 | 462.85 | 15880 | CLOSE | 2023-08-18 | 2023-08-17 | KW1-11019 | 4 | 2023-08-18 | CLOSE | 2023-12-02 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-25 03:00 | COMP | 2023-08-22 | 5.00 |  | AJ | AJ table | August | 2023
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6110-60-V00-0166 | SENSOR, PHOTOCELL CONTROL, 15A, 50/60 HZ | 39144 | 2023-08-06 | 2023-08-15 | CLOSE | 7 | EA | 1 | 63.94 | 63.94 | 15880 | CLOSE | 2023-08-18 | 2023-08-17 | KW1-11019 | 8 | 2023-08-18 | CLOSE | 2023-12-02 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-25 03:00 | COMP | 2023-08-22 | 1.00 |  | AJ | AJ table | August | 2023
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6130-60-V00-0097 | BATTERY, EMERGENCY LED DRIVER, 50/60HZ, 15W, 100-277V | 39144 | 2023-08-06 | 2023-08-15 | CLOSE | 8 | EA | 4 | 113.22 | 452.88 | 15880 | CLOSE | 2023-08-18 | 2023-08-17 | KW1-11019 | 9 | 2023-08-18 | CLOSE | 2023-12-02 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-25 03:00 | COMP | 2023-08-22 | 4.00 |  | AJ | AJ table | August | 2023
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6210-60-V00-0040 | FIXTURE, LIGHTING, LED, WALL PACK, 5000K, 100-277 VAC, 30W | 39146 | 2023-08-06 | 2023-08-24 | CLOSE | 3 | EA | 4 | 141 | 564 | 15929 | CLOSE | 2023-08-24 | 2023-08-20 | KW1-11148 | 3 | 2023-08-25 | APPR | 2023-08-25 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-02 | COMP | 2023-08-29 | 4.00 | Need Battery Back up | AJ | AJ table | August | 2023
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6210-60-V00-0082 | LIGHT, PANEL, LED, COOL WHITE, 50/60 HZ, 40W, w/ EMERGENCY BATTERY | 39147 | 2023-08-06 | 2023-08-15 | CLOSE | 1 | EA | 21 | 277.56 | 5828.76 | 15907 | CLOSE | 2023-09-01 | 2023-08-19 | KW1-11321 | 1 | 2023-09-04 | CLOSE | 2023-12-09 | Jayaraj, Sudha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-16 | COMP | 2023-09-09 | 21.00 |  | AJ | AJ table | August | 2023
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 9905-60-V00-0066 | SIGN, DANGER, 415 VOLTS , 5 X 3-3/4 INCHES | 39145 | 2023-08-06 | 2023-08-14 | CLOSE | 1 | RO | 2 | 17.48 | 34.96 | 15906 | CLOSE | 2023-09-03 | 2023-08-19 | KW1-11378 | 3 | 2023-09-04 | CLOSE | 2023-12-09 | Jayaraj, Sudha - No Export | COMMERCIAL UNITED GINCO EST. | 2023-11-05 | COMP | 2023-09-11 | 2.00 |  | AJ | AJ table | August | 2023
24 | 2023-08-16 | 60 | AJ21-0038 | Z7 Relocation of Building 370 | 5876937 | 5975-00-156-3253 | STRAP, TIE DOWN, ELECTRICAL COMPONE, 13-7/20 INCHES | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 10 | HD | 1 | 18.64 | 18.64 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 36 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-09-03 | 1.00 |  | AJ | AJ table | August | 2023
25 | 2023-08-16 | 60 | AJ22-0004 | Z7 Relocation of Building 370 | 5876937 | 5640-60-V00-0030 | INSULATION SLEEVING, THERMAL, 3/8 X 72 INCHES | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 14 | EA | 10 | 2.62 | 26.2 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 40 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-08-31 | 10.00 |  | AJ | AJ table | August | 2023
26 | 2023-08-16 | 60 | AJ22-0073 | Z7 Relocation of Building 370 | 5876937 | 5640-60-V00-0031 | INSULATION SLEEVING, THERMAL, 5/8 X 72 INCHES | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 15 | EA | 10 | 3.92 | 39.2 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 41 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-08-31 | 10.00 |  | AJ | AJ table | August | 2023
27 | 2023-08-16 | 60 | AJ22-0123 | Z7 Relocation of Building 370 | 5876937 | 4710-60-V00-0110 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 7 | EA | 4 | 19.62 | 78.48 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 33 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-08-30 | 4.00 |  | AJ | AJ table | August | 2023
28 | 2023-08-16 | 60 | AJ22-0149 | Z7 Relocation of Building 370 | 5876937 | 5970-01-013-9369 | TAPE, INSULATION, ELECTRICAL, RED, 3/4 X 792 INCHES | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 1 | RO | 1 | 9.81 | 9.81 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 27 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-08-31 | 1.00 |  | AJ | AJ table | August | 2023
29 | 2023-08-16 | 60 | AJ22-0184 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0504 | UNION, ELECTRICAL CONDUIT, NYLON POLYAMIDE, LONG THREAD, 5-10 MM | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 8 | EA | 10 | 3.27 | 32.7 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 34 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-08-31 | 10.00 |  | AJ | AJ table | August | 2023
30 | 2023-08-16 | 40 | AJ22-0222 | Z7 Relocation of Building 370 | 5876937 | 5315-60-V00-0052 | PIN, HINGE, BLACK, 2 INCHES | 40058 | 2023-08-16 | 2023-08-20 | CLOSE | 1 | EA | 12 | 13.32 | 159.84 | 16111 | CLOSE | 2023-08-27 | 2023-08-26 | KW1-11206 | 7 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 | COMP | 2023-09-07 | 12.00 |  | AJ | AJ table | August | 2023
31 | 2023-08-16 | 40 | AJ22-0322 | Z7 Relocation of Building 370 | 5876937 | 8030-60-V00-0053 | FOAM, CONSTRUCTION, CREAM, 700ML | 40058 | 2023-08-16 | 2023-08-20 | CLOSE | 3 | EA | 3 | 19.65 | 98.25 | 16111 | CLOSE | 2023-08-27 | 2023-08-26 | KW1-11206 | 9 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 | COMP | 2023-09-03 | 5.00 |  | AJ | AJ table | August | 2023
32 | 2023-08-16 | 60 | AJ22-0323 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 11 | RO | 1 | 64.42 | 64.42 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 37 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-09-05 | 1.00 |  | AJ | AJ table | August | 2023
33 | 2023-08-16 | 40 | AJ22-0326 | Z7 Relocation of Building 370 | 5876937 | 8030-01-075-1156 | CAULKING COMPOUND, CARTRIDGE, WHITE, 10 OZ | 40055 | 2023-08-16 | 2023-08-20 | CLOSE | 1 | CA | 4 | 14.99 | 59.96 | 16109 | CLOSE | 2023-08-27 | 2023-08-26 | KW1-11204 | 3 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 | COMP | 2023-09-02 | 4.00 |  | AJ | AJ table | August | 2023
34 | 2023-08-16 | 60 | AJ22-0390 | Z7 Relocation of Building 370 | 5876937 | 4130-60-V00-0288 | TAPE, WRAP, INSULATION, 3 INCHES X 150 FEET | 40098 | 2023-08-16 | 2023-08-20 | CLOSE | 2 | RO | 6 | 31.72 | 190.32 | 16109 | CLOSE | 2023-08-27 | 2023-08-26 | KW1-11204 | 6 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 | COMP | 2023-09-02 | 6.00 |  | AJ | AJ table | August | 2023
35 | 2023-08-16 | 40 | AJ22-0547 | Z7 Relocation of Building 370 | 5876937 | 8040-00-273-8713 | ADHESIVE, FLOORING, WHITE, 1 GL | 40057 | 2023-08-16 | 2023-08-20 | CLOSE | 1 | GL | 5 | 186.81 | 934.05 | 16111 | CLOSE | 2023-08-27 | 2023-08-26 | KW1-11206 | 6 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-22 | COMP | 2023-10-24 | 5.00 |  | AJ | AJ table | August | 2023
36 | 2023-08-16 | 40 | AJ23-0006 | Z7 Relocation of Building 370 | 5876937 | 5340-60-V00-0461 | HANDLE, DOOR, ALUMINUM, BLACK | 40059 | 2023-08-16 | 2023-08-20 | CLOSE | 1 | EA | 2 | 27.74 | 55.48 | 16111 | CLOSE | 2023-08-27 | 2023-08-26 | KW1-11206 | 10 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 | COMP | 2023-09-07 | 2.00 |  | AJ | AJ table | August | 2023
37 | 2023-08-16 | 60 | AJ23-0079 | Z7 Relocation of Building 370 | 5876937 | 8030-60-V00-0053 | FOAM, CONSTRUCTION, CREAM, 700ML | 40058, 40100 | 2023-08-16 | 2023-08-20 |  | 1,3 | EA | 7 | [6 empty] | KW1-11206 | 9 | [5 empty] | 2023-09-03 | COMP | 2023-09-03 | 7 |  | AJ | AJ table | August | 2023
38 | 2023-08-16 | 60 | AJ23-0172 | Z7 Relocation of Building 370 | 5876937 | 4710-60-V00-0098 | TUBE, METALLIC, REFRIGERATION, COPPER, 5/8 INCH X 50 FEET | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 17 | RO | 1 | 100.39 | 100.39 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 43 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-08-31 | 1.00 |  | AJ | AJ table | August | 2023
39 | 2023-08-16 | 60 | AJ23-0300 | Z7 Relocation of Building 370 | 5876937 | 4130-60-V00-0137 | MOUNTING BASE, AIR-CONDITIONER, POLYPROPYLENE, IVORY, 17 X 3 X 5.12 INCHES | 40100 | 2023-08-16 | 2023-08-20 | CLOSE | 2 | PG | 16 | 61.8 | 988.8 | 16109 | CLOSE | 2023-08-27 | 2023-08-26 | KW1-11204 | 9 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 | COMP | 2023-09-02 | 16.00 |  | AJ | AJ table | August | 2023
40 | 2023-08-16 | 60 | AJ23-0365 | Z7 Relocation of Building 370 | 5876937 | 5970-01-174-5651 | TAPE, INSULATION, ELECTRICAL, YELLOW, 3/4 X 792 INCHES | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 3 | RO | 1 | 9.81 | 9.81 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 29 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-08-31 | 1.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0521 | CLAMP, GROUNDING, BRONZE, 5/8 - 1/2 INCH | 33618 | 2023-08-16 | 2023-05-20 | CLOSE | 1 | EA | 10 | 24.98 | 249.8 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 1 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 10.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0349 | STRAP, TIE DOWN, ELECTRICAL COMPONENT, (CABLE TIE) NYLON, BLACK, 360.68 X 4.83 MM | 33620 | 2023-08-16 | 2023-05-13 | CLOSE | 1 | PG | 1 | 104.2 | 104.2 | 13490 | INPRG | 2023-05-19 | 2023-05-16 | KW1-9546 | 5 | 2023-05-17 | CLOSE | 2023-09-09 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-07-12 | COMP | 2023-05-30 | 1.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 33618 | 2023-08-16 | 2023-05-20 | CLOSE | 2 | RO | 1 | 13.65 | 13.65 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 2 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 1.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-01-613-4740 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 33618 | 2023-08-16 | 2023-05-20 | CLOSE | 3 | PG | 1 | 62.44 | 62.44 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 3 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 1.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-01-015-5060 | TAPE, INSULATION, ELECTRICAL, BLUE, 3/4 X 792 INCHES | 33620 | 2023-08-16 | 2023-05-13 | CLOSE | 2 | RO | 1 | 9.5 | 9.5 | 13490 | INPRG | 2023-05-19 | 2023-05-16 | KW1-9546 | 6 | 2023-05-17 | CLOSE | 2023-09-09 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-31 | COMP | 2023-05-21 | 1.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-01-174-5651 | TAPE, INSULATION, ELECTRICAL, YELLOW, 3/4 X 792 INCHES | 33618 | 2023-08-16 | 2023-05-20 | CLOSE | 4 | RO | 1 | 9.99 | 9.99 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 4 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-06-01 | 1.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-01-013-9369 | TAPE, INSULATION, ELECTRICAL, RED, 3/4 X 792 INCHES | 33621 | 2023-08-16 | 2023-05-13 | CLOSE | 1 | RL | 1 | 11 | 11 | 13582 | CLOSE | 2023-05-25 | 2023-05-21 | KW1-9671 | 23 | 2023-05-27 | CLOSE | 2023-09-24 | Bharadwajan, Sajan - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-31 | COMP | 2023-05-30 | 1.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0516 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, BRASS, CW, 50S | 33619 | 2023-08-16 | 2023-05-13 | CLOSE | 1 | EA | 5 | 43.29 | 216.45 | 13582 | CLOSE | 2023-05-25 | 2023-05-21 | KW1-9671 | 22 | 2023-05-27 | CLOSE | 2023-09-24 | Bharadwajan, Sajan - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-31 | COMP | 2023-05-30 | 5.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0521 | CLAMP, GROUNDING, BRONZE, 5/8 - 1/2 INCH | 39911 | 2023-08-20 | 2023-08-20 | CLOSE | 1 | EA | 10 | 24.53 | 245.3 | 16112 | SENT | 2023-09-06 | 2023-08-26 | KW1-11208 | 1 | 2023-08-27 | CLOSE | 2023-12-16 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 10.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6350-01-094-4171 | ALARM, SMOKE, AUTOMATIC, 9 V DC | 39861 | 2023-08-17 | 2023-08-17 | CLOSE | 1 | EA | 13 | 59.4 | 772.2 | 15929 | CLOSE | 2023-08-24 | 2023-08-20 | KW1-11148 | 6 | 2023-08-25 | APPR | 2023-08-25 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-02 | COMP | 2023-08-29 | 13.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6210-60-V00-0082 | LIGHT, PANEL, LED, COOL WHITE, 50/60 HZ, 40W, w/ EMERGENCY BATTERY | 39911 | 2023-08-20 | 2023-08-20 | CLOSE | 2 | EA | 12 | 277.8 | 3333.6 | 16112 | SENT | 2023-09-06 | 2023-08-26 | KW1-11208 | 2 | 2023-08-27 | CLOSE | 2023-12-16 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 12.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6110-60-V00-0166 | SENSOR, PHOTOCELL CONTROL, 15A, 50/60 HZ | 39860 | 2023-08-19 | 2023-08-19 | CLOSE | 1 | EA | 1 | 71.2 | 71.2 | 15985 | CLOSE | 2023-08-23 | 2023-08-22 | KW1-11135 | 3 | 2023-08-23 | CLOSE | 2023-11-21 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-31 | COMP | 2023-08-28 | 1.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 39911 | 2023-08-20 | 2023-08-20 | CLOSE | 3 | RO | 2 | 13.41 | 26.82 | 16112 | SENT | 2023-09-06 | 2023-08-26 | KW1-11208 | 3 | 2023-08-27 | CLOSE | 2023-12-16 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 2.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5930-60-V00-0387 | SWITCH, TOGGLE, METALCLAD, W/MOUNTING BOX, 1-WAY, 1-GANG, 250V, 10 A | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 7 | EA | 8 | 34.13 | 273.04 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 7 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-22 | COMP | 2023-10-08 | 8.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 11 | EA | 5 | 52.28 | 261.4 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 11 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 5.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5930-60-V00-0243 | LIGHT-SWITCH, METAL, 2 WAY, 1 GANG, 250V, 10A | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 6 | EA | 4 | 33.33 | 133.32 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 6 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 4.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0158 | WIRE, ELECTRICAL, RED, 1 CORE, 2.5 MM ² | 39859 | 2023-08-17 | 2023-08-17 | CLOSE | 1 | RL | 1 | 57.78 | 57.78 | 15929 | CLOSE | 2023-08-24 | 2023-08-20 | KW1-11148 | 5 | 2023-08-25 | APPR | 2023-08-25 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-02 | COMP | 2023-08-30 | 1.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5940-60-V00-0060 | TERMINAL, LUG, ROUND TYPE, COPPER, ONE-HOLE, 4 - 6 MM² X M3 | 39911 | 2023-08-20 | 2023-08-20 | CLOSE | 4 | PG | 1 | 68.67 | 68.67 | 16112 | SENT | 2023-09-06 | 2023-08-26 | KW1-11208 | 4 | 2023-08-27 | CLOSE | 2023-12-16 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 1.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5305-60-V00-0001 | SCREW, SELF DRILLING, HEX WASHER HEAD, STEEL, 5/16 X 1 INCH | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 1 | BX | 2 | 19.31 | 38.62 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 1 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 2.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5935-60-V00-0160 | SOCKET, OUTLET, WEATHERPROOF, 2 GANG, 2 POLES, 13 AMPS | 39857 | 2023-08-19 | 2023-08-19 | CLOSE | 1 | EA | 2 | 39.96 | 79.92 | 15985 | CLOSE | 2023-08-23 | 2023-08-22 | KW1-11135 | 2 | 2023-08-23 | CLOSE | 2023-11-21 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-30 | COMP | 2023-08-28 | 2.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 39911 | 2023-08-20 | 2023-08-20 | CLOSE | 5 | EA | 34 | 10.33 | 351.22 | 16112 | SENT | 2023-09-06 | 2023-08-26 | KW1-11208 | 5 | 2023-08-27 | CLOSE | 2023-12-16 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-22 | COMP | 2023-09-02 | 34.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5935-60-V00-0167 | CONNECTOR, WIRE, RED, 18 -10 AWG | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 19 | PG | 30 | 25.64 | 769.2 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 19 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 30.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-01-613-4740 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 10 | PG | 4 | 62.94 | 251.76 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 10 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 4.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0462 | TIE, CABLE, BLACK, 8 INCHES X 4.8 MILLIMETER | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 4 | PG | 3 | 24.48 | 73.44 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 4 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 3.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 39911 | 2023-08-20 | 2023-08-20 | CLOSE | 6 | RO | 3 | 92.65 | 277.95 | 16282 | CLOSE | 2023-08-30 |  | KW1-11271 | 1 | 2023-08-30 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-25 | COMP | 2023-09-12 | 3.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0376 | COUPLING, CONDUIT, w/ SET SCREW, STEEL, 3/4 INCH | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 5 | EA | 50 | 1.96 | 98 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 5 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 50.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 8 | EA | 3 | 61.27 | 183.81 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 8 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 3.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0379 | CLAMP, ELECTRICAL, CONDUIT, 2 HOLE, GALVANIZED STEEL, 3/4 INCH | 39911 | 2023-08-20 | 2023-08-20 | CLOSE | 7 | EA | 100 | 2.66 | 266 | 16112 | SENT | 2023-09-06 | 2023-08-26 | KW1-11208 | 6 | 2023-08-27 | CLOSE | 2023-12-16 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 100.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-00-178-1217 | CONDUIT, METAL, RIGID, STEEL, 3/4 INCH X 10 FEET | 39911 | 2023-08-20 | 2023-08-20 | CLOSE | 8 | LG | 30 | 13.66 | 409.8 | 16112 | SENT | 2023-09-06 | 2023-08-26 | KW1-11208 | 7 | 2023-08-27 | CLOSE | 2023-12-16 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 30.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0159 | WIRE, ELECTRICAL, BLUE, 1 CORE, 4 MM ² | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 13 | RL | 3 | 91.41 | 274.23 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 13 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 3.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0157 | WIRE, ELECTRICAL, YELLOW, 1 CORE, 4MM ² | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 17 | MR | 270 | 1.33 | 359.1 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 17 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 270.00 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0136 | WIRE, ELECTRICAL, RED, 1 CORE, 4 MM ² | 39856 | 2023-08-16 | 2023-08-20 |  | 16 | RL | 3 | [6 empty] | KW1-11214 | 16 | [5 empty] | 2023-09-04 | COMP | 2023-09-02 | 3 |  | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0001 | WIRE, ELECTRICAL, BLACK, 1 CORE, 4MM ² | 39856 | 2023-08-16 | 2023-05-13 |  | 13 | MR | 810 | [18 empty] | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6210-60-V00-0081 | LIGHT, PANEL, LED, COOL WHITE, 50/60 HZ, 40W | 39856 | 2023-08-16 | 2023-08-20 |  | 1 | EA | 20 | [6 empty] | KW1-11214 | [11 empty] | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0210 | RACEWAY, METALLIC, GALVANIZED STEEL, 3 X 2 INCHES, 10 FEET | 39856 | 2023-08-16 | 2023-08-20 |  | 6 | EA | 6 | [6 empty] | KW1-11214 | [11 empty] | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 39856 | 2023-08-16 | 2023-08-20 |  | 17 | EA | 30 | [6 empty] | KW1-11214 | [11 empty] | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0042 | BOX CONNECTOR, ELECTRICAL, STRAIGHT, LIQUID TIGHT CONDUIT, NICKEL PLATED BRASS, 1/2 INCH | 39856 | 2023-08-16 | 2023-08-20 |  | 18 | EA | 200 | [6 empty] | KW1-11214 | [11 empty] | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0484 | BOX CONNECTOR, ELECTRICAL, METALLIC CONDUIT, ZINC, 3/4 INCH | 39856 | 2023-08-16 | 2023-08-20 |  | 11 | EA | 300 | [6 empty] | KW1-11214 | [11 empty] | AJ | AJ table | August | 2023
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0143 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4 MM² | 39856 | 2023-08-16 | 2023-08-20 |  | 12 | RL | 9 | [6 empty] | KW1-11214 | [11 empty] | AJ | AJ table | August | 2023
42 | 2023-08-16 | 60 | AJ23-0493 | Z7 Relocation of Building 370 | 5876937 | 4710-60-V00-0097 | TUBE, METALLIC, REFRIGERATION, COPPER, 3/8 INCH X 50 FEET | 40097 | 2023-08-16 | 2023-08-21 |  | 17 | RO | 1 | [6 empty] | KW1-11171 | 43 | [6 empty] | COMP | 2023-08-31 | 1 |  | AJ | AJ table | August | 2023
43 | 2023-08-16 | 60 | AJ23-0499 | Z7 Relocation of Building 370 | 5876937 | 5970-01-013-9366 | TAPE, INSULATION, ELECTRICAL, GREEN, 1/2 X 240 INCHES | 40102 | 2023-08-16 | 2023-08-21 | CLOSE | 1 | RO | 1 | 1.69 | 1.69 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 44 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-08-31 | 1.00 |  | AJ | AJ table | August | 2023
44 | 2023-08-16 | 60 | AJ23-0540 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 6 | EA | 8 | 60.17 | 481.36 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 32 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-08-31 | 8.00 |  | AJ | AJ table | August | 2023
45 | 2023-08-16 | 60 | AJ23-0563 | Z7 Relocation of Building 370 | 5876937 | 4730-60-V00-0427 | ELBOW, PIPE, SOCKET X SOCKET, 90°, CPVC, OFFWHITE, 25 X 25 MM | 40101 | 2023-08-16 | 2023-08-20 | CLOSE | 1 | EA | 10 | 13.57 | 135.7 | 16109 | CLOSE | 2023-08-27 | 2023-08-26 | KW1-11204 | 10 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 | COMP | 2023-09-02 | 10.00 |  | AJ | AJ table | August | 2023
46 | 2023-08-17 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0041 | PANEL, CEILING (ACOUSTICAL TILE), MINERAL FIBER, WHITE, 24 X 24 X 3/4 INCHES | 39794 | 2023-08-17 | 2023-08-19 | CLOSE | 1 | EA | 250 | 8.83 | 2207.5 | 15983 | CLOSE | 2023-08-29 | 2023-08-23 | KW1-11249 | 29 | 2023-09-07 | APPR | 2023-09-07 | Kandankara, Thomas -Vectrus -GSD -No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2023-09-21 | COMP | 2023-09-11 | 250.00 |  | AJ | AJ table | August | 2023
46 | 2023-08-17 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 39795 | 2023-08-17 | 2023-08-19 | CLOSE | 1 | CN | 10 | 36.79 | 367.9 | 15983 | CLOSE | 2023-08-29 | 2023-08-23 | KW1-11249 | 30 | 2023-09-07 | APPR | 2023-09-07 | Kandankara, Thomas -Vectrus -GSD -No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2023-09-21 | COMP | 2023-09-11 | 10.00 |  | AJ | AJ table | August | 2023
47 | 2023-08-17 |  | AJ22-0400 | REPLACE WOODEN DOOR WITH METAL DOOR | 7177768 |  | COST OF LABOR, MATERIALS AND EQUIPMENT TO REPLACE WOODEN DOOR WITH METAL DOOR, CAMP BUEHRING, KUWAIT | 49519 | 2023-08-17 | 2023-08-19 | [22 empty] | AJ | AJ table | August | 2023
48 | 2023-08-26 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 3040-60-V00-0075 | : EXTENSION SHAFT, LOAD BREAK SWITCH, EXTERNAL HANDLE, 150 MM | 40730 | 2023-08-26 | 2023-09-02 | CLOSE | 2 | EA | 4 | 3.69 | 14.76 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 3 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-18 | COMP | 2023-10-05 | 4.00 |  | AJ | AJ table | August | 2023
48 | 2023-08-26 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5930-60-V00-0405 | SWITCH DISCONNECT, AC, 3POLE, 400-690V, 100A | 40730 | 2023-08-26 | 2023-09-02 | CLOSE | 3 | EA | 4 | 52.03 | 208.12 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 4 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-18 | COMP | 2023-10-08 | 4.00 |  | AJ | AJ table | August | 2023
48 | 2023-08-26 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5935-60-V00-0253 | CONNECTOR, WIRE, w/ QUICK-GRIP SPRING, WING NUTS, THERMOPLASTIC, BLUE, 600V, 14-6 AWG | 40730 | 2023-08-26 | 2023-09-02 | CLOSE | 1 | PG | 4 | 11.59 | 46.36 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 2 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-18 | COMP | 2023-09-23 | 4.00 |  | AJ | AJ table | August | 2023
48 | 2023-08-26 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6110-60-V00-0275 | SWITCH, DISCONNECT, NEUTRAL POLE, UNSWITCHED, SINGLE POLE, M3, 100-125 A | 40730 | 2023-08-26 | 2023-09-02 | CLOSE | 4 | EA | 4 | 23 | 92 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 5 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-18 | COMP | 2023-10-08 | 4.00 |  | AJ | AJ table | August | 2023
48 | 2023-08-26 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 9515-60-V00-0016 | SHEET, METAL, ALUMINIUM, FLAT, 4 X 8 FEET X 1/16 INCH | 40729 | 2023-08-26 | 2023-09-02 | CLOSE | 1 | EA | 5 | 88.25 | 441.25 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 1 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-14 | 5.00 |  | AJ | AJ table | August | 2023
49 | 2023-08-27 |  | AJ23-0508 | T357 Relocation | 2141526 | 6210-60-V00-0165 | FIXTURE, LIGHTING, LED, FLOOD, 50W, 100-240V, 50/60HZ | 40852 | 2023-08-27 | 2023-08-29 | CLOSE | 1 | EA | 4 | 601.35 | 2405.4 | 16291 | CLOSE | 2023-09-01 | 2023-08-31 | KW1-11331 | 1 | 2023-09-01 | CLOSE | 2023-12-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-16 | COMP | 2023-12-08 | 4.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5640-60-V00-0048 | DRYWALL SHEET, (GYPSUM BOARD), 4 X 8 FEET X 1/2 INCH | 40879 | 2023-08-28 | 2023-09-02 | CLOSE | 7 | EA | 120 | 19.31 | 2317.2 | 16429 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11425 | 8 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 120.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5305-60-V00-0157 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, COARSE THREAD, #7 X 1-3/8 INCHES | 40887 | 2023-08-28 | 2023-09-02 | CLOSE | 8 | BX | 9 | 29.37 | 264.33 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 9 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 9.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0136 | WIRE, ELECTRICAL, RED, 1 CORE, 4MM² | 40909 | 2023-08-28 | 2023-09-02 | CLOSE | 6 | RL | 5 | 90.58 | 452.9 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 11 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-18 | COMP | 2023-09-14 | 5.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0157 | WIRE, ELECTRICAL, YELLOW, 1 CORE, 4MM² | 40909 | 2023-08-28 | 2023-09-02 | CLOSE | 5 | MR | 460 | 1.32 | 607.2 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 10 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-18 | COMP | 2023-09-14 | 460.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0159 | WIRE, ELECTRICAL, BLUE, 1 CORE, 4 MM² | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | RL | 15 | 90.58 | 452.9 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 1 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-12 | 5.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0154 | WIRE, ELECTRICAL, BLACK, 1 CORE, 4MM² | 40909 | 2023-08-28 | 2023-09-02 | CLOSE | 4 | RO | 15 | 89.76 | 1346.4 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 9 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-14 | 15.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6000-CA-255-0142 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4MM² | 40873 | 2023-08-28 |  |  | 1 | MR | 1380 | [18 empty] | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0013 | WIRE, ELECTRICAL, RED, 1 CORE,6MM² | 40909 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | RL | 5 | 135.38 | 676.9 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 8 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-14 | 5.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0011 | WIRE, ELECTRICAL, YELLOW , 1 CORE,6MM² | 40909 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | RO | 5 | 135.38 | 676.9 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 7 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-14 | 5.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0012 | WIRE, ELECTRICAL, BLUE, 1 CORE,6MM² | 40909 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | RO | 5 | 135.38 | 676.9 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 6 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-14 | 5.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0048 | WIRE, ELECTRICAL, BLACK, 1 CORE,6MM² | 40908 | 2023-08-28 |  |  | 8 | RO | 8 | [18 empty] | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0046 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE,6MM² | 40911 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | RO | 15 | 121.44 | 1821.6 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 7 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-14 | 15.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-00-178-1217 | CONDUIT, RIGID, EMT, GALVANIZED STEEL, 3/4" INCH X 10 FEET | 40908 | 2023-08-28 | 2023-09-02 | CLOSE | 7 | LG | 30 | 13.41 | 402.3 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 10 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 30.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0379 | CLAMP, ELECTRICAL, CONDUIT, 2 HOLE, GALVANIZED STEEL, ¾ INCH | 40908 | 2023-08-28 | 2023-09-02 | CLOSE | 6 | EA | 100 | 2.62 | 262 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 9 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 100.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0376 | COUPLING, CONDUIT, WITH SET SCREW, GALVANIZED, 5XC28, 3/4" | 40908 | 2023-08-28 | 2023-09-02 | CLOSE | 5 | EA | 20 | 1.93 | 38.6 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 8 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 20.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0484 | CONNECTOR, EMT, SET SCREW, 3/4" | 40908 | 2023-08-28 | 2023-09-02 | CLOSE | 4 | EA | 100 | 3.27 | 327 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 7 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 100.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0203 | ELBOW, ELECTRICAL CONDUIT, ZINC PLATED, 3/4 INCH | 40908 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | EA | 10 | 30.08 | 300.8 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 6 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 10.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5305-60-V00-0001 | SCREW, SELF DRILLING, HEX HEAD, METAL WASHER, #14 X 1 INCH | 40908 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | BX | 2 | 18.97 | 37.94 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 5 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-10 | 2.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6350-60-V00-0102 | ALARM, SMOKE, AUTOMATIC, PLASTIC | 40871 | 2023-08-28 | 2023-08-30 | CLOSE | 1 | EA | 12 | 28.97 | 347.64 | 16416 | CLOSE | 2023-09-12 | 2023-09-05 | KW1-11634 | 7 | 2023-09-12 | CLOSE | 2023-12-23 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-15 | COMP | 2023-09-17 | 12.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5970-01-013-9369 | TAPE, INSULATION ELECTRICAL, RED | 40907 | 2023-08-28 | 2023-09-02 | CLOSE | 4 | RO | 1 | 9.9 | 9.9 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 5 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-12 | 1.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5970-01-015-5060 | TAPE, INSULATION ELECTRICAL BLUE | 40907 | 2023-08-28 |  |  | 4 | RO | 1 | [18 empty] | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5970-01-174-5651 | TAPE, INSULATION ELECTRICAL, YELLOW | 40907 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | RO | 1 | 9.9 | 9.9 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 4 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-12 | 1.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK 3/4" | 40907 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | RL | 2 | 20.7 | 41.4 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 3 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-12 | 2.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW & GREEN, 3/4", | 40908 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | RO | 4 | 13.41 | 53.64 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 4 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 4.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0529 | CONDUIT, PIPE FLEXIBLE, CORRUGATED, GALVANIZED, PVC COATED, 3/4" | 40907 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | RO | 5 | 96.6 | 483 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 2 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-20 | 5.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0042 | BOX CONNECTOR, ELECTRICAL, STRAIGHT, LIQUID TIGHT CONDUIT, NICKEL PLATED BRASS, 1/2 INCH | 40870 | 2023-08-28 |  |  | 13 | EA | 13 | [18 empty] | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-CA-005-0006 | RACEWAY, METALLIC, GALVANIZED STEEL, 4 X 4 INCHES X 10 FEET | 40874 | 2023-08-28 |  |  | 1 | EA | 6 | [18 empty] | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0335 | STRAP, TIE DOWN, ELECTRICAL, COMPON (CABLE TIE), BLACK, 50 LBS, 4.6 MM X 11.02 INCHES | 40906 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | PG | 2 | 14.72 | 29.44 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 3 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 2.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6210-60-V00-0099 | FIXTURE, LIGHTING, LED, FLOOD, 5000K, 50/60HZ, 90W | 40906 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | EA | 2 | 656.37 | 1312.74 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 2 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 2.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6210-60-V00-0082 | LIGHT, PANEL, LED, COOL WHITE, 50/60 HZ, 40W, w/ EMERGENCY BATTERY | 40906 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | EA | 11 | 276.85 | 3045.35 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 1 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 11.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6210-60-V00-0011 | FIXTURE, LIGHTING, LED, 5000K, 100-277V, 20W, 2 FEET | 40911 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | EA | 18 | 167.47 | 3014.46 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 6 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-12 | 18.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 10 | EA | 27 | 10.33 | 278.91 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 10 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 27.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5935-60-V00-0167 | CONNECTOR, WIRE, RED, 18 -10 AWG | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 9 | PG | 30 | 25.41 | 762.3 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 9 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 30.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5930-60-V00-0243 | LIGHT-SWITCH, METAL, 2 WAY, 1 GANG, 250V, 10A | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 8 | EA | 2 | 33.3 | 66.6 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 8 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 2.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5930-60-V00-0387 | LIGHT-SWITCH, METAL, 1 WAY, 1 GANG, 250V, 10A | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 7 | EA | 8 | 33.82 | 270.56 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 7 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-17 | COMP | 2023-10-18 | 8.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5930-60-V00-0387 | LIGHT-SWITCH, METAL, 1 WAY, 1 GANG, 250V, 10A weather proof | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 6 | EA | 2 | 33.82 | 67.64 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 6 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-17 | COMP | 2023-10-18 | 2.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 5 | EA | 10 | 52.28 | 522.8 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 5 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 10.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 4 | EA | 30 | 27.13 | 813.9 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 4 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-11 | 30.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5940-60-V00-0060 | TERMINAL LUGS 4mm x 6M | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | PG | 1 | 69.3 | 69.3 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 3 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 1.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6110-60-V00-0166 | SENSOR, PHOTOCELL CONTROL, 15A, 50/60 HZ | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | EA | 1 | 63.36 | 63.36 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 2 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-17 | COMP | 2023-10-18 | 1.00 |  | AJ | AJ table | August | 2023
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 4720-60-V00-0370 | ALUMINUM SEMI RIGID FLEXIBLE DUCT Diameter 170mm, Length 9 meters. | 41149 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | EA | 3 | 15.43 | 46.29 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 21 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-19 | 3.00 |  | AJ | AJ table | August | 2023
51 | 2023-08-28 |  | AJ22-0189 | T357 Relocation | 2141526 | 5305-60-V00-0158 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, COARSE THREAD, #7 X 1-1/2 INCHES | 40887 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | BX | 2 | 26.67 | 53.34 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 3 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 2.00 |  | AJ | AJ table | August | 2023
52 | 2023-08-28 |  | AJ22-0240 | T357 Relocation | 2141526 | 8030-60-V00-0052 | PUTTY, ALL PURPOSE, LIGHT GRAY, 3.43 KG | 40882 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | CN | 2 | 141.53 | 283.06 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 4 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-20 | 2.00 |  | AJ | AJ table | August | 2023
53 | 2023-08-28 |  | AJ22-0380 | T357 Relocation | 2141526 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 40876 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | EA | 20 | 13.99 | 279.8 | 16430 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11427 | 3 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-19 | COMP | 2023-09-20 | 20.00 |  | AJ | AJ table | August | 2023
54 | 2023-08-28 |  | AJ22-0406 | T357 Relocation | 2141526 | 8010-60-V00-0095 | PRIMER, COATING, RED OXIDE, LIQUID, 3.78 TO 4 LITERS | 40879 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | CN | 3 | 41.63 | 124.89 | 16429 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11425 | 4 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-12 | 3.00 |  | AJ | AJ table | August | 2023
55 | 2023-08-28 |  | AJ22-0455 | T357 Relocation | 2141526 | 5640-60-V00-0012 | INSULATION BLANKET, THERMAL, GLASS WOOL, YELLOW, 4 FEET X 10 METER | 40876 | 2023-08-28 | 2023-09-02 | CLOSE | 4 | RO | 22 | 214.45 | 4717.9 | 16430 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11427 | 4 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-19 | COMP | 2023-09-16 | 21.00 |  | AJ | AJ table | August | 2023
56 | 2023-08-28 |  | AJ22-0465 | T357 Relocation | 2141526 | 8030-60-V00-0008 | SEALING COMPOUND, GUTTER & SEAM, WHITE, 10 OZ. | 40885 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | CQ | 12 | 23.31 | 279.72 | 16430 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11427 | 7 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-19 | COMP | 2023-09-20 | 12.00 |  | AJ | AJ table | August | 2023
57 | 2023-08-28 |  | AJ22-0497 | T357 Relocation | 2141526 | 5680-60-V00-0007 | GRID, CEILING, T-RUNNER, WHITE, 12 FEET | 40880 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | EA | 60 | 19.15 | 1149 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 2 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 60.00 |  | AJ | AJ table | August | 2023
58 | 2023-08-28 |  | AJ22-0524 | T357 Relocation | 2141526 | 5510-01-433-1244 | LUMBER, SOFTWOOD, 2 X 4 INCHES X 16 FEET | 40879 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | EA | 20 | 30.64 | 612.8 | 16429 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11425 | 2 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 20.00 |  | AJ | AJ table | August | 2023
59 | 2023-08-28 |  | AJ22-0549 | T357 Relocation | 2141526 | 5305-60-V00-0169 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 3 INCHES | 40879 | 2023-08-28 | 2023-09-02 | CLOSE | 4 | BX | 3 | 30.97 | 92.91 | 16429 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11425 | 5 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 3.00 |  | AJ | AJ table | August | 2023
60 | 2023-08-28 |  | AJ23-0004 | T357 Relocation | 2141526 | 5680-60-V00-0006 | GRID, CEILING, TEE, WHITE, 24 INCHES | 40882 | 2023-08-28 | 2023-09-02 | CLOSE | 8 | EA | 260 | 4.33 | 1125.8 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 10 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 260.00 |  | AJ | AJ table | August | 2023
61 | 2023-08-28 |  | AJ23-0005 | T357 Relocation | 2141526 | 5640-60-V00-0041 | TILES, ACOUSTIC CEILING, 2' X 2' X 3/4" | 40878 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | EA | 260 | 8.99 | 2337.4 | 16429 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11425 | 1 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 260.00 |  | AJ | AJ table | August | 2023
62 | 2023-08-28 |  | AJ23-0007 | T357 Relocation | 2141526 | 5650-60-V00-0004 | CHANNEL, STRUCTURAL, C-SHAPE, STEEL, 1-5/8 X 3-5/8 INCHES X 10 FEET | 40880 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | EA | 100 | 9.66 | 966 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 1 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-19 | 100.00 |  | AJ | AJ table | August | 2023
63 | 2023-08-28 |  | AJ23-0068 | T357 Relocation | 2141526 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GL | 40886 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | GL | 3 | 228.5 | 685.5 | 16430 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11427 | 9 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-19 | COMP | 2023-09-21 | 3.00 |  | AJ | AJ table | August | 2023
64 | 2023-08-28 |  | AJ23-0101 | T357 Relocation | 2141526 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 40876 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | EA | 10 | 29.14 | 291.4 | 16430 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11427 | 2 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-19 | COMP | 2023-09-10 | 10.00 |  | AJ | AJ table | August | 2023
65 | 2023-08-28 |  | AJ23-0166 | T357 Relocation | 2141526 | 5640-60-V00-0038 | STRIP, ALUMINIUM, 3MM X 1-1/2 INCHES X 12FEET | 40877 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | EA | 2 | 44.96 | 224.8 | 16430 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11427 | 5 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-19 | COMP | 2023-09-10 | 5.00 |  | AJ | AJ table | August | 2023
66 | 2023-08-28 |  | AJ23-0179 | T357 Relocation | 2141526 | 5640-05-V00-0005 | PANEL, DRYWALL, WALL BOARD, REGULAR, MOLD-GUARD, 1/2 INCH X 4 X 8 FEET | 40882 | 2023-08-28 | 2023-09-02 | CLOSE | 6 | EA | 30 | 28.14 | 844.2 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 8 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 30.00 |  | AJ | AJ table | August | 2023
67 | 2023-08-28 |  | AJ23-0225 | T357 Relocation | 2141526 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 40881 | 2023-08-28 | 2023-09-10 | CLOSE | 2 | EA | 40 | 45.62 | 1824.8 | 16744 | CLOSE | 2023-09-15 | 2023-09-13 | KW1-11708 | 2 | 2023-09-15 | APPR | 2023-09-15 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2023-09-29 | COMP | 2023-09-20 | 40.00 |  | AJ | AJ table | August | 2023
68 | 2023-08-28 |  | AJ23-0258 | T357 Relocation | 2141526 | 5305-60-V00-0197 | SCREW, PHILLIPS DRIVE, SELF-DRILLING, ZINC PLATED, TRUSS HEAD, # 8, 8 X 1/2 INCH | 40884 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | BX | 4 | 29.3 | 117.2 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 12 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 4.00 |  | AJ | AJ table | August | 2023
69 | 2023-08-28 |  | AJ23-0260 | T357 Relocation | 2141526 | 5510-60-V00-0031 | WOOD, SOLID, MOULDING/ DECORATIVE, NATURAL, 1/2 X 2 INCHES X 10 FEET | 40887 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | EA | 55 | 24.75 | 1361.25 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 4 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 55.00 |  | AJ | AJ table | August | 2023
69 | 2023-08-28 |  | AJ23-0260 | T357 Relocation | 2141526 | 8010-00-598-5460 | PAINT, ENAMEL, FLAT, SAND, 1 GL | 40887 | 2023-08-28 | 2023-09-02 | CLOSE | 4 | GL | 4 | 55.35 | 221.4 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 5 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-17 | 4.00 |  | AJ | AJ table | August | 2023
70 | 2023-08-28 |  | AJ23-0268 | T357 Relocation | 2141526 | 9540-60-V00-0009 | ANGLE, STRUCTURAL, ALUMINUM, CREAM, 2 X 2 INCH X 20 FEET | 40884 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | EA | 15 | 43.62 | 654.3 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 11 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 15.00 |  | AJ | AJ table | August | 2023
71 | 2023-08-28 |  | AJ23-0337 | T357 Relocation | 2141526 | 8030-60-V00-0029 | SEALING COMPOUND, GAPS AND CRACKS, POLYURETHANE FOAM, 24 OZ | 40884 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | CS | 1 | 265.57 | 265.57 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 13 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-20 | 1.00 |  | AJ | AJ table | August | 2023
72 | 2023-08-28 |  | AJ23-0467 | T357 Relocation | 2141526 | 5305-60-V00-0174 | SCREW, HEX, STEEL, w/ RUBBER WASHER, # 14 X 2 ½ INCHES | 40882 | 2023-08-28 | 2023-09-02 |  | 15 | BX | 1 | [6 empty] | KW1-11429 | 3 | [5 empty] | 2023-09-19 | COMP | 2023-09-10 | 1 |  | AJ | AJ table | August | 2023
73 | 2023-08-28 |  | AJ23-0482 | T357 Relocation | 2141526 | 5530-00-129-7721 | PLYWOOD, CONSTRUCTION, 1/4 X 48 X 96 INCHES | 40883 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | SH | 42 | 48.12 | 2021.04 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 1 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 42.00 |  | AJ | AJ table | August | 2023
74 | 2023-08-28 |  | AJ23-0508 | B506 Electrical Box faceplates | 2141526 | 5640-60-V00-0044 | TAPE, SELF ADHESIVE, DRYWALL JOINT, FIBERGLASS, 2 INCHES X 300 FEET | 40882 | 2023-08-28 | 2023-09-02 | CLOSE | 5 | EA | 3 | 18.65 | 55.95 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 7 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 3.00 |  | AJ | AJ table | August | 2023
75 | 2023-08-28 |  | AJ23-0574 | T357 Relocation | 2141526 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 40879 | 2023-08-28 | 2023-09-02 | CLOSE | 6 | CN | 5 | 37.46 | 187.3 | 16429 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11425 | 7 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 5.00 |  | AJ | AJ table | August | 2023
76 | 2023-08-28 |  | AJ23-0579 | T357 Relocation | 2141526 | 4710-60-V00-0160 | PIPE, METALLIC, SEAMLESS, MILD STEEL, 41.3 X 3.25 X 5700 MM | 40887 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | EA | 4 | 193.68 | 774.72 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 2 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 4.00 |  | AJ | AJ table | August | 2023
77 | 2023-08-28 |  | AJ23-0598 | T357 Relocation | 2141526 | 5340-60-V00-0492 | STOPPER, DOOR, DROP DOWN, METAL, 5 INCHES | 40882 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | EA | 12 | 19.65 | 235.8 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 5 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 12.00 |  | AJ | AJ table | August | 2023
78 | 2023-08-28 |  | AJ23-0668 | T357 Relocation | 2141526 | 5640-60-V00-0035 | WEATHER STRIP, DOOR, W/BRUSH, 2 X 36 INCHES | 40879 | 2023-08-28 | 2023-09-02 | CLOSE | 5 | EA | 12 | 30.47 | 365.64 | 16429 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11425 | 6 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 12.00 |  | AJ | AJ table | August | 2023
79 | 2023-08-28 |  | AJ23-0782 | T357 Relocation | 2141526 | 4710-60-V00-0004 | TUBE, METALLIC, SQUARE, UNPOLISHED 2 X 2 X 1/8 INCHES | 40879 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | FT | 400 | 2.83 | 1132 | 16429 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11425 | 3 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-16 | 400.00 |  | AJ | AJ table | August | 2023
80 | 2023-08-28 |  | BU23-0193 | T357 Relocation | 2141526 | 5510-01-433-1371 | LUMBER, SOFTWOOD, 2 X 6 INCHES X 16 FEET | 40881 | 2023-08-28 | 2023-09-10 | CLOSE | 1 | EA | 40 | 30.64 | 1225.6 | 16744 | CLOSE | 2023-09-15 | 2023-09-13 | KW1-11708 | 1 | 2023-09-15 | APPR | 2023-09-15 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2023-09-29 | COMP | 2023-09-20 | 40.00 |  | BU | AJ table | August | 2023
81 | 2023-08-28 |  | BU23-0353 | T357 Relocation | 2141526 | 8010-60-V00-0050 | PAINT, ENAMEL, GLOSS, DARK BROWN, 3.2 AND 3.6 LITER | 40885 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | CN | 5 | 34 | 170 | 16430 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11427 | 8 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-19 | COMP | 2023-09-21 | 5.00 |  | BU | AJ table | August | 2023
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0027 | DRAIN, FLOOR, TRAP, MINI, 2 WAY, UPVC, GRAY, 4 X 2 INCHES | 41139 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 1 | 23.81 | 23.81 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 13 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 1.00 |  | AJ | AJ table | August | 2023
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0029 | DRAIN, FLOOR, COVER, UPVC, BEIGE, 160/110MM | 41145 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 3 | 11.19 | 33.57 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 12 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 3.00 |  | AJ | AJ table | August | 2023
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0030 | DRAIN, FLOOR, TRAP, EXTENSION, UPVC, GRAY, 4 INCHES | 41146 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 1 | 6.6 | 6.6 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 15 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 1.00 |  | AJ | AJ table | August | 2023
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0094 | TRAP, BOTTLE, ADJUSTABLE INLET, 1-1/4 INCHES | 41142 | 2023-08-31 | 2023-09-02 | CLOSE | 3 | EA | 3 | 19.15 | 57.45 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 17 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 3.00 |  | AJ | AJ table | August | 2023
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0095 | TRAP, BOTTLE, ADJUSTABLE INLET, 1-1/2 INCHES | 41145 | 2023-08-31 | 2023-09-02 | CLOSE | 2 | EA | 1 | 56.01 | 56.01 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 13 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 1.00 |  | AJ | AJ table | August | 2023
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0131 | SPRAYER, TOILET, 48 INCHES | 41145 | 2023-08-31 | 2023-09-02 | CLOSE | 3 | ST | 2 | 33.47 | 66.94 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 14 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 2.00 |  | AJ | AJ table | August | 2023
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4720-60-V00-0266 | HOSE, METALLIC, FLEXIBLE, DOUBLE NUT, STAINLESS STEEL BRAIDED, 1/2 INCH X 1-1/2 FEET | 41140 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 10 | 11.66 | 116.6 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 8 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 10.00 |  | AJ | AJ table | August | 2023
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4720-60-V00-0370 | HOSE, AIR DUCT, FLEXIBLE, SEMI-RIGID, ALUMINUM, 125 MM X 3 METER | 41149 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 3 | 15.43 | 46.29 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 21 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-19 | 3.00 |  | AJ | AJ table | August | 2023
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0444 | ELBOW, PIPE, SOCKET X FPT, 90 °, CPVC, OFFWHITE, 25MM X 1/2 INCH | 41146 | 2023-08-31 | 2023-09-02 | CLOSE | 2 | EA | 6 | 3.15 | 18.9 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 16 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 6.00 |  | AJ | AJ table | August | 2023
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0845 | WYE, TRUE, PIPE, SCH 40, UPVC, GRAY, 45 °, 50MM | 41141 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 2 | 11.99 | 23.98 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 10 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-12 | 2.00 |  | AJ | AJ table | August | 2023
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0917 | BUSHING, PIPE, REDUCER, SPIGOT X SOCKET, UPVC, GRAY, 2 X 1-1/2 INCHES | 41142 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 1 | 4.5 | 4.5 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 15 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 1.00 |  | AJ | AJ table | August | 2023
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0929 | TEE, PIPE, SOCKET X SOCKET X SOCKET, SCH-80, CPVC, OFF-WHITE, 25 MM | 41141 | 2023-08-31 | 2023-09-02 | CLOSE | 2 | EA | 10 | 7.66 | 76.6 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 11 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 10.00 |  | AJ | AJ table | August | 2023
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 6130-60-V00-0097 | BATTERY, EMERGENCY LED DRIVER, 50/60HZ, 15W, 100-277V | 41148 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 4 | 118.88 | 475.52 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 20 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-12 | 4.00 |  | AJ | AJ table | August | 2023
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 8030-60-V00-0051 | TAPE, ANTISEIZING, (TEFLON TAPE), 0.5 X 520 INCHES | 41142 | 2023-08-31 | 2023-09-02 | CLOSE | 2 | EA | 10 | 1.67 | 16.7 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 16 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 10.00 |  | AJ | AJ table | August | 2023
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 41138 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | BX | 1 | 143.19 | 143.19 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 10 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 1.00 |  | AJ | AJ table | August | 2023
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 9330-60-V00-0015 | SHEET, ACRYLIC, WHITE, 48 X 96 INCHES | 41146 | 2023-08-31 | 2023-09-02 | CLOSE | 3 | SH | 2 | 122.87 | 245.74 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 17 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-14 | 2.00 |  | AJ | AJ table | August | 2023
83 | 2023-08-31 |  | AJ22-0371 | T357 Relocation | 2141526 | 4730-60-V00-0430 | ELBOW, PIPE, SOCKET X SOCKET, 45 °, CPVC, OFF WHITE, 25 MM | 41138 | 2023-08-31 | 2023-09-02 | CLOSE | 3 | EA | 10 | 3.16 | 31.6 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 12 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 10.00 |  | AJ | AJ table | August | 2023
84 | 2023-08-31 |  | AJ22-0475 | T357 Relocation | 2141526 | 4820-60-V00-0227 | VALVE, ANGLE, 1/2 X 1/2 INCHES | 41143 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 12 | 17.65 | 211.8 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 18 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 12.00 |  | AJ | AJ table | August | 2023
85 | 2023-08-31 |  | AJ23-0040 | T357 Relocation | 2141526 | 4730-60-V00-0632 | BUSHING, PIPE, REDUCER, SOCKET X SOCKET, CPVC, OFFWHITE, 32 X 25 MM | 41140 | 2023-08-31 | 2023-09-02 | CLOSE | 2 | EA | 2 | 10.49 | 41.96 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 9 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 4.00 |  | AJ | AJ table | August | 2023
86 | 2023-08-31 |  | AJ23-0450 | T357 Relocation | 2141526 | 4730-60-V00-0427 | ELBOW, PIPE, SOCKET X SOCKET, 90°, CPVC, OFFWHITE, 25 X 25 MM | 41138 | 2023-08-31 | 2023-09-02 | CLOSE | 2 | EA | 10 | 13.82 | 138.2 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 11 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 10.00 |  | AJ | AJ table | August | 2023
87 | 2023-08-31 |  | BU23-0264 | T357 Relocation | 2141526 | 4730-60-V00-0326 | COUPLING, PIPE, SOCKET X SOCKET, CPVC, OFFWHITE, 25MM | 41144 | 2023-08-31 | 2023-09-02 | CLOSE | 2 | EA | 5 | 25.97 | 129.85 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 20 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 5.00 |  | BU | AJ table | August | 2023
88 | 2023-08-31 |  |  | T357 Relocation | 2141526 | 4730-60-V00-0718 | UNION, PIPE, SOCKET, CPVC, GRAY, SCH 80, 3/4 INCH | 41146 | 2023-08-31 | 2023-09-02 | CLOSE | 5 | EA | 5 | 50 | 150 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 19 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 3.00 |  | #VALUE! | AJ table | August | 2023
88 | 2023-08-31 |  |  | T357 Relocation | 2141526 | 4730-60-V00-0810 | CLAMP, PIPE, CPVC, BEIGE, 25 MM | 41146 | 2023-08-31 | 2023-09-02 | CLOSE | 4 | EA | 20 | 0.93 | 18.6 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 18 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 20.00 |  | #VALUE! | AJ table | August | 2023
88 | 2023-08-31 |  |  | T357 Relocation | 2141526 | 4730-60-V00-0812 | MONO D' CLIPS, CPVC PIPE, 32MM | 41144 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 20 | 2.5 | 50 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 19 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 20.00 |  | #VALUE! | AJ table | August | 2023
88 | 2023-08-31 |  |  | T357 Relocation | 2141526 | 4730-60-V00-0927 | TEE, PIPE, SOCKET X SOCKET X FIPT, SCH-80, CPVC, OFF-WHITE, 25 MM X 1/2 INCH | 41139 | 2023-08-31 | 2023-09-02 | CLOSE | 2 | EA | 5 | 17.32 | 86.6 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 14 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 5.00 |  | #VALUE! | AJ table | August | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-09-V00-0065 | DOWNSPOUT, GUTTER, B ELBOW, ALUMINUM, MUSKET BROWN, 3 X 4 INCHES | 41343 | 2023-09-02 | 2023-09-06 | CLOSE | 3 | EA | 6 | 4.49 | 26.94 | 16646 | CLOSE | 2023-09-12 | 2023-09-09 | KW1-11642 | 8 | 2023-09-12 | APPR | 2023-09-12 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-10-30 03:00 | COMP | 2023-10-04 | 6.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 5345-60-V00-0026 | DISK, ABRASIVE,8 HOLE, ALUMINUM OXIDE, COATED, 9 INCHES | 41342 | 2023-09-02 | 2023-09-06 |  | 4 | PG | 4 | [6 empty] | KW1-11642 | 5 | [6 empty] | COMP | 2023-10-02 | 4 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 5680-09-V00-0001 | CORNER BEAD, QUICKSILVER, METAL, 8 FEET X 1-1/4 INCHES | 41343 | 2023-09-02 | 2023-09-06 | CLOSE | 2 | EA | 28 | 4.5 | 126 | 16646 | CLOSE | 2023-09-12 | 2023-09-09 | KW1-11642 | 7 | 2023-09-12 | APPR | 2023-09-12 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-10-31 | COMP | 2023-10-25 | 28.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 8030-09-V01-0003 | SEALING COMPOUND, CAULK, ACRYLIC, WHITE, 5.5 OZ | 41343 | 2023-09-02 | 2023-09-06 | CLOSE | 1 | EA | 50 | 9 | 450 | 16646 | CLOSE | 2023-09-12 | 2023-09-09 | KW1-11642 | 6 | 2023-09-12 | APPR | 2023-09-12 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-10-30 03:00 | COMP | 2023-10-02 | 50.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 5130-60-V00-0125 | DISK, ABRASIVE, SANDING, HOOK AND LOOP, 220 GRIT, 8 HOLE, 5 INCHES | 41340 | 2023-09-02 | 2023-09-05 | CLOSE | 1 | PK | 3 | 95.04 | 285.12 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 15 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 3.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 41341 | 2023-09-02 | 2023-09-06 | CLOSE | 1 | BX | 3 | 11.8 | 35.4 | 16727 | CLOSE | 2023-09-17 | 2023-09-12 | KW1-11770 | 3 | 2023-09-17 | APPR | 2023-09-17 | Bharadwajan, Sajan - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-20 | COMP | 2023-09-23 | 3.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | Zone 7 Fire Station 4 Refer Power Connec | 2141526 | 8010-60-V00-0238 | PAINT, LATEX, GLOSSY, BRIGHT WHITE, 1 GL | 41343 | 2023-09-02 | 2023-09-06 | CLOSE | 4 | CN | 6 | 48.52 | 291.12 | 16646 | CLOSE | 2023-09-12 | 2023-09-09 | KW1-11642 | 9 | 2023-09-12 | APPR | 2023-09-12 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-09-26 03:00 | COMP | 2023-09-24 | 6.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 8010-60-V00-0237 | PAINT, LATEX, INTERIOR, WATER BASED, WHITE, 16 LITERS | 41343 | 2023-09-02 | 2023-09-06 | CLOSE | 5 | CN | 3 | 45.4 | 136.2 | 16646 | CLOSE | 2023-09-12 | 2023-09-09 | KW1-11642 | 10 | 2023-09-12 | APPR | 2023-09-12 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-10-03 03:00 | COMP | 2023-09-21 | 3.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0094 | TRAP, BOTTLE, ADJUSTABLE INLET, 1-1/4 INCHES | 41336 | 2023-09-02 | 2023-09-05 | CLOSE | 3 | EA | 1 | 14.09 | 14.09 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 7 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 1.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T7282 and T7283 TI Repairs Z7 | 2141526 | 4510-60-V00-0124 | FAUCET, LEVER, SINGLE, CHROME, BRASS, WASH BASIN MIXER | 41335 | 2023-09-02 | 2023-09-05 | CLOSE | 1 | EA | 2 | 59.51 | 119.02 | 16605 | CLOSE | 2023-09-13 | 2023-09-07 | KW1-11652 | 1 | 2023-09-13 | CLOSE | 2023-12-16 | Kandankara, Thomas -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-27 | COMP | 2023-09-18 | 2.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0131 | SPRAYER, TOILET, 48 INCHES | 41335 | 2023-09-02 | 2023-09-05 | CLOSE | 2 | EA | 1 | 44.96 | 44.96 | 16605 | CLOSE | 2023-09-13 | 2023-09-07 | KW1-11652 | 2 | 2023-09-13 | CLOSE | 2023-12-16 | Kandankara, Thomas -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-27 | COMP | 2023-09-18 | 1.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4720-60-V00-0266 | HOSE, METALLIC, FLEXIBLE, DOUBLE NUT, STAINLESS STEEL BRAIDED, 1/2 INCH X 1-1/2 FEET | 41335 | 2023-09-02 | 2023-09-05 | CLOSE | 3 | EA | 4 | 9.83 | 39.32 | 16605 | CLOSE | 2023-09-13 | 2023-09-07 | KW1-11652 | 3 | 2023-09-13 | CLOSE | 2023-12-16 | Kandankara, Thomas -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-27 | COMP | 2023-09-18 | 4.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0435 | ELBOW, PIPE, 87.5 °, SPIGOT X SOCKET, UPVC, GRAY, 50MM | 41339 | 2023-09-02 | 2023-09-05 | CLOSE | 2 | EA | 6 | 10 | 60 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 13 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 6.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0448 | ELBOW, PIPE, SOCKET X SPIGOT, 45°, UPVC, GRAY, 50MM | 41338 | 2023-09-02 | 2023-09-05 | CLOSE | 1 | EA | 4 | 13.73 | 54.92 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 10 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 4.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0734 | WYE, TRUE, PIPE, BRANCH, UPVC, 45 DEG, 50 MM | 41339 | 2023-09-02 | 2023-09-05 | CLOSE | 1 | EA | 2 | 3 | 6 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 12 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 2.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0965 | COUPLING, SEWAGE, w/RUBBER GASKET, PVC, ORANGE, 160 MM | 41336 | 2023-09-02 | 2023-09-05 | CLOSE | 2 | EA | 2 | 20.11 | 40.22 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 6 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 2.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0968 | ELBOW, DRAINAGE PIPE, SEWAGE, 45 °, PVC, SCH-80, ORANGE, 160 MM | 41336 | 2023-09-02 | 2023-09-05 | CLOSE | 1 | EA | 2 | 30.25 | 60.5 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 5 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 2.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4820-60-V00-0227 | VALVE, ANGLE, 1/2 X 1/2 INCHES | 41337 | 2023-09-02 |  |  | 2 | EA | 2 | [18 empty] | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0203 | HINGE, BUTT, DOOR, FULL MORTISE, STEEL, 3 HOLES PER LEAF, 3-1/2 X 1-1/2 INCHES | 41334 | 2023-09-02 | 2023-09-05 | CLOSE | 1 | EA | 32 | 15.26 | 488.32 | 16623 | CLOSE | 2023-09-16 | 2023-09-09 | KW1-11743 | 4 | 2023-09-16 | APPR | 2023-09-16 | Bharadwajan, Sajan - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-10-20 | COMP | 2023-09-21 | 32.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0870 | STRIKE, CATCH (PLATE), SASHLOCK, W/FOREND, POLISHED BRASS, 30 X 45 X 180 MM | 41334 | 2023-09-02 | 2023-09-05 | CLOSE | 2 | EA | 12 | 6.89 | 82.68 | 16623 | CLOSE | 2023-09-16 | 2023-09-09 | KW1-11743 | 5 | 2023-09-16 | APPR | 2023-09-16 | Bharadwajan, Sajan - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-10-20 | COMP | 2023-10-07 | 12.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 7920-00-148-9666 | RAG, WIPING, COTTON (MIXED COLOR), 50LB | 41333 | 2023-09-02 | 2023-09-05 | CLOSE | 1 | BE | 2 | 30.87 | 61.74 | 16623 | CLOSE | 2023-09-16 | 2023-09-09 | KW1-11743 | 3 | 2023-09-16 | APPR | 2023-09-16 | Bharadwajan, Sajan - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-22 | COMP | 2023-09-21 | 2.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 8010-60-V00-0146 | PRIMER COATING, WOOD, WHITE, 5 GL | 41481 | 2023-09-02 | 2023-09-06 | CLOSE | 1 | CN | 1 | 98.8 | 98.8 | 16646 | CLOSE | 2023-09-12 | 2023-09-09 | KW1-11642 | 29 | 2023-09-12 | APPR | 2023-09-12 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-09-26 03:00 | COMP | 2023-09-21 | 1.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 8040-60-V00-0065 | TAPE, PRESSURE SENSITIVE ADHESIVE, SEALANT, BLACK, 4 INCHES X 50 FEET | 41334 | 2023-09-02 | 2023-09-05 | CLOSE | 3 | RO | 10 | 70.3 | 703 | 16623 | CLOSE | 2023-09-16 | 2023-09-09 | KW1-11743 | 6 | 2023-09-16 | APPR | 2023-09-16 | Bharadwajan, Sajan - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-10-20 | COMP | 2023-10-04 | 10.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0335 | COUPLING, PIPE, w/ RUBBER SEAL, SOCKET X SOCKET, UPVC, GRAY, 50 MM | 41338 | 2023-09-02 | 2023-09-05 | CLOSE | 2 | EA | 3 | 10.79 | 32.37 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 11 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 3.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0112 | VALVE, FLUSH, URINAL, TOP PUSH, MECHANICAL RELEASE, CHROME PLATED BRASS, 1/2 INCH | 41335 | 2023-09-02 | 2023-09-05 | CLOSE | 4 | EA | 1 | 58.86 | 58.86 | 16605 | CLOSE | 2023-09-13 | 2023-09-07 | KW1-11652 | 4 | 2023-09-13 | CLOSE | 2023-12-16 | Kandankara, Thomas -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-27 | COMP | 2023-09-18 | 1.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-01-660-7689 | URINAL, STATIONARY, WALL MOUNTED, PORCELAIN, WHITE, 14 X 17-1/2 INCHES | 41339 | 2023-09-02 | 2023-09-05 | CLOSE | 3 | EA | 1 | 219.74 | 219.74 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 14 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 1.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0004 | COMMODE, WATER CLOSET, ONE-PIECE TOILET, FLOOR MOUNTED, WHITE | 41336 | 2023-09-02 | 2023-09-05 | CLOSE | 4 | EA | 1 | 429.19 | 429.19 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 8 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 1.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-03 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-05-V01-0827 | FLANGE, PIPE, (TOILET SEAL), WAX FREE, PVC, 3 INCHES | 41429 | 2023-09-03 |  |  | 3 | EA | 3 | [18 empty] | AJ | AJ table | September | 2023
89 | 2023-09-03 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-05-V00-0022 | COVER, TOILET SEAT, W/ SEAT, ROUND, PLASTIC, WHITE, 455 X 375 MM | 41429 | 2023-09-03 |  |  | 2 | EA | 2 | [18 empty] | AJ | AJ table | September | 2023
89 | 2023-09-05 |  | AJ22-0135 | T357 Relocation | 2141526 | 5650-60-V00-0002 | ROOFING METAL, WHITE, 0.35 MM X 3 METER | 41532 | 2023-09-05 | 2023-09-06 | CLOSE | 1 | SH | 30 | 25.02 | 750.6 | 16645 | CLOSE | 2023-09-13 | 2023-09-10 | KW1-11670 | 20 | 2023-09-14 | APPR | 2023-09-14 | Kandankara, Thomas -Vectrus -GSD -No Export | AL-IRTEKAZ NATIONAL GEN.TRDG.C | 2023-09-28 | COMP | 2023-09-19 | 30.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-05 |  | AJ22-0135 | T357 Relocation | 2141526 | 5640-05-V00-0005 | PANEL, DRYWALL, WALL BOARD, REGULAR, MOLD-GUARD, 1/2 INCH X 4 X 8 FEET | 41534 | 2023-09-05 | 2023-09-06 | CLOSE | 1 | EA | 10 | 27.63 | 276.3 | 16645 | CLOSE | 2023-09-13 | 2023-09-10 | KW1-11670 | 22 | 2023-09-14 | APPR | 2023-09-14 | Kandankara, Thomas -Vectrus -GSD -No Export | AL-IRTEKAZ NATIONAL GEN.TRDG.C | 2023-09-28 | COMP | 2023-09-20 | 10.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-05 |  | AJ22-0135 | T357 Relocation | 2141526 | 5640-60-V00-0042 | TILE, CEILING, PVC, WHITE, 2 X 2 FEET | 41534 | 2023-09-05 | 2023-09-06 | CLOSE | 2 | BX | 2 | 343.93 | 687.86 | 16645 | CLOSE | 2023-09-13 | 2023-09-10 | KW1-11670 | 23 | 2023-09-14 | APPR | 2023-09-14 | Kandankara, Thomas -Vectrus -GSD -No Export | AL-IRTEKAZ NATIONAL GEN.TRDG.C | 2023-09-28 | COMP | 2023-09-20 | 2.00 |  | AJ | AJ table | September | 2023
89 | 2023-09-07 |  | AJ22-0135 | T357 Relocation | 2141526 | 7105-60-V00-0019 | FABRICATION PANEL, DISTRIBUTION BOARD, APPROVED SUBMITTAL VIA TRANSMITTAL # AJ220135-LCV-ELE-DSN-0001. | 50213 | 2023-09-07 | 2023-09-07 |  | 1 | AY | 1 | [18 empty] | AJ | AJ table | September | 2023
90 | 2023-09-07 |  | AJ22-0198 | Replacing The Main Distribution Panel | 6669460 | PANEL | FABRICATION PANEL, MDP APPROVED SUBMITTAL VIA TRANSMITTAL#AJ230540-LCV-ELEDSN- 0001 | 50205 | 2023-09-07 | 2023-09-07 |  | 1 | AY | 1 | [18 empty] | AJ | AJ table | September | 2023
91 | 2023-09-07 |  | BU23-0372 | 43 Electrical Meter Installation | 2141526 | PANEL | FABRICATION PANEL, DISTRIBUTION BOARD, APPROVED SUBMITTAL VIA TRANSMITTAL #AJ220135-LCV-ELE-DSN-0001. | 50213 | 2023-09-07 | 2023-09-07 |  | 1 | AY | 1 | [18 empty] | BU | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 8020-00-260-1302 | BRUSH, PAINT, BRISTLES, CHISELED, 2 INCHES | 41919 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | EA | 10 | 13.15 | 131.5 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 20 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-10-13 | COMP | 2023-09-20 | 10.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5130-60-V00-0125 | DISK, ABRASIVE, SANDING, HOOK AND LOOP, 220 GRIT, 8 HOLE, 5 INCHES | 41912 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | PK | 1 | 49.28 | 49.28 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 13 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 1.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 8030-01-075-1156 | CAULKING COMPOUND, CARTRIDGE, WHITE, 10 OZ | 41911 | 2023-09-09 | 2023-09-11 |  | 1 | CA | 12 | [6 empty] | KW1-11721 | 11 | [5 empty] | 2023-09-20 | COMP | 2023-09-20 | 12 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5305-60-V00-0151 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, COARSE THREAD, #10 X 3-1/2 INCHES | 41918 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | BX | 1 | 316.25 | 316.25 | 16829 | CLOSE | 2023-09-19 | 2023-09-16 | KW1-11801 | 22 | 2023-09-19 | APPR | 2023-09-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-26 | COMP | 2023-09-24 | 1.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5530-60-V00-0008 | PLYWOOD, CONSTRUCTION, HEAT TREATED, 1/2 INCH X 4 X 8 FEET | 41914 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | SH | 12 | 32.97 | 395.64 | 16829 | CLOSE | 2023-09-19 | 2023-09-16 | KW1-11801 | 14 | 2023-09-19 | APPR | 2023-09-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-26 | COMP | 2023-09-24 | 12.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5340-60-V00-0473 | CLOSER, DOOR, HEAVY DUTY, HOLD OPEN, 12 X 2-1/4 INCHES | 41921 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | EA | 1 | 745.9 | 745.9 | 16787 | CLOSE | 2023-09-17 | 2023-09-13 | KW1-11771 | 1 | 2023-09-17 | CLOSE | 2023-10-17 | Vishwanath, Shet -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-21 | 1.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 8030-60-V00-0008 | SEALING COMPOUND, GUTTER & SEAM, WHITE, 10 OZ. | 41920 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | CQ | 12 | 23.31 | 279.72 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 26 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-10-15 | COMP | 2023-10-17 | 12.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5640-60-V00-0015 | INSULATION BLANKET, THERMAL, FIBERGLASS, R4.1, 50 MM X 1.2 X 10 METER | 41911 | 2023-09-09 | 2023-09-29 |  | 2 | RL | 6 | [6 empty] | KW1-11721 | 12 | [5 empty] | 2023-09-29 | COMP | 2023-09-21 | 6 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 7510-00-266-6710 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 41911 | 2023-09-09 | 2023-09-11 | CLOSE | 3 | RO | 10 | 8.33 | 83.3 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 8 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 10.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 41913 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | BX | 10 | 17.82 | 178.2 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 16 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 10.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 8010-60-V00-0028 | PAINT, ENAMEL, GLOSS, DESERT SAND, 3.6 LITER | 41919 | 2023-09-09 | 2023-09-11 | CLOSE | 2 | CN | 8 | 39.96 | 319.68 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 21 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-30 | COMP | 2023-09-30 | 8.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 8010-60-V00-0089 | PRIMER, COATING, WHITE, 4 - 5 LITERS | 41919 | 2023-09-09 | 2023-09-11 | CLOSE | 3 | CN | 4 | 41.63 | 166.52 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 22 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-30 | COMP | 2023-09-30 | 4.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 8010-60-V00-0113 | THINNER, PAINT PRODUCTS, 5 LITER | 41919 | 2023-09-09 | 2023-09-11 | CLOSE | 4 | CN | 3 | 54.95 | 164.85 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 23 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-30 | COMP | 2023-09-21 | 3.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 6850-60-V00-0005 | ADDITIVE, MILDEWCIDE, LIQUID, 50-GRAM | 41913 | 2023-09-09 | 2023-09-11 | CLOSE | 2 | EA | 5 | 35.8 | 179 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 17 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 5.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 8010-60-V00-0018 | PAINT, LATEX, SEMIGLOSS, SAHARA SAND, 3.6 LT | 41915 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | CN | 12 | 65.1 | 781.2 | 16829 | CLOSE | 2023-09-19 | 2023-09-16 | KW1-11801 | 16 | 2023-09-19 | APPR | 2023-09-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-29 | COMP | 2023-09-30 | 12.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 41911 | 2023-09-09 |  |  | 4 | BX | 1 | [18 empty] | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 41912 | 2023-09-09 | 2023-09-11 | CLOSE | 2 | EA | 12 | 45.62 | 547.44 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 14 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 12.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 8040-60-V00-0032 | ADHESIVE, FLOOR/WOOD, 5 GL | 41920 | 2023-09-09 | 2023-09-11 | CLOSE | 2 | CN | 2 | 161.51 | 323.02 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 27 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-10-02 | COMP | 2023-10-01 | 2.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 7210-60-V00-0059 | FLOOR COVERING, VINYL RESIN, 3 MM X 40 FEET | 41919 | 2023-09-09 | 2023-09-11 | CLOSE | 5 | RO | 1 | 722.61 | 722.61 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 24 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-26 | 1.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 3455-60-V00-0004 | BLADE, CIRCULAR SAW, METAL CUTTING, ALUMINUM OXIDE, 4 X 5/8 INCHES | 41911 | 2023-09-09 |  |  | 5 | PK | 3 | [18 empty] | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 9515-60-V00-0016 | SHEET, METAL, ALUMINIUM, FLAT, 4 X 8 FEET X 1/16 INCH | 41911 | 2023-09-09 |  |  | 6 | SH | 1 | [18 empty] | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5305-60-V00-0191 | SCREW, PHILLIPS, FLAT HEAD, STEEL, # 10 X 1-1/2 INCHES | 41912 | 2023-09-09 | 2023-09-11 | CLOSE | 3 | BX | 1 | 30.24 | 30.24 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 15 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 1.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5305-60-V00-0179 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 1-1/2 INCHES | 41919 | 2023-09-09 | 2023-09-11 | CLOSE | 6 | BX | 1 | 10.66 | 10.66 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 25 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 1.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 41916 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | BX | 1 | 19.98 | 19.98 | 16829 | CLOSE | 2023-09-19 | 2023-09-16 | KW1-11801 | 19 | 2023-09-19 | APPR | 2023-09-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-26 | COMP | 2023-09-24 | 1.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5510-01-433-1244 | LUMBER, SOFTWOOD, 2 X 4 INCHES X 16 FEET | 41915 | 2023-09-09 | 2023-09-11 | CLOSE | 2 | EA | 1 | 30.64 | 30.64 | 16829 | CLOSE | 2023-09-19 | 2023-09-16 | KW1-11801 | 17 | 2023-09-19 | APPR | 2023-09-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-26 | COMP | 2023-09-24 | 1.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5350-60-V00-0002 | PAPER, ABRASIVE (SANDPAPER), 320 GRIT, 9 X 11 INCHES | 41913 | 2023-09-09 | 2023-09-11 | CLOSE | 3 | PK | 1 | 44.96 | 44.96 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 18 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 1.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5345-60-V00-0005 | DISK, ABRASIVE w/GRIP, SANDING, 80 GRIT, 8 HOLES, 5 INCHES | 41920 | 2023-09-09 | 2023-09-11 | CLOSE | 3 | BX | 1 | 59.77 | 59.77 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 28 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 1.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 41916 | 2023-09-09 | 2023-09-11 | CLOSE | 2 | CN | 1 | 37.46 | 37.46 | 16829 | CLOSE | 2023-09-19 | 2023-09-16 | KW1-11801 | 20 | 2023-09-19 | APPR | 2023-09-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-26 | COMP | 2023-09-24 | 1.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5640-60-V00-0045 | TAPE, JOINT, WALLBOARD, SELF-ADHESIVE, 50 MM X 90 METERS | 41923 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | EA | 1 | 11.99 | 11.99 | 16841 | CLOSE | 2023-09-20 | 2023-09-14 | KW1-11839 | 1 | 2023-09-21 | CLOSE | 2023-12-31 | Jayaraj, Sudha - No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-28 | 1.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5640-05-V00-0005 | PANEL, DRYWALL, WALL BOARD, REGULAR, MOLD-GUARD, 1/2 INCH X 4 X 8 FEET | 41913 | 2023-09-09 | 2023-09-11 | CLOSE | 4 | EA | 1 | 28.14 | 28.14 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 19 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 1.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5340-60-V00-0466 | HANDLE, DOOR, w/ LOCK, ALUMINUM | 41922 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | SE | 1 | 56.93 | 56.93 | 16787 | CLOSE | 2023-09-17 | 2023-09-13 | KW1-11771 | 3 | 2023-09-17 | CLOSE | 2023-10-17 | Vishwanath, Shet -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-07 | COMP | 2023-09-21 | 1.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 41911 | 2023-09-09 |  |  | 7 | BX | 2 | [18 empty] | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5650-60-V00-0002 | ROOFING METAL, WHITE, 0.35 MM X 3 METER | 41918 | 2023-09-09 | 2023-09-11 | CLOSE | 2 | SH | 34 | 25.47 | 865.98 | 16829 | CLOSE | 2023-09-19 | 2023-09-16 | KW1-11801 | 23 | 2023-09-19 | APPR | 2023-09-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-26 | COMP | 2023-09-24 | 34.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5620-60-V00-0002 | CONCRETE MASONRY UNIT, SOLID, 12 X 12 X 2 INCHES | 41917 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | EA | 30 | 43.62 | 1308.6 | 16804 | CLOSE | 2023-09-18 | 2023-09-14 | KW1-11778 | 4 | 2023-09-18 | APPR | 2023-09-18 | Kandankara, Thomas -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2023-09-30 | COMP | 2023-09-23 | 30.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 30 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 41952 | 2023-09-09 | 2023-09-19 |  | 33 | RL | 1 | [6 empty] | KW1-11894 | [6 empty] | 2023-10-01 |  |  |  |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 30 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5110-60-V00-0079 | STRIPPER, FIBER OPTIC, DUAL-DUROMETER, 5 IN 1 PRESETS | 41954 | 2023-09-09 | 2023-09-25 | CLOSE | 1 | EA | 4 | 98 | 392 | 16848 | CLOSE | 2023-10-04 | 2023-09-14 | KW1-12135 | 1 | 2023-10-10 | APPR | 2023-10-10 | Jayaraj, Sudha - No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-25 | COMP | 2023-10-19 | 4.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 30 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5120-60-V00-0111 | SCREW DRIVER / NUT DRIVER, HEAVY DUTY, MULTI-BIT | 41952 | 2023-09-09 | 2023-09-19 | CLOSE | 1 | SE | 2 | 35.92 | 71.84 | 17123 | CLOSE | 2023-09-23 | 2023-09-21 | KW1-11894 | 2 | 2023-09-23 | APPR | 2023-09-23 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-01 | COMP | 2023-09-28 | 2.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 30 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5110-01-563-4373 | STRIPPER, WIRE, HAND, 7.125 INCHES | 41956 | 2023-09-09 | 2023-09-25 | CLOSE | 1 | EA | 4 | 66.74 | 266.96 | 16853 | CLOSE | 2023-10-05 | 2023-09-14 | KW1-12137 | 1 | 2023-10-10 | APPR | 2023-10-10 | Jayaraj, Sudha - No Export | AL BAYADER INTER.GROUP COMPANY | 2023-11-18 | COMP | 2023-10-18 | 4.00 |  | AJ | AJ table | September | 2023
92 | 2023-09-09 | 30 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5120-60-V00-0001 | PLIER, CUTTING, DIAGONAL 8 INCHES | 41953 | 2023-09-09 | 2023-09-12 | CLOSE | 1 | EA | 4 | 39.48 | 157.92 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 29 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-10-28 | COMP | 2023-10-02 | 4.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5110-01-367-7278 | CUTTER, CABLE, HAND OPERATED, FORGED STEEL, PLASTIC DIPPED, 9-1/2 INCHES | 41957 | 2023-09-09 | 2023-09-12 | CLOSE | 1 | EA | 4 | 81.1 | 324.4 | 16859 | CLOSE | 2023-09-21 | 2023-09-14 | KW1-11850 | 1 | 2023-09-25 | APPR | 2023-09-25 | Jayaraj, Sudha - No Export | AL-IRTEKAZ NATIONAL GEN.TRDG.C | 2023-11-11 | COMP | 2023-10-04 | 4.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6210-60-V00-0165 | FIXTURE, LIGHTING, LED, FLOOD, 50W, 100-240V, 50/60HZ | 41984 | 2023-09-09 | 2023-09-12 |  | 1 | EA | 3 | [6 empty] | KW1-11698 | 2 | [5 empty] | 2023-12-16 | COMP | 2023-12-08 | 3 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6130-60-V00-0097 | BATTERY, EMERGENCY LED DRIVER, 50/60HZ, 15W, 100-277V | 41952 | 2023-09-09 | 2023-09-19 |  | 3 | EA | 1 | [6 empty] | KW1-11894 | 3 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 1 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0042 | BOX CONNECTOR, ELECTRICAL, STRAIGHT, LIQUID TIGHT CONDUIT, NICKEL PLATED BRASS, 1/2 INCH | 41952 | 2023-09-09 | 2023-09-19 |  | 4 | EA | 20 | [6 empty] | KW1-11894 | 4 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 20 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5940-60-V00-0129 | TERMINAL BLOCK, CONNECTOR, 2 WAY, GREY, 10AWG, 1000V, 125A | 41952 | 2023-09-09 | 2023-09-19 |  | 5 | EA | 5 | [6 empty] | KW1-11894 | 5 | [5 empty] | 2023-11-05 | COMP | 2023-10-08 | 5 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0769 | RACEWAY, METALLIC, (CABLE TRUNKING), HOT DIP GALVANIZED, 75 X 75 X 1.2 X 3000 MM | 41959 | 2023-09-09 | 2023-09-12 | CLOSE | 1 | EA | 14 | 39.08 | 547.12 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 31 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-11-10 | COMP | 2023-10-22 | 14.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 41952 | 2023-09-09 | 2023-09-19 |  | 6 | PG | 4 | [6 empty] | KW1-11894 | 6 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 4 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5935-60-V00-0156 | CONNECTOR, WIRE, RED, 18-6 AWG | 41952 | 2023-09-09 | 2023-09-19 |  | 7 | BX | 4 | [6 empty] | KW1-11894 | 7 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 4 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 41952 | 2023-09-09 | 2023-09-19 |  | 8 | BX | 1 | [6 empty] | KW1-11894 | 8 | [5 empty] | 2023-10-01 | COMP | 2023-10-01 | 1 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 41952 | 2023-09-09 | 2023-09-19 | CLOSE | 8 | RO | 1 | 13.41 | 13.41 | 17123 | CLOSE | 2023-09-23 | 2023-09-21 | KW1-11894 | 9 | 2023-09-23 | APPR | 2023-09-23 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-01 | COMP | 2023-09-28 | 1.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5970-60-V00-0044 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 INCH X 66 FEET | 41952 | 2023-09-09 | 2023-09-19 | CLOSE | 9 | RO | 1 | 14.72 | 14.72 | 17123 | CLOSE | 2023-09-23 | 2023-09-21 | KW1-11894 | 10 | 2023-09-23 | APPR | 2023-09-23 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-01 | COMP | 2023-09-28 | 1.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5970-60-V00-0040 | TAPE, INSULATION, RED, 3/4 INCH X 25 METER | 41952 | 2023-09-09 | 2023-09-19 |  | 11 | RO | 1 | [6 empty] | KW1-11894 | 9 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 1 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0505 | STUFFING TUBE (CABLE GLAND), PG16, POLYAMIDE, GRAY, 9 -14 MM | 41952 | 2023-09-09 | 2023-09-19 |  | 12 | EA | 10 | [6 empty] | KW1-11894 | 12 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 10 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0143 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4 MM² | 41952 | 2023-09-09 | 2023-09-19 |  | 13 | RL | 1 | [6 empty] | KW1-11894 | 13 | [5 empty] | 2023-10-01 | COMP | 2023-10-01 | 1 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0001 | WIRE, ELECTRICAL, BLACK, 1 CORE, 4MM ² | 41952 | 2023-09-09 | 2023-09-19 |  | 14 | MR | 50 | [6 empty] | KW1-11894 | 14 | [5 empty] | 2023-10-01 | COMP | 2023-10-01 | 50 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0136 | WIRE, ELECTRICAL, RED, 1 CORE, 4 MM ² | 41952 | 2023-09-09 | 2023-09-19 |  | 15 | RL | 1 | [6 empty] | KW1-11894 | 15 | [5 empty] | 2023-10-01 | COMP | 2023-10-01 | 1 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6110-60-V00-0166 | SENSOR, PHOTOCELL CONTROL, 15A, 50/60 HZ | 41952 | 2023-09-09 | 2023-09-19 |  | 16 | EA | 1 | [6 empty] | KW1-11894 | 16 | [5 empty] | 2023-11-05 | COMP | 2023-10-18 | 1 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5930-60-V00-0249 | BOX, SWITCH ENCLOSURE, 1 POLE, 3 GANG, 16A | 41952 | 2023-09-09 | 2023-09-19 |  | 17 | EA | 1 | [6 empty] | KW1-11894 | 17 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 1 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6210-60-V01-0091 | FIXTURE, LIGHT, LED, BULK HEAD, 120-277V, 50K | 41954 | 2023-09-09 | 2023-09-25 | CLOSE | 2 | EA | 1 | 190.46 | 190.46 | 16848 | CLOSE | 2023-10-04 | 2023-09-14 | KW1-12135 | 2 | 2023-10-10 | APPR | 2023-10-10 | Jayaraj, Sudha - No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-25 | COMP | 2023-11-20 | 1.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6210-60-V00-0099 | FIXTURE, LIGHTING, LED, FLOOD, 5000K, 50/60HZ, 90W | 41984 | 2023-09-09 | 2023-09-12 |  | 2 | EA | 3 | [6 empty] | KW1-11698 | 4 | [5 empty] | 2023-09-21 | COMP | 2023-09-19 | 3 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0480 | JUNCTION BOX, w/ BLANK SIDE, 100 X 100 X 50 MM | 41952 | 2023-09-09 | 2023-09-19 |  | 19 | EA | 2 | [6 empty] | KW1-11894 | 18 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 2 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0099 | WIRE, ELECTRICAL, BLACK, 1 CORE, 1.5 MM ² | 41952 | 2023-09-09 | 2023-09-19 |  | 20 | MR | 1 | [6 empty] | KW1-11894 | 19 | [5 empty] | 2023-10-01 | COMP | 2023-10-01 | 1 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0149 | WIRE, ELECTRICAL, RED, 1 CORE, 1.5 MM ² | 41952 | 2023-09-09 | 2023-09-19 |  | 21 | RO | 1 | [6 empty] | KW1-11894 | 20 | [5 empty] | 2023-10-01 | COMP | 2023-10-01 | 1 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0050 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 1.5 MM ² | 41952 | 2023-09-09 | 2023-09-19 |  | 22 | RL | 1 | [6 empty] | KW1-11894 | 21 | [5 empty] | 2023-10-01 | COMP | 2023-10-01 | 1 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 41952 | 2023-09-09 | 2023-09-19 |  | 23 | EA | 2 | [6 empty] | KW1-11894 | 22 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 2 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 41955 | 2023-09-09 | 2023-10-24 | CLOSE | 1 | EA | 8 | 4.23 | 33.84 | 16850 | CLOSE | 2023-11-03 | 2023-09-17 | KW1-12727 | 1 | 2023-11-06 | APPR | 2023-11-06 | Jayaraj, Sudha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-18 | COMP | 2023-11-16 | 8.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0462 | TIE, CABLE, BLACK, 8 INCHES X 4.8 MILLIMETER | 41952 | 2023-09-09 | 2023-09-19 |  | 24 | PG | 2 | [6 empty] | KW1-11894 | 22 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 2 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 41952 | 2023-09-09 | 2023-09-19 |  | 25 | EA | 10 | [6 empty] | KW1-11894 | 24 | [5 empty] | 2023-11-05 | COMP | 2023-10-01 | 10 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 41952 | 2023-09-09 | 2023-09-19 |  | 26 | RL | 1 | [6 empty] | KW1-11894 | 25 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 1 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 4210-60-V00-0189 | EXTINGUISHER, FIRE, DRY CHEMICAL, w/ BRASS VALVE, 10 LBS | 41953 | 2023-09-09 | 2023-09-12 | CLOSE | 2 | EA | 2 | 47.86 | 95.72 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 30 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-30 | COMP | 2023-09-21 | 2.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6350-60-V00-0102 | ALARM, SMOKE, AUTOMATIC, PLASTIC | 41952 | 2023-09-09 | 2023-09-19 |  | 27 | EA | 2 | [6 empty] | KW1-11894 | 26 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 2 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0358 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, CW, BRASS, 25 MM | 41952 | 2023-09-09 | 2023-09-19 |  | 28 | KT | 4 | [6 empty] | KW1-11894 | 27 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 4 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5940-60-V00-0016 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 16 MM ² | 41952 | 2023-09-09 | 2023-09-19 |  | 29 | EA | 14 | [6 empty] | KW1-11894 | 28 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 14 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 4240-60-V00-0054 | TAPE, BARRICADE, "CAUTION BURIED ELECTRIC LINE BELOW", 3 INCHES X 1000 FEET | 41952 | 2023-09-09 | 2023-09-19 |  | 30 | RO | 1 | [6 empty] | KW1-11894 | 29 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 1 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 41952 | 2023-09-09 | 2023-09-19 |  | 31 | PG | 3 | [6 empty] | KW1-11894 | 29 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 3 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5305-60-V00-0179 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 1-1/2 INCHES | 41955 | 2023-09-09 | 2023-10-24 | CLOSE | 2 | BX | 1 | 10.42 | 10.42 | 16850 | CLOSE | 2023-11-03 | 2023-09-17 | KW1-12727 | 2 | 2023-11-06 | APPR | 2023-11-06 | Jayaraj, Sudha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-18 | COMP | 2023-11-13 | 1.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5930-60-V00-0169 | SWITCH, DISCONNECT, 3 POLE, 600 V, 100 A | 41984 | 2023-09-09 | 2023-09-12 |  | 3 | EA | 1 | [6 empty] | KW1-11698 | 1 | [5 empty] | 2023-09-21 | COMP | 2023-09-19 | 1 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 41952 | 2023-09-09 | 2023-09-19 |  | 34 | EA | 1 | [6 empty] | KW1-11894 | 32 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 1 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 41952 | 2023-09-09 | 2023-09-19 |  | 35 | EA | 1 | [6 empty] | KW1-11894 | 33 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 1 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0118 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 16 MM² | 41952 | 2023-09-09 | 2023-09-19 |  | 36 | MR | 35 | [6 empty] | KW1-11894 | 34 | [5 empty] | 2023-10-01 | COMP | 2023-10-01 | 35 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6210-60-V00-0082 | LIGHT, PANEL, LED, COOL WHITE, 50/60 HZ, 40W, w/ EMERGENCY BATTERY | 41952 | 2023-09-09 | 2023-09-19 |  | 37 | EA | 3 | [6 empty] | KW1-11894 | 35 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 3 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6210-60-V00-0081 | LIGHT, PANEL, LED, COOL WHITE, 50/60 HZ, 40W | 41984 | 2023-09-09 | 2023-09-12 | CLOSE | 3 | EA | 7 | 283.3 | 1983.1 | 16801 | CLOSE | 2023-09-15 | 2023-09-13 | KW1-11698 | 3 | 2023-09-15 | CLOSE | 2024-01-02 | Thomas, Vinu - Vectrus -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-21 | COMP | 2023-09-19 | 7.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0042 | BOX CONNECTOR, ELECTRICAL, STRAIGHT, LIQUID TIGHT CONDUIT, NICKEL PLATED BRASS, 1/2 INCH | 41952 | 2023-09-09 | 2023-09-19 |  | 39 | EA | 20 | [6 empty] | KW1-11894 | 36 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 20 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 41952 | 2023-09-09 | 2023-09-19 |  | 40 | EA | 14 | [6 empty] | KW1-11894 | 37 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 14 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6210-60-V00-0043 | LIGHT UNIT, EMERGENCY, w/COMBO LAMP, RED LETTERS, 120/277V AC | 41955 | 2023-09-09 | 2023-10-24 | CLOSE | 3 | EA | 1 | 133.49 | 133.49 | 16850 | CLOSE | 2023-11-03 | 2023-09-17 | KW1-12727 | 3 | 2023-11-06 | APPR | 2023-11-06 | Jayaraj, Sudha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-18 | COMP | 2023-11-12 | 1.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0483 | BOX CONNECTOR, ELECTRICAL, ZINC DIE CAST, 1/2 INCH | 41952 | 2023-09-09 | 2023-09-19 |  | 41 | EA | 44 | [6 empty] | KW1-11894 | 38 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 44 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0381 | CLAMP, ELECTRICAL, CONDUIT, 2 HOLE, STEEL, 1/2 INCH | 41952 | 2023-09-09 | 2023-09-19 |  | 42 | EA | 50 | [6 empty] | KW1-11894 | 39 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 50 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 2 | RL | 2 | 21.26 | 42.52 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 2 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 2.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 3 | RO | 3 | 13.41 | 40.23 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 3 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 3.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 8030-60-V00-0029 | SEALING COMPOUND, GAPS AND CRACKS, POLYURETHANE FOAM, 24 OZ | 41974 | 2023-09-09 | 2023-09-10 | CLOSE | 1 | CS | 2 | 260.78 | 521.56 | 16746 | SENT | 2023-09-26 | 2023-09-13 | KW1-11705 | 16 | 2023-09-15 | APPR | 2023-09-15 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-11-05 | COMP | 2023-11-05 | 2.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5930-60-V00-0254 | SWITCH, DOUBLE POLE, METAL CLAD, 1 GANG, 32A | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 4 | EA | 2 | 69.81 | 139.62 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 4 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 2.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0502 | ROD, GROUNDING, KIT, WITH CLAMP, 5/8 INCH X 4 FEET | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 5 | KT | 2 | 145.35 | 290.7 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 5 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 2.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 6 | EA | 2 | 60.17 | 120.34 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 6 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-21 | 2.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5306-60-V00-0118 | NUT AND BOLT, 1-1/2 X 3/8 INCHES | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 7 | EA | 4 | 0.85 | 3.4 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 7 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 4.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5940-60-V00-0060 | TERMINAL, LUG, ROUND TYPE, COPPER, ONE-HOLE, 4 - 6 MM² X M3 | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 8 | PG | 1 | 68.67 | 68.67 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 8 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 1.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0046 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 6 MM² | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 9 | RL | 1 | 120.34 | 120.34 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 9 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-20 | 1.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 11 | RO | 1 | 161.7 | 161.7 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 10 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-20 | 1.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0505 | STUFFING TUBE (CABLE GLAND), PG16, POLYAMIDE, GRAY, 9 -14 MM | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 12 | EA | 6 | 4.09 | 24.54 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 11 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 6.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5340-60-V00-0449 | ANCHOR, KIT, CONICAL, PLASTIC, #10 X 1 INCHES | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 1 | KT | 1 | 34.34 | 34.34 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 1 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 1.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 4730-60-V00-0594 | C-CLAMP W/ RUBBER, GALVANIZED STEEL, 2 INCHES | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 13 | EA | 10 | 10.14 | 101.4 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 12 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 10.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 14 | EA | 3 | 51.5 | 154.5 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 13 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 3.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 4130-60-V00-0288 | TAPE, WRAP, INSULATION, 3 INCHES X 150 FEET | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 15 | RO | 3 | 31.72 | 95.16 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 14 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 3.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6850-01-192-2492 | SEALER, CHEMICAL, PLASTIC POLYURETHANE, WHITE, 12 OZ | 41975 | 2023-09-09 | 2023-09-10 | CLOSE | 1 | CN | 2 | 115.1 | 230.2 | 16746 | SENT | 2023-09-26 | 2023-09-13 | KW1-11705 | 17 | 2023-09-15 | APPR | 2023-09-15 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-11-10 | COMP | 2023-10-07 | 2.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 4710-60-V00-0110 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 16 | EA | 2 | 19.62 | 39.24 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 15 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-23 | 2.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5640-60-V00-0030 | INSULATION SLEEVING, THERMAL, 3/8 X 72 INCHES | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 17 | EA | 10 | 2.62 | 26.2 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 16 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 10.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5640-60-V00-0031 | INSULATION SLEEVING, THERMAL, 5/8 X 72 INCHES | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 18 | EA | 10 | 3.92 | 39.2 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 17 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 10.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 4710-60-V00-0097 | TUBE, METALLIC, REFRIGERATION, COPPER, 3/8 INCH X 50 FEET | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 19 | RO | 1 | 69.98 | 69.98 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 18 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 1.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 4710-60-V00-0098 | TUBE, METALLIC, REFRIGERATION, COPPER, 5/8 INCH X 50 FEET | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 20 | RO | 1 | 100.39 | 100.39 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 19 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 1.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5620-60-V00-0002 | CONCRETE MASONRY UNIT, SOLID, 12 X 12 X 2 INCHES | 41975 | 2023-09-09 | 2023-09-10 | CLOSE | 2 | EA | 8 | 42.84 | 342.72 | 16746 | SENT | 2023-09-26 | 2023-09-13 | KW1-11705 | 18 | 2023-09-15 | APPR | 2023-09-15 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-24 | COMP | 2023-09-20 | 8.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0435 | PAD, ANTI VIBRATION, RUBBER/CORK, 4 X 4 X 1 INCHES | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 21 | EA | 8 | 12.59 | 100.72 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 20 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-23 | 8.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 4120-60-V00-0018 | AIR CONDITIONER, SPLIT, INDOOR & OUTDOOR, 220-240V, 1 PH, 50/60 HZ, BTU 22000 | 41972 | 2023-09-09 | 2023-09-14 | CLOSE | 1 | EA | 2 | 1062.75 | 2125.5 | 17211 | CLOSE | 2023-09-28 | 2023-09-25 | KW1-12040 | 1 | 2023-09-28 | APPR | 2023-09-28 | Kannoth, Shajee -Vectrus -GSD -No Export | CARRIER KUWAIT AIR CONDITIONING | 2023-10-14 | COMP | 2023-10-16 | 2.00 |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5935-60-V00-0160 | SOCKET, OUTLET, WEATHERPROOF, 2 GANG, 2 POLES, 13 AMPS | 41958 | 2023-09-09 | 2023-09-12 | CLOSE | 1 | EA | 2 | 34.6 | 69.2 | 16805 | CLOSE | 2023-09-17 | 2023-09-14 | KW1-11755 | 3 | 2023-09-17 | CLOSE | 2023-10-17 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 |  |  |  |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5935-60-V00-0160 | SOCKET, OUTLET, WEATHERPROOF, 2 GANG, 2 POLES, 13 AMPS | 41958 | 2023-09-09 | 2023-09-12 | CLOSE | 2 | EA | 3 | 34.6 | 103.8 | 16805 | CLOSE | 2023-09-17 | 2023-09-14 | KW1-11755 | 4 | 2023-09-17 | CLOSE | 2023-10-17 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 |  |  |  |  | AJ | AJ table | September | 2023
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0093 | CABLE, POWER, ELECTRICAL, H07RN-F, BLACK, 5 CORE, 1.5 MM² | CANCELLED | 2023-09-09 |  |  |  | MR | 1 | [18 empty] | AJ | AJ table | September | 2023
94 | 2023-09-11 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0041 | PANEL, CEILING (ACOUSTICAL TILE), MINERAL FIBER, WHITE, 24 X 24 X 3/4 INCHES | 42021 | 2023-09-11 | 2023-09-14 |  | 500 | EA | 1 | [6 empty] | KW1-11811 | 9 | [5 empty] | 2023-09-27 | COMP | 2023-09-24 | 500 |  | AJ | AJ table | September | 2023
94 | 2023-09-11 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8010-60-V00-0089 | PRIMER, COATING, WHITE, 4 - 5 LITERS | 42022 | 2023-09-11 | 2023-09-12 | CLOSE | 1 | CN | 20 | 40.88 | 817.6 |  |  |  |  | KW1-11669 | 1 | 2023-09-13 | CLOSE | 2023-12-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RITAJ AL KUWAIT GENERAL TRADING CONTRACTING CO | 2023-09-14 03:00 | COMP | 2023-09-14 | 20.00 |  | AJ | AJ table | September | 2023
95 | 2023-09-12 | 150 | AJ22-0135 | T357 Relocation | 2141526 | 5305-60-V00-0001 | SCREW, SELF DRILLING, HEX WASHER HEAD, STEEL, 5/16 X 1 INCH | 44483 | 2023-09-12 | 2023-10-15 | CLOSE | 1 | BX | 1 | 19.31 | 19.31 | 18060 | CLOSE | 2023-10-19 | 2023-10-18 | KW1-12397 | 29 | 2023-10-19 | APPR | 2023-10-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-26 | COMP | 2023-10-23 | 1.00 |  | AJ | AJ table | September | 2023
95 | 2023-09-12 | 150 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0484 | BOX CONNECTOR, ELECTRICAL, METALLIC CONDUIT, ZINC, 3/4 INCH | 44483 | 2023-09-12 | 2023-10-15 | CLOSE | 2 | EA | 100 | 3.33 | 333 | 18060 | CLOSE | 2023-10-19 | 2023-10-18 | KW1-12397 | 30 | 2023-10-19 | APPR | 2023-10-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-24 | COMP | 2023-10-25 | 100.00 |  | AJ | AJ table | September | 2023
96 | 2023-09-12 | 60 | AJ23-0747 | Technical Inspection Repairs, T5802 | 7162722 | 5305-60-V00-0032 | SCREW, DRYWALL, FLAT COUNTERSUNK, PHILLIPS, COARSE THREAD, #6 X 1-1/4 INCHES | 42166 | 2023-09-12 | 2023-09-17 | CLOSE | 1 | BX | 20 | 15.04 | 300.8 | 17013 | SENT | 2023-09-27 | 2023-09-20 | KW1-11867 | 4 | 2023-09-22 | CLOSE | 2023-10-03 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-30 | COMP | 2023-09-26 | 20.00 |  | AJ | AJ table | September | 2023
97 | 2023-09-12 | 50 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5440-05-V01-0009 | LADDER, SAFETY STEP, ROLLING, 3 STEPS, STEEL, 30 INCHES, 450 LBS | 42126 | 2023-09-12 | 2023-09-14 | CLOSE | 1 | EA | 2 | 616.44 | 1232.88 | 16967 | CLOSE | 2023-09-23 | 2023-09-18 | KW1-11811 | 11 | 2023-11-17 | APPR | 2023-11-17 | Kannoth, Shajee -Vectrus -GSD -No Export | RITAJ AL KUWAIT GENERAL TRADING CONTRACTING CO | 2023-11-15 | COMP | 2023-10-05 | 2.00 |  | AJ | AJ table | September | 2023
97 | 2023-09-12 | 50 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 7510-05-V00-0023 | TAPE, PRESSURE SENSITIVE ADHESIVE, ANTI-SLIP, BLACK, 4 INCHES X 33 FEET | 42126 | 2023-09-12 | 2023-09-14 | CLOSE | 2 | EA | 8 | 45 | 360 | 16967 | CLOSE | 2023-09-23 | 2023-09-18 | KW1-11811 | 12 | 2023-11-17 | APPR | 2023-11-17 | Kannoth, Shajee -Vectrus -GSD -No Export | RITAJ AL KUWAIT GENERAL TRADING CONTRACTING CO | 2023-11-15 | COMP | 2023-10-04 | 8.00 |  | AJ | AJ table | September | 2023
98 | 2023-09-13 | 150 | AJ22-0135 | T357 Relocation | 2141526 | 5315-60-V00-0058 | NAIL, FLAT, STAINLESS-STEEL, 2D X 1 INCH | 42202 | 2023-09-13 | 2023-09-14 | CLOSE | 1 | BX | 3 | 12.49 | 37.47 | 16964 | CLOSE | 2023-09-20 | 2023-09-18 | KW1-11832 | 42 | 2023-09-20 | APPR | 2023-09-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-27 03:00 | COMP | 2023-09-26 | 3.00 |  | AJ | AJ table | September | 2023
98 | 2023-09-13 | 150 | AJ22-0135 | T357 Relocation | 2141526 | 5315-60-V00-0057 | NAIL, FLAT, STAINLESS STEEL, 3D X 1-1/4 INCHES | 42203 | 2023-09-13 | 2023-09-14 | CLOSE | 1 | BX | 3 | 47.29 | 141.87 | 16964 | CLOSE | 2023-09-20 | 2023-09-18 | KW1-11832 | 43 | 2023-09-20 | APPR | 2023-09-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-27 03:00 | COMP | 2023-09-26 | 3.00 |  | AJ | AJ table | September | 2023
99 | 2023-09-13 | 70 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0093 | CABLE, POWER, ELECTRICAL, H07RN-F, BLACK, 5 CORE, 1.5 MM² | 42192 | 2023-09-13 | 2023-09-17 | CLOSE | 1 | MR | 20 | 10.23 | 204.6 | 17006 | CLOSE | 2023-09-22 | 2023-09-20 | KW1-11873 | 1 | 2023-09-22 | CLOSE | 2023-11-14 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-26 | 20.00 |  | AJ | AJ table | September | 2023
100 | 2023-09-14 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 6530-60-V00-0021 | BASIN, WASH, w/ PEDESTAL, CERAMIC, WHITE, 54 X 20 X 46 CENTIMETERS | 42332 | 2023-09-14 | 2023-09-17 | CLOSE | 1 | EA | 1 | 107.97 | 107.97 | 17069 | CLOSE | 2023-09-28 | 2023-09-20 | KW1-12052 | 28 | 2023-11-17 | APPR | 2023-11-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | COMMERCIAL UNITED GINCO EST. | 2023-10-07 03:00 | COMP | 2023-10-04 | 1.00 |  | AJ | AJ table | September | 2023
100 | 2023-09-14 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0124 | FAUCET, LEVER, SINGLE, CHROME, BRASS, WASH BASIN MIXER | 41335 | 2023-09-14 | 2023-09-05 | CLOSE | 1 | EA | 1 | 59.51 | 119.02 | 16605 | CLOSE | 2023-09-13 | 2023-09-07 | KW1-11652 | 1 | 2023-09-13 | CLOSE | 2023-12-16 | Kandankara, Thomas -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-27 | COMP | 2023-09-18 | 2.00 |  | AJ | AJ table | September | 2023
100 | 2023-09-14 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0094 | TRAP, BOTTLE, ADJUSTABLE INLET, 1-1/4 INCHES | 41336 | 2023-09-14 | 2023-09-05 | CLOSE | 3 | EA | 1 | 14.09 | 14.09 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 7 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 1.00 |  | AJ | AJ table | September | 2023
100 | 2023-09-14 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0017 | DISPENSER, SOAP, HORIZONTAL, STEEL, 1200 ML | 42329 | 2023-09-14 | 2023-09-17 | CLOSE | 2 | EA | 1 | 126.54 | 126.54 | 17069 | CLOSE | 2023-09-28 | 2023-09-20 | KW1-12052 | 25 | 2023-11-17 | APPR | 2023-11-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | COMMERCIAL UNITED GINCO EST. | 2023-10-07 03:00 | COMP | 2023-10-03 | 1.00 |  | AJ | AJ table | September | 2023
100 | 2023-09-14 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0110 | FAUCET, SINK, HOT AND COLD, GOOSE NECK | 42328 | 2023-09-14 | 2023-09-17 | CLOSE | 1 | EA | 1 | 174.83 | 174.83 | 17069 | CLOSE | 2023-09-28 | 2023-09-20 | KW1-12052 | 23 | 2023-11-17 | APPR | 2023-11-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | COMMERCIAL UNITED GINCO EST. | 2023-10-07 03:00 | COMP | 2023-10-04 | 1.00 |  | AJ | AJ table | September | 2023
100 | 2023-09-14 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 7105-60-V00-0019 | MIRROR, GLASS, ROUND, WALL MOUNTED, WHITE, 50 CM | 42329 | 2023-09-14 | 2023-09-17 | CLOSE | 1 | EA | 3 | 19.65 | 58.95 | 17069 | CLOSE | 2023-09-28 | 2023-09-20 | KW1-12052 | 24 | 2023-11-17 | APPR | 2023-11-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | COMMERCIAL UNITED GINCO EST. | 2023-10-07 03:00 | COMP | 2023-10-04 | 3.00 |  | AJ | AJ table | September | 2023
100 | 2023-09-18 | 160 | AJ22-0135 | T357 Relocation | 2141526 | 5650-60-V00-0002 | ROOFING METAL, WHITE, 0.35 MM X 3 METER | 42572 | 2023-09-18 | 2023-09-25 | CLOSE | 1 | SH | 30 | 25.47 | 764.1 | 17327 | CLOSE | 2023-09-30 | 2023-09-27 | KW1-12081 | 1 | 2023-09-30 | CLOSE | 2023-11-14 | Vishwanath, Shet -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-21 | COMP | 2023-10-08 | 30.00 |  | AJ | AJ table | September | 2023
100 | 2023-09-20 | 160 | AJ22-0135 | T357 Relocation | 2141526 | 5940-60-V00-0003 | LUG, TERMINAL, FORK, INSULATED, BLUE, 16-14 AWG | 42817 | 2023-09-20 | 2023-09-28 | CLOSE | 1 | BG | 1 | 53.63 | 53.63 | 17397 | CLOSE | 2023-10-04 | 2023-10-01 | KW1-12130 | 7 | 2023-10-04 | CLOSE | 2023-11-14 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-12 | COMP | 2023-10-09 | 1.00 |  | AJ | AJ table | September | 2023
100 | 2023-09-20 | 160 | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0093 | CABLE, POWER, ELECTRICAL, H07RN-F, BLACK, 5 CORE, 1.5 MM² | 42816 | 2023-09-20 | 2023-09-28 | CLOSE | 1 | MR | 90 | 27.31 | 2457.9 | 17508 | CLOSE | 2023-10-12 | 2023-10-02 | KW1-12261 | 3 | 2023-11-17 | APPR | 2023-11-17 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-19 | COMP | 2023-10-17 | 90.00 |  | AJ | AJ table | September | 2023
100 | 2023-09-20 | 160 | AJ22-0135 | T357 Relocation | 2141526 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 40905 | 2023-09-20 | 2023-09-02 | CLOSE | 5 | EA | 5 | 52.28 | 522.8 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 5 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 10.00 |  | AJ | AJ table | September | 2023
100 | 2023-09-20 | 160 | AJ22-0135 | T357 Relocation | 2141526 | 5930-60-V00-0254 | SWITCH, DOUBLE POLE, METAL CLAD, 1 GANG, 32A | 42816 | 2023-09-20 | 2023-09-28 | CLOSE | 3 | EA | 11 | 71.1 | 782.1 | 17508 | CLOSE | 2023-10-12 | 2023-10-02 | KW1-12261 | 5 | 2023-11-17 | APPR | 2023-11-17 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-19 | COMP | 2023-10-17 | 11.00 |  | AJ | AJ table | September | 2023
101 | 2023-09-20 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 3030-60-V00-0252 | BELT, V, RIBBED, RUBBER, 21.5 X 18 X 0.7 CENTIMETERS | 42764 | 2023-09-20 | 2023-09-28 | CLOSE | 1 | EA | 3 | 21.05 | 63.15 | 17467 | CLOSE | 2023-10-06 | 2023-10-01 | KW1-12158 | 5 | 2023-10-06 | APPR | 2023-10-06 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL BAYADER INTER.GROUP COMPANY | 2023-11-22 | COMP | 2023-10-11 | 3.00 |  | AJ | AJ table | September | 2023
101 | 2023-09-20 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8030-60-V00-0050 | PUTTY, WOOD FILLER, MEDIUM OAK, 250 ML | 42831 | 2023-09-20 | 2023-09-28 | CLOSE | 1 | CN | 3 | 68.27 | 204.81 | 17486 | CLOSE | 2023-10-05 | 2023-10-02 | KW1-12145 | 9 | 2023-10-05 | APPR | 2023-10-05 | Kannoth, Shajee -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2023-10-21 | COMP | 2023-10-19 | 3.00 |  | AJ | AJ table | September | 2023
102 | 2023-09-21 |  | AJ22-0135 | T357 Relocation | 2141526 | 8030-60-V00-0008 | SEALING COMPOUND, GUTTER & SEAM, WHITE, 10 OZ. | 42899 | 2023-09-21 | 2023-09-28 | CLOSE | 1 | CQ | 12 | 23.31 | 279.72 | 17511 | CLOSE | 2023-10-06 | 2023-10-02 | KW1-12161 | 1 | 2023-10-25 | APPR | 2023-10-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-10-30 | COMP | 2023-11-01 | 12.00 |  | AJ | AJ table | September | 2023
102 | 2023-10-01 |  | AJ22-0135 | T357 Relocation | 2141526 | 8010-60-V00-0050 | PAINT, ENAMEL, GLOSS, DARK BROWN, 3.2 AND 3.6 LITER | 43584 | 2023-10-01 | 2023-10-09 | CLOSE | 1 | CN | 6 | 39.96 | 239.76 | 17823 | CLOSE | 2023-10-19 | 2023-10-12 | KW1-12361 | 7 | 2023-10-17 | APPR | 2023-10-17 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-05 | COMP | 2023-11-07 | 6.00 |  | AJ | AJ table | October | 2023
103 | 2023-10-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4140-60-V00-0120 | FAN, VENTILATING, SQUARE, 220V, 8 INCHES | 43886 | 2023-10-05 | 2023-10-10 | CLOSE | 1 | EA | 3 | 85.32 | 255.96 | 17855 | CLOSE | 2023-10-17 | 2023-10-12 | KW1-12375 | 1 | 2023-10-17 | CLOSE | 2023-11-14 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-31 | COMP | 2023-10-22 | 3.00 |  | AJ | AJ table | October | 2023
103 | 2023-10-08 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5315-60-V00-0057 | NAIL, FLAT, STAINLESS STEEL, 3D X 1-1/4 INCHES | 44114 | 2023-10-08 | 2023-10-15 | CLOSE | 1 | BX | 5 | 47.29 | 236.45 | 18112 | CLOSE | 2023-10-24 | 2023-10-19 | KW1-12486 | 1 | 2023-10-24 | APPR | 2023-10-24 | Bharadwajan, Sajan - Vectrus - No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2023-10-30 | COMP | 2023-10-28 | 5.00 |  | AJ | AJ table | October | 2023
103 | 2023-10-08 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5315-60-V00-0058 | NAIL, FLAT, STAINLESS-STEEL, 2D X 1 INCH | 44114 | 2023-10-08 | 2023-10-15 | CLOSE | 2 | BX | 5 | 13.65 | 68.25 | 18112 | CLOSE | 2023-10-24 | 2023-10-19 | KW1-12486 | 2 | 2023-10-24 | APPR | 2023-10-24 | Bharadwajan, Sajan - Vectrus - No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2023-10-30 | COMP | 2023-10-28 | 5.00 |  | AJ | AJ table | October | 2023
103 | 2023-10-08 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5510-60-V00-0028 | PLYWOOD, CONSTRUCTION, MARINE GRADE, 1/2 INCH X 8 X 4 FEET | 44115 | 2023-10-08 | 2023-10-15 | CLOSE | 1 | SH | 10 | 58.28 | 582.8 | 18112 | CLOSE | 2023-10-24 | 2023-10-19 | KW1-12486 | 3 | 2023-10-24 | APPR | 2023-10-24 | Bharadwajan, Sajan - Vectrus - No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2023-10-30 | COMP | 2023-10-28 | 10.00 |  | AJ | AJ table | October | 2023
103 | 2023-10-08 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8040-60-V00-0033 | ADHESIVE, RESIN, SYNTHETIC, WHITE, 5 KG | 44144 | 2023-10-08 | 2023-10-15 | CLOSE | 1 | CN | 3 | 26.64 | 79.92 | 18112 | CLOSE | 2023-10-24 | 2023-10-19 | KW1-12486 | 4 | 2023-10-24 | APPR | 2023-10-24 | Bharadwajan, Sajan - Vectrus - No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2023-10-30 | COMP | 2023-10-28 | 3.00 |  | AJ | AJ table | October | 2023
104 | 2023-10-15 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0102 | COVER, DRAIN, w/HOLE, SQUARE, METAL, 6 X 6 INCHES | 44761 | 2023-10-15 | 2023-10-16 | CLOSE | 1 | EA | 2 | 20.46 | 40.92 | 18082 | CLOSE | 2023-11-01 | 2023-10-19 | KW1-12689 | 10 | 2023-11-01 | APPR | 2023-11-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-11-07 | COMP | 2023-11-05 | 2.00 |  | AJ | AJ table | October | 2023
104 | 2023-10-15 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0304 | COUPLING, DRAINAGE PIPE, (PAN CONNECTOR), POLYPROPYLENE, WHITE, 4 INCHES X 110 MM | 44760 | 2023-10-15 | 2023-10-16 | CLOSE | 1 | EA | 4 | 15.04 | 60.16 | 18082 | CLOSE | 2023-11-01 | 2023-10-19 | KW1-12689 | 8 | 2023-11-01 | APPR | 2023-11-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-11-07 | COMP | 2023-11-05 | 4.00 |  | AJ | AJ table | October | 2023
105 | 2023-10-15 |  | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5340-60-V00-0169 | LOCK SET, MORTISE, RIM EXIT DEVICE, KEY OUTSIDE UNLOCKS/LOCKS TRIM | 44762 | 2023-10-15 | 2023-10-16 | CLOSE | 1 | EA | 1 | 2317.61 | 2317.61 | 18098 | CLOSE | 2023-10-29 | 2023-10-19 | KW1-12624 | 1 | 2023-10-29 | APPR | 2023-10-29 | Reghunath, Rajesh -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2023-11-05 | COMP | 2023-11-02 | 1.00 |  | AJ | AJ table | October | 2023
106 | 2023-10-18 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5510-60-V00-0031 | WOOD, SOLID, MOULDING/ DECORATIVE, NATURAL, 1/2 X 2 INCHES X 10 FEET | 45096 | 2023-10-18 | 2023-10-22 | CLOSE | 1 | EA | 25 | 25.83 | 645.75 | 18243 | CLOSE | 2023-10-29 | 2023-10-23 | KW1-12638 | 7 | 2023-10-29 | APPR | 2023-10-29 | Bharadwajan, Sajan - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2023-11-03 | COMP | 2023-11-04 | 25.00 |  | AJ | AJ table | October | 2023
107 | 2023-10-22 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0883 | CAP, PROTECTIVE (COVER CAP), PUSH FITTING, PLASTIC, LIGHT GREY, 15 MM | 45319 | 2023-10-22 | 2023-11-01 | CLOSE | 1 | EA | 200 | 0.14 | 28 | 18566 | CLOSE | 2023-11-03 | 2023-11-02 | KW1-12736 | 5 | 2023-11-03 | APPR | 2023-11-03 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-11-17 | COMP | 2023-11-08 | 200.00 |  | AJ | AJ table | October | 2023
107 | 2023-10-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 8010-60-V00-0238 | PAINT, LATEX, GLOSSY, BRIGHT WHITE, 1 GL | 45847 | 2023-10-28 | 2023-11-01 | CLOSE | 1 | GL | 12 | 39.96 | 479.52 | 18543 | CLOSE | 2023-11-03 | 2023-11-02 | KW1-12735 | 5 | 2023-11-17 | APPR | 2023-11-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2023-11-11 | COMP | 2023-11-13 | 12.00 |  | AJ | AJ table | October | 2023
107 | 2023-10-29 |  | AJ22-0135 | T357 Relocation | 2141526 | 5930-60-V00-0246 | SWITCH, WEATHERPROOF, GRAY, 1 GANG, 16 A | 45910 | 2023-10-29 | 2023-11-04 | CLOSE | 1 | EA | 5 | 21.15 | 105.75 | 18674 | CLOSE | 2023-11-15 |  | KW1-12993 | 1 | 2023-11-15 | APPR | 2023-11-15 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-20 | COMP | 2023-11-19 | 5.00 |  | AJ | AJ table | October | 2023
107 | 2023-10-30 |  | AJ22-0135 | T357 Relocation | 2141526 | 5210-60-V00-0040 | CHALK LINE AND REEL, w/ BLUE CHALK, 100 FEET | 45917 | 2023-10-30 | 2023-11-05 | CLOSE | 1 | EA | 5 | 43.96 | 219.8 |  |  |  |  | KW1-12801 | 5 | 2023-11-17 | APPR | 2023-11-17 | Thomas, Vinu - Vectrus -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-20 | COMP | 2023-11-21 | 5.00 |  | AJ | AJ table | October | 2023
107 | 2023-10-30 |  | AJ22-0135 | T357 Relocation | 2141526 | 5670-60-V00-0026 | WALL ANGLE / GRID, CEILING, TEE, GALVANIZED STEEL, WHITE, 12 FEET | 45939 | 2023-10-30 | 2023-11-05 | CLOSE |  | EA | 50 | 18.48 | 924 | 18706 | CLOSE | 2023-11-10 | 2023-11-08 | KW1-12881 | 6 | 2023-11-10 | APPR | 2023-11-10 | Thomas, Vinu - Vectrus -No Export | CREDENCE TRADING EST. | 2023-11-16 | COMP | 2023-11-15 | 50.00 |  | AJ | AJ table | October | 2023
107 | 2023-11-01 |  | AJ22-0135 | T357 Relocation | 2141526 | 4020-60-V00-0004 | TWINE, NYLON, FLOURESCENT YELLOW, 500 FEET | 46216 | 2023-11-01 | 2023-11-05 | CLOSE |  | RO | 5 | 21.45 | 107.25 | 18708 | SENT | 2023-11-07 | 2023-11-08 | KW1-12883 | 9 | 2023-11-10 | APPR | 2023-11-10 | Thomas, Vinu - Vectrus -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-12-10 | COMP | 2023-12-07 | 5.00 |  | AJ | AJ table | November | 2023
107 | 2023-11-06 |  | AJ22-0135 | T357 Relocation | 2141526 | 6210-60-V00-0136 | LIGHT UNIT, EMERGENCY, (EXIT LIGHT), LED, 120-277 V, 50/60 HZ, 2 W | 46744 | 2023-11-06 | 2023-11-08 | CLOSE | 1 | EA | 6 | 134.07 | 804.42 | 18809 | CLOSE | 2023-11-15 | 2023-11-12 | KW1-13012 | 12 | 2023-11-16 | APPR | 2023-11-16 | Thomas, Vinu - Vectrus -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-22 | COMP | 2023-11-20 | 6.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 5120-60-V00-0267 | KNIFE, PUTTY, STAINLESS STEEL, BLACK/BLUE, 5 INCHES | 46722 | 2023-11-08 | 2023-11-19 | CLOSE | 1 | EA | 3 | 16.48 | 49.44 | 19144 | CLOSE | 2023-11-30 | 2023-11-22 | KW1-13216 | 4 | 2023-11-23 | APPR | 2023-11-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-11-28 | COMP | 2023-11-27 | 3.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 4240-60-V00-0121 | TAPE, WARNING, BARRICADE, "CAUTION", YELLOW/BLACK | 46722 | 2023-11-08 | 2023-11-19 | CLOSE | 2 | RL | 1 | 185.31 | 185.31 | 19144 | CLOSE | 2023-11-30 | 2023-11-22 | KW1-13216 | 5 | 2023-11-23 | APPR | 2023-11-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-11-28 | COMP | 2023-11-26 | 1.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8105-01-175-5533 | BAG, PLASTIC, NATURAL, 24 X 24 INCHES, 7-10 GL | 46728 | 2023-11-08 | 2023-11-08 | CLOSE | 1 | BX | 2 | 92.57 | 185.14 | 18852 | CLOSE | 2023-11-10 |  | KW1-12884 | 39 | 2023-11-13 | APPR | 2023-11-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-24 | COMP | 2023-11-15 | 2.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 5345-60-V00-0007 | DISK, ABRASIVE, SANDING, GOLD, 100 GRIT, 6 INCHES | 46731 | 2023-11-08 | 2023-11-09 | CLOSE | 2 | RO | 5 | 77.55 | 387.75 | 18889 | CLOSE | 2023-11-15 | 2023-11-13 | KW1-13011 | 2 | 2023-11-15 | APPR | 2023-11-15 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-12-24 | COMP | 2023-12-05 | 5.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8415-01-013-7382 | GLOVES, CHEMICAL AND OIL PROTECTION, GREEN, SIZE 10 | 46727 | 2023-11-08 | 2023-11-08 | CLOSE | 1 | PR | 20 | 31.5 | 630 | 18787 | CLOSE | 2023-11-12 | 2023-11-11 | KW1-12926 | 12 | 2023-11-12 | APPR | 2023-11-12 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-25 | COMP | 2023-12-05 | 20.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8415-01-610-7322 | GLOVES, IMPACT, LEATHER, BLACK, X-SMALL | 46731 | 2023-11-08 | 2023-11-09 | CLOSE | 3 | PR | 6 | 99.42 | 596.52 | 18889 | CLOSE | 2023-11-15 | 2023-11-13 | KW1-13011 | 3 | 2023-11-15 | APPR | 2023-11-15 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-11-30 | COMP | 2023-11-29 | 6.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 4240-01-463-5449 | RESPIRATOR, PARTICULATE, DISPOSABLE | 46725 | 2023-11-08 | 2023-11-08 | CLOSE | 1 | BX | 3 | 44.12 | 132.36 | 18907 | CLOSE | 2023-11-16 | 2023-11-15 | KW1-13025 | 3 | 2023-11-19 | APPR | 2023-11-19 | Kandankara, Thomas -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-12-07 | COMP | 2023-11-23 | 3.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 7920-60-V00-0039 | MOP, DUST, W/HANDLE, SWIVEL HEAD, LEIGHT WEIGHT, 24 X 60 INCHES | 46726 | 2023-11-08 | 2023-11-08 | CLOSE | 1 | EA | 4 | 81.59 | 326.36 | 18787 | CLOSE | 2023-11-12 | 2023-11-11 | KW1-12926 | 11 | 2023-11-12 | APPR | 2023-11-12 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-21 | COMP | 2023-11-16 | 4.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 7920-00-148-9666 | RAG, WIPING, COTTON (MIXED COLOR), 50LB | 46728 | 2023-11-08 | 2023-11-08 | CLOSE | 2 | BE | 1 | 72.26 | 72.26 | 18787 | CLOSE | 2023-11-12 | 2023-11-11 | KW1-12926 | 13 | 2023-11-12 | APPR | 2023-11-12 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-25 | COMP | 2023-11-15 | 1.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 7510-00-266-6707 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 3 INCHES X 60 YARDS | 46729 | 2023-11-08 | 2023-11-08 | CLOSE | 1 | RO | 30 | 21.5 | 645 | 18873 | CLOSE | 2023-11-10 |  | KW1-12899 | 1 | 2023-11-10 | APPR | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-01-19 | COMP | 2023-11-13 | 30.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8020-00-260-1302 | BRUSH, PAINT, BRISTLES, CHISELED, 2 INCHES | 46730 | 2023-11-08 | 2023-11-08 | CLOSE | 1 | EA | 25 | 13.1 | 327.5 | 18789 | CLOSE | 2023-11-10 | 2023-11-08 | KW1-12892 | 7 | 2023-11-10 | APPR | 2023-11-10 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2023-11-18 | COMP | 2023-11-14 | 25.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 46730 | 2023-11-08 | 2023-11-08 | CLOSE | 2 | EA | 50 | 13.9 | 695 | 18789 | CLOSE | 2023-11-10 | 2023-11-08 | KW1-12892 | 8 | 2023-11-10 | APPR | 2023-11-10 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2023-11-22 | COMP | 2023-11-22 | 50.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 46724 | 2023-11-08 | 2023-11-08 | CLOSE | 1 | EA | 20 | 29.3 | 586 |  |  |  |  | KW1-12860 | 5 | 2023-11-08 | APPR | 2023-11-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-12 | COMP | 2023-11-12 | 20.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 5120-60-V00-0276 | DISPENSER, SEALANT, RED, 500 ML | 46723 | 2023-11-08 | 2023-11-08 | CLOSE | 1 | EA | 2 | 276.89 | 553.78 | 18787 | CLOSE | 2023-11-12 | 2023-11-11 | KW1-12926 | 10 | 2023-11-12 | APPR | 2023-11-12 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-30 | COMP | 2023-11-27 | 2.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8030-60-V00-0081 | PUTTY, MULTI PURPOSE, PLASTIC, GRAY, 1-QUART | 46725 | 2023-11-08 | 2023-11-08 | CLOSE | 2 | CN | 5 | 141.53 | 707.65 | 18907 | CLOSE | 2023-11-16 | 2023-11-15 | KW1-13025 | 4 | 2023-11-19 | APPR | 2023-11-19 | Kandankara, Thomas -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-11-30 | COMP | 2023-11-29 | 5.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8040-60-V00-0020 | ADHESIVE, INJECTABLE MORTAR, HYBRID, ANCHORING SYSTEM, GREY/WHITE, 500ML | 46722 | 2023-11-08 | 2023-11-19 | CLOSE | 3 | PG | 20 | 104.73 | 2094.6 | 19144 | CLOSE | 2023-11-30 | 2023-11-22 | KW1-13216 | 6 | 2023-11-23 | APPR | 2023-11-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-11-28 | COMP | 2023-11-29 | 20.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8010-60-V00-0091 | EPOXY PRIMER COATING, CLEAR, GALLON | 46722 | 2023-11-08 | 2023-11-19 | CLOSE | 4 | GL | 4 | 193.14 | 772.56 | 19144 | CLOSE | 2023-11-30 | 2023-11-22 | KW1-13216 | 7 | 2023-11-23 | APPR | 2023-11-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-06 | COMP | 2023-11-27 | 4.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8010-60-V00-0100 | EPOXY COATING KIT, GRAY, PART A&B, 20 LITER | 46722 | 2023-11-08 | 2023-11-19 | CLOSE | 5 | KT | 9 | 243.92 | 2195.28 | 19144 | CLOSE | 2023-11-30 | 2023-11-22 | KW1-13216 | 8 | 2023-11-23 | APPR | 2023-11-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-11-28 | COMP | 2023-11-26 | 9.00 |  | AJ | AJ table | November | 2023
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8415-60-V00-0336 | SUIT, CHEMICAL PROTECTIVE, WHITE, XL | 46782 | 2023-11-08 | 2023-11-15 | CAN | 1 | CA | 4 | 1084.99 | 4339.96 | [14 empty] | CAN |  | AJ | AJ table | November | 2023
109 | 2023-11-08 | 30 | AJ23-0508 | Bay 3 Floor Painting | 7971778 | 3895-60-V00-0006 | MIXER, PAINT, STEEL, 4 X 23-1/2 INCHES | 46731 | 2023-11-08 | 2023-11-09 | CLOSE | 1 | EA | 3 | 10.39 | 31.17 | 18889 | CLOSE | 2023-11-15 | 2023-11-13 | KW1-13011 | 1 | 2023-11-15 | APPR | 2023-11-15 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-11-22 | COMP | 2023-11-19 | 3.00 |  | AJ | AJ table | November | 2023
110 | 2023-11-09 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 7930-05-V00-0002 | CLEANER, ALL PURPOSE, LIQUID, ALCOHOL, PK2, GREEN, 1GAL | 47114 | 2023-11-09 | 2023-11-09 | CLOSE | 1 | PK | 3 | 11.4 | 34.2 | 18889 | CLOSE | 2023-11-15 | 2023-11-13 | KW1-13011 | 13 | 2023-11-15 | APPR | 2023-11-15 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-12-13 | COMP | 2023-11-21 | 3.00 |  | AJ | AJ table | November | 2023
110 | 2023-11-09 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 5110-05-V01-0010 | KNIFE, PUTTY, STEEL, 4 INCHES | 47115 | 2023-11-09 | 2023-11-15 |  | 13 | EA | 5 | [6 empty] | KW1-12994 | 13 | [5 empty] | 2023-11-15 |  |  |  |  | AJ | AJ table | November | 2023
112 | 2023-11-12 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8415-60-V00-0352 | COVERALLS, DISPOSABLE PROTECTIVE, TYVEK400, WHITE, XL | 47327 | 2023-11-12 | 2023-11-15 |  | 5 | BX | 2 | [6 empty] | KW1-13276 | 5 | [5 empty] | 2023-11-25 |  |  |  |  | AJ | AJ table | November | 2023
112 | 2023-11-12 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 4240-60-V00-0143 | RESPIRATOR, AIR FILTERING, REUSABLE, MEDIUM | 47327 | 2023-11-12 | 2023-11-15 |  | 6 | BX | 1 | [6 empty] | KW1-13276 | 6 | [5 empty] | 2023-11-25 |  |  |  |  | AJ | AJ table | November | 2023
112 | 2023-12-24 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 4240-60-V00-0093 | RETAINER, PREFILTER, RESPIRATOR, POLYPROPYLENE, TRANSLUCENT WHITE, 8.5 X 4.5 X 4 INCHES | 50489 | 2023-12-24 | 2023-12-25 | CLOSE | 1 | BX | 1 | 251.82 | 251.82 | 20354 | CLOSE | 2024-01-15 | 2024-01-10 | KW1-14235 | 3 | 2024-01-15 | APPR | 2024-01-15 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-11 | COMP | 2024-01-21 | 1.00 |  | AJ | AJ table | December | 2023
112 | 2023-12-24 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 4240-01-342-2857 | CARTRIDGE, RESPIRATOR, AIR FILTERING, 3.4 X 4.2 INCHES | 50488 | 2023-12-24 | 2023-12-25 | CLOSE | 1 | PG | 1 | 759.2 | 759.2 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 28 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-11 | COMP | 2024-01-20 | 1.00 |  | AJ | AJ table | December | 2023
112 | 2023-12-24 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 4240-60-V00-0004 | FILTER, RESPIRATOR, AIR FILTERING, PARTICULATE, 3.4 X 4.2 INCHES | 50487 | 2023-12-24 | 2023-12-25 | CLOSE | 1 | BX | 1 | 27.64 | 55.28 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 27 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 2.00 |  | AJ | AJ table | December | 2023
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0891 | STRIKE AND KEEPER, INSWING, STAINLESS STEEL, SATIN, 3/4 X 1-1/2 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 24 | EA | 2 | 43.5 | 87 | 19396 | CLOSE | 2023-11-30 |  | KW1-13396 | 6 | 2023-11-30 | CLOSE | 2024-01-09 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-24 | COMP | 2023-12-24 | 2.00 |  | AJ | AJ table | November | 2023
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0892 | LATCH, SLIDE, SURFACE MOUNTED, ZAMAC, POLISHED CHROME, 3-1/2 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 23 | EA | 2 | 16.5 | 33 | 19396 | CLOSE | 2023-11-30 |  | KW1-13396 | 5 | 2023-11-30 | CLOSE | 2024-01-09 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-24 | COMP | 2023-12-24 | 2.00 |  | AJ | AJ table | November | 2023
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0893 | DOORSTOP, ZAMAC, POLISHED CHROME, 2-1/8 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 22 | EA | 1 | 5 | 5 | 19396 | CLOSE | 2023-11-30 |  | KW1-13396 | 4 | 2023-11-30 | CLOSE | 2024-01-09 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-24 | COMP | 2023-12-24 | 1.00 |  | AJ | AJ table | November | 2023
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0894 | COVER STRIP (PRIVACY STRIP), ALUMINIUM, OFFSET, 1/8 X 60 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 21 | EA | 8 | 16.5 | 132 | 19396 | CLOSE | 2023-11-30 |  | KW1-13396 | 3 | 2023-11-30 | CLOSE | 2024-01-09 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-24 | COMP | 2023-12-30 | 8.00 |  | AJ | AJ table | November | 2023
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0887 | BRACKET, MOUNTING(U-BRACKET), STAINLESS STEEL, SATIN, 3/4 X 54 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 20 | EA | 10 | 99.5 | 995 | 19396 | CLOSE | 2023-11-30 |  | KW1-13396 | 2 | 2023-11-30 | CLOSE | 2024-01-09 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-24 | COMP | 2023-12-25 | 10.00 |  | AJ | AJ table | November | 2023
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0888 | BRACKET, MOUNTING(H-BRACKET), STAINLESS STEEL, 3/4 X 57 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 19 | EA | 8 | 235 | 1880 | 19396 | CLOSE | 2023-11-30 |  | KW1-13396 | 1 | 2023-11-30 | CLOSE | 2024-01-09 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-24 | COMP | 2023-12-25 | 8.00 |  | AJ | AJ table | November | 2023
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0889 | BRACKET, MOUNTING, WALL, HINGED, STAINLESS STEEL, SATIN, 3/4 X 3 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 18 | EA | 4 | 40 | 160 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 22 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-24 | COMP | 2023-12-24 | 4.00 |  | AJ | AJ table | November | 2023
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0890 | BRACKET, MOUNTING (WALL BRACKET), TWO EAR, STAINLESS STEEL, SATIN, 3/4 X 57 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 17 | EA | 4 | 253.5 | 1014 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 21 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-24 | COMP | 2024-01-07 | 4.00 |  | AJ | AJ table | November | 2023
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5530-60-V00-0006 | PLYWOOD, DECOR, MELAMINE, 18MM X 4 X 8 FEET | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 16 | EA | 5 | 26 | 130 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 20 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-05 | 5.00 |  | AJ | AJ table | November | 2023
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5305-60-V00-0054 | SCREW, TAPPING, TRUSS HEAD, PHILLIPS, STAINLESS STEEL, #8 X 1/2 INCHES | 48350 | 2023-11-26 | 2023-11-27 | CLOSE | 1 | BG | 2 | 28 | 56 | 19316 | CLOSE | 2023-11-28 |  | KW1-13345 | 2 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-01 | 2.00 |  | AJ | AJ table | November | 2023
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5640-60-V00-0072 | SHEET, WALL, ACRYLIC, WHITE, PLEXIGLASS, 1/4 X 24 X 96 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 15 | EA | 3 | 336.86 | 1010.58 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 19 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 3.00 |  | AJ | AJ table | November | 2023
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 7230-00-849-9839 | CURTAIN, SHOWER, VINYL FILM, PLASTIC, WHITE, 36 X 72 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 14 | EA | 1 | 11.79 | 11.79 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 18 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-24 | COMP | 2023-12-05 | 1.00 |  | AJ | AJ table | November | 2023
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0143 | ROD, SHOWER CURTAIN, EXTENDABLE, ALUMINIUM ALLOY, WHITE, 25 X 25 MM X 2.2 METERS | 48355 | 2023-11-26 | 2023-11-27 | CLOSE | 5 | EA | 1 | 22.8 | 22.8 | 19316 | CLOSE | 2023-11-28 |  | KW1-13339 | 9 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-10 | COMP | 2023-12-01 | 1.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 8040-60-V00-0040 | CEMENT, HEAVY BODIED, CPVC, ORANGE, 16 OZ | 48353 | 2023-11-26 | 2023-11-27 | CLOSE | 2 | CN | 1 | 17.99 | 17.99 | 19316 | CLOSE | 2023-11-28 |  | KW1-13339 | 4 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-10 | COMP | 2023-12-01 | 1.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4510-60-V00-0001 | SHOWER FLOOR, MOLDED STONE, WHITE, 6 X 36 X 36 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 13 | EA | 1 | 208.49 | 208.49 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 17 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-05 | 1.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-1715 | END CAP, SOCKET, CPVC, OFF WHITE, 32 MM | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 7 | EA | 6 | 5.85 | 35.1 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 11 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 6.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-0862 | ELBOW, PIPE, CPVC, BRASS, STANDARD, 90 °, SOCKET X SOCKET, PN25, OFF-WHITE, 20 MM | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 12 | EA | 6 | 7.37 | 44.22 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 16 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 6.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-1714 | SOCKET, PIPE, PVC, GRAY, 1-1/2 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 6 | EA | 6 | 5.51 | 33.06 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 10 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 6.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-1091 | ELBOW, PIPE, CPVC, 45 DEGREE, SOCKET X SOCKET, 25 MM | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 11 | EA | 10 | 2.9 | 29 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 15 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 10.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4710-60-V00-0164 | PIPE, PLASTIC, PVC, GRAY, 1-1/2 INCHES X 6 METERS | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 5 | EA | 1 | 25.77 | 25.77 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 9 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 1.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-0850 | ELBOW, CPVC, SOCKET X SOCKET, SCH 40, OFF-WHITE, 25 MM | 48354 | 2023-11-26 | 2023-11-27 | CLOSE | 5 | EA | 7 | 3.63 | 25.41 | 19316 | CLOSE | 2023-11-28 |  | KW1-13345 | 7 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-01 | 7.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-1716 | REDUCER, PIPE (NIPPLE), MALE X FEMALE, BRASS, 3/4 X 1/2 INCHES X 15MM | 48357, 48400 | 2023-11-26 | 2023-11-27 |  | 4 | EA | 6 | [6 empty] | KW1-13395 | 8 | [5 empty] | 2023-12-10 | COMP | 2023-12-04 | 6 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-0759 | ADAPTER, PRESSURE FITTINGS, FEMALE, CPVC, STANDARD, SOCKET X SR FIPT, SCH- 40, OFF-WHITE, 25 MM | 48352 | 2023-11-26 | 2023-11-27 | CLOSE | 2 | EA | 4 | 3.63 | 14.52 | 19316 | CLOSE | 2023-11-28 |  | KW1-13345 | 3 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-01 | 4.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 48354 | 2023-11-26 | 2023-11-27 | CLOSE | 2 | BX | 10 | 29 | 290 | 19316 | CLOSE | 2023-11-28 |  | KW1-13345 | 5 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-01 | 10.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-0940 | TEE, PIPE, SOCKET X SOCKET X SOCKET, CPVC, OFF-WHITE, SCH 40, 25 MM | 48354 | 2023-11-26 | 2023-11-27 | CLOSE | 4 | EA | 4 | 7.2 | 28.8 | 19316 | CLOSE | 2023-11-28 |  | KW1-13345 | 6 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-01 | 4.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 48355 | 2023-11-26 | 2023-11-27 | CLOSE | 4 | EA | 10 | 13.9 | 139 | 19316 | CLOSE | 2023-11-28 |  | KW1-13339 | 8 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-10 | COMP | 2023-12-01 | 10.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4510-60-V00-0049 | TRAP, BOTTLE, ADJUSTABLE INLET, WHITE, 1-1/2 INCHES | 48349 | 2023-11-26 | 2023-11-27 | CLOSE | 2 | EA | 1 | 22.73 | 22.73 | 19316 | CLOSE | 2023-11-28 |  | KW1-13339 | 2 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-10 | COMP | 2023-12-01 | 1.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 9515-60-V00-0016 | SHEET, METAL, ALUMINIUM, FLAT, 4 X 8 FEET X 1/16 INCH | 48352 | 2023-11-26 | 2023-11-27 | CLOSE | 1 | SH | 3 | 86.66 | 259.98 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 4 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 3.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4510-60-V00-0094 | TRAP, BOTTLE, ADJUSTABLE INLET, 1-1/4 INCHES | 48354 | 2023-11-26 | 2023-11-27 | CLOSE | 3 | EA | 1 | 18.98 | 18.98 | 19316 | CLOSE | 2023-11-28 |  | KW1-13352 | 1 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2023-12-24 | COMP | 2023-12-01 | 1.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 48355 | 2023-11-26 | 2023-11-27 | CLOSE | 3 | BX | 1 | 141.9 | 141.9 | 19316 | CLOSE | 2023-11-28 |  | KW1-13339 | 7 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-10 | COMP | 2023-12-01 | 1.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-1708 | REDUCER, BOSS (REDUCER BUSH), PVC, GRAY, 1-1/4 X 1-1/2 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 10 | EA | 2 | 4.38 | 8.76 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 14 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 2.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GL | 48353 | 2023-11-26 | 2023-11-27 | CLOSE | 1 | GL | 5 | 227.7 | 1138.5 | 19316 | CLOSE | 2023-11-28 |  | KW1-13339 | 3 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-10 | COMP | 2023-12-01 | 5.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-1709 | REDUCER, PIPE, BUSHING, PVC, GRAY, 1-1/2 X 1-1/4 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 9 | EA | 2 | 4.38 | 8.76 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 13 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 2.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 5640-60-V00-0005 | WEATHER STRIP, THRESHOLD, ALUMINUM, 3.2 X 6.4 X 12.7 X 127.0 MM | 48351 | 2023-11-26 | 2023-11-27 | CLOSE | 2 | EA | 1 | 16.02 | 16.02 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 3 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-14 | COMP | 2023-12-04 | 1.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-1711 | ADAPTER, STRAIGHT, THREAD, PVC, GRAY, 1-1/4 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 8 | EA | 2 | 5.84 | 11.68 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 12 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 2.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 5340-60-V00-0492 | STOPPER, DOOR, DROP DOWN, METAL, 5" | 48354 | 2023-11-26 | 2023-11-27 | CLOSE | 1 | EA | 1 | 19.47 | 19.47 | 19316 | CLOSE | 2023-11-28 |  | KW1-13345 | 4 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-01 | 1.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-1710 | ADAPTER, STRAIGHT, THREAD, PVC, GRAY, 1-1/2 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 1 | EA | 2 | 6 | 12 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 5 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 2.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 8030-60-V00-0053 | FOAM, CONSTRUCTION, CREAM, 700ML | 48355 | 2023-11-26 | 2023-11-27 | CLOSE | 2 | EA | 15 | 19.5 | 292.5 | 19316 | CLOSE | 2023-11-28 |  | KW1-13339 | 6 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-10 | COMP | 2023-12-01 | 15.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-00-162-2560 | ELBOW, PIPE, PVC, 90°, SOCKET X SOCKET, SCH 80, GRAY, 1-1/2 INCHES | 48356 | 2023-11-26 | 2023-11-27 | CLOSE | 1 | TE | 1 | 43.9 | 43.9 | 19316 | CLOSE | 2023-11-28 |  | KW1-13345 | 8 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-01 | 1.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 5305-60-V00-0174 | SCREW, HEX, STEEL, w/ RUBBER WASHER, # 14 X 2 ½ INCHES | 48349 | 2023-11-26 | 2023-11-27 | CLOSE | 1 | BX | 4 | 37.77 | 151.08 | 19316 | CLOSE | 2023-11-28 |  | KW1-13345 | 1 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-01 | 4.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 8030-60-V00-0017 | COATING COMPOUND, PROTECTIVE, 900 CERAMIC FINISH, WHITE, 5 GL | 48348 | 2023-11-26 | 2023-11-27 | CLOSE | 1 | CN | 3 | 236.58 | 709.74 | 19316 | CLOSE | 2023-11-28 |  | KW1-13339 | 1 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-10 | COMP | 2023-12-02 | 3.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 5975-60-V00-0413 | ANCHOR, PLASTIC, BUTTERFLY, WHITE, 6MM | 48355 | 2023-11-26 | 2023-11-27 |  | 1 | BX | 5 | [6 empty] | KW1-13339 | 5 | [5 empty] | 2023-12-10 | COMP | 2023-12-01 | 5 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 5305-60-V00-0155 | SCREW, DRYWALL, PHILLIPS, BUGLE HEAD, STEEL, #6 X 1-5/8 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 3 | BX | 1 | 14.85 | 14.85 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 7 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 1.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 5305-60-V00-0220 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, STEEL, #6 X 2 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 2 | BX | 1 | 52 | 52 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 6 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 1.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 9320-60-V00-0007 | TAPE, ADHESIVE, RUBBER, BUTYL, 4 INCHES X 50 FEET | 48351 | 2023-11-26 | 2023-11-27 |  | 1 | EA | 20 | [6 empty] | KW1-13395 | 3 | [5 empty] | 2023-12-24 |  |  |  |  | AJ | AJ table | November | 2023
114 | 2023-11-27 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-00-201-8409 | ELBOW, PIPE, PVC, 45°, SOCKET X SOCKET, SCH 80, GRAY, 1-1/2 INCHES | 48388 | 2023-11-27 | 2023-11-30 | CLOSE | 2 | EA | 6 | 5.12 | 30.72 | 19411 | CLOSE | 2023-12-06 | 2023-12-03 | KW1-13514 | 4 | 2023-12-06 | APPR | 2023-12-06 | Thomas, Vinu - Vectrus -No Export | MARATHON INC TRADING LLC | 2023-12-13 | COMP | 2023-12-09 | 6.00 |  | AJ | AJ table | November | 2023
114 | 2023-11-27 |  | AJ23-0508 | T357 Relocation | 2141526 | 4510-05-V00-0042 | DISH SOAP, STAINESS STEEL, SILVER, 2.25 X 5 X 3 INCHES | 48388 | 2023-11-27 | 2023-11-30 | CLOSE | 1 | EA | 1 | 58.18 | 58.18 | 19411 | CLOSE | 2023-12-06 | 2023-12-03 | KW1-13514 | 3 | 2023-12-06 | APPR | 2023-12-06 | Thomas, Vinu - Vectrus -No Export | MARATHON INC TRADING LLC | 2024-01-17 | COMP | 2023-12-21 | 1.00 |  | AJ | AJ table | November | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5530-60-V00-0004 | PLYWOOD, CONSTRUCTION, MARINE, 13 PLY BOARD, 3/4 INCH, 8 X 4 FEET | 49621 | 2023-12-14 | 2023-12-16 | CLOSE | 2 | SH | 85 | 137.36 | 11675.6 | 19909 | CLOSE | 2023-12-26 | 2023-12-21 | KW1-13925 | 4 | 2023-12-26 | APPR | 2023-12-26 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-10 | COMP | 2024-01-08 | 85.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 49625 | 2023-12-14 | 2023-12-16 | CLOSE | 6 | BX | 24 | 19.6 | 470.4 |  |  |  |  | KW1-13754 | 29 | 2023-12-18 | APPR | 2023-12-18 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-04 | COMP | 2023-12-21 | 24.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5305-60-V00-0170 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATE, # 8 X 3 INCHES | 49625 | 2023-12-14 | 2023-12-16 | CLOSE | 5 | BX | 12 | 35 | 420 |  |  |  |  | KW1-13754 | 28 | 2023-12-18 | APPR | 2023-12-18 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-04 | COMP | 2023-12-21 | 12.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 7210-60-V00-0059 | FLOOR COVERING, VINYL RESIN, 3 MM X 40 FEET | 49625 | 2023-12-14 | 2023-12-16 | CLOSE | 4 | RL | 3 | 716.1 | 2148.3 |  |  |  |  | KW1-13754 | 27 | 2023-12-18 | APPR | 2023-12-18 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-04 | COMP | 2023-12-27 | 3.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5640-60-V00-0034 | WEATHER STRIP, FLUTE TOPPED ALUMINUM THRESHOLD, 3' (L) X 4-1/4" (W) | 49623 | 2023-12-14 | 2023-12-16 | CLOSE | 7 | EA | 2 | 49 | 98 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 38 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 2.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 8040-00-273-8713 | ADHESIVE, FLOORING, WHITE, 1 GL | 49620 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | GL | 15 | 187.48 | 2812.2 |  |  |  |  | KW1-13755 | 9 | 2023-12-18 | APPR | 2023-12-18 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-18 | COMP | 2024-01-08 | 15.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 49623 | 2023-12-14 | 2023-12-16 | CLOSE | 6 | EA | 15 | 45.4 | 681 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 37 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2024-01-06 | 15.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 49621 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | BX | 2 | 29.64 | 59.28 | 19909 | CLOSE | 2023-12-26 | 2023-12-21 | KW1-13925 | 3 | 2023-12-26 | APPR | 2023-12-26 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-02 | COMP | 2023-12-30 | 2.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 49626 | 2023-12-14 | 2023-12-16 | CLOSE | 4 | BX | 1 | 142 | 142 | 19854 | CLOSE | 2023-12-19 |  | KW1-13782 | 3 | 2023-12-19 | APPR | 2023-12-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-31 | COMP | 2023-12-22 | 1.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5640-60-V00-0032 | WEATHER STRIP, DOOR, W/RUBBER BOTTOM SWEEP, 39 INCHES | 49617 | 2023-12-14 | 2023-12-16 | CLOSE | 5 | EA | 4 | 16.62 | 66.48 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 31 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 4.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 8105-01-336-6163 | BAG, SAND, TAN, 26 INCHES (EXCESS ) |  | 2023-12-14 |  |  |  | HD | [18 empty] | EXCESS | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 49622 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | BX | 1 | 16.5 | 16.5 |  |  |  |  | KW1-13868 | 3 | 2023-12-22 | APPR | 2023-12-22 | Bharadwajan, Sajan - Vectrus - No Export | TRADEX INTERNATIONAL TRADING LLC | 2023-12-28 | COMP | 2023-12-26 | 1.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 3230-60-V00-0024 | BLADE, CIRCULAR SAW, WOOD CUTTING, 36 TOOTH, 7-1/4 INCHES | 49623 | 2023-12-14 | 2023-12-16 | CLOSE | 5 | EA | 4 | 52.45 | 209.8 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 36 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-28 | COMP | 2024-02-29 | 4.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 3230-60-V00-0028 | BLADE SET, JIG SAW, BI-METAL, T-SHANK, 14-PIECES | 49617 | 2023-12-14 | 2023-12-16 | CLOSE | 4 | PG | 2 | 44.29 | 88.58 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 30 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 2.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 8415-01-610-7323 | GLOVES, BLACK, MEDIUM | 49619 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | PG | 3 | 133.1 | 399.3 |  |  |  |  | KW1-13868 | 2 | 2023-12-22 | APPR | 2023-12-22 | Bharadwajan, Sajan - Vectrus - No Export | TRADEX INTERNATIONAL TRADING LLC | 2023-12-28 | COMP | 2023-12-26 | 3.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5120-60-V00-0305 | BIT, SCREW DRIVER, SILVER, PH2, 69 MM | 49623 | 2023-12-14 | 2023-12-16 | CLOSE | 4 | EA | 5 | 8.33 | 41.65 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 35 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 5.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5110-00-277-4592 | BLADE, HAND HACKSAW, STEEL, 12 X 0.025 INCH | 49625 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | PK | 5 | 31.6 | 158 |  |  |  |  | KW1-13754 | 24 | 2023-12-18 | APPR | 2023-12-18 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-04 | COMP | 2023-12-21 | 5.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5110-00-277-4590 | BLADE, HAND HACKSAW, STEEL, 18 TPI, 12 X 0.025 INCH | 49627 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | PG | 5 | 19.8 | 99 | 19855 | CLOSE | 2024-02-17 | 2023-12-20 | KW1-13927 | 6 | 2023-12-26 | APPR | 2023-12-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2023-12-30 | 5.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 6210-60-V00-0136 | LIGHT UNIT, EMERGENCY, (EXIT LIGHT), LED, 120-277 V, 50/60 HZ, 2 W | 49624 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | EA | 2 | 135.7 | 271.4 |  |  |  |  | KW1-13755 | 11 | 2023-12-18 | APPR | 2023-12-18 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-11 | COMP | 2023-12-21 | 2.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5970-60-V00-0040 | TAPE, INSULATION, RED, 3/4 INCH X 25 METER | 49626 | 2023-12-14 | 2023-12-16 | CLOSE | 3 | RO | 1 | 19 | 19 | 19854 | CLOSE | 2023-12-19 |  | KW1-13783 | 1 | 2023-12-19 | APPR | 2023-12-19 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-10 | COMP | 2023-12-22 | 1.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5970-60-V00-0044 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 INCH X 66 FEET | 49617 | 2023-12-14 | 2023-12-16 | CLOSE | 3 | RO | 1 | 14.99 | 14.99 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 29 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 49617 | 2023-12-14 | 2023-12-16 | CLOSE | 2 | RO | 1 | 16.83 | 16.83 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 28 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5935-60-V00-0156 | CONNECTOR, WIRE, RED, 18-6 AWG | 49617 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | BX | 1 | 36.13 | 36.13 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 27 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 6210-60-V00-0031 | LIGHT UNIT, EMERGENCY, TWIN SPOT, LED, WHITE, 220V, 50HZ | 49626 | 2023-12-14 | 2023-12-16 | CLOSE | 2 | EA | 2 | 100.13 | 200.26 | 19854 | CLOSE | 2023-12-19 |  | KW1-13782 | 2 | 2023-12-19 | APPR | 2023-12-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-31 | COMP | 2023-12-22 | 2.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 49625 | 2023-12-14 | 2023-12-16 | CLOSE | 3 | BX | 1 | 51.5 | 51.5 |  |  |  |  | KW1-13754 | 26 | 2023-12-18 | APPR | 2023-12-18 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-04 | COMP | 2023-12-21 | 1.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5940-60-V00-0137 | FERRULE KIT, ELECTRICAL CONDUCTOR, INSULATED, 4 TYPE, 600V, 4MM TO 16 MM | 49618 | 2023-12-14 | 2023-12-16 | CLOSE | 2 | KT | 1 | 42.12 | 42.12 | 19971 | CLOSE | 2023-12-27 | 2023-12-24 | KW1-13949 | 10 | 2023-12-28 | APPR | 2023-12-28 | Thomas, Vinu - Vectrus -No Export | MARATHON INC TRADING LLC | 2024-01-04 | COMP | 2024-01-02 | 1.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 49626 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | EA | 1 | 260.02 | 260.02 | 19854 | CLOSE | 2023-12-19 |  | KW1-13782 | 1 | 2023-12-19 | APPR | 2023-12-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-31 | COMP | 2023-12-22 | 1.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 6350-60-V00-0102 | ALARM, SMOKE, AUTOMATIC, PLASTIC | 49623 | 2023-12-14 | 2023-12-16 | CLOSE | 3 | EA | 4 | 28.97 | 115.88 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 34 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 4.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5910-60-V00-0057 | CAPACITOR, RUN, 3P, 55+5 MFD, 370/440V, 50/60HZ | 49623 | 2023-12-14 | 2023-12-16 | CLOSE | 2 | EA | 1 | 17.98 | 17.98 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 33 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5975-60-V00-0435 | PAD, ANTI VIBRATION, RUBBER/CORK, 4 X 4 X 1 INCHES | 49625 | 2023-12-14 | 2023-12-16 | CLOSE | 2 | EA | 20 | 13.2 | 264 |  |  |  |  | KW1-13754 | 25 | 2023-12-18 | APPR | 2023-12-18 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-04 | COMP | 2023-12-21 | 20.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5306-60-V00-0120 | BOLT AND NUT, HEX w/ WASHER, 2 INCHES X 10 MM | 49623 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | BX | 1 | 83.25 | 83.25 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 32 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | AJ | AJ table | December | 2023
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 6830-01-527-1691 | REFRIGERANT GAS MIXTURE, 407C, 25 LBS | 49618 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | CY | 1 | 162.9 | 162.9 | 19971 | CLOSE | 2023-12-27 | 2023-12-24 | KW1-13949 | 9 | 2023-12-28 | APPR | 2023-12-28 | Thomas, Vinu - Vectrus -No Export | MARATHON INC TRADING LLC | 2024-01-04 | COMP | 2024-01-02 | 1.00 |  | AJ | AJ table | December | 2023
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024

## Material Master BU
NO. OF PROJECTS | BOM Received date | TASK | PROJECT# | PROJECT DESCRIPTION | WO# | CATALOG | Item # | PR # | PR REQUESTED DATE | PR APPROVED DATE | PR Cur. Status | PR Line # | Unit of Issue | Order Qty. | Unit Cost | Ext. Cost (Line Cost) | RFQ # | RFQ Status | RFQ Status Date | RFQ Due Date | PO # | PO Line # | PO Award Date | PO Status | PO Status Date | Buyer | Vendor | Vendor Date (EDD) | Delivery Status | Delivery Date | Recv. Qty | Remarks | Color Code list | table | month | year
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 6115-60-V00-0037 | GENERATOR SET, DIESEL ENGINE, 4-CYCLE, 400V, 24 KW, 50HZ | 48879 | 2023-12-04 | 2023-12-11 | CLOSE | 1 | EA | 1 | 14186.7 | 14186.7 | 19796 | CLOSE | 2023-12-20 | 2023-12-17 | KW1-13841 | 1 | 2023-12-20 | APPR | 2023-12-20 | Reghunath, Rajesh -Vectrus -GSD -No Export | GULF PIONEER COMPANY LLC | 2024-01-24 | COMP | 2024-01-23 | 1.00 | Pending Stenciling | BU | BU table | December | 2023
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 48878 | 2023-12-04 | 2023-12-11 | CLOSE | 8 | EA | 2 | 300.19 | 600.38 |  |  |  |  | KW1-13652 | 7 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 2.00 |  | BU | BU table | December | 2023
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 48878 | 2023-12-04 | 2023-12-11 | CLOSE | 7 | EA | 2 | 60.17 | 120.34 |  |  |  |  | KW1-13652 | 6 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 2.00 |  | BU | BU table | December | 2023
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 6145-60-V00-0119 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 25 MM² | 48878 | 2023-12-04 | 2023-12-11 | CLOSE | 6 | MR | 15 | 204.38 | 3065.7 |  |  |  |  | KW1-13652 | 5 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 15.00 |  | BU | BU table | December | 2023
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM ² | 48878 | 2023-12-04 | 2023-12-11 | CLOSE | 5 | RO | 25 | 240.35 | 240.35 |  |  |  |  | KW1-13652 | 4 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 1.00 |  | BU | BU table | December | 2023
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 5940-60-V00-0016 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 16 MM² | 48878 | 2023-12-04 | 2023-12-11 | CLOSE | 4 | EA | 8 | 1.8 | 14.4 |  |  |  |  | KW1-13653 | 1 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-23 | COMP | 2023-12-15 | 8.00 |  | BU | BU table | December | 2023
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 5975-60-V00-0512 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, CW, BRASS, 32 MM | 48878 | 2023-12-04 | 2023-12-11 | CLOSE | 3 | KT | 2 | 21.26 | 42.52 |  |  |  |  | KW1-13652 | 3 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 2.00 |  | BU | BU table | December | 2023
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 5940-60-V00-0017 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 25 MM² | 48878 | 2023-12-04 | 2023-12-11 | CLOSE | 2 | EA | 8 | 1.8 | 14.4 |  |  |  |  | KW1-13652 | 2 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 8.00 |  | BU | BU table | December | 2023
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 48880 | 2023-12-04 | 2023-12-06 | CLOSE | 1 | RO | 1 | 163.35 | 163.35 |  |  |  |  | KW1-13557 | 8 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-13 | COMP | 2023-12-11 | 1.00 |  | BU | BU table | December | 2023
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 5975-60-V00-0209 | RACEWAY, METALLIC, GALVANIZED STEEL, 2 X 2 INCHES X 10 FEET | 48878 | 2023-12-04 | 2023-12-11 | CLOSE | 1 | EA | 1 | 55.59 | 55.59 |  |  |  |  | KW1-13652 | 1 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-07 | COMP | 2024-01-07 | 1.00 |  | BU | BU table | December | 2023
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 6115-60-V00-0037 | GENERATOR SET, DIESEL ENGINE, 4-CYCLE, 400V, 24 KW, 50HZ | 48882 | 2023-12-04 | 2023-12-11 | CLOSE | 1 | EA | 1 | 14186.7 | 14186.7 | 19796 | CLOSE | 2023-12-20 | 2023-12-17 | KW1-13841 | 3 | 2023-12-20 | APPR | 2023-12-20 | Reghunath, Rajesh -Vectrus -GSD -No Export | GULF PIONEER COMPANY LLC | 2024-01-24 | COMP | 2024-01-23 | 1.00 | Pending Stenciling | BU | BU table | December | 2023
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 48881 | 2023-12-04 | 2023-12-11 | CLOSE | 8 | EA | 2 | 300.19 | 600.38 |  |  |  |  | KW1-13654 | 7 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 2.00 |  | BU | BU table | December | 2023
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 48881 | 2023-12-04 | 2023-12-11 | CLOSE | 7 | EA | 2 | 60.17 | 120.34 |  |  |  |  | KW1-13654 | 6 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 2.00 |  | BU | BU table | December | 2023
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 6145-60-V00-0119 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 25 MM² | 48881 | 2023-12-04 | 2023-12-11 | CLOSE | 6 | MR | 15 | 204.38 | 3065.7 |  |  |  |  | KW1-13654 | 5 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 15.00 |  | BU | BU table | December | 2023
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 6145-60-V00-0148 | Thank | 48881 | 2023-12-04 | 2023-12-11 | CLOSE | 5 | RO | 25 | 240.35 | 240.35 |  |  |  |  | KW1-13654 | 4 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 1.00 |  | BU | BU table | December | 2023
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 5940-60-V00-0016 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 16 MM² | 48881 | 2023-12-04 | 2023-12-11 | CLOSE | 4 | EA | 8 | 1.8 | 14.4 |  |  |  |  | KW1-13655 | 1 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-23 | COMP | 2023-12-15 | 8.00 |  | BU | BU table | December | 2023
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 5975-60-V00-0512 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, CW, BRASS, 32 MM | 48881 | 2023-12-04 | 2023-12-11 | CLOSE | 3 | KT | 2 | 21.26 | 42.52 |  |  |  |  | KW1-13654 | 3 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 2.00 |  | BU | BU table | December | 2023
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 5940-60-V00-0017 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 25 MM² | 48881 | 2023-12-04 | 2023-12-11 | CLOSE | 2 | EA | 8 | 1.8 | 14.4 |  |  |  |  | KW1-13654 | 2 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 8.00 |  | BU | BU table | December | 2023
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 48883 | 2023-12-04 | 2023-12-06 | CLOSE | 1 | RO | 25 | 163.65 | 163.65 |  |  |  |  | KW1-13557 | 10 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-13 | COMP | 2023-12-11 | 1.00 |  | BU | BU table | December | 2023
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 5975-60-V00-0209 | RACEWAY, METALLIC, GALVANIZED STEEL, 2 X 2 INCHES X 10 FEET | 48881 | 2023-12-04 | 2023-12-11 | CLOSE | 1 | EA | 1 | 55.59 | 55.59 |  |  |  |  | KW1-13654 | 1 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-07 | COMP | 2024-01-07 | 1.00 |  | BU | BU table | December | 2023
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 6115-60-V00-0037 | GENERATOR SET, DIESEL ENGINE, 4-CYCLE, 400V, 24 KW, 50HZ | 48938 | 2023-12-05 | 2023-12-11 | CLOSE | 1 | EA | 1 | 14186.7 | 14186.7 | 19797 | CLOSE | 2023-12-20 | 2023-12-17 | KW1-13840 | 1 | 2023-12-20 | APPR | 2023-12-20 | Reghunath, Rajesh -Vectrus -GSD -No Export | GULF PIONEER COMPANY LLC | 2024-01-24 | COMP | 2024-01-23 | 1.00 | Pending Stenciling | BU | BU table | December | 2023
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 48937 | 2023-12-05 | 2023-12-11 | CLOSE | 8 | EA | 2 | 300.19 | 600.38 |  |  |  |  | KW1-13656 | 7 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 2.00 |  | BU | BU table | December | 2023
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 48937 | 2023-12-05 | 2023-12-11 | CLOSE | 7 | EA | 2 | 60.17 | 120.34 |  |  |  |  | KW1-13656 | 6 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 2.00 |  | BU | BU table | December | 2023
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 6145-60-V00-0119 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 25 MM² | 48937 | 2023-12-05 | 2023-12-11 | CLOSE | 1 | MR | 15 | 204.38 | 3065.7 |  |  |  |  | KW1-13656 | 1 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-19 | 15.00 |  | BU | BU table | December | 2023
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM ² | 48937 | 2023-12-05 | 2023-12-11 | CLOSE | 6 | RO | 25 | 240.35 | 240.35 |  |  |  |  | KW1-13656 | 5 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 1.00 |  | BU | BU table | December | 2023
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 5940-60-V00-0016 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 16 MM² | 48937 | 2023-12-05 | 2023-12-11 | CLOSE | 5 | EA | 8 | 1.8 | 14.4 |  |  |  |  | KW1-13657 | 1 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-23 | COMP | 2023-12-15 | 8.00 |  | BU | BU table | December | 2023
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 5975-60-V00-0512 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, CW, BRASS, 32 MM | 48937 | 2023-12-05 | 2023-12-11 | CLOSE | 4 | KT | 2 | 21.26 | 42.52 |  |  |  |  | KW1-13656 | 4 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 2.00 |  | BU | BU table | December | 2023
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 5940-60-V00-0017 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 25 MM² | 48937 | 2023-12-05 | 2023-12-11 | CLOSE | 3 | EA | 8 | 1.8 | 14.4 |  |  |  |  | KW1-13656 | 3 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 8.00 |  | BU | BU table | December | 2023
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 48939 | 2023-12-05 | 2023-12-06 | CLOSE | 1 | RO | 1 | 161.7 | 161.7 |  |  |  |  | KW1-13557 | 12 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-13 | COMP | 2023-12-11 | 1.00 |  | BU | BU table | December | 2023
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 5975-60-V00-0209 | RACEWAY, METALLIC, GALVANIZED STEEL, 2 X 2 INCHES X 10 FEET | 48937 | 2023-12-05 | 2023-12-11 | CLOSE | 2 | EA | 1 | 55.59 | 55.59 |  |  |  |  | KW1-13656 | 2 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-07 | COMP | 2024-01-07 | 1.00 |  | BU | BU table | December | 2023
4 | 2023-12-04 | 40 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 5975-60-V00-0793 | RACEWAY, METALLIC, (CABLE TRAY), MEDIUM DUTY, HOT-DIP GALVANIZED, 1.20 X 50 X 3000 X 450 MM | 49131 | 2023-12-07 | 2023-12-11 | CLOSE | 1 | EA | 1 | 55.1 | 55.1 | 19734 | CLOSE | 2023-12-20 | 2023-12-17 | KW1-13824 | 1 | 2023-12-20 | APPR | 2023-12-20 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
5 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 5975-60-V00-0793 | RACEWAY, METALLIC, (CABLE TRAY), MEDIUM DUTY, HOT-DIP GALVANIZED, 1.20 X 50 X 3000 X 450 MM | 49132 | 2023-12-07 | 2023-12-11 | CLOSE | 1 | EA | 1 | 55.1 | 55.1 | 19682 | CLOSE | 2023-12-20 | 2023-12-16 | KW1-13811 | 13 | 2023-12-20 | APPR | 2023-12-20 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
6 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 5975-60-V00-0793 | RACEWAY, METALLIC, (CABLE TRAY), MEDIUM DUTY, HOT-DIP GALVANIZED, 1.20 X 50 X 3000 X 450 MM | 49133 | 2023-12-07 | 2023-12-11 | CLOSE | 1 | PR-PAIR | 1 | 55.1 | 55.1 | 19682 | CLOSE | 2023-12-20 | 2023-12-16 | KW1-13811 | 15 | 2023-12-20 | APPR | 2023-12-20 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 6145-60-V00-0119 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 25 MM² | 49482 | 2023-12-13 | 2023-12-15 | CLOSE | 9 | MR | 35 | 26.5 | 927.5 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 9 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-28 | COMP | 2024-01-08 | 35.00 |  | BU | BU table | December | 2023
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 5975-60-V00-0512 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, CW, BRASS, 32 MM | 49482 | 2023-12-13 | 2023-12-15 | CLOSE | 8 | EA | 2 | 16 | 32 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 8 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 2.00 |  | BU | BU table | December | 2023
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 49482 | 2023-12-13 | 2023-12-15 | CLOSE | 7 | RO | 1 | 242.58 | 242.58 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 7 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | BU | BU table | December | 2023
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 5940-60-V00-0017 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 25 MM² | 49482 | 2023-12-13 | 2023-12-15 | CLOSE | 6 | EA | 10 | 1.9 | 19 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 6 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 10.00 |  | BU | BU table | December | 2023
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 6110-60-V00-0112 | SWITCH, DISCONNECT, 3P+N, Y4, 800V, 100A | 49484 | 2023-12-13 | 2023-12-15 | CLOSE | 3 | EA | 1 | 306.14 | 306.14 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 12 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-28 | COMP | 2024-01-07 | 1.00 |  | BU | BU table | December | 2023
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 6130-60-V00-0050 | CONVERTER, FREQUENCY, STATIC, 3 PHASE, 30KVA | 49484 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | EA | 1 | 11833.46 | 11833.46 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 11 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-28 | COMP | 2024-01-30 | 1.00 |  | BU | BU table | December | 2023
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 5925-60-V00-0087 | CIRCUIT BREAKER, 6 POLE, 277-480 VAC, 50A | 49484 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | EA | 1 | 326 | 326 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 10 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-28 | COMP | 2024-01-08 | 1.00 |  | BU | BU table | December | 2023
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 5975-60-V00-0512 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, CW, BRASS, 32 MM | 49482 | 2023-12-13 | 2023-12-15 | CLOSE | 5 | KT | 4 | 16 | 64 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 5 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 4.00 |  | BU | BU table | December | 2023
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 49482 | 2023-12-13 | 2023-12-15 | CLOSE | 4 | EA | 1 | 302.94 | 302.94 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 4 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | BU | BU table | December | 2023
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 49482 | 2023-12-13 | 2023-12-15 | CLOSE | 3 | EA | 1 | 58.91 | 58.91 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 3 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | BU | BU table | December | 2023
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 5975-60-V00-0418 | LUG, TERMINAL, ROUND TYPE, COPPER, ONE-HOLE, 16 mm²-M8 | 49482 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | EA | 20 | 1.07 | 21.4 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 2 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 20.00 |  | BU | BU table | December | 2023
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 9520-60-V00-0017 | ANGLE, STRUCTURAL, STEEL, 2 X 2 INCHES X 20 FEET | 49482 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | EA | 1 | 49.12 | 49.12 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 1 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-30 | 1.00 |  | BU | BU table | December | 2023
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 5620-60-V00-0027 | CONCRETE BLOCK, CUBE, 40 X 40 X 40 CM | 49483 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | EA | 1 | 221.28 | 221.28 | 19831 | CLOSE | 2023-12-20 | 2023-12-18 | KW1-13821 | 1 | 2023-12-26 | APPR | 2023-12-26 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-15 | COMP | 2024-01-13 | 1.00 |  | BU | BU table | December | 2023
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 4730-60-V00-0046 | ADAPTER, ELECTRICAL CONDUIT, w/BUSH, FEMALE, PVC, WHITE, 25 MM | 49470 | 2023-12-13 | 2023-12-15 | CLOSE | 5 | EA | 10 | 8.49 | 84.9 | 19827 | CLOSE | 2023-12-18 |  | KW1-13777 | 1 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-01-31 | COMP | 2023-12-21 | 10.00 |  | BU | BU table | December | 2023
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 5975-01-382-7318 | UNION, ELECTRICAL CONDUIT, PLASTIC, BLACK, 1/2 INCH | 49470 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | EA | 15 | 8.49 | 127.35 | 19826 | CLOSE | 2023-12-22 | 2023-12-18 | KW1-13875 | 3 | 2023-12-22 | APPR | 2023-12-23 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-02 | COMP | 2023-12-26 | 15.00 |  | BU | BU table | December | 2023
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 5975-60-V00-0526 | CONDUIT, NONMETALLIC, RIGID, PVC, BLACK, 3/4 INCH X 10 FEET | 49473 | 2023-12-13 | 2023-12-15 | CLOSE | 4 | EA | 20 | 2.75 | 55 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 8 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-23 | 20.00 |  | BU | BU table | December | 2023
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 5975-60-V00-0501 | CLAMP, ELECTRICAL, CONDUIT, PVC, BLACK, 25 MM | 49470 | 2023-12-13 | 2023-12-15 | CLOSE | 4 | EA | 30 | 3.16 | 94.8 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 4 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-22 | 30.00 |  | BU | BU table | December | 2023
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 5975-60-V00-0373 | COUPLING, ELECTRICAL CONDUIT, PVC, BLACK, 20 MM | 49473 | 2023-12-13 | 2023-12-15 | CLOSE | 3 | EA | 10 | 0.88 | 8.8 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 7 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 10.00 |  | BU | BU table | December | 2023
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 49470 | 2023-12-13 | 2023-12-15 | CLOSE | 3 | EA | 10 | 3.5 | 35 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 3 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 10.00 |  | BU | BU table | December | 2023
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 5925-60-V00-0269 | CIRCUIT BREAKER, MINIATURE, 1 POLE, 20A | 49470 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | EA | 1 | 11.66 | 11.66 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 2 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 49473 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | EA | 4 | 10.32 | 41.28 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 6 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-15 | COMP | 2023-12-21 | 4.00 |  | BU | BU table | December | 2023
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 6145-60-V00-0163 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORE, 4 MM² | 49473 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | RL | 1 | 248.88 | 248.88 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 5 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 49471 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | RL | 1 | 21.65 | 21.65 | 19857 | CLOSE | 2023-12-17 | 2023-12-17 | KW1-13758 | 3 | 2023-12-20 | APPR | 2023-12-20 | Vishwanath, Shet -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-24 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 5970-01-013-9369 | TAPE, INSULATION, ELECTRICAL, RED, 3/4 X 792 INCHES | 49472 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | RL | 1 | 11.2 | 11.2 | 19857 | CLOSE | 2023-12-17 | 2023-12-17 | KW1-13758 | 4 | 2023-12-20 | APPR | 2023-12-20 | Vishwanath, Shet -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-24 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 6145-60-V00-0118 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 16 MM² | 49587 | 2023-12-13 | 2023-12-15 | CLOSE | 6 | MR | 100 | 21.57 | 2157 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 26 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-30 | 100.00 |  | BU | BU table | December | 2023
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5975-60-V00-0511 | GLAND, ELECTRICAL CONDUIT, BRASS, BW, w/ EARTH TAG, 25 MM | 49587 | 2023-12-13 | 2023-12-15 | CLOSE | 5 | EA | 4 | 9.49 | 37.96 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 25 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 4.00 |  | BU | BU table | December | 2023
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5940-60-V00-0122 | TERMINAL, LUG, COPPER TUBE, STUD HOLE, 16MM² X M10 | 49587 | 2023-12-13 | 2023-12-15 | CLOSE | 4 | EA | 20 | 67.28 | 67.28 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 24 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | BU | BU table | December | 2023
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 49589 | 2023-12-13 | 2023-12-15 | CLOSE | 5 | EA | 1 | 352.98 | 352.98 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 19 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 49589 | 2023-12-13 | 2023-12-15 | CLOSE | 4 | EA | 1 | 61.27 | 61.27 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 18 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5975-60-V00-0794 | CONDUIT, METAL, FLEXIBLE, STEEL, GRAY, GALVANIZED, 1-1/2 INCHES X 50 FEET | 49590 | 2023-12-13 | 2023-12-22 | CLOSE | 1 | EA | 1 | 452.77 | 452.77 | 19902 | CLOSE | 2023-12-22 | 2023-12-21 | KW1-13866 | 2 | 2023-12-22 | APPR | 2023-12-22 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-17 07:00 | COMP | 2024-01-10 | 1.00 |  | BU | BU table | December | 2023
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 6145-60-V00-0139 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 6 MM ² | 49587 | 2023-12-13 | 2023-12-15 | CLOSE | 3 | RL | 1 | 28.47 | 28.47 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 23 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2024-01-04 | 1.00 |  | BU | BU table | December | 2023
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5975-60-V00-0421 | LUG, TERMINAL, ROUND TYPE, ONE-HOLE, 6MM² X 6MM | 49589 | 2023-12-13 | 2023-12-15 | CLOSE | 3 | PG | 1 | 51.82 | 51.82 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 17 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5975-60-V00-0029 | CLAMP, GROUNDING, 5/8 INCH | 49587 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | EA | 1 | 44.12 | 44.12 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 22 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | BU | BU table | December | 2023
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5975-00-074-2072 | STRAP, TIEDOWN, ELECTRICAL COMPONENT, PLASTIC, NATURAL, 6-3/10 INCHES | 49589 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | HD | 1 | 16.83 | 16.83 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 16 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5975-01-223-8533 | STRAP, TIE DOWN, ELECTRICAL COMPONENTS, PLASTIC POLYAMIDE, 0.1 X 8 INCHES | 49589 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | PG | 1 | 66.48 | 66.48 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 15 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 4240-60-V00-0122 | TAPE, WARNING, CAUTION BURIED ELECTRICAL CABLE BELOW, YELLOW 6 INCHES X 1000 FEET | 49587 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | RL | 1 | 176.82 | 176.82 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 21 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2024-01-04 | 1.00 |  | BU | BU table | December | 2023
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5610-60-V00-0014 | SAND, CONSTRUCTION, BEACH | 49588 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | CZ | 30 | 40.55 | 1216.5 | 19825 | CLOSE | 2023-12-20 | 2023-12-18 | KW1-13828 | 3 | 2023-12-20 | APPR | 2023-12-20 | Reghunath, Rajesh -Vectrus -GSD -No Export | GULF PIONEER COMPANY LLC | 2023-12-27 | COMP | 2023-12-23 | 30.00 |  | BU | BU table | December | 2023
10 | 2023-12-03 | 30 | BU24-0087 | Install Circuit Breakers Z8 TT803 | 8565458 | 5975-60-V00-0531 | PROTECTOR, ELECTRICAL CABLE, PVC, WHITE, 1 INCH X 9 FEET | 48795 | 2023-12-03 | 2023-12-07 | CLOSE | 3 | EA | 8 | 16.19 | 129.52 | 19578 | CLOSE | 2023-12-11 | 2023-12-10 | KW1-13609 | 7 | 2023-12-13 | APPR | 2023-12-13 | Thomas, Vinu - Vectrus -No Export | COMMERCIAL UNITED GINCO EST. | 2023-12-20 | COMP | 2023-12-16 | 8.00 |  | BU | BU table | December | 2023
10 | 2023-12-03 | 30 | BU24-0087 | Install Circuit Breakers Z8 TT803 | 8565458 | 5975-60-V00-0161 | RACEWAY, NON-METALLIC (CABLE TRUNKING), UPVC, WHITE, 50 X 50MM X 3 METER | 48795 | 2023-12-03 | 2023-12-07 | CLOSE | 2 | EA | 8 | 36.14 | 289.12 | 19578 | CLOSE | 2023-12-11 | 2023-12-10 | KW1-13609 | 6 | 2023-12-13 | APPR | 2023-12-13 | Thomas, Vinu - Vectrus -No Export | COMMERCIAL UNITED GINCO EST. | 2023-12-20 | COMP | 2023-12-16 | 8.00 |  | BU | BU table | December | 2023
10 | 2023-12-03 | 30 | BU24-0087 | Install Circuit Breakers Z8 TT803 | 8565458 | 6145-60-V00-0163 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORE, 4 MM² | 48797 | 2023-12-03 | 2023-12-06 | CLOSE | 2 | RO | 3 | 249 | 747 |  |  |  |  | KW1-13557 | 2 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-13 | COMP | 2023-12-11 | 3.00 |  | BU | BU table | December | 2023
10 | 2023-12-03 | 30 | BU24-0087 | Install Circuit Breakers Z8 TT803 | 8565458 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 48795 | 2023-12-03 | 2023-12-07 | CLOSE | 1 | EA | 16 | 3.43 | 54.88 | 19578 | CLOSE | 2023-12-11 | 2023-12-10 | KW1-13609 | 5 | 2023-12-13 | APPR | 2023-12-13 | Thomas, Vinu - Vectrus -No Export | COMMERCIAL UNITED GINCO EST. | 2023-12-20 | COMP | 2023-12-16 | 16.00 |  | BU | BU table | December | 2023
10 | 2023-12-03 | 30 | BU24-0087 | Install Circuit Breakers Z8 TT803 | 8565458 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 48797 | 2023-12-03 | 2023-12-06 | CLOSE | 1 | EA | 6 | 12.4 | 74.4 |  |  |  |  | KW1-13557 | 1 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-29 | COMP | 2023-12-11 | 6.00 |  | BU | BU table | December | 2023
10 | 2023-12-03 | 30 | BU24-0087 | Install Circuit Breakers Z8 TT803 | 8565458 | 5305-60-V00-0182 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATE, #8 X 1-1/4 INCHES | 48796 | 2023-12-03 | 2023-12-06 | CLOSE | 1 | BX | 2 | 29.54 | 59.08 |  |  |  |  | KW1-13558 | 1 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-13 | COMP | 2023-12-12 | 2.00 |  | BU | BU table | December | 2023
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5975-60-V00-0066 | CONDUIT, METAL, RIGID, GALVANIZED STEEL, 1/2 INCH X 10 FEET | 49486 | 2023-12-13 | 2023-12-15 | CLOSE | 5 | EA | 3 | 214.79 | 644.37 | 19827 | CLOSE | 2023-12-18 |  | KW1-13776 | 1 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-10 | COMP | 2023-12-23 | 3.00 |  | BU | BU table | December | 2023
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5975-60-V00-0461 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, GALVANIZED STEEL, ½ INCH | 49487 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | EA | 10 | 1.6 | 16 | 19869 | CLOSE | 2023-12-27 | 2023-12-20 | KW1-13955 | 5 | 2023-12-27 | CLOSE | 2024-02-06 | Vishwanath, Shet -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-14 | COMP | 2023-12-30 | 10.00 |  | BU | BU table | December | 2023
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5975-60-V00-0374 | COUPLING, ELECTRICAL CONDUIT, ZINC PLATED STEEL, 1/2 INCH | 49489 | 2023-12-13 | 2023-12-15 | CLOSE | 3 | PG | 1 | 129.1 | 129.1 | 19869 | CLOSE | 2023-12-27 | 2023-12-20 | KW1-13955 | 7 | 2023-12-27 | CLOSE | 2024-02-06 | Vishwanath, Shet -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-14 | COMP | 2023-12-30 | 1.00 |  | BU | BU table | December | 2023
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5975-00-578-3643 | BOX CONNECTOR, ELECTRICAL, ANGLE, LIQUIDTIGHT, IRON MALLEABLE, 1/2 INCH | 49490 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | EA | 5 | 12.54 | 62.7 | 19826 | CLOSE | 2023-12-22 | 2023-12-18 | KW1-13875 | 5 | 2023-12-22 | APPR | 2023-12-23 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-02 | COMP | 2024-01-21 | 5.00 |  | BU | BU table | December | 2023
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5935-60-V00-0153 | BOX CONNECTOR, ELECTRICAL, ZINC PLATED STEEL, 1/2 INCH | 49486 | 2023-12-13 | 2023-12-15 | CLOSE | 4 | PG | 1 | 84.08 | 84.08 | 19826 | CLOSE | 2023-12-22 | 2023-12-18 | KW1-13875 | 4 | 2023-12-22 | APPR | 2023-12-23 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-31 | COMP | 2023-12-26 | 1.00 |  | BU | BU table | December | 2023
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 49486 | 2023-12-13 | 2023-12-15 | CLOSE | 3 | EA | 2 | 27.31 | 54.62 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 11 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 2.00 |  | BU | BU table | December | 2023
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5930-60-V00-0243 | LIGHT-SWITCH, METAL, 2 WAY, 1 GANG, 250V, 10A | 49486 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | EA | 2 | 33.3 | 66.6 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 10 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 2.00 |  | BU | BU table | December | 2023
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 6145-60-V00-0158 | WIRE, ELECTRICAL, RED, 1 CORE, 2.5 MM² | 49486 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | RO | 1 | 60.94 | 60.94 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 9 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-22 | 1.00 |  | BU | BU table | December | 2023
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5975-60-V00-0042 | BOX CONNECTOR, ELECTRICAL, STRAIGHT, LIQUID TIGHT CONDUIT, NICKEL PLATED BRASS, 1/2 INCH | 49489 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | EA | 10 | 23.7 | 237 | 19857 | CLOSE | 2023-12-17 | 2023-12-17 | KW1-13758 | 7 | 2023-12-20 | APPR | 2023-12-20 | Vishwanath, Shet -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-24 | COMP | 2023-12-21 | 10.00 |  | BU | BU table | December | 2023
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5305-60-V00-0001 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 49488 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | BX | 1 | 18.9 | 18.9 | 19857 | CLOSE | 2023-12-17 | 2023-12-17 | KW1-13758 | 5 | 2023-12-20 | APPR | 2023-12-20 | Vishwanath, Shet -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-24 | COMP | 2023-12-27 | 1.00 |  | BU | BU table | December | 2023
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 49489 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | PG | 2 | 26.93 | 53.86 | 19857 | CLOSE | 2023-12-17 | 2023-12-17 | KW1-13758 | 6 | 2023-12-20 | APPR | 2023-12-20 | Vishwanath, Shet -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-24 | COMP | 2023-12-21 | 2.00 |  | BU | BU table | December | 2023
12 | 2023-12-13 | 30 | BU24-0097 | Install Exit Lights Z2 B211 | 8564897 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 48798 | 2023-12-13 | 2023-12-06 | CLOSE | 4 | EA | 2 | 160.23 | 320.46 |  |  |  |  | KW1-13557 | 6 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-13 | COMP | 2023-12-13 | 2.00 |  | BU | BU table | December | 2023
12 | 2023-12-13 | 30 | BU24-0097 | Install Exit Lights Z2 B211 | 8564897 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 48799 | 2023-12-13 | 2023-12-05 | CLOSE | 1 | RO | 1 | 163.35 | 163.35 |  |  |  |  | KW1-13518 | 5 | 2023-12-06 | APPR | 2023-12-06 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-18 | COMP | 2023-12-09 | 1.00 |  | BU | BU table | December | 2023
12 | 2023-12-13 | 30 | BU24-0097 | Install Exit Lights Z2 B211 | 8564897 | 5975-60-V00-0462 | TIE, CABLE, BLACK, 8 INCHES X 4.8 MILLIMETER | 48798 | 2023-12-13 | 2023-12-06 | CLOSE | 3 | PG | 1 | 24.03 | 24.03 |  |  |  |  | KW1-13557 | 5 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-13 | COMP | 2023-12-11 | 1.00 |  | BU | BU table | December | 2023
12 | 2023-12-13 | 30 | BU24-0097 | Install Exit Lights Z2 B211 | 8564897 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 48798 | 2023-12-13 | 2023-12-06 | CLOSE | 2 | RO | 1 | 120.45 | 120.45 |  |  |  |  | KW1-13557 | 4 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-13 | COMP | 2023-12-12 | 1.00 |  | BU | BU table | December | 2023
12 | 2023-12-13 | 30 | BU24-0097 | Install Exit Lights Z2 B211 | 8564897 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 48798 | 2023-12-13 | 2023-12-06 | CLOSE | 1 | EA | 5 | 4.25 | 21.25 |  |  |  |  | KW1-13558 | 3 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-13 | COMP | 2023-12-12 | 5.00 |  | BU | BU table | December | 2023
13 | 2023-12-13 | 30 | BU24-0098 | Install Exit Signs Basewide | 8570569 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 49511 | 2023-12-13 | 2023-12-16 | CLOSE | 2 | EA | 8 | 3.26 | 26.08 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 21 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 8.00 |  | BU | BU table | December | 2023
13 | 2023-12-13 | 30 | BU24-0098 | Install Exit Signs Basewide | 8570569 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 49514 | 2023-12-13 | 2023-12-16 | CLOSE | 3 | EA | 2 | 146.47 | 292.94 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 25 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 2.00 |  | BU | BU table | December | 2023
13 | 2023-12-13 | 30 | BU24-0098 | Install Exit Signs Basewide | 8570569 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 49514 | 2023-12-13 | 2023-12-16 | CLOSE | 2 | RO | 1 | 145 | 145 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 24 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023
13 | 2023-12-13 | 30 | BU24-0098 | Install Exit Signs Basewide | 8570569 | 5305-60-V00-0205 | SCREW, PHILLIPS, FLAT HEAD, STEEL, #8 X 1 INCH | 49513 | 2023-12-13 | 2023-12-16 | CLOSE | 1 | HD | 1 | 28.97 | 28.97 | 19827 | CLOSE | 2023-12-18 |  | KW1-13776 | 5 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023
13 | 2023-12-13 | 30 | BU24-0098 | Install Exit Signs Basewide | 8570569 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 49512 | 2023-12-13 | 2023-12-16 | CLOSE | 1 | RO | 1 | 21.65 | 21.65 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 22 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023
13 | 2023-12-13 | 30 | BU24-0098 | Install Exit Signs Basewide | 8570569 | 5975-60-V00-0531 | PROTECTOR, ELECTRICAL CABLE, PVC, WHITE, 1 INCH X 9 FEET | 49511 | 2023-12-13 | 2023-12-16 | CLOSE | 1 | EA | 4 | 16.48 | 65.92 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 20 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-23 | 4.00 |  | BU | BU table | December | 2023
13 | 2023-12-13 | 30 | BU24-0098 | Install Exit Signs Basewide | 8570569 | 5975-60-V00-0480 | JUNCTION BOX, w/ BLANK SIDE, 100 X 100 X 50 MM | 49514 | 2023-12-13 | 2023-12-16 | CLOSE | 1 | EA | 1 | 12.14 | 12.14 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 23 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023
14 | 2023-12-13 | 30 | BU24-0107 | Install Electrical Outlet FBF T008 | 8674569 | 5935-60-V00-0164 | SOCKET OUTLET, PLUG-IN, SWITCHED, 2 POLE, 2 GANG, 250V, 13A | 49517 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | EA | 2 | 56 | 112 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 14 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 2.00 |  | BU | BU table | December | 2023
14 | 2023-12-13 | 30 | BU24-0107 | Install Electrical Outlet FBF T008 | 8674569 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 49517 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | RO | 1 | 163 | 163 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 13 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023
14 | 2023-12-13 | 30 | BU24-0107 | Install Electrical Outlet FBF T008 | 8674569 | 5925-60-V00-0264 | CIRCUIT BREAKER, (MCB), 3 POLE, 230-400 V, 20A | 49515 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | EA | 1 | 32.47 | 32.47 | 19826 | CLOSE | 2023-12-22 | 2023-12-18 | KW1-13875 | 6 | 2023-12-22 | APPR | 2023-12-23 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-31 | COMP | 2023-12-27 | 1.00 |  | BU | BU table | December | 2023
14 | 2023-12-13 | 30 | BU24-0107 | Install Electrical Outlet FBF T008 | 8674569 | 5925-60-V00-0129 | CIRCUIT BREAKER, MCB, 1 POLE, 240/415V, 16A | 49518 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | EA | 1 | 24 | 24 | 19872 | CLOSE | 2024-02-23 | 2023-12-21 | KW1-14010 | 1 | 2023-12-30 | CLOSE | 2024-01-09 | Vishwanath, Shet -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-07 | COMP | 2024-01-04 | 1.00 |  | BU | BU table | December | 2023
14 | 2023-12-13 | 30 | BU24-0107 | Install Electrical Outlet FBF T008 | 8674569 | 4730-60-V00-0045 | ADAPTER, ELECTRICAL CONDUIT, w/BUSH, FEMALE, PVC, WHITE, 20 MM | 49516 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | EA | 6 | 6.2 | 37.2 |  |  |  |  | KW1-13754 | 1 | 2023-12-18 | APPR | 2023-12-18 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-04 | COMP | 2023-12-21 | 6.00 |  | BU | BU table | December | 2023
14 | 2023-12-13 | 30 | BU24-0107 | Install Electrical Outlet FBF T008 | 8674569 | 5975-60-V00-0083 | CONDUIT, NONMETALLIC, HEAVY GAUGE, UPVC, WHITE, 20 MM X 3M | 49515 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | EA | 4 | 10.99 | 43.96 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 12 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-23 | 4.00 |  | BU | BU table | December | 2023
15 | 2023-12-16 | 30 | BU24-0073 | Install Covers Ring 4 Power Plant | 8530135 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 49762 | 2023-12-16 | 2023-12-16 | CLOSE | 1 | EA | 15 | 61.27 | 919.05 | 19909 | CLOSE | 2023-12-26 | 2023-12-21 | KW1-13925 | 10 | 2023-12-26 | APPR | 2023-12-26 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-06 | COMP | 2023-12-30 | 15.00 |  | BU | BU table | December | 2023
16 | 2023-12-16 | 30 | BU24-0095 | Install Vestibule Doors Z5 Pad21 TT14 | 8563372 | 9905-60-V00-0004 | SIGNS, ADVERTISING DISPLAYS, AND IDENTIFICATION PLATES (CUSTOMIZED). | 49784 | 2023-12-16 | 2023-12-19 | CLOSE | 1 | PK | 2 | 58.35 | 116.7 | 19954 | CLOSE | 2023-12-24 |  | KW1-13903 | 8 | 2023-12-24 | APPR | 2023-12-24 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-01-21 | COMP | 2024-01-10 | 2.00 |  | BU | BU table | December | 2023
17 | 2023-12-16 | 30 | BU24-0096 | Install Vestibule Doors Z5 Pad21 TT09 | 8564095 | 9905-60-V00-0004 | SIGNS, ADVERTISING DISPLAYS, AND IDENTIFICATION PLATES (CUSTOMIZED). | 49785 | 2023-12-16 | 2023-12-19 | CLOSE | 1 | PK | 2 | 58.35 | 116.7 | 19954 | CLOSE | 2023-12-24 |  | KW1-13903 | 9 | 2023-12-24 | APPR | 2023-12-24 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-01-21 | COMP | 2024-01-10 | 2.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 49844 | 2023-12-17 | 2023-12-19 | CLOSE | 3 | EA | 1 | 349.8 | 349.8 |  |  |  |  | KW1-13827 | 4 | 2023-12-22 | APPR | 2023-12-22 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 | COMP | 2023-12-26 | 1.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 49840 | 2023-12-17 | 2023-12-19 | CLOSE | 1 | EA | 1 | 60.72 | 60.72 | 19959 | CLOSE | 2023-12-23 |  | KW1-13877 | 5 | 2023-12-23 | APPR | 2023-12-23 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-26 | 1.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 6145-60-V00-0112 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 95 MM² | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 11 | MR | 60 | 85.91 | 5154.6 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 52 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-30 | 60.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM ² | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 10 | YD | 25 | 267.6 | 267.6 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 51 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-25 | 1.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5940-60-V00-0016 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 16 MM² | 49828 | 2023-12-17 | 2023-12-19 | CLOSE | 1 | EA | 8 | 1.8 | 14.4 | 19959 | CLOSE | 2023-12-23 |  | KW1-13877 | 4 | 2023-12-23 | APPR | 2023-12-23 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-26 | 8.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5975-60-V00-0515 | STUFFING TUBE (CABLE GLAND), BRASS, BW, 50 MM | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 9 | EA | 2 | 29.8 | 59.6 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 50 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-25 | 2.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5940-60-V00-0025 | TERMINAL, LUG, TIN-PLATED, M12, 95MM², 3 X 24.5 X 60.5 INCHES | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 8 | EA | 8 | 28.84 | 230.72 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 49 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-25 | 8.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 4240-60-V00-0122 | TAPE, WARNING, CAUTION BURIED ELECTRICAL CABLE BELOW, YELLOW 6 INCHES X 1000 FEET | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 7 | RL | 1 | 176.82 | 176.82 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 48 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-27 | 1.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 6145-60-V00-0047 | WIRE, ELECTRICAL, GREEN/YELLOW, 1 CORE, 50MM ² | 49844 | 2023-12-17 | 2023-12-19 | CLOSE | 2 | MR | 60 | 10.3 | 618 |  |  |  |  | KW1-13827 | 3 | 2023-12-22 | APPR | 2023-12-22 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 | COMP | 2023-12-29 | 60.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5940-60-V00-0086 | LUG, TERMINAL, ROUND TYPE, ONE-HOLE, 50MM² X 10MM | 49827 | 2023-12-17 | 2023-12-19 |  | 6 | PG | 1 | 74.93 | 74.93 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 47 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 | COMP | 2023-12-30 | 6 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5610-60-V00-0014 | SAND | 49841 | 2023-12-17 | 2023-12-19 | CLOSE | 1 | CZ | 30 | 41.25 | 1237.5 | 19943 | CLOSE | 2023-12-26 | 2023-12-21 | KW1-13930 | 1 | 2023-12-26 | APPR | 2023-12-26 | Reghunath, Rajesh -Vectrus -GSD -No Export | GULF PIONEER COMPANY LLC | 2024-01-06 | COMP | 2023-12-27 | 30.00 | Catalog changed | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5620-60-V00-0006 | CONCRETE MASONRY UNIT, SOLID, 15 X 15 X 15 INCHES | 49842 | 2023-12-17 | 2023-12-19 | CLOSE | 1 | EA | 4 | 102.27 | 409.08 | 19939 | CLOSE | 2024-01-13 | 2023-12-23 | KW1-13992 | 7 | 2023-12-29 | APPR | 2024-01-03 | Reghuraman, Karthik -Vectrus -GSD -No Export | COMMERCIAL UNITED GINCO EST. | 2024-01-06 07:00 | COMP | 2024-01-13 | 4.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5306-60-V00-0005 | BOLT, CONCRETE ANCHOR, w/NUT & WASHER, M16 X 6 INCHES | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 5 | EA | 10 | 3.33 | 33.3 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 46 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-27 | 10.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5975-60-V00-0521 | CLAMP, GROUNDING, 5/8 INCH | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 4 | EA | 10 | 24.98 | 249.8 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 45 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-25 | 10.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5970-01-013-9369 | TAPE, INSULATION ELECTRICAL, 3M, 792", RED | 49843 | 2023-12-17 | 2023-12-19 | CLOSE | 2 | RO | 1 | 11.2 | 11.2 | 19959 | CLOSE | 2023-12-23 |  | KW1-13877 | 7 | 2023-12-23 | APPR | 2023-12-23 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-26 | 1.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5970-01-174-5651 | TAPE, INSULATION ELECTRICAL, 3M, 792", YELLOW | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 3 | RO | 1 | 10.1 | 10.1 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 44 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-25 | 1.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5970-01-015-5060 | TAPE, INSULATION ELECTRICAL, 3M, 792", BLUE | 49843 | 2023-12-17 | 2023-12-19 | CLOSE | 1 | RO | 1 | 10.23 | 10.23 | 19959 | CLOSE | 2023-12-23 |  | KW1-13877 | 6 | 2023-12-23 | APPR | 2023-12-23 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-26 | 1.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5970-00-685-9059 | TAPE, INSULATION ELECTRICAL, 3M, 792", BLOCK | 49844 | 2023-12-17 | 2023-12-19 | CLOSE | 1 | RO | 1 | 39.58 | 39.58 |  |  |  |  | KW1-13827 | 2 | 2023-12-22 | APPR | 2023-12-22 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 | COMP | 2023-12-26 | 1.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5970-60-V00-0032 | TAPE, INSULATION ELECTRICAL, 3M, 792", YELLOW & GREEN | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 2 | RO | 1 | 16.98 | 16.98 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 43 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-25 | 1.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5975-60-V00-0504 | UNION, ELECTRICAL CONDUIT, NYLON POLYAMIDE, WHITE, 5-10 MM | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 1 | EA | 5 | 3.33 | 16.65 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 42 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-25 | 5.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 |  | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5975-60-V00-0498 | SPLICING KIT, CABLE JOINT, 25MM | [5 empty] | EA | 0 | [17 empty] | Not Required | BU | BU table | December | 2023
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5975-60-V00-0395 | STRAP, TIE DOWN, WHITE, 12 INCHES | 49845 | 2023-12-17 | 2023-12-19 | CLOSE | 1 | PG | 1 | 12.38 | 12.38 | 19986 | SENT | 2023-12-27 | 2023-12-24 | KW1-13963 | 1 | 2023-12-27 | APPR | 2023-12-27 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-10 | COMP | 2024-01-02 | 1.00 |  | BU | BU table | December | 2023
18 | 2023-12-17 |  | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5940-60-V00-0091 | SPLICE, CONDUCTOR, BUTT, STANDARD BARREL, COPPER, BLUE, 16 MM | [5 empty] | PG | 0 | [17 empty] | Not Required | BU | BU table | December | 2023
19 | 2023-12-21 | 30 | BU24-0027 | Service HVAC Units Z1 B1999 | 8236954 | 4130-60-V00-0484 | FILTER ELEMENT, AIR CONDITIONING, WASHABLE, ALUMINUM, 19.5 X 19.5 X 1.75 INCHES | 50183 | 2023-12-21 | 2023-12-23 | CLOSE | 1 | EA | 4 | 60.21 | 240.84 | 20126 | SENT | 2024-01-11 | 2024-01-05 | KW1-14093 | 1 | 2024-01-07 | APPR | 2024-01-07 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-01-25 | COMP | 2024-01-16 | 4.00 |  | BU | BU table | December | 2023
20 | 2023-12-21 | 30 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 8135-60-V00-0003 | PLASTIC SHEET, POLYETHYLENE, CLEAR, 6 MIL, 32 X 100 FEET | 50298 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | RO | 1 | 442.89 | 442.89 | 20210 | SENT | 2024-01-09 |  | KW1-14124 | 11 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
20 | 2023-12-21 | 30 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 5510-60-V00-0004 | LUMBER, SOFTWOOD, DIMENSION, 4 X 4 INCHES X 13 FEET | 50300 | 2023-12-23 | 2023-12-23 | CLOSE | 2 | EA | 60 | 37.46 | 2247.6 | 20018 | CLOSE | 2023-12-26 |  | KW1-13937 | 2 | 2023-12-26 | APPR | 2023-12-27 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-06 | COMP | 2023-12-30 | 60.00 |  | BU | BU table | December | 2023
20 | 2023-12-21 | 30 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 5510-01-433-1244 | LUMBER, SMOOTH THREATED, 4 INCH X 16 FEET | 50525 | 2023-12-23 | 2023-12-25 | CLOSE | 1 | EA | 10 | 30.36 | 303.6 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 29 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 10.00 |  | BU | BU table | December | 2023
20 | 2023-12-21 | 30 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 5530-00-618-8073 | PLYWOOD, CONSTRUCTION, 3/4 INCH X 4 X 8 FEET | 50299 | 2023-12-23 | 2023-12-23 | CLOSE | 2 | SH | 30 | 47.45 | 1423.5 | 20123 | CLOSE | 2024-01-04 |  | KW1-14040 | 1 | 2024-01-04 | APPR | 2024-01-04 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-15 | COMP | 2024-01-07 | 30.00 |  | BU | BU table | December | 2023
20 | 2023-12-21 | 30 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 5530-60-V00-0010 | PLYWOOD, CONSTRUCTION, BLACK, 3/4 INCH X 4 X 8 FEET | 50299 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 25 | 61.61 | 1540.25 | 20102 | CLOSE | 2024-01-07 | 2024-01-04 | KW1-14079 | 10 | 2024-01-07 | APPR | 2024-01-07 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-21 | COMP | 2024-01-11 | 25.00 |  | BU | BU table | December | 2023
20 | 2023-12-21 | 30 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 5305-60-V00-0147 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #7 X 2 INCHES | 50302 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | BX | 4 | 29.7 | 118.8 | 20206 | CLOSE | 2024-02-17 | 2024-01-10 | KW1-14188 | 10 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-20 | COMP | 2024-01-17 | 4.00 |  | BU | BU table | December | 2023
20 | 2023-12-21 | 30 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 5305-60-V00-0169 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 3 INCHES | 50300 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | BX | 3 | 30.97 | 92.91 | 20018 | CLOSE | 2023-12-26 |  | KW1-13937 | 1 | 2023-12-26 | APPR | 2023-12-27 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-20 | COMP | 2023-12-30 | 3.00 |  | BU | BU table | December | 2023
20 | 2023-12-21 | 30 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 5510-01-433-1244 | LUMBER, SOFTWOOD, 2 X 4 INCHES X 16 FEET | 50607 | 2023-12-23 | 2023-12-26 | CLOSE | 1 | EA | 6 | 30.55 | 183.3 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 34 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 6.00 |  | BU | BU table | December | 2023
20 | 2023-12-21 | 30 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 5530-00-129-7777 | PLYWOOD, CONSTRUCTION, EXTERIOR, 1/2 INCH X 8 X 4 FEET | 50301 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 2 | 36.4 | 72.8 | 20206 | CLOSE | 2024-02-17 | 2024-01-10 | KW1-14188 | 14 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-26 | COMP | 2024-01-17 | 2.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 5530-00-618-8073 | PLYWOOD, CONSTRUCTION, 3/4 INCH X 4 X 8 FEET | 50426 | 2023-12-23 | 2023-12-24 | CLOSE | 3 | SH | 25 | 46.4 | 1160 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 15 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 25.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 5510-01-433-1244 | LUMBER, SMOOTH THREATED, 4 INCH X 16 FEET | 50424 | 2023-12-23 | 2023-12-24 | CLOSE | 1 | EA | 10 | 29.97 | 299.7 | 20210 | SENT | 2024-01-09 |  | KW1-14124 | 29 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-23 | COMP | 2024-01-14 | 10.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 5510-60-V00-0004 | LUMBER, SOFTWOOD, DIMENSION, 4 X 4 INCHES X 13 FEET | 50427 | 2023-12-23 | 2023-12-24 | CLOSE | 3 | EA | 10 | 36.63 | 366.3 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 18 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 10.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 5510-01-433-1371 | LUMBER, SOFTWOOD, 2 X 6 INCHES X 16 FEET | 50421 | 2023-12-23 | 2024-01-13 | CLOSE | 1 | EA | 25 | 17.75 | 443.75 | 20334 | CLOSE | 2024-01-13 | 2024-01-10 | KW1-14211 | 1 | 2024-01-13 | CLOSE | 2024-01-30 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-24 | 25.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 5305-60-V00-0147 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #7 X 2 INCHES | 50430 | 2023-12-23 | 2023-12-24 | CLOSE | 1 | BX | 1 | 29.7 | 29.7 | 20206 | CLOSE | 2024-02-17 | 2024-01-10 | KW1-14188 | 36 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-26 | COMP | 2024-01-17 | 1.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 5305-60-V00-0151 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, COARSE THREAD, #10 X 3-1/2 INCHES | 50426 | 2023-12-23 | 2023-12-24 | CLOSE | 2 | BX | 1 | 65.12 | 65.12 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 14 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 1.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 7210-60-V00-0059 | FLOOR COVERING, VINYL RESIN, 3 MM X 40 FEET | 50428 | 2023-12-23 | 2023-12-24 | CLOSE | 1 | RO | 1 | 716.1 | 716.1 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 19 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-24 | 1.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 8040-00-273-8713 | ADHESIVE, FLOORING, WHITE, | 50429 | 2023-12-23 | 2023-12-24 | CLOSE | 1 | GL | 3 | 185.7 | 557.1 | 20225 | CLOSE | 2024-01-10 | 2024-01-10 | KW1-14138 | 1 | 2024-01-11 | APPR | 2024-01-11 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 3.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 5640-60-V00-0038 | STRIP, ALUMINIUM, 3MM X 1-1/2 INCHES X 12FEET | 50426 | 2023-12-23 | 2023-12-24 | CLOSE | 1 | EA | 5 | 43.96 | 219.8 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 13 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 5.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 50423 | 2023-12-23 | 2023-12-24 | CLOSE | 3 | EA | 15 | 44.61 | 669.15 | 20214 | CLOSE | 2024-01-09 |  | KW1-14130 | 21 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 15.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 8030-01-075-1156 | CAULKING COMPOUND, LATEX, WHITE, 10.3 OZ | 50427 | 2023-12-23 | 2023-12-24 | CLOSE | 2 | EA | 12 | 14.65 | 175.8 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 17 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 12.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 8010-60-V00-0122 | PAINT, LATEX, MATT, WHITE, 16 LT | 50622 | 2023-12-23 | 2023-12-27 | CLOSE |  | CN | 2 | 66.14 | 132.28 | 20206 | CLOSE | 2024-02-17 | 2024-01-10 | KW1-14188 | 56 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-26 | COMP | 2024-01-25 | 2.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 50423 | 2023-12-23 | 2023-12-24 | CLOSE | 2 | CN | 1 | 36.63 | 36.63 | 20242 | CLOSE | 2024-01-10 |  | KW1-14159 | 1 | 2024-01-10 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-20 | COMP | 2024-01-13 | 1.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 50425 | 2023-12-23 | 2023-12-24 | CLOSE | 2 | EA | 3 | 28.65 | 85.95 |  |  |  |  | KW1-14173 | 2 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 3.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 50425 | 2023-12-23 | 2023-12-24 | CLOSE | 1 | EA | 10 | 13.67 | 136.7 |  |  |  |  | KW1-14173 | 1 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 10.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 50428 | 2023-12-23 | 2023-12-24 | CLOSE | 3 | EA | 3 | 14.6 | 43.8 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 21 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 3.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 8010-60-V00-0089 | PRIMER, COATING, WHITE, 4 - 5 LITERS | 50423 | 2023-12-23 | 2023-12-24 | CLOSE | 1 | CN | 3 | 40.5 | 121.5 | 20214 | CLOSE | 2024-01-09 |  | KW1-14130 | 20 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 3.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 6515-60-V00-0015 | GLOVES, EXAM, DISPOSABLE, NITRILE, PURPLE, X-LARGE | 50422 | 2023-12-23 | 2023-12-24 | CLOSE | 1 | EA | 1 | 48.84 | 48.84 | 20206 | CLOSE | 2024-02-17 | 2024-01-10 | KW1-14188 | 30 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-20 | COMP | 2024-01-21 | 1.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 5120-60-V00-0295 | CAULKING GUN, RATCHET ROD, PLASTIC, YELLOW/BLACK, 10 OZ | 50427 | 2023-12-23 | 2023-12-24 | CLOSE | 1 | EA | 1 | 163.61 | 163.61 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 16 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 1.00 |  | BU | BU table | December | 2023
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 7510-00-266-6710 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 50428 | 2023-12-23 | 2023-12-24 | CLOSE | 2 | RO | 5 | 8 | 40 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 20 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 5.00 |  | BU | BU table | December | 2023
22 | 2023-12-23 | 30 | BU24-0119 | Install Electrical Outlet Z2 T2072 | 8789414 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 50469 | 2023-12-24 | 2023-12-24 | CLOSE | 5 | EA | 3 | 10.1 | 30.3 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 26 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 3.00 |  | BU | BU table | December | 2023
22 | 2023-12-23 | 30 | BU24-0119 | Install Electrical Outlet Z2 T2072 | 8789414 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 50469 | 2023-12-24 | 2023-12-24 | CLOSE | 4 | RO | 1 | 163 | 163 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 25 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 1.00 |  | BU | BU table | December | 2023
22 | 2023-12-23 | 30 | BU24-0119 | Install Electrical Outlet Z2 T2072 | 8789414 | 5975-60-V00-0652 | CONDUIT, EMT, STANDARD, GALVANIZED, GRAY, STEEL, 10 FEET X 3/4 INCHES | 50469 | 2023-12-24 | 2023-12-24 | CLOSE | 3 | EA | 4 | 158.18 | 632.72 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 24 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 4.00 |  | BU | BU table | December | 2023
22 | 2023-12-23 | 30 | BU24-0119 | Install Electrical Outlet Z2 T2072 | 8789414 | 5975-01-252-3611 | HANGER, CABLE, EMT, 1-HOLE PUSH-ON STRAP, STEEL, 3/4 X 1.99 INCHES | 50469 | 2023-12-24 | 2023-12-24 | CLOSE | 2 | EA | 15 | 6.49 | 97.35 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 23 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 15.00 |  | BU | BU table | December | 2023
22 | 2023-12-23 | 30 | BU24-0119 | Install Electrical Outlet Z2 T2072 | 8789414 | 5975-09-V00-0137 | ADAPTER, ELECTRICAL CONDUIT, EMT, SET SCREW, ZINC PLATED STEEL, GRAY/YELLOW, 3/4 X 1-15/32 INCH | 50471 | 2023-12-24 | 2023-12-24 | CLOSE | 1 | EA | 8 | 1.18 | 9.44 | 20343 | CLOSE | 2024-01-23 | 2024-01-15 | KW1-14388 | 5 | 2024-01-23 | APPR | 2024-01-23 | Visakh, Ajith - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-23 | COMP | 2024-02-22 | 8.00 |  | BU | BU table | December | 2023
22 | 2023-12-23 | 30 | BU24-0119 | Install Electrical Outlet Z2 T2072 | 8789414 | 5305-60-V00-0205 | SCREW, PHILLIPS, FLAT HEAD, STEEL, #8 X 1 INCH | 50470 | 2023-12-24 | 2023-12-24 | CLOSE | 1 | PG | 1 | 28.4 | 28.4 | 20210 | SENT | 2024-01-09 |  | KW1-14124 | 35 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-23 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
22 | 2023-12-23 | 30 | BU24-0119 | Install Electrical Outlet Z2 T2072 | 8789414 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50469 | 2023-12-24 | 2023-12-24 | CLOSE | 1 | EA | 4 | 3.7 | 14.8 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 22 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 4.00 |  | BU | BU table | December | 2023
23 | 2023-12-28 | 40 | BU-24-0098 | BUH-Z3-00-TRLR3020 | 7286430 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50798 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EA | 8 | 3.5 | 28 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 16 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 8.00 |  | BU | BU table | December | 2023
23 | 2023-12-28 | 40 | BU-24-0098 | BUH-Z3-00-TRLR3020 | 7286430 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50800 | 2023-12-29 | 2023-12-30 | CLOSE | 2 | EA | 1 | 146.47 | 146.47 |  |  |  |  | KW1-14173 | 19 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023
23 | 2023-12-28 | 40 | BU-24-0098 | BUH-Z3-00-TRLR3020 | 7286430 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 50798 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | RO | 1 | 146.52 | 146.52 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 15 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
23 | 2023-12-28 | 40 | BU-24-0098 | BUH-Z3-00-TRLR3020 | 7286430 | 5305-60-V00-0205 | SCREW, PHILLIPS, FLAT HEAD, STEEL, #8 X 1 INCH | 50799 | 2023-12-29 | 2023-12-30 | CLOSE | 1 | HD | 1 | 28.4 | 28.4 | 20213 | SENT | 2024-01-10 |  | KW1-14128 | 7 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-23 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
23 | 2023-12-28 | 40 | BU-24-0098 | BUH-Z3-00-TRLR3020 | 7286430 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 50800 | 2023-12-29 | 2023-12-30 | CLOSE | 1 | RO | 1 | 21.11 | 21.11 |  |  |  |  | KW1-14173 | 18 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023
24 | 2023-12-28 | 50 | BU-24-0098 | BUH-00-ECP1-TRLR2000-00-00 | 5839058 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 50806 | 2023-12-29 | 2023-12-31 | CLOSE | 4 | ROLL | 1 | 146.52 | 146.52 | 20262 | CLOSE | 2024-01-19 | 2024-01-15 | KW1-14302 | 26 | 2024-01-19 | APPR | 2024-01-19 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-01-27 07:00 | COMP | 2024-01-23 | 1.00 |  | BU | BU table | December | 2023
24 | 2023-12-28 | 50 | BU-24-0098 | BUH-00-ECP1-TRLR2000-00-00 | 5839058 | 5975-60-V00-0533 | RACEWAY, CABLE, PVC, WHITE, 1-1/2 INCH X 10 FEET | 50806 | 2023-12-29 | 2023-12-31 | CLOSE | 3 | EACH | 7 | 1.64 | 11.49 | 20262 | CLOSE | 2024-01-19 | 2024-01-15 | KW1-14302 | 25 | 2024-01-19 | APPR | 2024-01-19 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-01-27 07:00 | COMP | 2024-01-23 | 7.00 |  | BU | BU table | December | 2023
24 | 2023-12-28 | 50 | BU-24-0098 | BUH-00-ECP1-TRLR2000-00-00 | 5839058 | 6220-60-V00-0165 | LIGHT UNIT, EMERGENCY, EXIT SIGN, SELF-TEST, GREEN, 220-240V AC, 50/60 HZ, 3W | 50808 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | EACH | 2 | 147.3 | 294.6 |  |  |  |  | KW1-14173 | 20 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023
24 | 2023-12-28 | 50 | BU-24-0098 | BUH-00-ECP1-TRLR2000-00-00 | 5839058 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50806 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EACH | 10 | 3.5 | 35 | 20262 | CLOSE | 2024-01-19 | 2024-01-15 | KW1-14302 | 24 | 2024-01-19 | APPR | 2024-01-19 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-01-27 07:00 | COMP | 2024-01-23 | 10.00 |  | BU | BU table | December | 2023
24 | 2023-12-28 | 50 | BU-24-0098 | BUH-00-ECP1-TRLR2000-00-00 | 5839058 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 50806 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | PG | 3 | 27.31 | 81.93 | 20262 | CLOSE | 2024-01-19 | 2024-01-15 | KW1-14302 | 23 | 2024-01-19 | APPR | 2024-01-19 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-01-27 07:00 | COMP | 2024-01-23 | 3.00 |  | BU | BU table | December | 2023
24 | 2023-12-28 | 50 | BU-24-0098 | BUH-00-ECP1-TRLR2000-00-00 | 5839058 | 5305-60-V00-0180 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #6 X 1 INCHES | 50807 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | BX | 1 | 25.8 | 25.8 |  |  |  |  | KW1-14180 | 12 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 1.00 |  | BU | BU table | December | 2023
25 | 2023-12-28 | 60 | BU-24-0098 | BUH-ECP1-TRLR2001-00 | 5930537 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50809 | 2023-12-29 | 2023-12-31 | CLOSE | 3 | EA | 10 | 3.5 | 35 |  |  |  |  | KW1-14173 | 23 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 10.00 |  | BU | BU table | December | 2023
25 | 2023-12-28 | 60 | BU-24-0098 | BUH-ECP1-TRLR2001-00 | 5930537 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50810 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | EA | 3 | 146.47 | 439.41 |  |  |  |  | KW1-14173 | 24 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 3.00 |  | BU | BU table | December | 2023
25 | 2023-12-28 | 60 | BU-24-0098 | BUH-ECP1-TRLR2001-00 | 5930537 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 50809 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | RO | 1 | 146.52 | 146.52 |  |  |  |  | KW1-14173 | 22 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023
25 | 2023-12-28 | 60 | BU-24-0098 | BUH-ECP1-TRLR2001-00 | 5930537 | 5975-60-V00-0532 | PROTECTOR, ELECTRICAL CABLE, PVC, WHITE, 1/2 INCH X 10 FEET | 50811 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | EA | 4 | 8.82 | 35.28 | 20262 | CLOSE | 2024-01-19 | 2024-01-15 | KW1-14302 | 27 | 2024-01-19 | APPR | 2024-01-19 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-01-27 07:00 | COMP | 2024-01-23 | 4.00 |  | BU | BU table | December | 2023
25 | 2023-12-28 | 60 | BU-24-0098 | BUH-ECP1-TRLR2001-00 | 5930537 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 50809 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | PG | 2 | 27.31 | 54.62 |  |  |  |  | KW1-14173 | 21 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023
26 | 2023-12-28 | 70 | BU-24-0098 | ECP2-TRLR-T003-00 | 5930556 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50814 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EACH | 2 | 146.47 | 292.94 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 18 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 2.00 |  | BU | BU table | December | 2023
26 | 2023-12-28 | 70 | BU-24-0098 | ECP2-TRLR-T003-00 | 5930556 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 50812 | 2023-12-29 | 2023-12-31 | CLOSE | 3 | ROLL | 1 | 146.52 | 146.52 |  |  |  |  | KW1-14173 | 27 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023
26 | 2023-12-28 | 70 | BU-24-0098 | ECP2-TRLR-T003-00 | 5930556 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50812 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EACH | 6 | 3.5 | 21 |  |  |  |  | KW1-14173 | 26 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 6.00 |  | BU | BU table | December | 2023
26 | 2023-12-28 | 70 | BU-24-0098 | ECP2-TRLR-T003-00 | 5930556 | 5975-60-V00-0531 | PROTECTOR, ELECTRICAL CABLE, PVC, WHITE, 1 INCH X 9 FEET | 50812 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | EACH | 4 | 16.48 | 65.92 |  |  |  |  | KW1-14173 | 25 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 4.00 |  | BU | BU table | December | 2023
26 | 2023-12-28 | 70 | BU-24-0098 | ECP2-TRLR-T003-00 | 5930556 | 5305-60-V00-0180 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #6 X 1 INCHES | 50813 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | BOX | 1 | 25.8 | 25.8 |  |  |  |  | KW1-14180 | 13 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 1.00 |  | BU | BU table | December | 2023
26 | 2023-12-28 | 70 | BU-24-0098 | ECP2-TRLR-T003-00 | 5930556 | 5975-60-V00-0480 | JUNCTION BOX, w/ BLANK SIDE, 100 X 100 X 50 MM | 50814 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | EACH | 1 | 12 | 12 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 17 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
27 | 2023-12-28 | 80 | BU-24-0098 | BUH-Z1-00-TT106 | 6779272 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50815 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EA | 8 | 3.5 | 28 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 20 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 8.00 |  | BU | BU table | December | 2023
27 | 2023-12-28 | 80 | BU-24-0098 | BUH-Z1-00-TT106 | 6779272 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50818 | 2023-12-29 | 2023-12-31 | CLOSE | 5 | EA | 2 | 146.47 | 292.94 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 25 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 2.00 |  | BU | BU table | December | 2023
27 | 2023-12-28 | 80 | BU-24-0098 | BUH-Z1-00-TT106 | 6779272 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 50818 | 2023-12-29 | 2023-12-31 | CLOSE | 4 | RO | 1 | 163 | 163 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 24 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
27 | 2023-12-28 | 80 | BU-24-0098 | BUH-Z1-00-TT106 | 6779272 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 50817 | 2023-12-29 | 2023-12-30 | CLOSE | 1 | BX | 1 | 51.5 | 51.5 | 20213 | SENT | 2024-01-10 |  | KW1-14128 | 10 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-23 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
27 | 2023-12-28 | 80 | BU-24-0098 | BUH-Z1-00-TT106 | 6779272 | 5930-60-V00-0240 | SWITCH, 1 WAY, 1 GANG, 10 AMPS | 50816 | 2023-12-29 | 2024-01-10 | CLOSE | 1 | EA | 2 | 17.3 | 34.6 | 20242 | CLOSE | 2024-01-10 |  | KW1-14158 | 1 | 2024-01-10 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-20 | COMP | 2024-01-14 | 2.00 |  | BU | BU table | December | 2023
27 | 2023-12-28 | 80 | BU-24-0098 | BUH-Z1-00-TT106 | 6779272 | 5975-60-V00-0272 | SWITCH BOX, SURFACE, PVC, WHITE, 3 X 3 INCHES | 50818 | 2023-12-29 | 2023-12-31 | CLOSE | 3 | EA | 2 | 12.24 | 24.48 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 23 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 2.00 |  | BU | BU table | December | 2023
27 | 2023-12-28 | 80 | BU-24-0098 | BUH-Z1-00-TT106 | 6779272 | 5975-60-V00-0187 | PLATE, WALL, ELECTRICAL, BLANK, 1 GANG, WHITE, 86 X 86 MM | 50818 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | BX | 1 | 13.46 | 13.46 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 22 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-20 | 1.00 |  | BU | BU table | December | 2023
27 | 2023-12-28 | 80 | BU-24-0098 | BUH-Z1-00-TT106 | 6779272 | 5975-00-156-3253 | STRAP, TIE DOWN, ELECTRICAL COMPONE, 13-7/20 INCHES | 50815 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | HD | 2 | 26.64 | 53.28 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 19 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 2.00 |  | BU | BU table | December | 2023
27 | 2023-12-28 | 80 | BU-24-0098 | BUH-Z1-00-TT106 | 6779272 | 5975-60-V00-0740 | CONDUIT, HIGHLY FLEXIBLE, CORE, GALVANIZED STEEL, BLACK, 20 MM X 25 M | 50818 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | RO | 1 | 92.57 | 92.57 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 21 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
28 | 2023-12-28 | 90 | BU-24-0098 | BUH-Z3-00-TRLR3000 | 7227578 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50819 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EA | 8 | 3.5 | 28 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 27 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 8.00 |  | BU | BU table | December | 2023
28 | 2023-12-28 | 90 | BU-24-0098 | BUH-Z3-00-TRLR3000 | 7227578 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50821 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EA | 1 | 146.47 | 146.47 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 32 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
28 | 2023-12-28 | 90 | BU-24-0098 | BUH-Z3-00-TRLR3000 | 7227578 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 50819 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | RO | 1 | 146.52 | 146.52 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 26 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
28 | 2023-12-28 | 90 | BU-24-0098 | BUH-Z3-00-TRLR3000 | 7227578 | 5305-60-V00-0205 | SCREW, PHILLIPS, FLAT HEAD, STEEL, #8 X 1 INCH | 50820 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | HD | 1 | 28.4 | 28.4 | 20213 | SENT | 2024-01-10 |  | KW1-14128 | 11 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-23 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
28 | 2023-12-28 | 90 | BU-24-0098 | BUH-Z3-00-TRLR3000 | 7227578 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 50821 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | RO | 1 | 21.11 | 21.11 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 31 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
29 | 2023-12-28 | 100 | BU-24-0098 | BUH-Z6-00-TRLR3013 | 7227613 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50908 | 2023-12-30 | 2023-12-31 | CLOSE | 2 | EA | 1 | 146.47 | 146.47 |  |  |  |  | KW1-14173 | 48 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 1.00 |  | BU | BU table | December | 2023
29 | 2023-12-28 | 100 | BU-24-0098 | BUH-Z6-00-TRLR3013 | 7227613 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 50908 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | RO | 1 | 145 | 145 |  |  |  |  | KW1-14173 | 47 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023
29 | 2023-12-28 | 100 | BU-24-0098 | BUH-Z6-00-TRLR3013 | 7227613 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 50907 | 2023-12-30 | 2023-12-31 | CLOSE | 2 | BX | 1 | 170.5 | 170.5 | 20261 | CLOSE | 2024-01-11 | 2024-01-11 | KW1-14183 | 2 | 2024-01-11 | APPR | 2024-01-11 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023
29 | 2023-12-28 | 100 | BU-24-0098 | BUH-Z6-00-TRLR3013 | 7227613 | 5975-60-V00-0091 | CONDUIT, NONMETALLIC, RIGID, PVC, WHITE, 20 MM X 1.5 METERS | 50905 | 2023-12-30 | 2023-12-31 | CLOSE | 2 | EA | 5 | 9.32 | 46.6 |  |  |  |  | KW1-14173 | 45 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 5.00 | Requested catalog not Active | BU | BU table | December | 2023
29 | 2023-12-28 | 100 | BU-24-0098 | BUH-Z6-00-TRLR3013 | 7227613 | 4730-60-V00-0045 | ADAPTER, ELECTRICAL CONDUIT, w/BUSH, FEMALE, PVC, WHITE, 20 MM | 50907 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | EA | 5 | 6.2 | 31 | 20261 | CLOSE | 2024-01-11 | 2024-01-11 | KW1-14183 | 1 | 2024-01-11 | APPR | 2024-01-11 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-16 | 5.00 |  | BU | BU table | December | 2023
29 | 2023-12-28 | 100 | BU-24-0098 | BUH-Z6-00-TRLR3013 | 7227613 | 5365-60-V00-0026 | SADDLE, SPACER BAR, CONDUIT, PVC, WHITE, 20 MM | 50906 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | EA | 10 | 3.16 | 31.6 |  |  |  |  | KW1-14173 | 46 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 10.00 |  | BU | BU table | December | 2023
29 | 2023-12-28 | 100 | BU-24-0098 | BUH-Z6-00-TRLR3013 | 7227613 | 5975-60-V00-0372 | COUPLING, ELECTRICAL CONDUIT, PVC, WHITE, 20 MM | 50905 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | EA | 10 | 4.66 | 46.6 |  |  |  |  | KW1-14173 | 44 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 10.00 |  | BU | BU table | December | 2023
29 | 2023-12-28 | 100 | BU-24-0098 | BUH-Z6-00-TRLR3013 | 7227613 | 5975-60-V00-0085 | ELBOW ,CONDUIT , PVC, WHITE, 20 MILLIMETERS | 50903 | 2023-12-30 | 2023-12-30 | CLOSE | 1 | EA | 10 | 13.99 | 139.9 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 56 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 10.00 |  | BU | BU table | December | 2023
30 | 2023-12-28 | 110 | BU-24-0098 | BUH-Z3-00-TRLR3017 | 7286407 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50822 | 2023-12-29 | 2023-12-31 | CLOSE | 3 | EA | 4 | 3.5 | 14 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 30 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 4.00 |  | BU | BU table | December | 2023
30 | 2023-12-28 | 110 | BU-24-0098 | BUH-Z3-00-TRLR3017 | 7286407 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50824 | 2023-12-29 | 2023-12-31 | CLOSE | 3 | EA | 1 | 146.47 | 146.47 |  |  |  |  | KW1-14173 | 30 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 1.00 |  | BU | BU table | December | 2023
30 | 2023-12-28 | 110 | BU-24-0098 | BUH-Z3-00-TRLR3017 | 7286407 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 50822 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | RO | 1 | 146.52 | 146.52 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 29 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
30 | 2023-12-28 | 110 | BU-24-0098 | BUH-Z3-00-TRLR3017 | 7286407 | 5305-60-V00-0205 | SCREW, PHILLIPS, FLAT HEAD, STEEL, #8 X 1 INCH | 50823 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | HD | 1 | 28.4 | 28.4 | 20213 | SENT | 2024-01-10 |  | KW1-14128 | 8 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-23 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
30 | 2023-12-28 | 110 | BU-24-0098 | BUH-Z3-00-TRLR3017 | 7286407 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 50824 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | RO | 1 | 21.11 | 21.11 |  |  |  |  | KW1-14173 | 29 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023
30 | 2023-12-28 | 110 | BU-24-0098 | BUH-Z3-00-TRLR3017 | 7286407 | 5975-60-V00-0531 | PROTECTOR, ELECTRICAL CABLE, PVC, WHITE, 1 INCH X 9 FEET | 50822 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | EA | 4 | 16.48 | 65.92 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 28 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 4.00 |  | BU | BU table | December | 2023
30 | 2023-12-28 | 110 | BU-24-0098 | BUH-Z3-00-TRLR3017 | 7286407 | 5975-60-V00-0480 | JUNCTION BOX, w/ BLANK SIDE, 100 X 100 X 50 MM | 50824 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | EA | 1 | 12 | 12 |  |  |  |  | KW1-14173 | 28 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023
31 | 2023-12-28 | 120 | BU-24-0098 | BUH-Z3-00-TRLR3021 | 7286435 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50822 | 2023-12-29 | 2023-12-31 | CLOSE | 3 | EA | 8 | 3.5 | 14 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 30 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 4.00 |  | BU | BU table | December | 2023
31 | 2023-12-28 | 120 | BU-24-0098 | BUH-Z3-00-TRLR3021 | 7286435 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50824 | 2023-12-29 | 2023-12-31 | CLOSE | 3 | EA | 1 | 146.47 | 146.47 |  |  |  |  | KW1-14173 | 30 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 1.00 |  | BU | BU table | December | 2023
31 | 2023-12-28 | 120 | BU-24-0098 | BUH-Z3-00-TRLR3021 | 7286435 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 50822 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | RO | 1 | 146.52 | 146.52 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 29 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
31 | 2023-12-28 | 120 | BU-24-0098 | BUH-Z3-00-TRLR3021 | 7286435 | 5305-60-V00-0205 | SCREW, PHILLIPS, FLAT HEAD, STEEL, #8 X 1 INCH | 50823 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | HD | 1 | 28.4 | 28.4 | 20213 | SENT | 2024-01-10 |  | KW1-14128 | 8 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-23 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
31 | 2023-12-28 | 120 | BU-24-0098 | BUH-Z3-00-TRLR3021 | 7286435 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 50824 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | RO | 1 | 21.11 | 21.11 |  |  |  |  | KW1-14173 | 29 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023
32 | 2023-12-28 | 130 | BU-24-0098 | UD-AF-9602-00 | 7372091 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50830 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EA | 2 | 146.47 | 292.94 |  |  |  |  | KW1-14173 | 38 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 2.00 |  | BU | BU table | December | 2023
32 | 2023-12-28 | 130 | BU-24-0098 | UD-AF-9602-00 | 7372091 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 50830 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | RO | 1 | 163 | 163 |  |  |  |  | KW1-14173 | 37 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023
32 | 2023-12-28 | 130 | BU-24-0098 | UD-AF-9602-00 | 7372091 | 5975-60-V00-0531 | PROTECTOR, ELECTRICAL CABLE, PVC, WHITE, 1 INCH X 9 FEET | 50828 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EA | 8 | 16.48 | 131.84 |  |  |  |  | KW1-14173 | 36 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 8.00 |  | BU | BU table | December | 2023
32 | 2023-12-28 | 130 | BU-24-0098 | UD-AF-9602-00 | 7372091 | 5975-60-V00-0506 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, WHITE, PG29, 18-25MM | 50828 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | EA | 5 | 28.31 | 141.55 |  |  |  |  | KW1-14173 | 35 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 5.00 |  | BU | BU table | December | 2023
32 | 2023-12-28 | 130 | BU-24-0098 | UD-AF-9602-00 | 7372091 | 5305-60-V00-0187 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATE, #6 X 1 INCH | 50829 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | BX | 1 | 14.82 | 14.82 |  |  |  |  | KW1-14180 | 15 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 1.00 |  | BU | BU table | December | 2023
33 | 2023-12-28 | 140 | BU-24-0098 | UD-AF-9206-00 | 7372568 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50837 | 2023-12-29 | 2023-12-30 | CLOSE | 2 | EA | 2 | 161.7 | 323.4 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 38 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 2.00 |  | BU | BU table | December | 2023
33 | 2023-12-28 | 140 | BU-24-0098 | UD-AF-9206-00 | 7372568 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 50837 | 2023-12-29 | 2023-12-30 | CLOSE | 1 | RO | 1 | 163.35 | 163.35 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 37 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
33 | 2023-12-28 | 140 | BU-24-0098 | UD-AF-9206-00 | 7372568 | 5975-60-V00-0531 | PROTECTOR, ELECTRICAL CABLE, PVC, WHITE, 1 INCH X 9 FEET | 50835 | 2023-12-29 | 2023-12-30 | CLOSE | 2 | EA | 2 | 16.12 | 32.24 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 36 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 2.00 |  | BU | BU table | December | 2023
33 | 2023-12-28 | 140 | BU-24-0098 | UD-AF-9206-00 | 7372568 | 5975-60-V00-0506 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, WHITE, PG29, 18-25MM | 50835 | 2023-12-29 | 2023-12-30 | CLOSE | 1 | EA | 5 | 28 | 140 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 35 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 5.00 |  | BU | BU table | December | 2023
33 | 2023-12-28 | 140 | BU-24-0098 | UD-AF-9206-00 | 7372568 | 5305-60-V00-0187 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATE, #6 X 1 INCH | 50836 | 2023-12-29 | 2023-12-30 | CLOSE | 1 | BX | 1 | 14.69 | 14.69 | 20213 | SENT | 2024-01-10 |  | KW1-14128 | 12 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-23 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023
34 | 2023-12-28 | 150 | BU-24-0098 | UD-AF-9410-00 | 7372576 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50833 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EA | 2 | 146.47 | 292.94 |  |  |  |  | KW1-14173 | 43 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 2.00 |  | BU | BU table | December | 2023
34 | 2023-12-28 | 150 | BU-24-0098 | UD-AF-9410-00 | 7372576 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 50833 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | RO | 1 | 163 | 163 |  |  |  |  | KW1-14173 | 42 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023
34 | 2023-12-28 | 150 | BU-24-0098 | UD-AF-9410-00 | 7372576 | 5975-60-V00-0531 | PROTECTOR, ELECTRICAL CABLE, PVC, WHITE, 1 INCH X 9 FEET | 50831 | 2023-12-29 | 2023-12-31 | CLOSE | 3 | EA | 2 | 16.48 | 32.96 |  |  |  |  | KW1-14173 | 41 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 2.00 |  | BU | BU table | December | 2023
34 | 2023-12-28 | 150 | BU-24-0098 | UD-AF-9410-00 | 7372576 | 5975-60-V00-0534 | PROTECTOR, CABLE, PVC, WHITE, 2 INCHES X 10 FEET | 50831 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EA | 2 | 167.83 | 335.66 |  |  |  |  | KW1-14173 | 40 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-25 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | December | 2023
34 | 2023-12-28 | 150 | BU-24-0098 | UD-AF-9410-00 | 7372576 | 5975-60-V00-0506 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, WHITE, PG29, 18-25MM | 50831 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | EA | 6 | 28.31 | 169.86 |  |  |  |  | KW1-14173 | 39 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 6.00 |  | BU | BU table | December | 2023
34 | 2023-12-28 | 150 | BU-24-0098 | UD-AF-9410-00 | 7372576 | 5305-60-V00-0187 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATE, #6 X 1 INCH | 50832 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | BX | 1 | 14.82 | 14.82 |  |  |  |  | KW1-14180 | 16 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 1.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 14 | EA | 13 | 9.9 | 128.7 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 33 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 13.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5935-60-V00-0172 | SOCKET, ELECTRICAL, FEMALE, 3 PIN, 220V, 32A | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 14 | EA | 1 | 35.82 | 35.82 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 19 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5935-60-V00-0173 | CONNECTOR, PLUG, ELECTRICAL, MALE, 3 PIN, 32A | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 13 | EA | 1 | 11.07 | 11.07 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 18 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 |  | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 6145-60-V00-0163 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORE, 4 MM² |  | 2023-12-30 |  |  |  | RO | 3 | [17 empty] | As per the BOM this items are not required | BU | BU table | December | 2023
35 | 2023-12-30 |  | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V01-0053 | RACEWAY, METALLIC, (CABLE TRUNKING), GALVANIZED STEEL, 3 X 3 INCHES X 10 FEET |  | 2023-12-30 |  |  |  | EA | 30 | [17 empty] | As per the BOM this items are not required | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0504 | UNION, ELECTRICAL CONDUIT, NYLON POLYAMIDE, LONG THREAD, 5-10 MM | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 12 | EA | 4 | 3.26 | 13.04 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 17 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 4.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 6145-60-V00-0038 | CABLE, POWER, ELECTRICAL, CU/PVC/PVC, WHITE, 3 CORE, 6 MM² | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 11 | MR | 80 | 8.47 | 677.6 | 20300 | SENT | 2024-02-15 | 2024-01-14 | KW1-14272 | 11 | 2024-01-18 | APPR | 2024-01-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-23 | 80.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5935-60-V00-0169 | CONNECTOR, WIRE, ORANGE, 18-14 AWG | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 13 | PG | 2 | 25.3 | 50.6 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 32 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 |  | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5305-60-V00-0148 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES |  | 2023-12-30 |  |  |  | BX | 1 | [17 empty] | As per the BOM this items are not required | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 12 | RO | 1 | 92 | 92 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 31 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-17 | 1.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 |  | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5305-60-V00-0205 | SCREW, PHILLIPS, FLAT HEAD, STEEL, #8 X 1 INCH |  | 2023-12-30 |  |  |  | BX | 1 | [17 empty] | As per the BOM this items are not required | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5970-60-V00-0040 | TAPE, INSULATION, RED, 3/4 INCH X 25 METER | 50934 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | RO | 1 | 19 | 38 | 20305 | INPRG | 2024-02-03 |  | KW1-14209 | 6 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 2 | RO | 1 | 16.83 | 33.66 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 22 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 |  | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-00-178-1217 | CONDUIT, METAL, RIGID, STEEL, 3/4 INCH X 10 FEET |  | 2023-12-30 |  |  |  | LG | 10 | [17 empty] | As per the BOM this items are not required | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0379 | CLAMP, ELECTRICAL, CONDUIT, 2 HOLE, GALVANIZED STEEL, 3/4 INCH | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 10 | EA | 15 | 2.6 | 39 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 16 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 15.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0017 | COUPLING, ELECTRICAL CONDUIT, ZINC PLATED STEEL, 3/4 INCH | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 9 | PG | 1 | 87.75 | 87.75 | 20300 | SENT | 2024-02-15 | 2024-01-14 | KW1-14272 | 10 | 2024-01-18 | APPR | 2024-01-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-23 | 1.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5925-60-V00-0145 | CIRCUIT BREAKER, MINIATURE, 1 POLE, 230VAC, 32A | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 11 | EA | 1 | 7.29 | 7.29 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 30 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 6145-60-V00-0143 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4 MM² | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 10 | RO | 3 | 90.56 | 271.68 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 29 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 3.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 6145-60-V00-0154 | WIRE, ELECTRICAL, BLACK, 1 CORE, 4 MM ² | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 8 | RO | 3 | 89.38 | 268.14 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 15 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-17 | 3.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 6145-60-V00-0159 | WIRE, ELECTRICAL, BLUE, 1 CORE, 4 MM ² | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 9 | RO | 3 | 90.56 | 271.68 | 20305 | INPRG | 2024-02-03 |  | KW1-14207 | 2 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-02-29 | COMP | 2024-01-16 | 3.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 6145-60-V00-0136 | WIRE, ELECTRICAL, RED, 1 CORE, 4 MM ² | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 8 | RO | 3 | 90.7 | 272.1 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 28 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 3.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 6145-60-V00-0157 | WIRE, ELECTRICAL, YELLOW, 1 CORE, 4MM ² | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 7 | MR | 270 | 1.4 | 378 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 27 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-20 | 270.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5935-60-V00-0167 | CONNECTOR, WIRE, RED, 18 -10 AWG | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 7 | PG | 3 | 25.07 | 75.21 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 14 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 3.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0528 | CONDUIT, RIGID, EMT, GALVANIZED STEEL, 1/2 INCH X 10 FEET | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 6 | EA | 35 | 24.3 | 850.5 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 26 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-17 | 35.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0197 | ELBOW, ELECTRICAL CONDUIT, ½ INCH | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 6 | EA | 6 | 12.54 | 75.24 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 13 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 6.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0487 | COUPLING, ELECTRICAL CONDUIT, w/ SCREW, ½ INCH | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 5 | EA | 50 | 4.23 | 211.5 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 12 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-10 | COMP | 2024-01-16 | 47.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0381 | CLAMP, ELECTRICAL, CONDUIT, 2 HOLE, STEEL, 1/2 INCH | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | EA | 50 | 3.91 | 195.5 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 9 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-17 | 11.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0026 | BOX CONNECTOR, ELECTRICAL, LIQUID-TIGHT, ZINC, 1/2 INCH | 50936 | 2023-12-30 | 2023-12-31 | CLOSE | 2 | BX | 2 | 115.5 | 231 | 20300 | SENT | 2024-02-15 | 2024-01-14 | KW1-14272 | 13 | 2024-01-18 | APPR | 2024-01-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-23 | 2.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0413 | ANCHOR, PLASTIC, BUTTERFLY, WHITE, 6MM | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 5 | BX | 1 | 33.7 | 33.7 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 25 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-20 | 1.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0284 | JUNCTION BOX, w/ KNOCKOUT, STEEL, 73 X 73 X 40 MM | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 4 | EA | 5 | 6.61 | 33.05 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 11 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 5.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0254 | COVER, JUNCTION BOX, BLANKING PLATE, STEEL, 1 GANG, GRAY, 79 X 79 X 42 MM | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 4 | EA | 5 | 6.27 | 31.35 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 24 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 5.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 3 | RO | 2 | 21.11 | 42.22 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 23 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 2 | RO | 1 | 16.83 | 33.66 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 22 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5970-60-V00-0040 | TAPE, INSULATION, RED, 3/4 INCH X 25 METER | 50934 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | RO | 1 | 19 | 38 | 20305 | INPRG | 2024-02-03 |  | KW1-14209 | 6 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 50933 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | BX | 2 | 29.27 | 58.54 | 20305 | INPRG | 2024-02-03 |  | KW1-14209 | 5 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 3 | EA | 4 | 3.42 | 13.68 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 10 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 4.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5305-60-V00-0150 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, TWIN FAST THREAD, #10 X 1-1/2 INCHES | 50936 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | BX | 1 | 27.85 | 27.85 | 20300 | SENT | 2024-02-15 | 2024-01-14 | KW1-14272 | 12 | 2024-01-18 | APPR | 2024-01-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-23 | 1.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-00-178-1217 | CONDUIT, METAL, RIGID, STEEL, 3/4 INCH X 10 FEET | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | EA | 2 | 13.6 | 27.2 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 21 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-17 | 2.00 |  | BU | BU table | December | 2023
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5935-60-V00-0154 | BOX CONNECTOR, ELECTRICAL, CONCRETE-TIGHT CONDUIT, STEEL, 3/4 INCH | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 2 | PG | 1 | 98.77 | 98.77 | 20748 | CLOSE | 2024-02-03 |  | KW1-14620 | 1 | 2024-02-03 | CLOSE | 2024-02-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 1.00 |  | BU | BU table | December | 2023
36 | 2023-12-30 | 40 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 5510-00-220-6242 | LUMBER, SOFTWOOD, DIMENSION, 4 X 2 INCHES X 10 FEET | 51196 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 4 | 21.65 | 86.6 | 20305 | INPRG | 2024-02-03 |  | KW1-14209 | 17 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 | COMP | 2024-01-16 | 4.00 |  | BU | BU table | December | 2023
36 | 2023-12-30 | 40 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 5530-60-V00-0011 | PLYWOOD, CONSTRUCTION, INTERIOR, 3/4 INCH X 8 X 4 FEET | 51198 | 2024-01-04 | 2024-01-06 | CLOSE | 2 | EA | 3 | 57.25 | 171.75 | 20263 | CLOSE | 2024-01-20 | 2024-01-15 | KW1-14320 | 6 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-03 07:00 | COMP | 2024-01-24 | 3.00 |  | BU | BU table | December | 2023
36 | 2023-12-30 | 40 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 9330-60-V00-0016 | SHEET, ACRYLIC, WHITE, 48 X 96 X 0.250 INCHES | 51195 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 1 | 183.15 | 183.15 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 48 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-17 | 1.00 |  | BU | BU table | December | 2023
36 | 2023-12-30 | 40 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 5305-60-V00-0149 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, TWIN FAST THREAD, #8 X 2-1/2 INCHES | 51197 | 2024-01-04 | 2024-01-06 | CLOSE | 2 | PG | 1 | 38.8 | 38.8 |  |  |  |  | KW1-14180 | 26 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 1.00 |  | BU | BU table | December | 2023
36 | 2023-12-30 | 40 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 8010-00-297-0584 | PAINT, ENAMEL, SEMIGLOSS, WHITE, 1 GL | 51199 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | GL | 1 | 41.53 | 41.53 | 20263 | CLOSE | 2024-01-20 | 2024-01-15 | KW1-14320 | 7 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-03 07:00 | COMP | 2024-01-28 | 1.00 |  | BU | BU table | December | 2023
36 | 2023-12-30 | 40 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 8020-00-205-6500 | BRUSH, PAINT, BRISTLES, CHISELED, 3 INCHES | 51197 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 4 | 21.9 | 87.6 |  |  |  |  | KW1-14173 | 70 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 4.00 |  | BU | BU table | December | 2023
36 | 2023-12-30 | 40 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 8010-60-V00-0003 | PRIMER COATING, WOOD, ALKYD, WHITE, 16 LITER | 51230 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | CN | 1 | 162.1 | 162.1 | 20302 | CLOSE | 2024-01-21 | 2024-01-14 | KW1-14335 | 3 | 2024-01-21 | APPR | 2024-01-21 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-11 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | December | 2023
36 | 2023-12-30 | 40 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GALLON | 51198 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | CN | 1 | 228.7 | 228.7 |  |  |  |  | KW1-14173 | 71 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-18 | 1.00 |  | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0966 | ELBOW, SEWER AND DRAIN FITTINGS, PVC, STANDARD, 87.5 °, SPIGOT X SOCKET, SCH- 40, GREY, 50 MM | 50320 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 4 | 10.81 | 43.24 | 20209 | CLOSE | 2024-01-25 | 2024-01-11 | KW1-14294 | 21 | 2024-01-19 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-27 | 4.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0335 | COUPLING, PIPE, w/ RUBBER SEAL, SOCKET X SOCKET, UPVC, GRAY, 50 MM | 50317 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 4 | 10.8 | 43.2 |  |  |  |  | KW1-14123 | 7 | 2024-01-09 | APPR | 2024-01-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-30 07:00 | COMP | 2024-01-14 | 4.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 9150-60-V00-0050 | LUBRICANT, PIPE JOINT, 32 FL OUNCES | 50312 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | CN | 1 | 21.98 | 21.98 | 20210 | SENT | 2024-01-09 |  | KW1-14124 | 13 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-25 | COMP | 2024-01-14 | 1.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 8030-00-889-3535 | TAPE, ANTISEIZING, POLYTETRAFLUOROETHYLENE, ½ X 260 INCHES | 50318 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 10 | 7 | 70 | 20209 | CLOSE | 2024-01-25 | 2024-01-11 | KW1-14294 | 18 | 2024-01-19 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-27 | 10.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 50315 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | BX | 6 | 143.19 | 859.14 | 20214 | CLOSE | 2024-01-09 |  | KW1-14130 | 6 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 6.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 8040-60-V00-0040 | CEMENT, HEAVY BODIED, CPVC, ORANGE, 16 OZ | 50315 | 2023-12-23 | 2023-12-23 | CLOSE | 2 | CN | 1 | 18.32 | 18.32 | 20214 | CLOSE | 2024-01-09 |  | KW1-14130 | 7 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4510-60-V00-0077 | DRAIN, SINK, STAINLESS STEEL | 50313 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 2 | 27.47 | 54.94 | 20223 | CLOSE | 2024-01-10 |  | KW1-14135 | 1 | 2024-01-10 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-02-29 | COMP | 2024-01-14 | 2.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 7105-60-V00-0019 | MIRROR, GLASS, ROUND, WALL MOUNTED, WHITE, 50 CM | 50318 | 2023-12-23 | 2023-12-23 | CLOSE | 2 | EA | 2 | 21 | 42 | 20209 | CLOSE | 2024-01-25 | 2024-01-11 | KW1-14294 | 19 | 2024-01-19 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-27 | 2.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4820-60-V00-0127 | VALVE, BALL, THREADED, w/ HANDLE, BRASS, PN32, 3/4 INCH | 50316 | 2023-12-23 | 2023-12-23 | CLOSE | 2 | EA | 4 | 18.32 | 73.28 |  |  |  |  | KW1-14053 | 2 | 2024-01-04 | APPR | 2024-01-04 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-18 07:00 | COMP | 2024-01-10 | 4.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0940 | TEE, PIPE, SOCKET X SOCKET X SOCKET, CPVC, OFF-WHITE, SCH 40, 25 MM | 50527 | 2023-12-23 | 2023-12-25 | CLOSE | 1 | EA | 6 | 7.26 | 43.56 |  |  |  |  | KW1-14180 | 4 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 6.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0754 | ADAPTER, PRESSURE FITTINGS, MALE, CPVC, STANDARD, SOCKET X MIPT, PN16, OFF-WHITE, 25 MM | 50316 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 10 | 3.33 | 33.3 |  |  |  |  | KW1-14053 | 1 | 2024-01-04 | APPR | 2024-01-04 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-18 07:00 | COMP | 2024-01-10 | 10.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0448 | ELBOW, PIPE, SOCKET X SPIGOT, 45°, UPVC, GRAY, 50MM | 50314 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 8 | 13.99 | 111.92 | 20210 | SENT | 2024-01-09 |  | KW1-14124 | 14 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-23 | COMP | 2024-01-14 | 8.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0930 | TEE, PIPE, SOCKET X SOCKET X SOCKET, PVC, GRAY, SCH 40, 50 MM | 50317 | 2023-12-23 | 2023-12-23 | CLOSE | 2 | EA | 2 | 17.17 | 34.34 |  |  |  |  | KW1-14123 | 8 | 2024-01-09 | APPR | 2024-01-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-30 07:00 | COMP | 2024-01-14 | 2.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0734 | WYE, TRUE, PIPE, BRANCH, UPVC, 45 DEG, 50 MM | 50319 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 4 | 12.15 | 48.6 | 20209 | CLOSE | 2024-01-25 | 2024-01-11 | KW1-14294 | 20 | 2024-01-19 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-27 | 4.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0863 | ELBOW, PRESSURE FITTINGS, CPVC, BRASS, REDUCTION, 90 °, SOCKET X FIPT, SCH- 40, OFF-WHITE, 25 x 20 MM | 50317 | 2023-12-23 | 2023-12-23 | CLOSE | 3 | EA | 6 | 14.8 | 88.8 |  |  |  |  | KW1-14123 | 9 | 2024-01-09 | APPR | 2024-01-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-30 07:00 | COMP | 2024-01-14 | 6.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0927 | TEE, PIPE, SOCKET X SOCKET X FIPT, SCH-80, CPVC, OFF-WHITE, 25 MM X 1/2 INCH | 50317 | 2023-12-23 | 2023-12-23 | CLOSE | 4 | EA | 4 | 17 | 68 |  |  |  |  | KW1-14123 | 10 | 2024-01-09 | APPR | 2024-01-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-30 07:00 | COMP | 2024-01-14 | 4.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0834 | COUPLING, CPVC, SCH-40, TAN, 25 MM | 50316 | 2023-12-23 | 2023-12-23 | CLOSE | 3 | EA | 4 | 5.16 | 20.64 |  |  |  |  | KW1-14053 | 3 | 2024-01-04 | APPR | 2024-01-04 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-18 07:00 | COMP | 2024-01-10 | 4.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4720-60-V00-0268 | HOSE, METALLIC, FLEXIBLE, SINGLE NUT, STAINLESS STEEL BRAIDED, 1/2 X 1-1/2 FEET | 50316 | 2023-12-23 | 2023-12-23 | CLOSE | 4 | EA | 4 | 11.99 | 47.96 |  |  |  |  | KW1-14053 | 4 | 2024-01-04 | APPR | 2024-01-04 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-18 07:00 | COMP | 2024-01-10 | 4.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4820-60-V00-0227 | VALVE, ANGLE, 1/2 X 1/2 INCHES | 50316 | 2023-12-23 | 2023-12-23 | CLOSE | 5 | EA | 4 | 17.65 | 70.6 |  |  |  |  | KW1-14053 | 5 | 2024-01-04 | APPR | 2024-01-04 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-18 07:00 | COMP | 2024-01-10 | 4.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4510-60-V00-0096 | TRAP, BOTTLE, ADJUSTABLE INLET, w/FLEXIBLE HOSE, 1-1/2 INCHES | 50313 | 2023-12-23 | 2023-12-23 | CLOSE | 2 | EA | 2 | 21.31 | 42.62 | 20214 | CLOSE | 2024-01-09 |  | KW1-14130 | 8 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 2.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4510-60-V00-0124 | FAUCET, LEVER, SINGLE, CHROME, BRASS, WASH BASIN MIXER | 50317 | 2023-12-23 | 2023-12-23 | CLOSE | 5 | EA | 2 | 65.63 | 131.26 |  |  |  |  | KW1-14121 | 41 | 2024-01-09 | APPR | 2024-01-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-16 07:00 | COMP | 2024-01-14 | 2.00 | O&M Order | BU | BU table | December | 2023
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4510-60-V00-0071 | BASIN, WASH, CERAMIC, OVAL, WHITE, 570 X 490 MM | 50311 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 2 | 241.43 | 482.86 | 20210 | SENT | 2024-01-09 |  | KW1-14124 | 12 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-25 | COMP | 2024-01-18 | 2.00 | O&M Order | BU | BU table | December | 2023
37 | 2023-12-30 | 30 | BU24-0112 | Install Bollards Ring 4 | 8920496 | 4240-60-V00-0132 | BOLLARD, SAFETY, PROTECTIVE, STEEL, BLACK/YELLOW, 100 X 1450 MM | 50950 | 2023-12-31 | 2024-01-02 | CLOSE | 1 | EA | 24 | 366.3 | 8791.2 | 20132 | CLOSE | 2024-01-10 | 2024-01-06 | KW1-14163 | 15 | 2024-01-10 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-07 | COMP | 2024-01-16 | 3.00 | Pending Remaining items | BU | BU table | December | 2023
37 | 2023-12-30 | 30 | BU24-0112 | Install Bollards Ring 4 | 8920496 | 5610-60-V00-0010 | GATCH AND GRAVEL, MIXED, CUBIC METER | 50951 | 2023-12-31 | 2023-12-31 | CLOSE | 1 | CZ | 1 | 58.28 | 58.28 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 60 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-21 | 1.00 |  | BU | BU table | December | 2023
37 | 2023-12-30 | 30 | BU24-0112 | Install Bollards Ring 4 | 8920496 | 9905-01-282-2285 | TAPE, FLAGGING, CAUTION DO NOT ENTER, POLYETHYLENE, BLACK ON YELLOW, 3 INCHES X 200 FEET | 50952 | 2023-12-31 | 2023-12-31 | CLOSE | 1 | RO | 1 | 90.91 | 90.91 | 20301 | CLOSE | 2024-01-18 | 2024-01-14 | KW1-14277 | 2 | 2024-01-18 | APPR | 2024-01-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-23 | 1.00 |  | BU | BU table | December | 2023
38 | 2023-12-30 | 30 | BU24-0018 | Install Generator Z2 PWD Yard - C to TDP | 8894903 | 6115-60-V00-0039 | GENERATOR SET, DIESEL ENGINE, 1500 RPM, 400V, 3PH, 50HZ, 135KVA | 51194 | 2024-01-04 | 2024-01-07 | CLOSE | 1 | EA | 1 | 28591.5 | 28591.5 | 20273 | CLOSE | 2024-01-15 | 2024-01-14 | KW1-14241 | 1 | 2024-01-16 | APPR | 2024-01-16 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 |  |  |  | ON-HOLD | BU | BU table | December | 2023
38 | 2023-12-30 | 30 | BU24-0018 | Install Generator Z2 PWD Yard - C to TDP | 8894903 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 51193 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 2 | 302.94 | 605.88 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 47 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023
38 | 2023-12-30 | 30 | BU24-0018 | Install Generator Z2 PWD Yard - C to TDP | 8894903 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM ² | 51192 | 2024-01-04 | 2024-01-06 | CLOSE | 2 | RL | 1 | 244.76 | 244.76 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 46 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023
38 | 2023-12-30 | 30 | BU24-0018 | Install Generator Z2 PWD Yard - C to TDP | 8894903 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 51192 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 2 | 61.27 | 122.54 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 45 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 5305-60-V00-0170 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATE, # 8 X 3 INCHES | 51120 | 2024-01-03 | 2024-01-04 | CLOSE | 5 | BX | 7 | 35 | 245 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 80 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 7.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 51120 | 2024-01-03 | 2024-01-04 | CLOSE | 4 | BX | 7 | 19.6 | 137.2 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 79 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 7.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 5510-60-V00-0003 | LUMBER, SOFTWOOD, DIMENSION, 2 X 4 INCHES X 13 FEET | 51114 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | EA | 10 | 29.97 | 299.7 |  |  |  |  | KW1-14180 | 23 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 10.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 5510-60-V00-0024 | LUMBER, SOFTWOOD, 2 X 2 INCHES X 14 FEET | 51112 | 2024-01-03 | 2024-01-04 | CLOSE | 3 | EA | 10 | 27.47 | 274.7 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 71 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 10.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8010-60-V00-0028 | PAINT, ENAMEL, GLOSS, DESERT SAND, 3.6 LITER | 51118 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | CN | 34 | 39.6 | 1346.4 | 20136 | CLOSE | 2024-01-04 |  | KW1-14058 | 1 | 2024-01-04 | APPR | 2024-01-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-09 | 34.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8105-01-517-1363 | BAG, PLASTIC, CLEAR, 24 X 24 INCHES, 10 GALLONS | 51119 | 2024-01-03 | 2024-01-04 | CLOSE | 3 | BX | 1 | 91.1 | 91.1 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 75 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 1.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8340-00-068-7908 | DROP CLOTH, PAINTER'S, 9 FT X 12 FT | 51115 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | EA | 4 | 28.97 | 115.88 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 72 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 4.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 51116 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | BX | 4 | 19.65 | 78.6 |  |  |  |  | KW1-14179 | 5 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-01-25 07:00 | COMP | 2024-01-15 | 4.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8020-00-245-4519 | BRUSH, PAINT, BRISTLES, FLAT, 4 INCHES | 51117 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | EA | 8 | 16.48 | 131.84 |  |  |  |  | KW1-14173 | 59 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 8.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 51119 | 2024-01-03 | 2024-01-04 | CLOSE | 2 | EA | 6 | 14.6 | 87.6 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 74 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 6.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 51121 | 2024-01-03 | 2024-01-04 | CLOSE | 3 | EA | 8 | 12.4 | 99.2 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 42 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 8.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 51121 | 2024-01-03 | 2024-01-04 | CLOSE | 2 | EA | 4 | 13.9 | 55.6 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 41 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 4.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 5350-60-V00-0004 | PAPER, ABRASIVE (SANDPAPER), 80 GRIT, 9 X 11 INCHES | 51120 | 2024-01-03 | 2024-01-04 | CLOSE | 3 | PK | 5 | 34.2 | 171 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 78 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 5.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 5350-60-V00-0011 | PAPER, ABRASIVE (SANDPAPER), 220 GRIT, 9 X 11 INCHES | 51113 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | SH | 40 | 3.33 | 133.2 |  |  |  |  | KW1-14180 | 22 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 40.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8010-60-V00-0089 | PRIMER, COATING, WHITE, 4 - 5 LITERS | 51114 | 2024-01-03 | 2024-01-04 | CLOSE | 2 | CN | 12 | 41.63 | 499.56 |  |  |  |  | KW1-14173 | 58 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 12.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 51121 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | EA | 10 | 29 | 290 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 40 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 10.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 5530-00-618-8073 | PLYWOOD, MAPLE, PUREBOND, 3/4 IN x 4 FT x 8 FT | 51120 | 2024-01-03 | 2024-01-04 | CLOSE | 2 | EA | 11 | 47 | 517 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 77 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 11.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 5510-60-V00-0011 | LUMBER, HEAT TREATED, IPPC, 4 X 4 INCHES X 16 FEET | 51120 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | EA | 14 | 56.9 | 796.6 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 76 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-23 | 14.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 6350-60-V00-0102 | ALARM, SMOKE, AUTOMATIC, PLASTIC | 51112 | 2024-01-03 | 2024-01-04 | CLOSE | 2 | EA | 6 | 28.97 | 173.82 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 70 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 6.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 4210-60-V00-0189 | EXTINGUISHER, FIRE, DRY CHEMICAL, w/ BRASS VALVE, 10 LBS | 51119 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | EA | 4 | 244.8 | 979.2 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 73 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-11 | COMP | 2024-01-20 | 4.00 |  | BU | BU table | January | 2024
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 6210-60-V00-0112 | LIGHT UNIT, EMERGENCY, 230/240V AC, 50/60 HZ, 8W | 51112 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | EA | 4 | 94.74 | 378.96 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 69 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 4.00 |  | BU | BU table | January | 2024
40 | 2024-01-03 | 30 | BU24-0103 | Fence Repair | 8873806 | 5660-60-V00-0074 | FENCE, CHAIN LINK, GALVANIZED STEEL, GREEN, 8 X 50 FEET | 51336 | 2024-01-06 | 2024-01-07 | CLOSE | 1 | RO | 10 | 249.52 | 2495.2 | 20195 | CLOSE | 2024-01-07 |  | KW1-14089 | 1 | 2024-01-07 | APPR | 2024-01-07 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-25 | COMP | 2024-01-14 | 10.00 |  | BU | BU table | January | 2024
40 | 2024-01-03 | 30 | BU24-0103 | Fence Repair | 8873806 | 5660-60-V00-0044 | FENCING, WIRE, (TENSION WIRE), PVC, GREEN, 16 GAGE, 100 METERS | 51337 | 2024-01-06 | 2024-01-07 | CLOSE | 1 | RO | 5 | 58.9 | 294.5 | 20305 | INPRG | 2024-02-03 |  | KW1-14209 | 19 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 | COMP | 2024-01-16 | 5.00 |  | BU | BU table | January | 2024
40 | 2024-01-03 | 30 | BU24-0103 | Fence Repair | 8873806 | 5660-60-V00-0046 | FENCING, WIRE, PVC COATED, GREEN, 2.5 MM | 51338 | 2024-01-06 | 2024-01-07 | CLOSE | 1 | RO | 7 | 44.55 | 311.85 | 20302 | CLOSE | 2024-01-21 | 2024-01-14 | KW1-14335 | 9 | 2024-01-21 | APPR | 2024-01-21 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-04 | COMP | 2024-01-24 | 7.00 |  | BU | BU table | January | 2024
40 | 2024-01-03 | 30 | BU24-0103 | Fence Repair | 8873806 | 5110-60-V00-0138 | CUTTER, BOLT, COMPACT, STEEL, 8 INCHES | 51339 | 2024-01-06 | 2024-01-07 | CLOSE | 3 | EA | 5 | 42.5 | 212.5 | 20263 | CLOSE | 2024-01-20 | 2024-01-15 | KW1-14320 | 11 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-19 | 5.00 |  | BU | BU table | January | 2024
40 | 2024-01-03 | 30 | BU24-0103 | Fence Repair | 8873806 | 5120-60-V00-0504 | PULLER, FENCE, STANDARD, TYPE A, ALLOY STEEL, 3.5 X 48 INCHES | 51339 | 2024-01-06 | 2024-01-07 | CLOSE | 2 | EA | 6 | 136.17 | 817.02 | 20263 | CLOSE | 2024-01-20 | 2024-01-15 | KW1-14320 | 10 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 |  |  |  |  | BU | BU table | January | 2024
40 | 2024-01-03 | 30 | BU24-0103 | Fence Repair | 8873806 | 5120-60-V00-0505 | PULLER, FENCE, REVERSED, TYPE A, ALLOY STEEL, 3.5 X 48 INCHES | 51339 | 2024-01-06 | 2024-01-07 | CLOSE | 1 | EA | 6 | 140.51 | 843.06 | 20263 | CLOSE | 2024-01-20 | 2024-01-15 | KW1-14320 | 9 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-12 | 6.00 |  | BU | BU table | January | 2024
40 | 2024-01-03 |  | BU24-0103 | Fence Repair | 8873806 | 5660-60-V00-0072 | TENSION BAND, CHAIN LINK FENCE, FLAT, GALVANIZED METAL, 1-5/8 INCH | [5 empty] | EA | 500 | [17 empty] | Not required | BU | BU table | January | 2024
40 | 2024-01-03 | 40 | BU24-0103 | Fence Repair | 8873806 | 3950-60-V00-0033 | WINCH, WIRE ROPE (CABLE PULLER), HAND OPERATED, ALUMINIUM, 1600 KG | 51340 | 2024-01-06 | 2024-01-07 | CLOSE | 1 | EA | 2 | 531.81 | 1063.62 | 20263 | CLOSE | 2024-01-20 | 2024-01-15 | KW1-14320 | 12 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-05 | 2.00 |  | BU | BU table | January | 2024
40 | 2024-01-03 |  | BU24-0103 | Fence Repair | 8873806 | To be fabricated by welding | Pipe&Hook | [5 empty] | EA | 1 | [17 empty] | AJ Team will Fabricate | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 6145-60-V00-0112 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 95 MM² | 51161 | 2024-01-04 | 2024-01-04 | CLOSE | 8 | MR | 140 | 85.91 | 12027.4 | 20139 | CLOSE | 2024-01-08 | 2024-01-07 | KW1-14096 | 8 | 2024-01-08 | APPR | 2024-01-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-13 | 140.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5940-60-V00-0025 | TERMINAL, LUG, TIN-PLATED, M12, 95MM², 3 X 24.5 X 60.5 INCHES | 51161 | 2024-01-04 | 2024-01-04 | CLOSE | 7 | EA | 8 | 28.84 | 230.72 | 20139 | CLOSE | 2024-01-08 | 2024-01-07 | KW1-14096 | 7 | 2024-01-08 | APPR | 2024-01-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-11 | 8.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5975-60-V00-0515 | STUFFING TUBE (CABLE GLAND), BRASS, BW, 50 MM | 51161 | 2024-01-04 | 2024-01-04 | CLOSE | 6 | EA | 2 | 29.8 | 59.6 | 20139 | CLOSE | 2024-01-08 | 2024-01-07 | KW1-14096 | 6 | 2024-01-08 | APPR | 2024-01-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-11 | 2.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5975-00-074-2072 | STRAP, TIEDOWN, ELECTRICAL COMPONENT, PLASTIC, NATURAL, 6-3/10 INCHES | 51167 | 2024-01-04 | 2024-01-07 | CLOSE | 7 | HD | 2 | 16.83 | 33.66 |  |  |  |  | KW1-14173 | 69 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5975-01-223-8533 | STRAP, TIE DOWN, ELECTRICAL COMPONENTS, PLASTIC POLYAMIDE, 0.1 X 8 INCHES | 51161 | 2024-01-04 | 2024-01-04 | CLOSE | 5 | PG | 2 | 67.1 | 134.2 | 20139 | CLOSE | 2024-01-08 | 2024-01-07 | KW1-14096 | 5 | 2024-01-08 | APPR | 2024-01-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-11 | 2.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 4240-60-V00-0122 | TAPE, WARNING, CAUTION BURIED ELECTRICAL CABLE BELOW, YELLOW 6 INCHES X 1000 FEET | 51161 | 2024-01-04 | 2024-01-04 | CLOSE | 4 | RL | 1 | 176.82 | 176.82 | 20139 | CLOSE | 2024-01-08 | 2024-01-07 | KW1-14096 | 4 | 2024-01-08 | APPR | 2024-01-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-13 | 1.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5940-60-V00-0085 | LUG, TERMINAL, ROUND TYPE, COPPER, ONE-HOLE, 50 MM² X 6MM | 51161 | 2024-01-04 | 2024-01-04 | CLOSE | 1 | PG | 1 | 249.75 | 249.75 | 20139 | CLOSE | 2024-01-08 | 2024-01-07 | KW1-14096 | 1 | 2024-01-08 | APPR | 2024-01-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-11 | 1.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 6145-60-V00-0047 | WIRE, ELECTRICAL, GREEN/YELLOW, 1 CORE, 50MM ² | 51167 | 2024-01-04 | 2024-01-07 | CLOSE | 6 | MR | 130 | 10.3 | 1339 |  |  |  |  | KW1-14173 | 68 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 130.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5970-01-174-5651 | TAPE, INSULATION, ELECTRICAL, YELLOW, 3/4 X 792 INCHES | 51167 | 2024-01-04 | 2024-01-07 | CLOSE | 5 | EA | 1 | 10.1 | 10.1 |  |  |  |  | KW1-14173 | 67 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5970-01-015-5060 | TAPE, INSULATION, ELECTRICAL, BLUE, 3/4 X 792 INCHES | 51167 | 2024-01-04 | 2024-01-07 | CLOSE | 4 | RO | 1 | 10.1 | 10.1 |  |  |  |  | KW1-14173 | 66 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5970-01-013-9369 | TAPE, INSULATION, ELECTRICAL, RED, 3/4 X 792 INCHES | 51167 | 2024-01-04 | 2024-01-07 | CLOSE | 3 | RO | 1 | 10.1 | 10.1 |  |  |  |  | KW1-14173 | 65 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5970-01-013-9368 | TAPE, INSULATION, ELECTRICAL, GREEN, 3/4 X 792 INCHES | 51167 | 2024-01-04 | 2024-01-07 | CLOSE | 2 | RO | 1 | 16.83 | 16.83 |  |  |  |  | KW1-14173 | 64 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 51167 | 2024-01-04 | 2024-01-07 | CLOSE | 1 | RO | 1 | 21.11 | 21.11 |  |  |  |  | KW1-14173 | 63 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5610-60-V00-0014 | SAND | 51163 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | TN | 40 | 34.13 | 1365.2 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 86 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-21 | 40.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5610-60-V00-0010 | GATCH AND GRAVEL, MIXED, CUBIC METER | 51231 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | CZ | 2 | 56.1 | 112.2 | 20302 | CLOSE | 2024-01-21 | 2024-01-14 | KW1-14335 | 4 | 2024-01-21 | APPR | 2024-01-21 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-04 | COMP | 2024-02-05 | 2.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5610-60-V00-0018 | CONCRETE MIX, GRAY, 4000 PSI, 80 LBS | 51165 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 30 | 42.5 | 1275 |  |  |  |  | KW1-14180 | 24 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 30.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 9510-60-V00-0013 | BAR, STEEL, REBAR, ROUND, 12 MM X 9 METER | 51164 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 8 | 33.3 | 266.4 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 87 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 8.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5660-60-V00-0045 | WIRE, STEEL, GALVANIZED, 28 GAGE, 100 FEET | 51162 | 2024-01-04 | 2024-01-06 | CLOSE | 3 | RO | 2 | 58.28 | 116.56 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 85 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 2.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 8135-60-V00-0003 | PLASTIC SHEET, POLYETHYLENE, CLEAR, 6 MIL, 32 X 100 FEET | 51162 | 2024-01-04 | 2024-01-06 | CLOSE | 2 | RO | 1 | 442.89 | 442.89 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 84 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 1.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 8030-60-V00-0005 | SEALING COMPOUND, TWO PART POLYSULPHIDE, GREY, 2 LITRES | 51161 | 2024-01-04 | 2024-01-04 | CLOSE | 3 | PG | 1 | 149.85 | 149.85 | 20139 | CLOSE | 2024-01-08 | 2024-01-07 | KW1-14096 | 3 | 2024-01-08 | APPR | 2024-01-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-12 | 1.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5620-60-V00-0012 | CONCRETE SPACER (COVER BLOCK), w/TIE-WIRE ATTACHMENT HOLE, 65/75 MM | 51161 | 2024-01-04 | 2024-01-04 | CLOSE | 2 | PG | 1 | 41.63 | 41.63 | 20139 | CLOSE | 2024-01-08 | 2024-01-07 | KW1-14096 | 2 | 2024-01-08 | APPR | 2024-01-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-13 | 1.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5640-60-V00-0026 | BACKER ROD, GAPS, CLOSED-CELL POLYETHYLENE, 3/8 INCH X 20 FEET | 51162 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 2 | 18.32 | 36.64 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 83 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 2.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 8430-60-V00-0001 | BOOTS, SLIP-ON, RUBBER, ROUND TOE, #10.5 | 51168 | 2024-01-04 | 2024-01-06 | CLOSE | 3 | PR | 2 | 38.61 | 77.22 | 20263 | CLOSE | 2024-01-20 | 2024-01-15 | KW1-14320 | 5 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-15 | 2.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5120-01-604-5657 | GLOVES, WELDING | 51166 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 4 | 60.6 | 242.4 |  |  |  |  | KW1-14180 | 25 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 4.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5180-60-V00-0030 | TOOL KIT, MASON AND CONCRETE FINISHER'S, 7 COMPONENETS | 51168 | 2024-01-04 | 2024-01-06 | CLOSE | 2 | KT | 2 | 213.7 | 427.4 | 20263 | CLOSE | 2024-01-20 | 2024-01-15 | KW1-14320 | 4 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-05 | 1.00 |  | BU | BU table | January | 2024
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 3895-60-V00-0012 | BOARD, BITUMEN, 2400 X 75 X 9.5MM | 51168 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 2 | 179.37 | 358.74 | 20263 | CLOSE | 2024-01-20 | 2024-01-15 | KW1-14320 | 3 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-17 07:00 | COMP | 2024-01-24 | 2.00 |  | BU | BU table | January | 2024
42 | 2024-01-06 | 30 | BU24-0081 | Replace Sandbags Bunkers Z5 BA2 | 8417604 | 5110-00-892-5071 | KNIFE, CRAFTSMAN'S, RETRACTABLE BLADE | 51318 | 2024-01-06 | 2024-01-07 | CLOSE | 1 | EA | 5 | 19.3 | 96.5 | 20305 | INPRG | 2024-02-03 |  | KW1-14209 | 18 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 | COMP | 2024-01-16 | 5.00 |  | BU | BU table | January | 2024
42 | 2024-01-06 | 30 | BU24-0081 | Replace Sandbags Bunkers Z5 BA2 | 8417604 | 8105-01-331-3704 | BAG, SAND, TAN, PROTECTIVE, 26 INCHES | 51317 | 2024-01-06 | 2024-01-07 | CLOSE | 1 | HD | 110 | 699.3 | 76923 | 20190 | CLOSE | 2024-01-11 | 2024-01-08 | KW1-14171 | 1 | 2024-01-11 | APPR | 2024-01-11 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-02-22 | COMP | 2024-01-15 | 40.00 |  | BU | BU table | January | 2024
43 | 2024-01-07 | 30 | BU24-0015 | Replace Generator Z2 Bldg. 209 -C To TDP | 8944274 | 6115-60-V00-0040 | GENERATOR SET, DIESEL ENGINE, 3-PHASE, 400V, 50HZ, 1500 RPM, 330 KVA/264 KWE | 51875 | 2024-01-16 | 2024-01-27 | CLOSE | 2 | EA | 1 | 57539.38 | 57539.38 | 20594 | CLOSE | 2024-02-11 | 2024-01-30 | KW1-14808 | 2 | 2024-02-11 | APPR | 2024-02-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-28 |  |  |  |  | BU | BU table | January | 2024
43 | 2024-01-07 | 30 | BU24-0015 | Replace Generator Z2 Bldg. 209 -C To TDP | 8944274 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 51874 | 2024-01-16 | 2024-01-18 | CLOSE | 3 | EA | 4 | 348.15 | 1392.6 | 20446 | CLOSE | 2024-01-22 | 2024-01-22 | KW1-14376 | 8 | 2024-01-22 | APPR | 2024-01-28 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-05 | COMP | 2024-01-31 | 4.00 |  | BU | BU table | January | 2024
43 | 2024-01-07 | 30 | BU24-0015 | Replace Generator Z2 Bldg. 209 -C To TDP | 8944274 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM ² | 51874 | 2024-01-16 | 2024-01-18 | CLOSE | 2 | RL | 1 | 304.2 | 304.2 | 20446 | CLOSE | 2024-01-22 | 2024-01-22 | KW1-14376 | 7 | 2024-01-22 | APPR | 2024-01-28 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-05 | COMP | 2024-01-31 | 1.00 |  | BU | BU table | January | 2024
43 | 2024-01-07 | 30 | BU24-0015 | Replace Generator Z2 Bldg. 209 -C To TDP | 8944274 | 5975-60-V00-0418 | LUGS, CABLE, TUBE TERMINALS, COPPER, 16 X 8 MILLIMETERS | 51875 | 2024-01-16 | 2024-01-27 | CLOSE | 1 | EA | 4 | 1.05 | 4.2 | 20594 | CLOSE | 2024-02-11 | 2024-01-30 | KW1-14808 | 1 | 2024-02-11 | APPR | 2024-02-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 | COMP | 2024-02-14 | 4.00 |  | BU | BU table | January | 2024
43 | 2024-01-07 | 30 | BU24-0015 | Replace Generator Z2 Bldg. 209 -C To TDP | 8944274 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 51874 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | EA | 4 | 60.72 | 242.88 | 20446 | CLOSE | 2024-01-22 | 2024-01-22 | KW1-14376 | 6 | 2024-01-22 | APPR | 2024-01-28 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-05 | COMP | 2024-01-31 | 4.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5307-60-V00-0021 | STUD, DRYWALL FRAME, U-CHANNEL, GALVANIZED STEEL, 3 X 1-1/4 INCHES X 12 FEET | 51540 | 2024-01-10 | 2024-01-10 | CLOSE | 4 | EA | 200 | 6.34 | 1268 | 20372 | CLOSE | 2024-01-25 | 2024-01-20 | KW1-14437 | 13 | 2024-01-25 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-08 07:00 | COMP | 2024-02-01 | 200.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5650-60-V01-0003 | C-STUD RUNNER, GALVANIZED STEEL, 0.0366 X 1 1/4 X 3 INCHES X 12 FEET | 51540 | 2024-01-10 | 2024-01-10 | CLOSE | 3 | EA | 40 | 6.18 | 247.2 | 20372 | CLOSE | 2024-01-25 | 2024-01-20 | KW1-14437 | 12 | 2024-01-25 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-08 07:00 | COMP | 2024-02-01 | 40.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 40 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5305-05-V00-0025 | SCREW, PHILLIPS, TRUSS HEAD, STAINLESS STEEL, 10 X 3/4 INCHES 100pc / bx | 51576 | 2024-01-10 | 2024-01-13 | CLOSE | 2 | PG | 25 | 12.99 | 324.75 | 20372 | CLOSE | 2024-01-25 | 2024-01-20 | KW1-14437 | 15 | 2024-01-25 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-01 07:00 | COMP | 2024-01-30 | 25.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5305-60-V00-0022 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #10, 1-1/2 INCHES | 51530 | 2024-01-10 | 2024-01-10 | CLOSE | 2 | PG | 6 | 48.12 | 288.72 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 53 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-23 | 6.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 9520-60-V00-0044 | L CHANNEL GALVANIZE 3MM X 1 1/2" X 12' | 51540 | 2024-01-10 | 2024-01-10 | CLOSE | 2 | EA | 8 | 117 | 936 | 20372 | CLOSE | 2024-01-25 | 2024-01-20 | KW1-14437 | 11 | 2024-01-25 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-01 07:00 | COMP | 2024-01-30 | 8.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5640-60-V00-0048 | DRYWALL SHEET, (GYPSUM BOARD), 4 X 8 FEET X 1/2 INCH | 51533 | 2024-01-10 | 2024-01-10 | CLOSE | 2 | EA | 80 | 19.31 | 1544.8 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 57 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-23 | 80.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5305-60-V00-0157 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, COARSE THREAD, #7 X 1-3/8 INCHES 1000pc/box | 51536 | 2024-01-10 | 2024-01-13 | CLOSE | 8 | BX | 5 | 23.31 | 116.55 | 20370 | CLOSE | 2024-01-20 | 2024-01-18 | KW1-14329 | 44 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-27 | COMP | 2024-01-25 | 5.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5640-60-V00-0044 | TAPE, SELF ADHESIVE, DRYWALL JOINT, FIBERGLASS, 2 INCHES X 300 FEET | 51539 | 2024-01-10 | 2024-01-10 | CLOSE | 5 | EA | 2 | 18.5 | 37 | 20318 | CLOSE | 2024-01-22 | 2024-01-15 | KW1-14372 | 14 | 2024-01-22 | APPR | 2024-01-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-10 | COMP | 2024-01-27 | 2.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 51533 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | CN | 4 | 37.3 | 149.2 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 56 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-23 | 4.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 7510-00-680-2395 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 51536 | 2024-01-10 | 2024-01-13 | CLOSE | 7 | RO | 2 | 12.99 | 25.98 | 20370 | CLOSE | 2024-01-20 | 2024-01-18 | KW1-14329 | 43 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-27 | COMP | 2024-01-25 | 2.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5130-60-V00-0125 | DISK, ABRASIVE, SANDING, HOOK AND LOOP, 220 GRIT, 8 HOLE, 5 INCHES-DUSTLESS HOOK AND LOOP SANDING DISC | 51536 | 2024-01-10 | 2024-01-13 | CLOSE | 6 | PG | 3 | 49.28 | 147.84 | 20370 | CLOSE | 2024-01-20 | 2024-01-18 | KW1-14329 | 42 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-27 | COMP | 2024-01-25 | 3.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5680-60-V01-0002 | CORNER BEAD, STAINLESS STEEL, 25 MM X2.5 METER | 51536 | 2024-01-10 | 2024-01-13 | CLOSE | 5 | EA | 10 | 109.89 | 1098.9 | 20370 | CLOSE | 2024-01-20 | 2024-01-18 | KW1-14329 | 41 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-15 | COMP | 2024-02-05 | 10.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5350-60-V00-0007 | PAPER, ABRASIVE (SANDPAPER), 120 GRIT, 9 X 11 INCHES | 51536 | 2024-01-10 | 2024-01-13 | CLOSE | 4 | EA | 20 | 4.33 | 86.6 | 20370 | CLOSE | 2024-01-20 | 2024-01-18 | KW1-14329 | 40 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-27 | COMP | 2024-01-25 | 20.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 40 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8010-60-V00-0241 | PRIMER, PAINT, LATEX, INTERIOR, WATERBASED, WHITE, 5 GALLON | 51576 | 2024-01-10 | 2024-01-13 | CLOSE | 1 | CN | 2 | 55.08 | 110.16 | 20372 | CLOSE | 2024-01-25 | 2024-01-20 | KW1-14437 | 14 | 2024-01-25 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-08 07:00 | COMP | 2024-01-30 | 2.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8010-60-V00-0130 | PAINT, LATEX, MATT, WHITE, 1 GL (3.2 TO 3.6 LT) | 51536 | 2024-01-10 | 2024-01-13 | CLOSE | 3 | CN | 16 | 42.62 | 681.92 | 20370 | CLOSE | 2024-01-20 | 2024-01-18 | KW1-14329 | 39 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-27 | COMP | 2024-01-25 | 16.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 51537 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | EA | 6 | 14.6 | 87.6 | 20326 | CLOSE | 2024-01-13 |  | KW1-14200 | 5 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-02-29 | COMP | 2024-01-17 | 6.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 51539 | 2024-01-10 | 2024-01-10 | CLOSE | 4 | EA | 8 | 12.4 | 99.2 | 20327 | CLOSE | 2024-01-13 |  | KW1-14201 | 17 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-16 | 8.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 51539 | 2024-01-10 | 2024-01-10 | CLOSE | 3 | EA | 12 | 13.99 | 167.88 | 20327 | CLOSE | 2024-01-13 |  | KW1-14201 | 16 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-16 | 12.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUAR | 51539 | 2024-01-10 | 2024-01-10 | CLOSE | 2 | EA | 6 | 29.3 | 175.8 | 20327 | CLOSE | 2024-01-13 |  | KW1-14201 | 15 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-16 | 6.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8415-01-492-0179 | GLOVES, DISPOSABLE, LATEX FREE, NITRILE, MEDIUM | 51534 | 2024-01-10 | 2024-01-10 | CLOSE | 3 | BX | 2 | 18.65 | 37.3 | 20326 | CLOSE | 2024-01-13 |  | KW1-14199 | 4 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-02-29 | COMP | 2024-01-17 | 2.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5510-60-V00-0022 | BOARD, MDF, INTERIOR, BROWN, 12 X 1220 X 2440 MM | 51540 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | EA | 10 | 29.7 | 297 | 20372 | CLOSE | 2024-01-25 | 2024-01-20 | KW1-14437 | 10 | 2024-01-25 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-01 07:00 | COMP | 2024-01-30 | 10.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8010-60-V00-0050 | PAINT, ENAMEL, GLOSS, DARK BROWN, 3.2 AND 3.6 LITER | 51530 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | CN | 3 | 39.96 | 119.88 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 52 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-25 | 3.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8010-60-V00-0146 | PRIMER COATING, WOOD, WHITE, 5 GL | 51535 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | CN | 1 | 123.21 | 123.21 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 58 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-28 | 1.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GL | 51539 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | GL | 2 | 228.7 | 457.4 | 20327 | CLOSE | 2024-01-13 |  | KW1-14201 | 14 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-18 | 2.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5340-00-116-2375 | CLOSER, HYDRAULIC DOOR, LIGHT DUTY | 51538 | 2024-01-10 | 2024-01-10 | CLOSE | 4 | EA | 2 | 97 | 194 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 63 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-23 | 2.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 50 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5340-09-V00-0029 | DOOR CLOSER, MANUAL HYDRAULIC, HEAVY-DUTY INTERIOR AND EXTERIOR, DARK BRONZE | 51577 | 2024-01-10 | 2024-01-13 | CLOSE | 1 | EA | 1 | 125.66 | 125.66 | 20373 | CLOSE | 2024-01-23 | 2024-01-20 | KW1-14389 | 1 | 2024-01-23 | APPR | 2024-01-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-02-29 07:00 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5340-60-V00-0492 | STOPPER, DOOR, DROP DOWN, METAL, 5" | 51531 | 2024-01-10 | 2024-01-10 | CLOSE | 2 | EA | 3 | 12.1 | 36.3 | 20325 | CLOSE | 2024-01-13 |  | KW1-14197 | 30 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-25 | COMP | 2024-01-16 | 3.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5340-60-V00-0141 | DOORSTOP, FLOOR MOUNT, BRASS, 1-3/4 X 1-1/4 INCHES | 51536 | 2024-01-10 | 2024-01-13 | CLOSE | 2 | EA | 3 | 9.66 | 28.98 | 20370 | CLOSE | 2024-01-20 | 2024-01-18 | KW1-14329 | 38 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-27 | COMP | 2024-01-25 | 3.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5640-60-V00-0035 | WEATHER STRIP, DOOR, W/BRUSH, 2 X 36 INCHES | 51534 | 2024-01-10 | 2024-01-10 | CLOSE | 2 | EA | 3 | 30.47 | 91.41 | 20318 | CLOSE | 2024-01-22 | 2024-01-15 | KW1-14372 | 12 | 2024-01-22 | APPR | 2024-01-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-10 | COMP | 2024-01-25 | 3.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8030-09-V01-0003 | SEALING COMPOUND, CAULK, ACRYLIC, WHITE, 5.5 OZ | 51535 | 2024-01-10 | 2024-01-10 | CLOSE | 2 | EA | 4 | 16.98 | 67.92 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 59 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-20 | 4.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5510-01-433-1244 | LUMBER, SOFTWOOD, 2 X 4 INCHES X 16 FEET | 51538 | 2024-01-10 | 2024-01-10 | CLOSE | 3 | EA | 6 | 30.8 | 184.8 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 62 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-30 | 6.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8030-60-V00-0050 | PUTTY, WOOD FILLER, MEDIUM OAK, 250 ML | 51531 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | CN | 2 | 68.27 | 136.54 | 20327 | CLOSE | 2024-01-13 |  | KW1-14201 | 13 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 | COMP | 2024-01-21 | 2.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5130-60-V00-0134 | BIT, SCREWDRIVER, (POWER BIT), PHILLIPS, STEEL, #2 X 2 INCHES | 51532 | 2024-01-10 | 2024-01-10 | CLOSE | 2 | PG | 1 | 14.99 | 14.99 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 55 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-23 | 1.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 40 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5130-60-V00-0123 | CUTTING WHEEL, METAL, ALUMINUM OXIDE, 4X0.05X5/8 INCHES | 51574 | 2024-01-10 | 2024-01-13 | CLOSE | 1 | EA | 6 | 14.99 | 89.94 |  |  |  |  | KW1-14446 | 12 | 2024-01-25 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-08 07:00 | COMP | 2024-01-30 | 6.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8020-60-V00-0017 | EXTENSION POLE, PAINT ROLLER, ALUMINUM, YELLOW, 2 - 4 FEET | 51536 | 2024-01-10 | 2024-01-13 | CLOSE | 1 | EA | 2 | 43.29 | 86.58 | 20370 | CLOSE | 2024-01-20 | 2024-01-18 | KW1-14329 | 37 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 40 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5120-60-V00-0418 | EXTENSION POLE, FIBER GLASS, 4 – 8 FT | 51575 | 2024-01-10 | 2024-01-13 | CLOSE | 1 | EA | 2 | 37.46 | 74.92 |  |  |  |  | KW1-14446 | 13 | 2024-01-25 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-08 07:00 | COMP | 2024-01-30 | 2.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5120-60-V00-0267 | KNIFE, PUTTY, STAINLESS STEEL, BLACK/BLUE, 5 INCHES | 51534 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | EA | 5 | 16.48 | 82.4 | 20318 | CLOSE | 2024-01-22 | 2024-01-15 | KW1-14372 | 15 | 2024-01-22 | APPR | 2024-01-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-10 | COMP | 2024-02-03 | 5.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5110-60-V00-0077 | KNIFE, PUTTY, 3 INCHES | 51538 | 2024-01-10 | 2024-01-10 | CLOSE | 2 | EA | 5 | 11.5 | 57.5 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 61 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-23 | 5.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5210-60-V00-0005 | TAPE, MEASURING, STEEL, 26 FEET | 51532 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | EA | 3 | 36.63 | 109.89 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 54 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-23 | 3.00 |  | BU | BU table | January | 2024
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5110-00-892-5071 | KNIFE, CRAFTSMAN'S, RETRACTABLE BLADE | 51538 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | EA | 3 | 19.3 | 57.9 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 60 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-23 | 3.00 |  | BU | BU table | January | 2024
45 | 2024-01-04 |  | BU24-0028 | Repair Runway Holes | 7894966 | 5610-60-V00-0029 | ASPHALT, COLD PATCH, READY TO USE, 50 LBS | [5 empty] | BG | 90 | [17 empty] | Allready received | BU | BU table | January | 2024
45 | 2024-01-04 | 50 | BU24-0028 | Repair Runway Holes | 7894966 | 8010-60-V00-0244 | PRIMER, SOLVENT BASED, BITUMEN, BLACK, 20 LITERS | 51809 | 2024-01-15 | 2024-01-17 | CLOSE | 4 | CN | 3 | 81.3 | 243.9 | 20429 | CLOSE | 2024-01-24 | 2024-01-23 | KW1-14393 | 6 | 2024-01-23 | APPR | 2024-01-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL BAYADER INTER.GROUP COMPANY | 2024-02-20 07:00 | COMP | 2024-02-12 | 3.00 |  | BU | BU table | January | 2024
45 | 2024-01-04 |  | BU24-0028 | Repair Runway Holes | 7894966 | 5610-60-V00-0010 | GATCH AND GRAVEL, MIXED, CUBIC METER | [5 empty] | CZ | 4 | [17 empty] | Allready received | BU | BU table | January | 2024
45 | 2024-01-04 | 50 | BU24-0028 | Repair Runway Holes | 7894966 | 7920-00-292-2365 | BROOM, PUSH, W/O HANDLE, 3 X 2-1/2 X 14 INCHES | 51809 | 2024-01-15 | 2024-01-17 | CLOSE | 3 | EA | 2 | 22.02 | 44.04 | 20429 | CLOSE | 2024-01-24 | 2024-01-23 | KW1-14393 | 5 | 2024-01-23 | APPR | 2024-01-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL BAYADER INTER.GROUP COMPANY | 2024-01-30 07:00 | COMP | 2024-01-28 | 2.00 |  | BU | BU table | January | 2024
45 | 2024-01-04 | 50 | BU24-0028 | Repair Runway Holes | 7894966 | 5130-05-V00-0043 | BLADE, CIRCULAR SAW, ASPHALT CUTTING, WET/DRY, DIAMOND, 5460 RPM, 14 X 0.125 INCHES | 51809 | 2024-01-15 | 2024-01-17 | CLOSE | 2 | EA | 1 | 291.68 | 291.68 | 20429 | CLOSE | 2024-01-24 | 2024-01-23 | KW1-14393 | 4 | 2024-01-23 | APPR | 2024-01-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL BAYADER INTER.GROUP COMPANY | 2024-02-29 07:00 | COMP | 2024-02-18 | 1.00 |  | BU | BU table | January | 2024
45 | 2024-01-04 | 50 | BU24-0028 | Repair Runway Holes | 7894966 | 7920-05-V00-0019 | SQUEEGEE, ASPHALT, NEOPRENE BLADE, 60 X 36 INCHES | 51809 | 2024-01-15 | 2024-01-17 | CLOSE | 1 | EA | 1 | 52.38 | 52.38 | 20429 | CLOSE | 2024-01-24 | 2024-01-23 | KW1-14393 | 3 | 2024-01-23 | APPR | 2024-01-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL BAYADER INTER.GROUP COMPANY | 2024-02-29 07:00 | COMP | 2024-02-05 | 1.00 |  | BU | BU table | January | 2024
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 8010-60-V00-0095 | PRIMER, COATING, RED OXIDE, LIQUID, 3.78 TO 4 LITERS | 51598 | 2024-01-11 | 2024-01-13 | CAN | 1 | CN | 5 | 25.71 | 128.55 | [15 empty] | Cancelled | BU | BU table | January | 2024
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 8010-60-V00-0028 | PAINT, ENAMEL, GLOSS, DESERT SAND, 3.6 LITER | 51604 | 2024-01-11 |  | APPR | 3 | CN | 5 | [17 empty] | Cancelled | BU | BU table | January | 2024
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 5345-60-V00-0019 | DISK, FLAP, ABRASIVE, 60 GRIT, ZIRCONIA, 4-1/2 X 7/8 INCHES | 51603 | 2024-01-11 | 2024-01-13 | CAN | 2 | EA | 8 | 12.99 | 103.92 | [15 empty] | Cancelled | BU | BU table | January | 2024
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 51604 | 2024-01-11 | 2024-01-13 | CLOSE | 2 | EA | 5 | 29.3 | 146.5 | 20340 | CLOSE | 2024-01-14 |  | KW1-14226 | 2 | 2024-01-14 | APPR | 2024-01-14 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 |  |  |  | Cancelled | BU | BU table | January | 2024
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 51604 | 2024-01-11 | 2024-01-13 | CLOSE | 1 | EA | 10 | 12.4 | 124 | 20340 | CLOSE | 2024-01-14 |  | KW1-14226 | 1 | 2024-01-14 | APPR | 2024-01-14 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 |  |  |  | Cancelled | BU | BU table | January | 2024
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 51602 | 2024-01-11 | 2024-01-13 | CAN | 1 | EA | 5 | 14.6 | 73 | [15 empty] | Cancelled | BU | BU table | January | 2024
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 6515-60-V00-0015 | GLOVES, EXAM, DISPOSABLE, NITRILE, PURPLE, X-LARGE | 51601 | 2024-01-11 | 2024-01-13 | CAN | 2 | EA | 1 | 49.95 | 49.95 | [15 empty] | Cancelled | BU | BU table | January | 2024
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 4020-00-246-0688 | CORD, FIBROUS, POLYAMIDE NYLON, OLIVE DRAB, 47/250 INCH X 1200 FEET | 51599 | 2024-01-11 | 2024-01-13 | CAN | 1 | RO | 6 | 182.98 | 1097.88 | [15 empty] | Cancelled | BU | BU table | January | 2024
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 5610-60-V00-0010 | GATCH AND GRAVEL, MIXED, CUBIC METER | 51600 | 2024-01-11 | 2024-01-13 | CAN | 1 | CZ | 10 | 58.28 | 582.8 | [15 empty] | Cancelled | BU | BU table | January | 2024
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 8105-01-336-6163 | BAG, SAND, TAN, 26 INCHES | 51603 | 2024-01-11 | 2024-01-13 | CAN | 1 | HD | 1 | 727.27 | 727.27 | [15 empty] | Cancelled | BU | BU table | January | 2024
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 9530-60-V00-0010 | BAR, METAL, FLAT, GALVANIZED MILD STEEL, 50 X 3 X 6000 MM | 51605 | 2024-01-11 | 2024-01-13 | CAN | 1 | EA | 6 | 58.37 | 350.22 | [15 empty] | Cancelled | BU | BU table | January | 2024
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 4020-60-V00-0006 | ROPE, NYLON DOUBLE-BRAIDED, (COILS TWISTED), 1/2 INCH X 50 FEET | 51601 | 2024-01-11 | 2024-01-13 | CAN | 1 | EA | 5 | 9.99 | 49.95 | [15 empty] | Cancelled | BU | BU table | January | 2024
47 | 2024-01-10 | 40 | BU23-0352 | Z6 B6016 Door Soundproofing | 7562147 | 8030-60-V00-0087 | SEALING COMPOUND (GLUE NOISEPROOFING COMPOUND), GREEN, 28 OZ, 12 PIECES | 51588 | 2024-01-10 | 2024-01-13 | CLOSE | 1 | PG | 2 | 326.53 | 653.06 | 20373 | CLOSE | 2024-01-23 | 2024-01-20 | KW1-14389 | 3 | 2024-01-23 | APPR | 2024-01-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-15 | COMP | 2024-03-09 | 1.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5640-60-V00-0048 | DRYWALL SHEET, (GYPSUM BOARD), 4 X 8 FEET X 1/2 INCH | 51857 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | EA | 15 | 19.14 | 287.1 | 20467 | CLOSE | 2024-01-27 | 2024-01-25 | KW1-14455 | 1 | 2024-01-27 | APPR | 2024-01-27 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-11 | COMP | 2024-01-30 | 15.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5305-60-V00-0179 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 1-1/2 INCHES | 51853 | 2024-01-16 | 2024-01-18 | CLOSE | 2 | BX | 2 | 10.5 | 21 | 20441 | CLOSE | 2024-01-21 | 2024-01-21 | KW1-14365 | 2 | 2024-01-21 | APPR | 2024-01-22 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-05 | COMP | 2024-01-24 | 2.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 51853 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | BX | 2 | 19.6 | 39.2 | 20441 | CLOSE | 2024-01-21 | 2024-01-21 | KW1-14365 | 1 | 2024-01-21 | APPR | 2024-01-22 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-05 | COMP | 2024-01-24 | 2.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 51912 | 2024-01-16 | 2024-01-18 | CLOSE | 2 | CN | 1 | 39.6 | 39.6 | 20573 | CLOSE | 2024-01-27 |  | KW1-14460 | 1 | 2024-01-27 | APPR | 2024-01-27 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-11 | COMP | 2024-01-30 | 1.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5640-60-V00-0044 | TAPE, SELF ADHESIVE, DRYWALL JOINT, FIBERGLASS, 2 INCHES X 300 FEET | 51862 | 2024-01-16 | 2024-01-18 | CLOSE | 2 | EA | 2 | 18.5 | 37 | 20467 | CLOSE | 2024-01-27 | 2024-01-25 | KW1-14455 | 3 | 2024-01-27 | APPR | 2024-01-27 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-11 | COMP | 2024-01-30 | 2.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5350-60-V00-0004 | PAPER, ABRASIVE (SANDPAPER), 80 GRIT, 9 X 11 INCHES | 51848 | 2024-01-16 | 2024-01-17 | CLOSE | 1 | EA | 1 | 34.48 | 34.48 | 20409 | CLOSE | 2024-01-19 |  | KW1-14300 | 30 | 2024-01-23 | APPR | 2024-01-23 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-04 |  |  |  |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8010-60-V00-0006 | PAINT, LATEX, MATT, WHITE, 3.2 LT | 51854 | 2024-01-16 | 2024-01-18 | CLOSE | 4 | CN | 5 | 44 | 220 | 20446 | CLOSE | 2024-01-22 | 2024-01-22 | KW1-14376 | 4 | 2024-01-22 | APPR | 2024-01-28 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-05 | COMP | 2024-02-01 | 5.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8010-60-V00-0048 | PAINT, LATEX, MATT, ALMOND, 3.2 AND 3.6 LITERS | 51851 | 2024-01-16 | 2024-01-17 | CLOSE | 1 | CN | 6 | 41.14 | 246.84 | 20410 | CLOSE | 2024-01-19 |  | KW1-14305 | 32 | 2024-01-19 | APPR | 2024-01-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-11 | 6.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 51854 | 2024-01-16 | 2024-01-18 | CLOSE | 3 | EA | 3 | 29 | 87 | 20446 | CLOSE | 2024-01-22 | 2024-01-22 | KW1-14376 | 3 | 2024-01-22 | APPR | 2024-01-28 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-05 | COMP | 2024-01-31 | 3.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 51854 | 2024-01-16 | 2024-01-18 | CLOSE | 2 | EA | 6 | 13.9 | 83.4 | 20446 | CLOSE | 2024-01-22 | 2024-01-22 | KW1-14376 | 2 | 2024-01-22 | APPR | 2024-01-28 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-05 | COMP | 2024-01-31 | 6.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 51852 | 2024-01-16 | 2024-01-17 | CLOSE | 1 | EA | 5 | 14.6 | 73 | 20412 | CLOSE | 2024-01-19 |  | KW1-14306 | 4 | 2024-01-19 | APPR | 2024-01-19 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-02-29 | COMP | 2024-01-23 | 5.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 7510-00-266-6710 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 51860 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | RO | 5 | 8.25 | 41.25 | 20442 | CLOSE | 2024-01-21 | 2024-01-21 | KW1-14366 | 1 | 2024-01-21 | APPR | 2024-01-22 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-02-05 | COMP | 2024-01-24 | 5.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 6515-60-V00-0015 | GLOVES, EXAM, DISPOSABLE, NITRILE, PURPLE, X-LARGE | 51856 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | BX | 1 | 48.78 | 48.78 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 1 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 9520-60-V00-0035 | CHANNEL, CEILING, METAL, 3600 X 0.55 MM | 51859 | 2024-01-16 | 2024-01-18 | CLOSE | 5 | EA | 25 | 17.32 | 433 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 6 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 25.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 9520-60-V00-0034 | CHANNEL, CEILING, PRIMARY, METAL, 3600 X 0.80 MM | 51859 | 2024-01-16 | 2024-01-18 | CLOSE | 4 | EA | 35 | 14.85 | 519.75 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 5 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 35.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 9540-60-V00-0014 | CHANNEL, STRUCTURAL, PERIMETER, MF6A, GALVANISED STEEL, 30 MM X 27 MM X 3.6 METERS | 51863 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | EA | 10 | 4.1 | 41 | 20467 | CLOSE | 2024-01-27 | 2024-01-25 | KW1-14455 | 4 | 2024-01-27 | APPR | 2024-01-27 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-11 | COMP | 2024-02-05 | 10.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5305-60-V00-0197 | SCREW, PHILLIPS DRIVE, SELF-DRILLING, ZINC PLATED, TRUSS HEAD, # 8, 8 X 1/2 INCH | 51849 | 2024-01-16 | 2024-01-17 | CLOSE | 1 | BX | 5 | 29.04 | 145.2 | 20409 | CLOSE | 2024-01-19 |  | KW1-14300 | 32 | 2024-01-23 | APPR | 2024-01-23 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-04 |  |  |  |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8030-60-V00-0081 | PUTTY, MULTI PURPOSE, PLASTIC, GRAY, 1-QUART | 51859 | 2024-01-16 | 2024-01-18 | CLOSE | 3 | CN | 2 | 150.15 | 300.3 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 4 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8030-60-V00-0052 | PUTTY, ALL PURPOSE, LIGHT GRAY, 3.43 KG | 51862 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | CN | 2 | 124 | 248 | 20571 | CLOSE | 2024-01-27 |  | KW1-14457 | 1 | 2024-01-27 | APPR | 2024-01-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-11 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5510-60-V00-0027 | PLYWOOD, CONSTRUCTION, MELAMINE COATED, 4 MM X 8 X 4 FEET | 51858 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | EA | 2 | 55.44 | 110.88 | 20467 | CLOSE | 2024-01-27 | 2024-01-25 | KW1-14455 | 2 | 2024-01-27 | APPR | 2024-01-27 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-11 | COMP | 2024-01-30 | 2.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5315-60-V00-0058 | NAIL, FLAT, STAINLESS-STEEL, 2D X 1 INCH | 51850 | 2024-01-16 | 2024-01-17 | CLOSE | 1 | BX | 2 | 13.53 | 27.06 | 20409 | CLOSE | 2024-01-19 |  | KW1-14300 | 19 | 2024-01-23 | APPR | 2024-01-23 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-04 |  |  |  |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5315-60-V00-0015 | NAIL, STRAIGHT, 16 GAGE, GALVANIZED, 3/4 INCHES | 51855 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | BX | 3 | 25.28 | 75.84 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 1 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-14 | 3.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8030-01-075-1156 | CAULKING COMPOUND, CARTRIDGE, WHITE, 10 OZ | 51859 | 2024-01-16 | 2024-01-18 | CLOSE | 2 | CQ | 12 | 14.85 | 178.2 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 3 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 | COMP | 2024-02-26 | 12.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8010-60-V00-0089 | PRIMER, COATING, WHITE, 4 - 5 LITERS | 51854 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | CN | 4 | 41.3 | 165.2 | 20446 | CLOSE | 2024-01-22 | 2024-01-22 | KW1-14376 | 1 | 2024-01-22 | APPR | 2024-01-28 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-05 | COMP | 2024-02-04 | 4.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8415-60-V00-0352 | COVERALLS, DISPOSABLE PROTECTIVE, TYVEK400, WHITE, XL | 51912 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | BX | 1 | 269.2 | 269.2 | 20467 | CLOSE | 2024-01-27 | 2024-01-25 | KW1-14455 | 5 | 2024-01-27 | APPR | 2024-01-27 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-29 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | January | 2024
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8340-00-068-7908 | DROP CLOTH, PAINTER'S, 9 FT X 12 FT | 51859 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | EA | 1 | 28.71 | 28.71 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 2 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024
49 | 2023-11-27 | 30 | BU23-0310 | Install New Emergency Shower | 6872738 | 4230-60-V00-0001 | SHOWER ASSEMBLY, DECONTAMINATING, GALVANIZED STEEL, 350 LITERS, HDPE, WHITE, 60.6 X 34.6 X 128.1 INCHES | 42734 | 2023-09-19 | 2023-12-30 | CLOSE | 1 | EA | 1 | 11238.75 | 11238.75 | 20132 | CLOSE | 2024-01-10 | 2024-01-06 | KW1-14163 | 1 | 2024-01-10 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 03:00 | COMP | 2024-01-15 | 1.00 |  | BU | BU table | November | 2023
50 | 2024-01-16 | 30 | BU24-0048 | New Signs ASP Z8 T8000 | 8418200 | 8105-01-336-6163 | BAG, SAND, TAN, 26 INCHES | 51928 | 2024-01-17 | 2024-01-18 | CLOSE | 1 | HD | 3 | 742.5 | 2227.5 | 20441 | CLOSE | 2024-01-21 | 2024-01-21 | KW1-14365 | 6 | 2024-01-21 | APPR | 2024-01-22 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-05 | COMP | 2024-01-24 | 3.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5935-60-V00-0160 | SOCKET, OUTLET, WEATHERPROOF, 2 GANG, 2 POLES, 13 AMPS | 52341 | 2024-01-22 | 2024-01-27 | CLOSE | 7 | EA | 8 | 41.4 | 331.2 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 7 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 8.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 52337 | 2024-01-22 | 2024-01-27 | CLOSE | 5 | EA | 4 | 27.31 | 109.24 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 25 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 4.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0743 | BOX CONNECTOR, ELECTRICAL, CONDUIT, SET SCREW, STEEL, 3/4 INCH | 52338 | 2024-01-22 | 2024-01-27 | APPR | 4 | EA | 5 | 10.66 | 53.3 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 29 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-21 | COMP |  |  |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0376 | COUPLING, CONDUIT, w/ SET SCREW, STEEL, 3/4 INCH | 52337 | 2024-01-22 | 2024-01-27 | CLOSE | 4 | EA | 20 | 2 | 40 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 24 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 20.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-00-178-1217 | CONDUIT, RIGID, EMT, GALVANIZED STEEL, 3/4" INCH X 10 FEET | 52341 | 2024-01-22 | 2024-01-27 | CLOSE | 6 | EA | 20 | 13.6 | 272 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 6 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 20.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0066 | CONDUIT, METAL, RIGID, GALVANIZED STEEL, 1/2 INCH X 10 FEET | 52340 | 2024-01-22 | 2024-01-27 | CLOSE | 1 | EA | 20 | 212.9 | 4258 | 20622 | CLOSE | 2024-01-29 |  | KW1-14510 | 1 | 2024-01-29 | APPR | 2024-01-29 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-11 | COMP | 2024-02-01 | 20.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0483 | BOX CONNECTOR, ELECTRICAL, ZINC DIE CAST, 1/2 INCH | 52337 | 2024-01-22 | 2024-01-27 | CLOSE | 3 | EA | 10 | 4 | 40 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 23 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-21 | COMP | 2024-02-15 | 10.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0487 | COUPLING, ELECTRICAL CONDUIT, w/ SCREW, Â½ INCH | 52341 | 2024-01-22 | 2024-01-27 | CLOSE | 5 | EA | 10 | 5 | 50 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 5 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-10 | 10.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0043 | COUPLING, ELECTRICAL, CONDUIT, COMBINATION, EMT TO FMC, DIE CAST ZINC, 1/2 INCH | 52342 | 2024-01-22 | 2024-01-27 | CLOSE | 3 | EA | 8 | 9.24 | 73.92 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 8 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-14 | 8.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0042 | BOX CONNECTOR, ELECTRICAL, STRAIGHT, LIQUID TIGHT CONDUIT, NICKEL PLATED BRASS, 1/2 INCH | 52341 | 2024-01-22 | 2024-01-27 | CLOSE | 4 | EA | 16 | 24 | 384 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 4 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 16.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0395 | STRAP, TIE DOWN, WHITE, 12 INCHES | 52338 | 2024-01-22 | 2024-01-27 | CLOSE | 3 | PG | 2 | 13.99 | 27.98 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 28 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0460 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, GALVANIZED STEEL, ¾ INCH | 52337 | 2024-01-22 | 2024-01-27 | CLOSE | 2 | EA | 20 | 2.04 | 40.8 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 22 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 20.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0461 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, GALVANIZED STEEL, ½ INCH | 52338 | 2024-01-22 | 2024-01-27 | CLOSE | 2 | EA | 30 | 1.6 | 48 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 27 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 30.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 6145-60-V00-0136 | WIRE, ELECTRICAL, RED, 1 CORE, 4MM² | 52341 | 2024-01-22 | 2024-01-27 | CLOSE | 3 | RL | 1 | 90.56 | 90.56 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 3 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 6145-60-V00-0159 | WIRE, ELECTRICAL, BLUE, 1 CORE, 4 MM² | 52339 | 2024-01-22 | 2024-01-27 | CLOSE | 1 | RL | 1 | 90.4 | 90.4 | 20708 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14585 | 1 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-03-01 | COMP | 2024-02-05 | 1.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 6145-60-V00-0154 | WIRE, ELECTRICAL, BLACK, 1 CORE, 4MM² | 52341 | 2024-01-22 | 2024-01-27 | CLOSE | 2 | RL | 2 | 90.56 | 181.12 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 2 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 2.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 6145-60-V00-0142 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4MM² | 52337 | 2024-01-22 | 2024-01-27 | CLOSE | 1 | RL | 2 | 66.1 | 132.2 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 21 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5305-60-V00-0001 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 52338 | 2024-01-22 | 2024-01-27 | CLOSE | 1 | BX | 1 | 19.31 | 19.31 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 26 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5925-60-V00-0051 | CIRCUIT BREAKER, MINIATURE, 1 POLE, 230/400V, 20A | 52342 | 2024-01-22 | 2024-01-27 | CLOSE | 2 | EA | 4 | 49.5 | 198 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 7 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 52341 | 2024-01-22 | 2024-01-27 | CLOSE | 1 | BX | 1 | 92.02 | 92.02 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 1 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-12 | 1.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5110-60-V00-0066 | CUTTER, PIPE, HEAVY DUTY, 1/8- 2 INCHES | 52342 | 2024-01-22 | 2024-01-27 | CLOSE | 1 | EA | 1 | 188.5 | 188.5 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 6 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5110-01-367-7278 | CUTTER, CABLE, HAND OPERATED, FORGED STEEL, PLASTIC DIPPED, 9-1/2 INCHES | 52552 | 2024-01-25 | 2024-01-27 | CLOSE | 1 | EA | 1 | 66.6 | 66.6 | 20680 | CLOSE | 2024-01-31 | 2024-01-31 | KW1-14567 | 2 | 2024-01-31 | APPR | 2024-01-31 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-25 | COMP | 2024-02-17 | 1.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4730-60-V00-0754 | ADAPTER, PRESSURE FITTINGS, MALE, CPVC, STANDARD, SOCKET X MIPT, PN16, OFF-WHITE, 25 MM | 52617 | 2024-01-25 | 2024-01-29 | CLOSE | 8 | EA | 4 | 3.2 | 12.8 | 20699 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14578 | 12 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 4.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4730-60-V00-0897 | BUSHING, PIPE, REDUCER, SCH-40, CPVC, OFF-WHITE, 2 X 1 INCHES | 52603 | 2024-01-25 | 2024-01-29 | CLOSE | 2 | EA | 4 | 5.16 | 20.64 | 20680 | CLOSE | 2024-01-31 | 2024-01-31 | KW1-14567 | 17 | 2024-01-31 | APPR | 2024-01-31 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 4.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 8040-60-V00-0040 | CEMENT, HEAVY BODIED, CPVC, ORANGE, 16 OZ | 52605 | 2024-01-25 | 2024-01-29 | CLOSE | 2 | CN | 2 | 18.32 | 36.64 | 20666 | CLOSE | 2024-01-31 | 2024-01-31 | KW1-14559 | 16 | 2024-01-31 | APPR | 2024-01-31 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-10 | COMP | 2024-02-04 | 2.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4730-60-V00-0893 | BUSHING, PIPE, REDUCTION, SCH- 40, CPVC, OFF-WHITE, 1 X 3/4 INCHES | 52617 | 2024-01-25 | 2024-01-29 | CLOSE | 7 | EA | 4 | 5 | 20 | 20699 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14578 | 11 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 4.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4730-60-V00-0854 | ELBOW, CPVC, 90 DEGREE, SCH- 40, OFF-WHITE, 2 INCHES | 52603 | 2024-01-25 | 2024-01-29 | CLOSE | 1 | EA | 6 | 10.07 | 60.42 | 20680 | CLOSE | 2024-01-31 | 2024-01-31 | KW1-14567 | 16 | 2024-01-31 | APPR | 2024-01-31 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 6.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4730-60-V00-0850 | ELBOW, CPVC, SOCKET X SOCKET, SCH 40, OFF-WHITE, 25 MM | 52617 | 2024-01-25 | 2024-01-29 | CLOSE | 6 | EA | 4 | 3.6 | 14.4 | 20699 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14578 | 10 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 4.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4710-60-V00-0107 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 2 INCHES | 52617 | 2024-01-25 | 2024-01-29 | CLOSE | 5 | EA | 2 | 51.15 | 102.3 | 20699 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14578 | 9 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 2.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4710-60-V00-0111 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 1 INCH | 52617 | 2024-01-25 | 2024-01-29 | CLOSE | 4 | EA | 1 | 31.18 | 31.18 | 20699 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14578 | 8 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 1.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4710-60-V00-0108 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 52617 | 2024-01-25 | 2024-01-29 | CLOSE | 3 | EA | 1 | 18.81 | 18.81 | 20699 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14578 | 7 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 1.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 8030-60-V00-0051 | TAPE, ANTISEIZING, (TEFLON TAPE), 0.5 X 520 INCHES | 52605 | 2024-01-25 | 2024-01-29 | CLOSE | 1 | EA | 10 | 1.67 | 16.7 | 20666 | CLOSE | 2024-01-31 | 2024-01-31 | KW1-14559 | 15 | 2024-01-31 | APPR | 2024-01-31 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-10 | COMP | 2024-02-04 | 10.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4510-60-V00-0132 | STRAP, METAL | 52618 | 2024-01-25 | 2024-01-29 | CLOSE | 2 | EA | 1 | 73.9 | 73.9 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 48 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4230-60-V00-0001 | SHOWER ASSEMBLY, DECONTAMINATING, GALVANIZED STEEL, 350 LITERS, HDPE, WHITE, 60.6 X 34.6 X 128.1 INCHES | 52602 | 2024-01-25 | 2024-01-29 | CLOSE | 1 | EA | 2 | 11938.05 | 23876.1 | 20638 | CLOSE | 2024-02-08 | 2024-02-01 | KW1-14725 | 1 | 2024-02-08 | APPR | 2024-02-08 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-07-31 |  |  |  |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 5306-60-V00-0006 | BOLT, CONCRETE ANCHOR, w/ NUT & WASHER, M10 X 4 INCHES | 52617 | 2024-01-25 | 2024-01-29 | CLOSE | 2 | BX | 8 | 7.26 | 58.08 | 20699 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14578 | 6 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 8.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4820-60-V00-0115 | VALVE, CHECK, PVC, 2 INCHES | 52606 | 2024-01-25 | 2024-01-27 | CLOSE | 2 | EA | 2 | 67.27 | 134.54 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 14 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4820-60-V00-0229 | VALVE, BALL, BRASS, PN25, RED, 3/4 INCH | 52617 | 2024-01-25 | 2024-01-29 | CLOSE | 1 | EA | 2 | 15.84 | 31.68 | 20699 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14578 | 5 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 2.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4730-60-V00-0775 | ADAPTER, MALE, CPVC, STANDARD, SOCKET X MIPT, SCH- 40, OFF-WHITE, 63 MM | 52604 | 2024-01-25 | 2024-01-29 | CLOSE | 3 | EA | 4 | 45.79 | 183.16 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 12 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-19 | 4.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4730-60-V00-0760 | ADAPTER, FEMALE, CPVC & METAL, STANDARD, SOCKET X SR FIPT, SCH- 40, OFF WHITE, 32 MM | 52604 | 2024-01-25 | 2024-01-29 | CLOSE | 2 | EA | 6 | 12.99 | 77.94 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 11 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-19 | 6.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4730-60-V00-0765 | ADAPTER, PRESSURE FITTINGS, FEMALE, CPVC, STANDARD, SOCKET X FIPT, SCH- 40, OFF-WHITE, 25 MM | 52607 | 2024-01-25 | 2024-01-29 | CLOSE | 2 | EA | 4 | 13.1 | 52.4 | 20680 | CLOSE | 2024-01-31 | 2024-01-31 | KW1-14567 | 19 | 2024-01-31 | APPR | 2024-01-31 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 4.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4730-60-V00-0788 | CAP, PIPE, UPVC, OCTAGON, FEMALE, SCH-40, GRAY, 63 MM | 52604 | 2024-01-25 | 2024-01-29 | CLOSE | 1 | EA | 2 | 9.16 | 18.32 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 10 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-19 | 2.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 5510-00-220-6242 | LUMBER, SOFTWOOD, DIMENSION, 4 X 2 INCHES X 10 FEET | 52607 | 2024-01-25 | 2024-01-29 | CLOSE | 1 | EA | 2 | 25.4 | 50.8 | 20680 | CLOSE | 2024-01-31 | 2024-01-31 | KW1-14567 | 18 | 2024-01-31 | APPR | 2024-01-31 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 2.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 5510-01-433-4221 | LUMBER, SOFTWOOD, 4 X 4 INCHES X 16 FEET | 52606 | 2024-01-25 | 2024-01-27 | CLOSE | 1 | EA | 2 | 37.46 | 74.92 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 13 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 5305-09-V00-0012 | SCREW, WOOD, DRYWALL, PHILLIPS, STEEL, 3 INCHES | 52619 | 2024-01-25 | 2024-01-29 | CLOSE | 1 | BX | 1 | 159.16 | 159.16 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 15 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 5133-60-V00-0020 | DRILL, MASONRY, ROTARY DRIVEN, (BIT), CONCRETE, SDS-PLUS, 1/2 X 8 INCHES | 52618 | 2024-01-25 | 2024-01-29 | CLOSE | 1 | EA | 2 | 10.73 | 21.46 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 47 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024
53 | 2024-01-25 | 30 | BU24-0140 | Install Cypher Locks T9601 | 9223619 | 5340-60-V00-0425 | LOCK SET, MORTISE, MECHANICAL, PUSH BUTTON, RIGHT HAND, 2-3/4 INCHES | 52621 | 2024-01-25 | 2024-01-27 | CLOSE | 1 | EA | 2 | 690.03 | 1380.06 | 20699 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14578 | 13 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 2.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6210-60-V00-0081 | LIGHT, PANEL, LED, COOL WHITE, 50/60 HZ, 40W | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 20 | EA | 2 | 274.38 | 548.76 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 25 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 2.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6210-60-V00-0082 | LIGHT, PANEL, LED, COOL WHITE, 50/60 HZ, 40W, w/ EMERGENCY BATTERY | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 19 | EA | 3 | 297.94 | 893.82 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 24 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 3.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6210-60-V00-0136 | EMERGENCY LIGHT, EXIT COMBO, LED | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 18 | EA | 1 | 130.86 | 130.86 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 23 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6210-60-V00-0040 | FIXTURE, LIGHTING, LED, WALL PACK, 5000K, 100-277 VAC, 30W | 53003 | 2024-01-30 | 2024-02-01 | CLOSE | 8 | EA | 1 | 127.05 | 127.05 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 27 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6130-60-V00-0097 | BATTERY, EMERGENCY LED DRIVER, 50/60HZ, 15W, 100-277V | 53003 | 2024-01-30 | 2024-02-01 | CLOSE | 7 | EA | 1 | 254.32 | 254.32 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 26 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6210-60-V00-0165 | LIGHT, LED FLOOD, W/EMERGENCY BATTERY,50W, 100-240 VAC, 50/60 Hz | 53003 | 2024-01-30 | 2024-02-01 | CLOSE | 6 | EA | 2 | 601.37 | 1202.74 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 25 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 2.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 17 | EA | 10 | 9.9 | 99 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 22 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-25 | COMP | 2024-02-07 | 10.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5930-60-V00-0387 | LIGHT-SWITCH, METAL, 1 WAY, 1 GANG, 250V, 10A | 53003 | 2024-01-30 | 2024-02-01 | CLOSE | 5 | EA | 3 | 17.63 | 52.89 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 24 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 3.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0118 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 16 MM² | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 1 | MT | 50 | 22 | 1100 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 6 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 50.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-60-V00-0511 | GLAND, ELECTRICAL CONDUIT, BRASS, BW, w/ EARTH TAG, 25 MM | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 16 | EA | 5 | 8 | 40 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 21 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 5.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5940-60-V00-0122 | TERMINAL, LUG, COPPER TUBE, STUD HOLE, 16MM² X M10 | 53003 | 2024-01-30 | 2024-02-01 | CLOSE | 4 | PK | 1 | 67.3 | 67.3 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 23 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 15 | RL | 1 | 242.58 | 242.58 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 20 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 07:00 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 14 | EA | 1 | 16.83 | 16.83 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 19 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5970-60-V00-0043 | TAPE, INSULATION, ELECTRICAL, SUPER 33 +,VINYL, BLACK, 3/4" X 66' | 53003 | 2024-01-30 | 2024-02-01 | CLOSE | 3 | EA | 2 | 13.99 | 27.98 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 22 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 2.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5970-01-013-9369 | TAPE, INSULATION ELECTRICAL, 3M, 792", RED | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 13 | EA | 1 | 10.1 | 10.1 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 18 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5970-01-174-5651 | TAPE, INSULATION ELECTRICAL, YELLOW | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 12 | EA | 1 | 10.1 | 10.1 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 17 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5970-01-015-5060 | TAPE, INSULATION ELECTRICAL BLUE | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 11 | EA | 1 | 10.1 | 10.1 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 16 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-01-559-8780 | STRAP, TIE DOWN,ELECTRICAL COMPONENT, BLACK, 50 PSI, 3 X 0.19 X 0.05 X 11.1 INCHES | 53006 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | PK | 2 | 2.48 | 4.96 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 16 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 53004 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 100 | 4.3 | 430 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 17 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 100.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 10 | BX | 1 | 92.02 | 92.02 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 15 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-12 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6110-60-V00-0104 | SWITCH, DISCONNECT (ISOLATOR), 4 POLES, 690V, 63A | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 9 | EA | 1 | 101.52 | 101.52 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 14 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-60-V00-0460 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, GALVANIZED STEEL, ¾ INCH | 53003 | 2024-01-30 | 2024-02-01 | CLOSE | 2 | PG | 10 | 2.11 | 84.4 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 21 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 40.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 9905-60-V00-0066 | SIGN, DANGER, 415 VOLTS , 5 X 3-3/4 INCHES | 53003 | 2024-01-30 | 2024-02-01 | CLOSE | 1 | PG | 2 | 17.08 | 34.16 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 20 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 2.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 8 | EA | 1 | 302.94 | 302.94 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 13 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 7 | EA | 1 | 58.91 | 58.91 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 12 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0158 | WIRE, ELECTRICAL, RED, 1 CORE, 2.5 MM² | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 6 | RO | 1 | 60.39 | 60.39 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 11 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0151 | WIRE, ELECTRICAL, BLACK 1 CORE, 2.5 MM² | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 5 | RO | 1 | 64.92 | 64.92 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 10 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 53004 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | RO | 1 | 64.5 | 64.5 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 16 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0154 | WIRE, ELECTRICAL, BLACK, 1 CORE, 4 MM ² | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 4 | RO | 1 | 90.56 | 90.56 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 9 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0143 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4 MM² | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 3 | RO | 1 | 90.56 | 90.56 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 8 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0136 | WIRE, ELECTRICAL, RED, 1 CORE, 4 MM ² | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 2 | RO | 1 | 90.56 | 90.56 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 7 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 70 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6110-60-V00-0166 | SENSOR, PHOTOCELL CONTROL, 15A, 50/60 HZ | 52975 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 1 | 63.36 | 63.36 | 20797 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14677 | 6 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 70 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4240-60-V00-0055 | TAPE, FLAGGING, CAUTION BURIED ELECTRIC LINE BELOW, ALUMINUM, RED, 6 INCHES X 1000 FEET | 52974 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | RO | 1 | 224.4 | 224.4 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 39 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 70 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 52975 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 2 | 51.81 | 103.62 | 20797 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14677 | 5 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-10 | 2.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 70 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 52972 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 10 | 26.67 | 266.7 | 20797 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14677 | 4 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-10 | 10.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 70 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5120-60-V00-0111 | SCREW DRIVER / NUT DRIVER, HEAVY DUTY, MULTI-BIT | 52973 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 2 | 41.25 | 82.5 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 14 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024
54 | 2024-01-30 | 70 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5180-39-V01-0007 | SCREW DRIVER SET , ELECTRONICS SLOTTED AND PHILLIPS , 4-PIECE. | 52974 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 2 | 51.48 | 102.96 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 38 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 | COMP | 2024-02-28 | 2.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4710-60-V00-0098 | TUBE, METALLIC, REFRIGERATION, COPPER, 5/8 INCH X 50 FEET | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 10 | RO | 1 | 100.5 | 100.5 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 41 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4710-60-V00-0097 | TUBE, METALLIC, REFRIGERATION, COPPER, 3/8 INCH X 50 FEET | 52816 | 2024-01-29 | 2024-01-30 | CLOSE | 3 | RO | 1 | 62.4 | 62.4 | 20708 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14585 | 11 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-03-01 | COMP | 2024-02-05 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5640-60-V00-0031 | INSULATION SLEEVING, THERMAL, 5/8 X 72 INCHES | 52817 | 2024-01-29 | 2024-01-30 | CLOSE | 4 | EA | 9 | 4 | 36 | 20831 | CLOSE | 2024-02-06 | 2024-02-06 | KW1-14688 | 4 | 2024-02-06 | APPR | 2024-02-06 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-11 | 9.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5640-60-V00-0030 | INSULATION SLEEVING, THERMAL, 3/8 X 72 INCHES | 52817 | 2024-01-29 | 2024-01-30 | CLOSE | 3 | EA | 9 | 2.6 | 23.4 | 20831 | CLOSE | 2024-02-06 | 2024-02-06 | KW1-14688 | 3 | 2024-02-06 | APPR | 2024-02-06 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-11 | 9.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4710-60-V00-0110 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 52816 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | EA | 1 | 17.5 | 17.5 | 20708 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14585 | 10 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-03-01 | COMP | 2024-02-05 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 9 | BX | 1 | 141.9 | 141.9 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 40 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4130-60-V00-0288 | TAPE, WRAP, INSULATION, 3 INCHES X 150 FEET | 52817 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | RO | 2 | 32 | 64 | 20831 | CLOSE | 2024-02-06 | 2024-02-06 | KW1-14688 | 2 | 2024-02-06 | APPR | 2024-02-06 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 8 | EA | 1 | 60 | 60 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 39 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4730-60-V00-0594 | C-CLAMP W/ RUBBER, GALVANIZED STEEL, 2 INCHES | 52816 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | EA | 4 | 9.4 | 37.6 | 20708 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14585 | 9 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-03-01 | COMP | 2024-02-05 | 4.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-60-V00-0505 | STUFFING TUBE (CABLE GLAND), PG16, POLYAMIDE, GRAY, 9 -14 MM | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 7 | EA | 4 | 3.2 | 12.8 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 38 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 4.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM ² | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 6 | RO | 1 | 163.2 | 163.2 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 37 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 52814 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | RO | 1 | 146.52 | 146.52 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 73 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5930-60-V00-0254 | SWITCH, DOUBLE POLE, METAL CLAD, 1 GANG, 32A | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 5 | EA | 1 | 70 | 70 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 36 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4130-60-V00-0353 | NUT, TUBE COUPLING, 3/8 INCH | 52812 | 2024-01-29 | 2024-01-29 | CLOSE | 2 | EA | 2 | 13.32 | 26.64 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 70 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5310-60-V00-0126 | NUT, TUBE COUPLING, 5/8 INCH | 52812 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | EA | 2 | 7.33 | 14.66 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 69 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4130-60-V00-0137 | MOUNTING BASE, AIR-CONDITIONER, POLYPROPYLENE, IVORY, 17 X 3 X 5.12 INCHES | 52813 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | PG | 1 | 68.6 | 68.6 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 71 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4120-60-V00-0018 | AIR CONDITIONER, SPLIT, INDOOR & OUTDOOR, 220-240V, 1 PH, 50/60 HZ, BTU 22000 | 52811 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | EA | 1 | 1098.9 | 1098.9 | 20723 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14732 | 3 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | CARRIER KUWAIT AIR CONDITIONING | 2024-04-01 |  |  |  |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4730-60-V00-0430 | ELBOW, PIPE, SOCKET X SOCKET, 45 DEGREE, CPVC, OFF WHITE, 25 MM | 52814 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | EA | 1 | 3.16 | 3.16 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 72 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4730-60-V00-0850 | ELBOW, CPVC, SOCKET X SOCKET, SCH 40, OFF-WHITE, 25 MM | 52817 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | EA | 1 | 3.6 | 3.6 | 20831 | CLOSE | 2024-02-06 | 2024-02-06 | KW1-14688 | 1 | 2024-02-06 | APPR | 2024-02-06 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-01-655-6053 | CONDUIT, METAL, FLEXIBLE, BLACK, 3/4 INCH X 100 FEET | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 4 | BX | 1 | 702.78 | 702.78 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 35 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 3 | RO | 1 | 242.58 | 242.58 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 34 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | RO | 1 | 21.11 | 21.11 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 33 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | EA | 1 | 16.83 | 16.83 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 32 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5940-60-V00-0003 | LUG, TERMINAL, FORK, INSULATED, BLUE, 16-14 AWG | 52820 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | BG | 1 | 53.63 | 53.63 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 25 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5620-60-V00-0004 | CONCRETE MASONRY UNIT, SOLID, 10 X 10 X 2 INCHES | 52815 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | EA | 4 | 91.74 | 366.96 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 74 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-20 | COMP | 2024-02-19 | 4.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-60-V00-0502 | ROD, GROUNDING, KIT, WITH CLAMP, 5/8 INCH X 4 FEET | 52819 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | KT | 1 | 145 | 145 | 20711 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14593 | 9 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-10 | COMP | 2024-02-06 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 30 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4210-60-V00-0189 | EXTINGUISHER, FIRE, ABC DRY CHEMICAL W/ WALL HOOK, 10 LBS | 52772 | 2024-01-28 | 2024-01-29 | CLOSE | 1 | EA | 1 | 277.22 | 277.22 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 67 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-21 |  |  |  |  | BU | BU table | January | 2024
54 | 2024-01-27 | 30 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6350-60-V00-0102 | ALARM, SMOKE, AUTOMATIC, PLASTIC | 52771 | 2024-01-28 | 2024-01-29 | CLOSE | 1 | EA | 3 | 28.97 | 86.91 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 66 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 3.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5640-60-V00-0012 | INSULATION BLANKET, THERMAL, GLASS WOOL, YELLOW, 4 FEET X 10 METER | 52801 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | RO | 1 | 214.45 | 214.45 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 6 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5620-60-V00-0015 | TILE, CEILING, LAMINATED, GYPSUM, 2 X 2 FEET | 52807 | 2024-01-29 | 2024-01-29 | CLOSE | 4 | EA | 60 | 37.46 | 299.68 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 12 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 8.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 10 | BX | 3 | 19.6 | 58.8 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 10 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-10 | 3.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5305-60-V00-0170 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATE, # 8 X 3 INCHES | 52807 | 2024-01-29 | 2024-01-29 | CLOSE | 3 | BX | 3 | 35.96 | 107.88 | 20743 | CLOSE | 2024-02-03 |  | KW1-14615 | 5 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-06 | 3.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 7210-60-V00-0059 | FLOOR COVERING, VINYL RESIN, 3 MM X 40 FEET | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 9 | RL | 1 | 716.1 | 716.1 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 9 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-15 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8040-00-273-8713 | ADHESIVE, FLOORING, WHITE, 1 GL | 52809 | 2024-01-29 | 2024-01-29 | CLOSE | 6 | GL | 4 | 185.7 | 742.8 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 30 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 4.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8010-60-V00-0130 | PAINT, LATEX, MATT, WHITE, 1 GL (3.2 TO 3.6 LT) | 52800 | 2024-01-29 | 2024-01-29 | CLOSE | 6 | CN | 8 | 42.62 | 340.96 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 10 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-06 | 8.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 52809 | 2024-01-29 | 2024-01-29 | CLOSE | 5 | EA | 10 | 13.9 | 139 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 29 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 10.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 52806 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | BX | 1 | 16.5 | 16.5 | 20781 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14652 | 4 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-03-15 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5350-60-V00-0010 | PAPER, ABRASIVE (SANDPAPER), 80 GRIT, 9 X 11 INCHES | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 8 | PG | 3 | 23 | 69 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 8 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-10 | 3.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8020-00-260-1302 | BRUSH, PAINT, BRISTLES, CHISELED, 2 INCHES | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 7 | EA | 10 | 15.2 | 152 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 7 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-10 | 10.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 52809 | 2024-01-29 | 2024-01-29 | CLOSE | 4 | EA | 8 | 29 | 232 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 28 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 8.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 6 | EA | 11 | 45.4 | 499.4 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 6 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-10 | 11.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8030-60-V00-0055 | SEALANT, SILICONE, WHITE, 300ml | 52809 | 2024-01-29 | 2024-01-29 | CLOSE | 3 | BX | 1 | 141.9 | 141.9 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 27 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8010-60-V00-0089 | PRIMER, COATING, WHITE, 4 - 5 LITERS | 52809 | 2024-01-29 | 2024-01-29 | CLOSE | 2 | CN | 3 | 41.3 | 123.9 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 26 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 3.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8010-60-V00-0013 | PAINT, ENAMEL, FLAT, WHITE, 3.20 LITER | 52800 | 2024-01-29 | 2024-01-29 | CLOSE | 5 | CN | 6 | 49.62 | 297.72 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 9 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-06 | 6.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 9515-60-V00-0016 | SHEET, METAL, ALUMINIUM, FLAT, 4 X 8 FEET X 1/16 INCH | 52807 | 2024-01-29 | 2024-01-29 | CLOSE | 2 | SH | 1 | 88.25 | 88.25 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 11 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5640-05-V00-0007 | CEMENT BOARD, WATER RESISTANT, 1/2 INCH X 4 X 8 FEET | 52810 | 2024-01-29 | 2024-01-29 | CLOSE | 3 | EA | 7 | 37.1 | 259.7 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 15 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 7.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5340-60-V00-0471 | CLOSER, DOOR, HYDRAULIC, ALUMINUM, NON-HOLD OPEN, 4 X 13 X 2-3/16 INCHES | 52807 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | EA | 1 | 599.4 | 599.4 | 20743 | CLOSE | 2024-02-03 |  | KW1-14615 | 3 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-06 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5340-60-V00-0220 | LATCH, SLIDING WINDOW, SPRING LOADED, PLASTIC, BLACK, 3 X 1-1/6 X 1-1/4 INCHES | 52810 | 2024-01-29 | 2024-01-29 | CLOSE | 2 | EA | 3 | 35.64 | 106.92 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 14 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-17 | 3.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5340-60-V01-0076 | LOCK, SLIDING WINDOW | 52981 | 2024-01-29 | 2024-01-31 | CLOSE | 1 | KT | 3 | 23.71 | 71.13 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 10 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-15 | 3.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5340-60-V00-0485 | HANDLE, SLIDING WINDOW, METAL, 5-3/4 INCHES | 52805 | 2024-01-29 | 2024-01-29 | CLOSE | 2 | EA | 3 | 19.65 | 58.95 | 20743 | CLOSE | 2024-02-03 |  | KW1-14615 | 4 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-06 | 3.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5640-60-V00-0044 | TAPE, SELF ADHESIVE, DRYWALL JOINT, FIBERGLASS, 2 INCHES X 300 FEET | 52805 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | EA | 1 | 18.65 | 18.65 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 10 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5340-60-V00-0481 | HINGE, DOOR, STAINLESS STEEL, 3 MM X 3-1/2 X 4 INCHES | 52802 | 2024-01-29 | 2024-01-29 | CLOSE | 2 | EA | 6 | 30.47 | 182.82 | 20780 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14649 | 8 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-15 | COMP | 2024-02-10 | 6.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8030-60-V00-0053 | FOAM, CONSTRUCTION, CREAM, 700ML | 52800 | 2024-01-29 | 2024-01-29 | CLOSE | 4 | EA | 5 | 19.5 | 97.5 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 8 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-06 | 5.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 5 | CN | 3 | 37 | 111 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 5 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-10 | 3.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6850-60-V00-0005 | ADDITIVE, MILDEWCIDE, LIQUID, 50-GRAM | 52803 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | EA | 7 | 35.8 | 250.6 | 20708 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14585 | 8 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-03-01 | COMP | 2024-02-07 | 7.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5305-60-V00-0169 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 3 INCHES | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 4 | BX | 1 | 30.4 | 30.4 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 4 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5320-60-V00-0014 | RIVET, BLIND, ALUMINUM, 2 INCHES | 52802 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | BX | 1 | 20.98 | 20.98 | 20780 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14649 | 7 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-15 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5320-60-V00-0005 | RIVET, BLIND, STAINLESS STEEL, SILVER, 6.4 MM | 52804 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | PG | 1 | 67.93 | 67.93 | 20780 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14649 | 9 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-15 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 3230-60-V00-0024 | BLADE, CIRCULAR SAW, WOOD CUTTING, 36 TOOTH, 7-1/4 INCHES | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 3 | EA | 1 | 52 | 52 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 3 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5510-60-V00-0003 | LUMBER, SOFTWOOD, DIMENSION, 2 X 4 INCHES X 13 FEET | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 2 | EA | 4 | 35.3 | 141.2 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 2 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-10 | 4.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8040-60-V00-0027 | TAPE, ADHESIVE, POLY FOAM, OPEN CELL, BLACK, 12.7 X 19 MM X 5 METERS | 52809 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | RO | 2 | 19.8 | 39.6 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 25 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 2.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5640-60-V00-0032 | WEATHER STRIP, DOOR, W/RUBBER BOTTOM SWEEP, 39" | 52800 | 2024-01-29 | 2024-01-29 | CLOSE | 3 | EA | 2 | 16.62 | 33.24 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 9 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5640-60-V00-0035 | WEATHER STRIP, DOOR, W/BRUSH, 2 X 36 INCHES | 52800 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | EA | 2 | 30.47 | 60.94 | 20766 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14752 | 9 | 2024-02-09 | APPR | 2024-02-09 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-02-20 | COMP | 2024-02-13 | 2.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5640-60-V00-0034 | WEATHER STRIP, FLUTE TOPPED ALUMINUM THRESHOLD, 3' (L) X 4-1/4" (W) | 52800 | 2024-01-29 | 2024-01-29 | CLOSE | 2 | EA | 1 | 49.45 | 49.45 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 8 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | BX | 2 | 29 | 58 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 1 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-10 | 2.00 |  | BU | BU table | January | 2024
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8010-60-V00-0245 | BRITISH GYPSUM GYPROC DRYWALL PRIMER 10L | 52810 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | CN | 1 | 76.19 | 76.19 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 13 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-12 | 1.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5650-60-V01-0003 | C-STUD RUNNER, GALVANIZED STEEL, 0.0366 X 1 1/4 X 3 INCHES X 12 FEET | 52874 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | EA | 12 | 6.17 | 74.04 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 32 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-14 | 12.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5305-60-V00-0022 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #10, 1-1/2 INCHES | 52875 | 2024-01-29 | 2024-01-30 | CLOSE | 7 | BX | 1 | 46.95 | 46.95 | 20743 | CLOSE | 2024-02-03 |  | KW1-14615 | 18 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-06 | 1.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5305-60-V00-0220 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, STEEL, #6 X 2 INCHES | 52875 | 2024-01-29 | 2024-01-30 | CLOSE | 6 | BX | 1 | 52.02 | 52.02 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 34 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5305-60-V00-0157 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, COARSE THREAD, #7 X 1-3/8 INCHES 1000pc/box | 52875 | 2024-01-29 | 2024-01-30 | CLOSE | 5 | bx | 2 | 22.74 | 45.48 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 33 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 7510-00-680-2395 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 52875 | 2024-01-29 | 2024-01-30 | CLOSE | 4 | EA | 8 | 12.67 | 101.36 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 32 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 8.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5680-60-V01-0002 | CORNER BEAD, STAINLESS STEEL, 25 MM X2.5 METER | 52875 | 2024-01-29 | 2024-01-30 | CLOSE | 3 | EA | 4 | 52.08 | 208.32 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 31 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-12 | 4.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8010-60-V00-0003 | PRIMER COATING, WOOD, ALKYD, WHITE, 16 LITER | 52872 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | CN | 1 | 162.1 | 162.1 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 88 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-20 | COMP | 2024-02-17 | 1.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8010-60-V00-0141 | PAINT, LATEX, SEMI MATT, BEIGE, 1 GL (3.6 L) | 52878 | 2024-01-29 | 2024-01-30 | CLOSE | 3 | CN | 5 | 55.4 | 277 | 20793 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14670 | 13 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-19 | COMP | 2024-02-11 | 5.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 52876 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | EA | 10 | 14.6 | 146 | 20778 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14641 | 9 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-04-04 | COMP | 2024-02-07 | 10.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 52878 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | EA | 6 | 12.54 | 75.24 | 20793 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14670 | 12 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-19 | COMP | 2024-02-10 | 6.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUAR | 52878 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | EA | 6 | 29.04 | 174.24 | 20793 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14670 | 11 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-19 | COMP | 2024-02-10 | 6.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 9515-60-V00-0016 | SHEET, METAL, ALUMINIUM, FLAT, 4 X 8 FEET X 1/16 INCH | 52875 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | EA | 8 | 86.1 | 688.8 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 30 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 8.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5530-00-129-7777 | PLYWOOD, CONSTRUCTION, EXTERIOR, 1/2 INCH X 8 X 4 FEET | 52872 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | EA | 3 | 36.3 | 108.9 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 89 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 3.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5340-60-V00-0492 | STOPPER, DOOR, DROP DOWN, METAL, 5" | 52876 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | EA | 1 | 19.47 | 19.47 | 20778 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14642 | 13 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8030-09-V01-0003 | SEALING COMPOUND, CAULK, ACRYLIC, WHITE, 5.5 OZ | 52875 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | EA | 4 | 49.83 | 199.32 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 29 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-03-11 | COMP | 2024-02-20 | 4.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5510-01-433-1244 | LUMBER, SOFTWOOD, 2 X 4 INCHES X 16 FEET | 52877 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | EA | 10 | 30.4 | 304 | 20831 | CLOSE | 2024-02-06 | 2024-02-06 | KW1-14688 | 21 | 2024-02-06 | APPR | 2024-02-06 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-11 | 10.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 40 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8010-60-V00-0241 | PRIMER COATING, PAINT, LATEX, INTERIOR, WATERBASED, WHITE, 16 LITERS | 52874 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | CN | 1 | 55.07 | 55.07 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 31 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 52954 | 2024-01-30 | 2024-01-31 | CLOSE | 4 | RO | 2 | 92.02 | 184.04 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 35 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 2.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 52953 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 20 | 27.06 | 541.2 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 22 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 20.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5930-60-V00-0243 | LIGHT-SWITCH, METAL, 2 WAY, 1 GANG, 250V, 10A | 52954 | 2024-01-30 | 2024-01-31 | CLOSE | 3 | EA | 6 | 33.25 | 199.5 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 34 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 6.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 4010-60-V00-0023 | CHAIN, WELDED, LINK, STEEL, 4 X 19 MM | 52956 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | MR | 50 | 6.51 | 325.5 | 20778 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14641 | 13 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-04-04 | COMP | 2024-02-07 | 50.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5306-60-V00-0120 | BOLT AND NUT, HEX w/ WASHER, 2 INCHES X 10 MM | 52958 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | PG | 3 | 82.5 | 247.5 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 96 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 3.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5306-60-V00-0173 | BOLT, U, ZINC PLATED SQUARE, 1/2 X 2 X 3 1/2 INCHES, 5 COMPONENTS | 52960 | 2024-01-30 | 2024-01-31 | CLOSE | 3 | EA | 50 | 5.29 | 264.5 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 8 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-03-11 | COMP | 2024-02-12 | 50.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5305-05-V00-0057 | SCREW, PIN SHACKLE, CLAMPING WINCH CABLE, 3/8 X 0.375 INCHES | 52960 | 2024-01-30 | 2024-01-31 | APPR | 2 | EA | 40 | 15.11 | 604.4 | [16 empty] | BU | BU table | January | 2024
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5306-60-V00-0174 | BOLT, EYE, UNWELDED, STAINLESS STEEL, 1/4 X 2-1/2 INCHES | 52960 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 50 | 1.94 | 97 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 6 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-03-11 | COMP | 2024-02-12 | 50.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 9520-60-V00-0005 | ANGLE, STRUCTURAL, STEEL, 4MM X 2 X 2 INCHES X 10 FEET | 52962 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 22 | 50.4 | 1108.8 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 9 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-12 | 22.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 6210-60-V00-0165 | LIGHT, LED FLOOD, W/EMERGENCY BATTERY,50W, 100-240 VAC, 50/60 Hz | 52953 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 2 | 631.95 | 1263.9 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 5 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 52959 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 50 | 4.3 | 215 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 11 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 50.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 4140-60-V00-0118 | FAN, VENTILATING, SQUARE, 220V, 12 INCHES | 52996 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 2 | 93.1 | 186.2 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 12 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5310-60-V00-0084 | WASHER, FLAT, STEEL, M8 | 52957 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 3 | 7.26 | 21.78 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 10 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 3.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0066 | CONDUIT, METAL, RIGID,EMT GALVANIZED STEEL, 1/2 INCH X 10 FEET | 52954 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 20 | 265 | 5300 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 24 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 20.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 6210-60-V00-0094 | FIXTURE, LIGHTING, LED, RETROFIT, POLYCARBONATE, PURE WHITE, 40W | 52954 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 20 | 242.35 | 4847 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 23 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 20.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 6145-60-V00-0098 | WIRE, ELECTRICAL, WHITE, 8 CORE, 18 AWG | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 10 | SL | 1 | 761.3 | 761.3 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 19 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 6685-60-V00-0166 | GUARD, THERMOSTAT, PLASTIC, CLEAR, 6-3/8 X 3-1/2 X 3-1/4 INCHES | 52997 | 2024-01-30 | 2024-02-01 | CLOSE | 9 | EA | 2 | 24.72 | 49.44 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 9 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 2.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 6685-60-V00-0163 | THERMOSTAT, DIGITAL, NON-PROGRAMMABLE | 52997 | 2024-01-30 | 2024-02-01 | CLOSE | 8 | EA | 2 | 91.07 | 182.14 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 8 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 2.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5306-60-V00-0001 | BOLT, CONCRETE ANCHOR, w/ NUT & WASHER, M10 X 3 INCHES | 52967 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | BX | 3 | 37 | 111 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 13 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 3.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0435 | PAD, ANTI VIBRATION, RUBBER/CORK, 4 X 4 X 1 INCHES | 53000 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 7 | 15.5 | 108.5 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 15 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 7.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 9520-60-V00-0005 | ANGLE, STRUCTURAL, STEEL, 4MM X 2 X 2 INCHES X 10 FEET | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 9 | EA | 5 | 50.4 | 252 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 18 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-14 | 5.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8010-60-V00-0143 | PAINT, ENAMEL, GLOSS, DESERT SAND, 1 GL (3.2 to 3.6 LITER) | 52966 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | CN | 1 | 49.1 | 49.1 | 20793 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14670 | 18 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-19 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8010-60-V00-0124 | PRIMER, RED OXIDE, OIL BASED, RED, 1 GL | 52968 | 2024-01-30 | 2024-01-31 | CLOSE | 3 | CN | 1 | 41.4 | 41.4 | 20797 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14677 | 3 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8020-00-205-6500 | BRUSH, PAINT, BRISTLES | 52969 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 4 | 21.8 | 87.2 | 20793 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14670 | 19 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-19 | COMP | 2024-02-10 | 4.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 52968 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 4 | 12.4 | 49.6 | 20797 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14677 | 2 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-10 | 4.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8020-60-V00-0032 | TRAY, PAINT ROLLER, METAL, 13 INCHES, 3 QT. | 52968 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 3 | 10 | 30 | 20797 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14677 | 1 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-12 | 3.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-01-655-6053 | CONDUIT, METAL, FLEXIBLE, BLACK, 3/4 INCH X 100 FEET | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 8 | RO | 1 | 702.78 | 702.78 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 17 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0042 | BOX CONNECTOR, ELECTRICAL, STRAIGHT, LIQUID TIGHT CONDUIT, NICKEL PLATED BRASS, 1/2 INCH | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 7 | EA | 16 | 24 | 384 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 16 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 16.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 6 | RO | 1 | 242.58 | 242.58 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 15 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 6145-60-V00-0149 | WIRE, ELECTRICAL, RED, 1 CORE, 1.5 MM ² | 52997 | 2024-01-30 | 2024-02-01 | CLOSE | 7 | RO | 1 | 48.14 | 48.14 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 7 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 6145-60-V00-0050 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 1.5 MM ² | 52997 | 2024-01-30 | 2024-02-01 | CLOSE | 6 | RO | 1 | 41.14 | 41.14 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 6 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5940-60-V00-0016 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 16 MM ² | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 5 | EA | 10 | 5 | 50 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 14 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 10.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5935-60-V00-0225 | CONNECTOR, TWIST ON SPLICE, STRAIGHT, YELLOW, 18-12 AWG, 600V | 52998 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | PG | 1 | 132.83 | 132.83 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 38 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 | COMP | 2024-02-28 | 1.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0237 | JUNCTION BOX, w/ KNOCKOUT, GALVANIZED STEEL, SQUARE, 4 INCHES | 52997 | 2024-01-30 | 2024-02-01 | CLOSE | 5 | EA | 4 | 5.27 | 21.08 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 5 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-08 07:00 | COMP | 2024-02-13 | 4.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0629 | COVER, JUNCTION BOX, STEEL, SQUARE, FLAT, 0.063 X 4 X 4 INCHES | 52997 | 2024-01-30 | 2024-02-01 | CLOSE | 4 | EA | 4 | 4.29 | 17.16 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 4 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 4.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5305-60-V00-0001 | SCREW, SELF DRILLING, HEX WASHER HEAD, STEEL, 5/16 X 1 INCH | 52965 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | BX | 2 | 19.14 | 38.28 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 12 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5305-60-V00-0206 | SCREW, SELF DRILLING, HEX HEAD, METAL WASHER, #14 X 1 INCH | 52964 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | PG | 1 | 4.72 | 4.72 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 97 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5305-05-V01-0080 | SCREW, SELF DRILLING, HEX, WASHER HEAD, 1/4 X 3 INCHES | 52995 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | PG | 2 | 3 | 6 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 11 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0394 | STRAP, TIE DOWN, ELECTRICAL COMPONENTS, NYLON, BLACK OR WHITE, 6 INCHES | 52998 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | PG | 2 | 5.28 | 10.56 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 37 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 2.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0395 | STRAP, TIE DOWN, WHITE, 12 INCHES | 52999 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | PG | 2 | 13.66 | 27.32 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 13 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-00-178-1217 | CONDUIT, METAL, RIGID, STEEL, 3/4 INCH X 10 FEET | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 4 | EA | 10 | 13.6 | 136 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 13 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 10.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0460 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, GALVANIZED STEEL, ¾ INCH | 52997 | 2024-01-30 | 2024-02-01 | CLOSE | 3 | EA | 40 | 2.11 | 84.4 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 3 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 40.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5920-60-V00-0059 | FUSE, CARTRIDGE, 250V,2A | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 3 | EA | 6 | 9.79 | 58.74 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 12 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 6.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5940-60-V00-0067 | TERMINAL JUNCTION BLOCK, SECTIONAL (FUSE TERMINAL), SCREW CLAMP, GRAY, 800V, 6.3A | 52997 | 2024-01-30 | 2024-02-01 | CLOSE | 2 | EA | 4 | 1.63 | 6.52 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 2 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 4.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5920-60-V00-0031 | FUSE, CARTRIDGE, 240 V, 3 A | 53002 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 4 | 0.73 | 2.92 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 15 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 4.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5970-01-013-9369 | TAPE, INSULATION, ELECTRICAL, RED, 3/4 X 792 INCHES | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 2 | RO | 1 | 10.1 | 10.1 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 11 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 1 | EA | 1 | 16.83 | 16.83 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 10 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5940-60-V00-0015 | TERMINAL, LUG, FORK, INSULATED, RED, 22-16 AWG | 53002 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | PG | 1 | 99 | 99 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 14 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5940-60-V00-0014 | TERMINAL, LUG, FORK, I | 52997 | 2024-01-30 | 2024-02-01 | CLOSE | 1 | PG | 1 | 99.82 | 99.82 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 1 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5110-60-V00-0077 | KNIFE, PUTTY, 3 INCHES | 52744 | 2024-01-27 | 2024-01-29 | CLOSE | 4 | EA | 4 | 11.38 | 45.52 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 63 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 4.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5640-60-V00-0048 | DRYWALL SHEET, (GYPSUM BOARD), 4 X 8 FEET X 1/2 INCH | 52741 | 2024-01-27 | 2024-01-29 | CLOSE | 4 | EA | 30 | 18.85 | 565.5 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 59 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 30.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 52738 | 2024-01-27 | 2024-01-29 | CLOSE | 2 | EA | 72 | 44.69 | 3217.68 | 20743 | CLOSE | 2024-02-03 |  | KW1-14615 | 2 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-06 | 72.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5640-60-V00-0045 | TAPE, JOINT, WALLBOARD, SELF-ADHESIVE, 50 MM X 90 METERS | 52741 | 2024-01-27 | 2024-01-29 | CLOSE | 3 | EA | 4 | 11.7 | 46.8 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 58 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 4.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8010-60-V00-0141 | PAINT, LATEX, SEMI MATT, BEIGE, 1 GL (3.6 L) | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 10 | CN | 43 | 55.4 | 2382.2 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 18 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-14 | 43.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 52746 | 2024-01-27 | 2024-01-29 | CLOSE | 5 | CN | 4 | 37 | 148 | 20778 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14642 | 8 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-07 | 4.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | EA | 10 | 29 | 290 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 9 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 10.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8020-00-682-6489 | COVER, PAINT ROLLER, ACRYLIC, 0.375 X 7 INCHES | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 9 | EA | 10 | 14.2 | 142 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 17 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 10.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 8 | EA | 6 | 13.9 | 83.4 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 16 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 6.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 52745 | 2024-01-27 | 2024-01-29 | CLOSE | 2 | EA | 10 | 14.6 | 146 | 20708 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14585 | 4 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-03-01 | COMP | 2024-02-05 | 10.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8010-00-286-7737 | PAINT, ENAMEL, GLOSS, BROWN, 1 GL | 52748 | 2024-01-27 | 2024-01-29 | CLOSE | 3 | CN | 4 | 29.02 | 116.08 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 24 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-17 | 4.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GALLON | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 7 | GL | 2 | 228.6 | 457.2 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 15 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 2.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8010-60-V00-0146 | PRIMER COATING, WOOD, WHITE, 5 GL | 52744 | 2024-01-27 | 2024-01-29 | CLOSE | 3 | CN | 1 | 120.27 | 120.27 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 62 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-20 | COMP | 2024-02-17 | 1.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 6850-60-V00-0005 | ADDITIVE, MILDEWCIDE, LIQUID, 50-GRAM | 52740 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | EA | 43 | 32.18 | 1383.74 | 20708 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14585 | 2 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-03-01 | COMP | 2024-02-07 | 6.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 52742 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | BX | 1 | 16.5 | 16.5 | 20781 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14652 | 2 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-03-15 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8105-01-517-1363 | BAG, PLASTIC, CLEAR, 24 X 24 INCHES, 10 GALLONS | 52739 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | BX | 2 | 93.29 | 186.58 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 4 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8340-00-068-7908 | DROP CLOTH, PAINTER'S, 9 FT X 12 FT | 52738 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | EA | 5 | 28.28 | 141.4 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 1 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 5.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 7510-00-266-6710 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 52745 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | EA | 15 | 8 | 120 | 20708 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14585 | 3 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-03-01 | COMP | 2024-02-05 | 15.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5305-60-V00-0157 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, COARSE THREAD, #7 X 1-3/8 INCHES 1000pc/box | 52744 | 2024-01-27 | 2024-01-29 | CLOSE | 2 | BX | 5 | 22.75 | 113.75 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 61 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 5.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5350-60-V00-0010 | PAPER, ABRASIVE (SANDPAPER), 80 GRIT, 9 X 11 INCHES | 52746 | 2024-01-27 | 2024-01-29 | CLOSE | 4 | PK | 5 | 23 | 115 | 20778 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14642 | 7 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-07 | 5.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5350-60-V00-0011 | PAPER, ABRASIVE (SANDPAPER), 220 GRIT, 9 X 11 INCHES | 52746 | 2024-01-27 | 2024-01-29 | CLOSE | 3 | SH | 30 | 3.2 | 96 | 20778 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14642 | 6 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-07 | 30.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8010-60-V00-0241 | PRIMER COATING, PAINT, LATEX, INTERIOR, WATERBASED, WHITE, 16 LITERS | 52743 | 2024-01-27 | 2024-01-29 | CLOSE | 2 | PA | 1 | 55.1 | 55.1 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 21 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 6 | BX | 4 | 142 | 568 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 14 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 4.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8010-60-V00-0028 | PAINT, ENAMEL, GLOSS, DESERT SAND, 3.6 LITER | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 5 | GAL | 1 | 39.6 | 39.6 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 13 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8030-60-V00-0052 | PUTTY, ALL PURPOSE, LIGHT GRAY, 3.43 KG | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 4 | CAN | 2 | 124 | 248 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 12 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5130-60-V00-0125 | DISK, ABRASIVE, SANDING, HOOK AND LOOP, 220 GRIT, 8 HOLE, 5 INCHES-DUSTLESS HOOK AND LOOP SANDING DISC | 52744 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | PG | 2 | 44.86 | 89.72 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 60 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5120-60-V00-0283 | ROLLER, HAND (BRAYER), SOFT RUBBER, BROWN, 2 INCHES | 52748 | 2024-01-27 | 2024-01-29 | CLOSE | 2 | EA | 2 | 44.55 | 89.1 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 23 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 | COMP | 2024-03-06 | 2.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 9540-60-V00-0001 | STUD, STRUCTURAL, DRYWALL, FRAMING, GALVANIZED STEEL, 20 GUAGE, 4 X 1-1/4 INCHES | 52748 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | EA | 10 | 14.19 | 141.9 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 22 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 | COMP | 2024-02-17 | 10.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5305-05-V00-0025 | SCREW, PHILLIPS, TRUSS HEAD, STAINLESS STEEL, 10 X 3/4 INCHES 100pc / bx | 52743 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | BX | 4 | 13 | 52 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 20 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-14 | 4.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5130-60-V00-0122 | CUTTING WHEEL, METAL, ALUMINUM OXIDE, 4X0.05X5/8 INCHES | 52741 | 2024-01-27 | 2024-01-29 | CLOSE | 2 | EA | 4 | 19.5 | 78 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 57 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-21 | COMP | 2024-02-14 | 4.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5110-60-V00-0028 | CHISEL SET, WOOD, STEEL, 9 PIECES | 52741 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | set | 1 | 196.65 | 196.65 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 56 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8030-01-075-1156 | CAULKING COMPOUND, CARTRIDGE, WHITE, 10 OZ | 52782 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | EA | 24 | 14.85 | 356.4 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 5 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-03-11 | COMP | 2024-02-24 | 24.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5110-01-273-5951 | SAW, JAB, 6 INCHES | 52746 | 2024-01-27 | 2024-01-29 | CLOSE | 2 | ea | 2 | 35.1 | 70.2 | 20778 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14641 | 4 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-04-04 | COMP | 2024-02-07 | 2.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 3 | EA | 4 | 12.4 | 49.6 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 11 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 4.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8020-01-317-2854 | COVER, PAINT ROLLER, POLYESTER FIBER, 3 INCHES | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 2 | EA | 8 | 14.2 | 113.6 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 10 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 8.00 |  | BU | BU table | January | 2024
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5120-60-V00-0295 | DISPENSER, SEALANT (CAULKING GUN), CAST STEEL, 12.8 OZ | 52746 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | EA | 2 | 164 | 328 | 20778 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14642 | 5 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-07 | 2.00 |  | BU | BU table | January | 2024
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 5975-60-V00-0083 | CONDUIT, NONMETALLIC, HEAVY GAUGE, UPVC, WHITE, 20 MM X 3M | 52781 | 2024-01-28 | 2024-01-29 | CLOSE | 4 | EA | 2 | 9.9 | 19.8 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 23 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-12 | 2.00 |  | BU | BU table | December | 2023
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 5975-60-V00-0276 | JUNCTION BOX, THREE WAY, RIGID PVC, WHITE, 20 MM | 52777 | 2024-01-28 | 2024-01-29 | CLOSE | 2 | EA | 2 | 9.9 | 19.8 | 20789 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14665 | 3 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-30 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | December | 2023
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 52781 | 2024-01-28 | 2024-01-29 | CLOSE | 3 | EA | 2 | 146.47 | 292.94 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 22 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 2.00 |  | BU | BU table | December | 2023
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 52779 | 2024-01-28 | 2024-01-29 | CLOSE | 1 | RO | 1 | 145.2 | 145.2 | 20779 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14645 | 3 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | December | 2023
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 5975-60-V00-0269 | COVER, JUNCTION BOX, CIRCULAR, PLASTIC, WHITE, 20 MM | 52776 | 2024-01-28 | 2024-01-29 | CLOSE | 1 | EA | 4 | 5.77 | 23.08 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 68 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 4.00 |  | BU | BU table | December | 2023
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 5975-60-V00-0573 | TEE, ELECTRICAL CONDUIT, INSPECTION, PVC, WHITE, 20 MM | 52777 | 2024-01-28 | 2024-01-29 | CLOSE | 1 | EA | 4 | 11.55 | 46.2 | 20789 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14666 | 6 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-10 | 4.00 |  | BU | BU table | December | 2023
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 4730-60-V00-0045 | .ADAPTER, ELECTRICAL CONDUIT, w/BUSH, FEMALE, PVC, WHITE, 20 MM | 52780 | 2024-01-28 | 2024-01-29 | CLOSE | 2 | EA | 4 | 6.2 | 24.8 | 20789 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14666 | 7 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-10 | 4.00 |  | BU | BU table | December | 2023
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 5975-60-V00-0377 | CLAMP, ELECTRICAL, CONDUIT, PVC, WHITE, 20 MM | 52780 | 2024-01-28 | 2024-01-29 | CLOSE | 1 | EA | 10 | 3.63 | 36.3 | 20789 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14665 | 4 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-30 | COMP | 2024-02-11 | 10.00 |  | BU | BU table | December | 2023
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 5975-60-V00-0372 | COUPLING, ELECTRICAL CONDUIT, PVC, WHITE, 20 MM | 52781 | 2024-01-28 | 2024-01-29 | CLOSE | 2 | EA | 6 | 4.54 | 27.24 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 21 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 6.00 |  | BU | BU table | December | 2023
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 52781 | 2024-01-28 | 2024-01-29 | CLOSE | 1 | EA | 1 | 3.5 | 3.5 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 20 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | December | 2023
57 | 2023-12-28 | 180 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 52783 | 2024-01-28 | 2024-01-29 | CLOSE | 1 | EA | 5 | 3.5 | 17.5 | 20779 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14645 | 4 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-07 | 5.00 |  | BU | BU table | December | 2023
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 5305-60-V00-0178 | SCREW, PHILLIPS, FLAT HEAD, STAINLESS STEEL, #8 X 3/4 INCHES | 52778 | 2024-01-28 | 2024-01-29 | CLOSE | 1 | BX | 1 | 12.68 | 12.68 | 20780 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14649 | 3 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-15 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | December | 2023
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 6210-60-V00-0099 | FIXTURE, LIGHTING, LED, FLOOD, 5000K, 50/60HZ, 90W | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 10 | EA | 2 | 656.37 | 1312.74 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 30 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 2.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 9 | EA | 2 | 260.02 | 520.04 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 29 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 2.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 52940 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 5 | 27.06 | 135.3 | 20793 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14670 | 16 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-19 | COMP | 2024-02-10 | 5.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 8 | PK | 2 | 28.9 | 57.8 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 28 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 2.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5975-60-V00-0461 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, GALVANIZED STEEL, ½ INCH | 52941 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 50 | 1.58 | 79 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 6 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 50.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5975-60-V00-0066 | CONDUIT, METAL, RIGID, GALVANIZED STEEL, 1/2 INCH X 10 FEET | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 7 | EA | 15 | 265 | 3975 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 27 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 15.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 6 | BX | 1 | 92.02 | 92.02 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 26 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 1.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5975-60-V00-0335 | STRAP, TIE DOWN, ELECTRICAL, COMPON (CABLE TIE), BLACK, 50 LBS, 4.6 MM X 11.02 INCHES | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 5 | PK | 1 | 15 | 15 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 25 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 1.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5970-60-V00-0043 | TAPE, INSULATION, ELECTRICAL, SUPER 33 +,VINYL, BLACK, 3/4" X 66' | 52940 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 1 | 14.19 | 14.19 | 20793 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14670 | 15 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-19 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 52942 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 50 | 4.3 | 215 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 8 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 50.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5975-60-V00-0043 | COUPLING, ELECTRICAL, CONDUIT, COMBINATION, EMT TO FMC, DIE CAST ZINC, 1/2 INCH | 52944 | 2024-01-30 | 2024-01-31 | CLOSE | 4 | EA | 10 | 9.24 | 92.4 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 4 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 10.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5975-60-V00-0487 | COUPLING, ELECTRICAL CONDUIT, w/ SCREW, Â½ INCH | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 4 | EA | 15 | 5 | 75 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 5 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-10 | 15.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 6145-60-V00-0158 | WIRE, ELECTRICAL, RED, 1 CORE, 2.5 MM² | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 3 | RO | 1 | 57 | 57 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 20 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 1.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 6145-60-V00-0151 | WIRE, ELECTRICAL, BLACK 1 CORE, 2.5 MM² | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | RO | 1 | 64.92 | 64.92 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 19 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 1.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 52942 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | RO | 1 | 65.01 | 65.01 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 7 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5305-60-V00-0001 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 52941 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | BX | 1 | 19.14 | 19.14 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 5 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 6110-60-V00-0166 | SENSOR, PHOTOCELL CONTROL, 15A, 50/60 HZ | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 1 | 74.8 | 74.8 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 18 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 1.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5925-60-V00-0128 | CIRCUIT BREAKER, MCB, 1 POLE, 240/415V, 10A | 52944 | 2024-01-30 | 2024-01-31 | CLOSE | 3 | EA | 1 | 16 | 16 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 21 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5110-60-V00-0022 | CUTTER, TUBE, STEEL, 1/4 TO 7/8 X 4-1/2 INCHES | 52944 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 2 | 22.63 | 45.26 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 3 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-03-11 | COMP | 2024-02-12 | 2.00 |  | BU | BU table | January | 2024
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5110-60-V00-0045 | CUTTER, WIRE, HAND, SHEAR CUT, STEEL, BLACK VINYL COVERED, 7 INCHES | 52944 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 2 | 36.3 | 72.6 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 2 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-03-11 | COMP | 2024-02-19 | 2.00 |  | BU | BU table | January | 2024
59 | 2024-02-07 | 30 | BU24-0147 | T-2028 New Cipher Lock | 9522604 | 5340-60-V00-0172 | LOCK SET, RIM, PUSHBUTTON, RHR, 5 INCHES | 53597 | 2024-02-07 | 2024-02-10 | CLOSE | 2 | EA | 1 | 656.4 | 656.4 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 47 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | February | 2024
59 | 2024-02-07 | 30 | BU24-0147 | T-2028 New Cipher Lock | 9522604 | 5340-60-V00-0169 | LOCK SET, MORTISE, RIM EXIT DEVICE, KEY OUTSIDE UNLOCKS/LOCKS TRIM | 53597 | 2024-02-07 | 2024-02-10 | CLOSE | 1 | EA | 1 | 2227.5 | 2227.5 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 46 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5307-60-V00-0021 | STUD, DRYWALL FRAME, U-CHANNEL, GALVANIZED STEEL, 3 X 1-1/4 INCHES X 12 FEET | 53647 | 2024-02-08 | 2024-02-10 | CLOSE | 6 | EA | 600 | 6.34 | 3804 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 26 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 600.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5650-60-V01-0003 | C-STUD RUNNER, STEEL, 0.0366IN X 1¼" X 3" X 12FT | 53647 | 2024-02-08 | 2024-02-10 | CLOSE | 5 | EA | 100 | 6.27 | 627 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 25 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 100.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5305-05-V00-0025 | SCREW, PHILLIPS, TRUSS HEAD, STAINLESS STEEL, 10 X 3/4 INCHES 100pc / bx | 53647 | 2024-02-08 | 2024-02-10 | CLOSE | 4 | PK | 35 | 21.15 | 740.25 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 24 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 35.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5305-60-V00-0022 | MATERIAL: STAINLESS STEELSIZE: #10SCREW LENGTH: 1-1/2 INCHESHEAD STYLE: TRUSS HEADDRIVE TYPE: PHILLIPSUNIT OF MEASURE: PACKAGE (CONTAINS 100 EACH) | 53650 | 2024-02-08 | 2024-02-10 | CLOSE | 9 | PG | 18 | 44.9 | 808.2 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 38 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 18.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5305-60-V00-0220 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, STEEL, #6 X 2 INCHES | 53645 | 2024-02-08 | 2024-02-10 | CLOSE | 7 | BX | 2 | 51.99 | 103.98 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 28 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-25 | 2.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5640-60-V00-0048 | DRYWALL SHEET, (GYPSUM BOARD), 4 X 8 FEET X 1/2 INCH | 53644 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 190 | 19.14 | 3636.6 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 29 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 190.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5305-60-V00-0157 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, COARSE THREAD, #7 X 1-3/8 INCHES 1000pc/box | 53645 | 2024-02-08 | 2024-02-10 | CLOSE | 6 | BX | 12 | 23.1 | 277.2 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 27 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-25 | 12.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5640-60-V00-0044 | TAPE, SELF ADHESIVE, DRYWALL JOINT, FIBERGLASS, 2 INCHES X 300 FEET | 53645 | 2024-02-08 | 2024-02-10 | CLOSE | 5 | EA | 6 | 18.48 | 110.88 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 43 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 6.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 53650 | 2024-02-08 | 2024-02-10 | CLOSE | 8 | CN | 8 | 37 | 296 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 37 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 8.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 7510-00-680-2395 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 53645 | 2024-02-08 | 2024-02-10 | CLOSE | 4 | ROLL | 6 | 12.69 | 76.14 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 26 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-25 | 6.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5130-60-V00-0125 | DISK, ABRASIVE, SANDING, HOOK AND LOOP, 220 GRIT, 8 HOLE, 5 INCHES-DUSTLESS HOOK AND LOOP SANDING DISC | 53648 | 2024-02-08 | 2024-02-10 | CLOSE | 5 | PG | 5 | 45.54 | 227.7 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 40 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 5.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5680-60-V01-0002 | CORNER BEAD, STAINLESS STEEL, 25 MM X2.5 METER | 53645 | 2024-02-08 | 2024-02-10 | CLOSE | 3 | EA | 70 | 108.9 | 7623 | 21348 | CLOSE | 2024-02-22 | 2024-02-16 | KW1-15106 | 3 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-10 | COMP | 2024-02-26 | 70.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5350-60-V00-0007 | PAPER, ABRASIVE (SANDPAPER), 120 GRIT, 9 X 11 INCHES | 53650 | 2024-02-08 | 2024-02-10 | CLOSE | 7 | EA | 40 | 4.2 | 168 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 36 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 40.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8010-60-V00-0241 | PRIMER COATING, PAINT, LATEX, INTERIOR, WATERBASED, WHITE, 16 LITERS | 53647 | 2024-02-08 | 2024-02-10 | CLOSE | 3 | CN | 1 | 55.08 | 55.08 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 23 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-07 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8010-60-V00-0050 | PAINT, ENAMEL, GLOSS, DARK BROWN, 3.2 AND 3.6 LITER( require vendor visit to match wall sample) | 53648 | 2024-02-08 | 2024-02-10 | CLOSE | 4 | CN | 8 | 39.6 | 316.8 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 25 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 |  |  |  | Need sample approval | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8010-60-V00-0146 | PRIMER COATING, WOOD, WHITE, 5 GL | 53648 | 2024-02-08 | 2024-02-10 | CLOSE | 3 | CN | 1 | 122.1 | 122.1 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 24 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-28 | 1.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8010-60-V00-0006 | PAINT, LATEX, MATT, OFF-WHITE, 3.2 LITER | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 10 | CN | 45 | 44 | 1980 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 28 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8010-60-V00-0095 | PRIMER, COATING, RED OXIDE, LIQUID, 3.78 TO 4 LITERS | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 9 | CN | 2 | 41.3 | 82.6 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 27 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8010-60-V00-0010 | PAINT, LATEX, GLOSS, WHITE, 3.6 LITERS | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 8 | GAL | 3 | 44.55 | 133.65 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 26 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 53649 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 12 | 14.6 | 175.2 | 21181 | CLOSE | 2024-02-17 |  | KW1-14961 | 4 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-03-23 | COMP | 2024-02-20 | 12.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 7 | EA | 4 | 12.4 | 49.6 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 25 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8020-60-V00-0045 | COVER, PAINT ROLLER, 3 INCHES | 53653 | 2024-02-08 | 2024-02-10 | CLOSE | 6 | EA | 10 | 8.2 | 82 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 12 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-31 | COMP | 2024-03-09 | 10.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 6 | EA | 15 | 13.9 | 208.5 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 24 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 5 | EA | 8 | 29 | 232 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 23 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 53646 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | BX | 3 | 16.5 | 49.5 | 21187 | CLOSE | 2024-02-17 |  | KW1-14969 | 5 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-03-23 | COMP | 2024-02-19 | 3.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5510-60-V00-0022 | BOARD, MDF, INTERIOR, BROWN, 12 X 1220 X 2440 MM | 53647 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | EA | 18 | 32.67 | 588.06 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 22 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 18.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GL | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 4 | GL | 5 | 220.5 | 1102.5 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 22 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5340-00-116-2375 | CLOSER, HYDRAULIC DOOR, LIGHT DUTY | 53650 | 2024-02-08 | 2024-02-10 | CLOSE | 6 | EA | 10 | 97.35 | 973.5 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 35 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 10.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5340-60-V00-0492 | STOPPER, DOOR, DROP DOWN, METAL, 5" | 53650 | 2024-02-08 | 2024-02-10 | CLOSE | 5 | EA | 10 | 18 | 180 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 34 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 10.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5340-60-V00-0141 | DOORSTOP, FLOOR MOUNT, BRASS, 1-3/4 X 1-1/4 INCHES | 53648 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | EA | 10 | 9.57 | 95.7 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 23 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-25 | 10.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5640-60-V00-0035 | WEATHER STRIP, DOOR, W/BRUSH, 2 X 36 INCHES | 53643 | 2024-02-08 | 2024-02-10 | CLOSE | 3 | EA | 10 | 30.19 | 301.9 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 29 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-25 | 10.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8030-01-075-1156 | CAULKING COMPOUND, CARTRIDGE, WHITE, 10 OZ | 53645 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | EA | 24 | 14.85 | 356.4 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 42 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 24.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5510-01-433-1244 | LUMBER, SOFTWOOD, 2 X 4 INCHES X 16 FEET | 53650 | 2024-02-08 | 2024-02-10 | CLOSE | 4 | EA | 35 | 30.4 | 1064 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 33 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 35.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8030-60-V00-0050 | PUTTY, WOOD FILLER, MEDIUM OAK, 250 ML | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 3 | CN | 4 | 85.19 | 340.76 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 21 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 | COMP | 2024-02-22 | 4.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5120-60-V00-0080 | BIT, SCREWDRIVER, PH2, STEEL, 50 MM | 53645 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | BX | 2 | 204.6 | 409.2 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 41 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 2.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5130-60-V00-0123 | WHEEL, ABRASIVE, ALUMINUM OXIDE, 12,225 RPM, 5 X 1/16 X 7/8 INCHES | 53650 | 2024-02-08 | 2024-02-10 | CLOSE | 3 | EA | 10 | 14.8 | 148 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 32 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-14 | COMP | 2024-02-19 | 10.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5335-60-V00-0001 | WIRE MESH, GALVANIZED STEEL, 21 GAGE, 4 X 50 FEET | 53652 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | RO | 7 | 41.9 | 293.3 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 28 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 7.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5660-60-V00-0033 | FENCE, GALVANIZED STEEL, CHAIN LINK MESH, 50 x 10 FEET (1 rool 50ft x 10ft) | 53643 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | RO | 3 | 422.4 | 1267.2 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 45 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-07 | COMP | 2024-02-19 | 3.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5340-01-306-9992 | LOCK SET, MORTISE, PUSH BUTTON, MECHANICAL, w/KNOB, SATIN CHROME, 2-3/4 INCHES, FACTORY LEFT; FIELD REVERSIBLE | 53650 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | EA | 5 | 607.7 | 3038.5 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 31 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-21 |  |  |  |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5340-60-V00-0429 | LOCK SET, MECHANICAL, PUSH BUTTON, RIGHT HAND, 2-3/4 INCHES | 53648 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 5 | 602.6 | 3013 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 39 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 5.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8010-60-V00-0124 | PRIMER, RED OXIDE, OIL BASED, RED, 1 GL | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | CN | 2 | 41.4 | 82.8 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 20 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024
60 | 2024-02-07 | 90 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 4710-05-V00-0007 | TUBE, RECTANGULAR, STEEL, 3 X 1-1/2 X 1/8 INCHES x 20ft | 53677 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 28 | 70 | 1960 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 18 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-21 | COMP | 2024-03-02 | 28.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5306-60-V00-0100 | BOLT, CARRIAGE w/HEX NUT, STEEL, ZINC PLATED, 10M X 4-1/2 INCHES | 53653 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 300 | 3.14 | 942 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 7 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-25 | 300.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5315-00-060-9315 | STAPLE, STEEL, 1/2 INCH | 53653 | 2024-02-08 | 2024-02-10 | CLOSE | 5 | BX | 5 | 11.29 | 56.45 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 11 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-31 | COMP | 2024-03-09 | 5.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5120-00-889-1796 | TACKER, GUN, STAPLE, 1/2 INCH | 53653 | 2024-02-08 | 2024-02-10 | CLOSE | 4 | EA | 1 | 25.66 | 25.66 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 10 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-31 | COMP | 2024-03-09 | 1.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5133-60-V00-0003 | DRILL, TWIST, (BIT), HIGH SPEED STEEL, 8 X 117 MM | 53653 | 2024-02-08 | 2024-02-10 | CLOSE | 3 | EA | 10 | 18.15 | 181.5 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 9 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-21 | COMP | 2024-02-25 | 10.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8030-60-V00-0052 | PUTTY, ALL PURPOSE, LIGHT GRAY, 3.43 KG | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 2 | 123.8 | 495.2 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 19 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5305-60-V00-0167 | SCREW, HEX WASHER HEAD, STEEL, #14 X 3 INCHES | 53652 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | BX | 3 | 37.9 | 113.7 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 27 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 3.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 9520-60-V00-0044 | ANGLE, STRUCTURAL, GALVANIZED STEEL, 1-1/2 X 1-1/2 X 1/8 INCH X 20 FEET | 53647 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 25 | 118.8 | 2970 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 21 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 25.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5130-60-V00-0127 | DISK, ABRASIVE, METAL CUTTING, ALUMINUM OXIDE, 1 X 0.10 X 12 INCHES | 53650 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | ea | 4 | 8 | 32 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 30 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 4.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 4240-60-V00-0043 | MASK, N95, PARTICULATE RESPIRATOR, 10EA/BOX, WHITE | 53653 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | BX | 2 | 81.76 | 163.52 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 8 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-21 | COMP | 2024-02-25 | 2.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5133-60-V00-0070 | BIT, SPADE, WOOD BORING, STEEL, 8 PIECES | 53643 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | set | 1 | 82.17 | 82.17 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 44 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-15 | COMP | 2024-03-06 | 1.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 80 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 9520-60-V00-0005 | ANGLE, STRUCTURAL, STEEL, 4MM X 2 X 2 INCHES X 10 FEET | 53655 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | EA | 10 | 45.54 | 455.4 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 22 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-03-02 | 10.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 80 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5305-60-V00-0001 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 53656 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | BX | 2 | 18.9 | 37.8 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 20 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 2.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 80 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5935-60-V00-0167 | CONNECTOR, WIRE, RED, 18 -10 AWG | 53657 | 2024-02-08 | 2024-02-10 | CLOSE | 3 | PG | 20 | 26.8 | 536 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 17 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024
60 | 2024-02-07 | 80 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5975-60-V00-0066 | CONDUIT, METAL, RIGID, EMT, GALVANIZED STEEL, 1/2 INCH X 10 FEET | 53657 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | EA | 10 | 265 | 2650 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 16 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024
60 | 2024-02-07 | 80 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5975-60-V00-0491 | BOX CONNECTOR, ELECTRICAL, COMPRESSION, RAIN TIGHT, STEEL, EMT, 1/2 INCH | 53658 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 40 | 8.25 | 330 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 18 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024
60 | 2024-02-07 | 80 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 53657 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 2 | 260.02 | 520.04 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 15 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024
60 | 2024-02-07 | 80 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5345-60-V00-0017 | WHEEL, ABRASIVE (CUTTING DISK), METAL CUTTING, 180 X 22.23 X 3 MM | 53659 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 10 | 3.61 | 36.1 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 19 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-31 |  |  |  |  | BU | BU table | February | 2024
60 | 2024-02-07 | 80 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 6625-60-V00-0093 | TESTER, SOCKET, W/ BEEPER, RCD, 250 V, 50 HZ | 53655 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 1 | 74.25 | 74.25 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 21 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-03-03 | 1.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 80 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5120-60-V00-0117 | SCREW DRIVER, INSULATED VINYL GRIP, SET, 10 PIECES | 53654 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 2 | 51.56 | 103.12 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 20 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-31 | COMP | 2024-03-09 | 2.00 |  | BU | BU table | February | 2024
60 | 2024-02-07 | 50 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5340-60-V00-0736 | LOCK, MORTISE, INTERCHANGEABLE CORE, 6-PIN, SATIN CHROME | 53777 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | EA | 1 | 178.16 | 890.8 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 5 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 5.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 9520-60-V00-0030 | STUD, FRAMING, GALVANIZED STEEL, 10 FEET | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 14 | EA | 44 | 10.2 | 448.8 |  |  |  |  | KW1-14917 | 14 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 44.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5650-60-V00-0004 | CHANNEL, STRUCTURAL, C-SHAPE, STEEL, 1-5/8 X 3-5/8 INCHES X 10 FEET | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 13 | EA | 40 | 9.7 | 388 |  |  |  |  | KW1-14917 | 13 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-15 | COMP | 2024-02-20 | 40.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5305-60-V00-0198 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATED, #6 X 2 INCHES | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 12 | EA | 400 | 0.3 | 120 |  |  |  |  | KW1-14917 | 12 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 400.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5530-60-V00-0010 | PLYWOOD, CONSTRUCTION, MARINE GRADE, 3/4 INCH X 8 X 4 FEET | 53878 | 2024-02-10 | 2024-02-12 | CLOSE | 5 | SH | 6 | 60.09 | 360.54 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 108 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 6.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5530-00-618-8073 | PLYWOOD, MAPLE, PUREBOND, 3/4 IN x 4 FT x 8 FT | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 11 | SH | 20 | 47 | 940 |  |  |  |  | KW1-14917 | 11 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 20.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5510-01-433-4221 | LUMBER, SOFTWOOD, 4 X 4 INCHES X 16 FEET | 53878 | 2024-02-10 | 2024-02-12 | CLOSE | 4 | EA | 10 | 50 | 500 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 107 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 10.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 10 | BX | 8 | 29.4 | 235.2 |  |  |  |  | KW1-14917 | 10 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 8.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 9 | BX | 8 | 19.6 | 156.8 |  |  |  |  | KW1-14917 | 9 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 8.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5305-60-V00-0169 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 3 INCHES | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 8 | BX | 4 | 30.4 | 121.6 |  |  |  |  | KW1-14917 | 8 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-15 | COMP | 2024-02-20 | 4.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8135-60-V00-0003 | PLASTIC SHEET, POLYETHYLENE, CLEAR, 6 MIL, 32 X 100 FEET | 53878 | 2024-02-10 | 2024-02-12 | CLOSE | 3 | RO | 1 | 475.17 | 475.17 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 106 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8010-60-V00-0084 | PAINT, FIRE RETARDANT, GRAY, 1 GALLON | 53873 | 2024-02-10 | 2024-02-12 | CLOSE | 3 | CN | 4 | 84.51 | 338.04 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15056 | 3 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-24 | 4.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 9540-60-V00-0009 | ANGLE, STRUCTURAL, ALUMINUM, CREAM, 2 X 2 INCH X 20 FEET | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 7 | EA | 2 | 51.2 | 102.4 |  |  |  |  | KW1-14917 | 7 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 2.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 53879 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | EA | 4 | 18.2 | 72.8 |  |  |  |  | KW1-14913 | 7 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 4.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 53876 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | BX | 1 | 16.5 | 16.5 |  |  |  |  | KW1-14908 | 1 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-03-15 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8020-00-260-1302 | BRUSH, PAINT, BRISTLES, CHISELED, 2 INCHES | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 6 | EA | 4 | 15.2 | 60.8 |  |  |  |  | KW1-14917 | 6 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 4.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 53879 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 4 | 30.6 | 122.4 |  |  |  |  | KW1-14913 | 6 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 4.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8030-60-V00-0055 | SEALANT, SILICONE, WHITE, 300ml | 53881 | 2024-02-10 | 2024-02-12 | CLOSE | 3 | BX | 1 | 141.9 | 141.9 |  |  |  |  | KW1-14913 | 11 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5320-60-V00-0014 | RIVET, BLIND, ALUMINUM, 2 INCHES | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 5 | BX | 6 | 20 | 120 |  |  |  |  | KW1-14917 | 5 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 6.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5320-60-V00-0005 | RIVET, BLIND, STAINLESS STEEL, SILVER, 6.4 MM | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 4 | PG | 6 | 60.5 | 363 |  |  |  |  | KW1-14917 | 4 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 6.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 3230-60-V00-0024 | BLADE, CIRCULAR SAW, WOOD CUTTING, 36 TOOTH, 7-1/4 INCHES | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 3 | EA | 1 | 52 | 52 |  |  |  |  | KW1-14917 | 3 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-10 | COMP | 2024-03-03 | 1.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8040-60-V00-0027 | TAPE, ADHESIVE, POLY FOAM, OPEN CELL, BLACK, 12.7 X 19 MM X 5 METERS | 53881 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | RO | 2 | 19.8 | 39.6 |  |  |  |  | KW1-14913 | 10 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 2.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5640-60-V00-0032 | WEATHER STRIP, DOOR, W/RUBBER BOTTOM SWEEP, 39" | 53882 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 2 | 17.4 | 34.8 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 109 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5640-60-V00-0035 | WEATHER STRIP, DOOR, W/BRUSH, 2 X 36 INCHES | 53874 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 2 | 29.72 | 59.44 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 101 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | BX | 6 | 29.4 | 176.4 |  |  |  |  | KW1-14917 | 2 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 6.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5340-60-V00-0505 | RAIN GUARD, DOOR, ALUMINUM, 236.22 X 4 INCHES | 53878 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | EA | 2 | 52.78 | 105.56 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 105 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8040-60-V00-0008 | ADHESIVE, GRIPFILL, MULTIPUROPSE, BUFF, C20, 310 ML | 53875 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | BX | 1 | 133.16 | 133.16 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 7 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 53878 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | BX | 6 | 51.15 | 306.9 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 104 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 6.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8010-60-V00-0146 | PRIMER COATING, WOOD, WHITE, 5 GL | 53877 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | CN | 1 | 120.17 | 120.17 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 103 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GALLON | 53882 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | GL | 2 | 220.5 | 441 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 110 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5670-05-V00-0001 | GRATING BAR, SERRATED, GALVANIZED STEEL, 240 X 24 X 1 INCHES | 53883 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 1 | 941.34 | 941.34 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 8 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-04-03 07:00 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 9905-01-282-2285 | TAPE, FLAGGING, CAUTION DO NOT ENTER, POLYETHYLENE, BLACK ON YELLOW, 3 INCHES X 200 FEET | 53877 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | RO | 1 | 88.67 | 88.67 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 102 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8105-01-336-6163 | BAG, SAND, TAN, 26 INCHES | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | HD | 1 | 742.5 | 742.5 |  |  |  |  | KW1-14917 | 1 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 7220-60-V00-0056 | CARPET, FLOOR, NYLON, GRAY, 20 X 20 INCHES | 53873 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | EA | 24 | 11.85 | 284.4 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 6 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 24.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8040-00-273-8713 | ADHESIVE, FLOORING, WHITE, 1 GL | 53881 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | GL | 1 | 185.7 | 185.7 |  |  |  |  | KW1-14913 | 9 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5610-60-V00-0010 | GATCH AND GRAVEL, MIXED, CUBIC METER | 53873 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | CZ | 1 | 55.21 | 55.21 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 5 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-03 | COMP | 2024-03-02 | 1.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 53871 | 2024-02-10 | 2024-02-12 | CLOSE | 4 | EA | 2 | 260.02 | 520.04 |  |  |  |  | KW1-14913 | 4 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 2.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 |  | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5975-00-178-1217 | CONDUIT, METAL, RIGID, STEEL, 3/4 INCH X 10 FEET | [5 empty] | LG | [18 empty] | Not Required | BU | BU table | February | 2024
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 53871 | 2024-02-10 | 2024-02-12 | CLOSE | 3 | RL | 1 | 92.02 | 92.02 |  |  |  |  | KW1-14913 | 3 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 |  | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5975-60-V00-0017 | COUPLING, ELECTRICAL CONDUIT, ZINC PLATED STEEL, 3/4 INCH | [5 empty] | PG | [18 empty] | Not Required | BU | BU table | February | 2024
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 53870 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | EA | 10 | 4.3 | 43 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 100 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 10.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 |  | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5975-60-V00-0405 | ADAPTER, ELECTRICAL CONDUIT, ZINC, 3/4 INCH | [5 empty] | EA | [18 empty] | Not Required | BU | BU table | February | 2024
61 | 2024-02-07 |  | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5975-60-V00-0379 | CLAMP, ELECTRICAL, CONDUIT, 2 HOLE, GALVANIZED STEEL, 3/4 INCH | [5 empty] | EA | [18 empty] | Not Required | BU | BU table | February | 2024
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5975-60-V00-0460 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, GALVANIZED STEEL, ¾ INCH | 53869 | 2024-02-10 | 2024-02-12 | CLOSE | 3 | PG | 10 | 2.11 | 21.1 | 21124 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14905 | 2 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 10.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 53871 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | RL | 1 | 163.2 | 163.2 |  |  |  |  | KW1-14913 | 2 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5305-60-V00-0001 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 53869 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | PG | 1 | 18.84 | 18.84 | 21124 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14904 | 1 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5120-05-V00-0014 | CUTTER, CABLE/WIRE, HAND OPERATED, ALLOY STEEL, 140MM | 53870 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 2 | 64.3 | 128.6 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 99 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-31 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5110-60-V00-0080 | STRIPPER, WIRE, 10-20 AWG | 53872 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 2 | 20.41 | 40.82 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 4 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-04-03 07:00 |  |  |  |  | BU | BU table | February | 2024
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 53871 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 1 | 28.9 | 28.9 |  |  |  |  | KW1-14913 | 1 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 53869 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 1 | 26.63 | 26.63 | 21124 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14905 | 1 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 9520-60-V00-0030 | STUD, FRAMING, GALVANIZED STEEL, 10 FEET | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 14 | EA | 44 | 10.2 | 448.8 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 29 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 44.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5650-60-V00-0004 | CHANNEL, STRUCTURAL, C-SHAPE, STEEL, 1-5/8 X 3-5/8 INCHES X 10 FEET | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 13 | EA | 40 | 9.7 | 388 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 28 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 40.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5305-60-V00-0198 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATED, #6 X 2 INCHES | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 12 | EA | 400 | 0.3 | 120 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 27 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 400.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5530-60-V00-0010 | PLYWOOD, CONSTRUCTION, MARINE GRADE, 3/4 INCH X 8 X 4 FEET | 53783 | 2024-02-10 | 2024-02-10 | CLOSE | 5 | SH | 6 | 61.61 | 369.66 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 13 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 6.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5530-00-618-8073 | PLYWOOD, MAPLE, PUREBOND, 3/4 IN x 4 FT x 8 FT | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 11 | SH | 20 | 47 | 940 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 26 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 20.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5510-01-433-4221 | LUMBER, SOFTWOOD, 4 X 4 INCHES X 16 FEET | 53783 | 2024-02-10 | 2024-02-10 | CLOSE | 4 | EA | 10 | 50 | 500 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 12 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 10.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 10 | BX | 8 | 29.4 | 235.2 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 25 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 8.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 9 | BX | 8 | 19.6 | 156.8 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 24 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 8.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5305-60-V00-0169 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 3 INCHES | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 8 | BX | 4 | 30.4 | 121.6 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 23 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 4.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8135-60-V00-0003 | PLASTIC SHEET, POLYETHYLENE, CLEAR, 6 MIL, 32 X 100 FEET | 53783 | 2024-02-10 | 2024-02-10 | CLOSE | 3 | RO | 1 | 487.18 | 487.18 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 11 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8010-60-V00-0084 | PAINT, FIRE RETARDANT, GRAY, 1 GALLON | 53778 | 2024-02-10 | 2024-02-10 | CLOSE | 3 | CN | 4 | 274.73 | 1098.92 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 7 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 9540-60-V00-0009 | ANGLE, STRUCTURAL, ALUMINUM, CREAM, 2 X 2 INCH X 20 FEET | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 7 | EA | 2 | 51.2 | 102.4 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 22 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 53784 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | EA | 4 | 18.2 | 72.8 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 15 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 4.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 53781 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | BX | 1 | 16.5 | 16.5 | 21187 | CLOSE | 2024-02-17 |  | KW1-14969 | 3 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-03-23 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8020-00-260-1302 | BRUSH, PAINT, BRISTLES, CHISELED, 2 INCHES | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 6 | EA | 4 | 15.2 | 60.8 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 21 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 4.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 53784 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | EA | 4 | 30.6 | 122.4 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 14 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 4.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8030-60-V00-0055 | SEALANT, SILICONE, WHITE, 300ml | 53786 | 2024-02-10 | 2024-02-10 | CLOSE | 3 | BX | 1 | 141.9 | 141.9 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 32 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5320-60-V00-0014 | RIVET, BLIND, ALUMINUM, 2 INCHES | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 5 | BX | 6 | 20 | 120 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 20 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 6.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5320-60-V00-0005 | RIVET, BLIND, STAINLESS STEEL, SILVER, 6.4 MM | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 4 | PG | 6 | 60.5 | 363 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 19 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 6.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 3230-60-V00-0024 | BLADE, CIRCULAR SAW, WOOD CUTTING, 36 TOOTH, 7-1/4 INCHES | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 3 | EA | 1 | 52 | 52 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 18 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-09 | COMP | 2024-03-07 | 1.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8040-60-V00-0027 | TAPE, ADHESIVE, POLY FOAM, OPEN CELL, BLACK, 12.7 X 19 MM X 5 METERS | 53786 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | RO | 2 | 19.8 | 39.6 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 31 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5640-60-V00-0032 | WEATHER STRIP, DOOR, W/RUBBER BOTTOM SWEEP, 39" | 53787 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | EA | 2 | 17.4 | 34.8 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 34 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5640-60-V00-0035 | WEATHER STRIP, DOOR, W/BRUSH, 2 X 36 INCHES | 53779 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | EA | 2 | 30.47 | 60.94 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 6 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | BX | 6 | 29.4 | 176.4 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 17 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 6.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5340-60-V00-0505 | RAIN GUARD, DOOR, ALUMINUM, 236.22 X 4 INCHES | 53783 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | EA | 2 | 54.11 | 108.22 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 10 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8040-60-V00-0008 | ADHESIVE, GRIPFILL, MULTIPUROPSE, BUFF, C20, 310 ML | 53780 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | BX | 1 | 227.27 | 227.27 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 1 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-26 | 1.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 53783 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | BX | 6 | 52.45 | 314.7 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 9 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 6.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8010-60-V00-0146 | PRIMER COATING, WOOD, WHITE, 5 GL | 53782 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | CN | 1 | 123.21 | 123.21 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 8 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GALLON | 53787 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | GL | 2 | 220.5 | 441 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 33 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5670-05-V00-0001 | GRATING BAR, SERRATED, GALVANIZED STEEL, 240 X 24 X 1 INCHES | 53788 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | EA | 1 | 941.34 | 941.34 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 2 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-04-03 07:00 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 9905-01-282-2285 | TAPE, FLAGGING, CAUTION DO NOT ENTER, POLYETHYLENE, BLACK ON YELLOW, 3 INCHES X 200 FEET | 53782 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | RO | 1 | 90.91 | 90.91 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 7 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8105-01-336-6163 | BAG, SAND, TAN, 26 INCHES | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | HD | 1 | 742.5 | 742.5 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 16 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 7220-60-V00-0056 | CARPET, FLOOR, NYLON, GRAY, 20 X 20 INCHES | 53778 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | EA | 24 | 12.15 | 291.6 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 3 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-25 | 24.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8040-00-273-8713 | ADHESIVE, FLOORING, WHITE, 1 GL | 53786 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | GL | 1 | 185.7 | 185.7 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 30 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5610-60-V00-0010 | GATCH AND GRAVEL, MIXED, CUBIC METER | 53778 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | CZ | 1 | 56.61 | 56.61 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 2 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-03-02 | 1.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 53820 | 2024-02-10 | 2024-02-10 | CLOSE | 4 | EA | 2 | 260.02 | 520.04 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 44 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 |  | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5975-00-178-1217 | CONDUIT, METAL, RIGID, STEEL, 3/4 INCH X 10 FEET | [5 empty] | LG | [18 empty] | Not Required | BU | BU table | February | 2024
62 | 2024-02-07 | 40 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 53820 | 2024-02-10 | 2024-02-10 | CLOSE | 3 | RL | 1 | 92.02 | 92.02 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 43 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 |  | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5975-60-V00-0017 | COUPLING, ELECTRICAL CONDUIT, ZINC PLATED STEEL, 3/4 INCH | [5 empty] | PG | [18 empty] | Not Required | BU | BU table | February | 2024
62 | 2024-02-07 | 40 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 53819 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | EA | 10 | 4.3 | 43 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 40 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 10.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 |  | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5975-60-V00-0405 | ADAPTER, ELECTRICAL CONDUIT, ZINC, 3/4 INCH | [5 empty] | EA | [18 empty] | Not Required | BU | BU table | February | 2024
62 | 2024-02-07 |  | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5975-60-V00-0379 | CLAMP, ELECTRICAL, CONDUIT, 2 HOLE, GALVANIZED STEEL, 3/4 INCH | [5 empty] | EA | [18 empty] | Not Required | BU | BU table | February | 2024
62 | 2024-02-07 | 40 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5975-60-V00-0460 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, GALVANIZED STEEL, ¾ INCH | 53817 | 2024-02-10 | 2024-02-10 | CLOSE | 3 | PG | 10 | 2.13 | 21.3 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 37 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 10.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 40 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 53820 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | RL | 1 | 163.2 | 163.2 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 42 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 40 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5305-60-V00-0001 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 53817 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | PG | 1 | 19.31 | 19.31 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 36 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 40 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5110-60-V00-0012 | FILE SET, HAND, CARBON-STEEL, 16 PIECES | 53818 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | EA | 2 | 54.1 | 108.2 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 38 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-31 | COMP | 2024-02-29 | 2.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 40 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5120-60-V00-0076 | SCREW DRIVER, PHILIPS, SET, 5 PIECES | 53819 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | EA | 2 | 76 | 152 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 39 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-31 | COMP | 2024-02-29 | 2.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 40 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 53820 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | EA | 1 | 28.9 | 28.9 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 41 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024
62 | 2024-02-07 | 40 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 53817 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | EA | 1 | 27.31 | 27.31 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 35 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024
63 | 2024-02-10 | 90 | BU23-0083 | Correct TI Deficiencies for FMR Tower | 5083138 | 5340-60-V00-0904 | SADDLE, CONDUCTOR, HEAVY DUTY, EARTHING PROTECTION, BRASS, NATURAL, 50 MM² | 53865 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 37 | 9.57 | 354.09 | 21344 | CLOSE | 2024-02-22 | 2024-02-16 | KW1-15089 | 9 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-26 | 37.00 |  | BU | BU table | February | 2024
64 | 2024-02-10 | 60 | BU23-0031 | Correct TI Deficiencies for UDR 5 ISBC Tower | 5069515 | 5340-60-V00-0904 | SADDLE, CONDUCTOR, HEAVY DUTY, EARTHING PROTECTION, BRASS, NATURAL, 50 MM² | 53867 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 37 | 9.57 | 354.09 | 21344 | CLOSE | 2024-02-22 | 2024-02-16 | KW1-15089 | 10 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-26 | 37.00 |  | BU | BU table | February | 2024
65 | 2024-02-10 | 90 | BU23-0082 | Correct TI Deficiencies for HSR Tower | 5083153 | 5340-60-V00-0904 | SADDLE, CONDUCTOR, HEAVY DUTY, EARTHING PROTECTION, BRASS, NATURAL, 50 MM² | 53868 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 37 | 0.58 | 21.46 | 21344 | CLOSE | 2024-02-22 | 2024-02-16 | KW1-15089 | 11 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-26 | 37.00 |  | BU | BU table | February | 2024
66 | 2024-02-12 | 30 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 | 6210-60-V00-0021 | FIXTURE, LIGHTING, LED, SAFETY AND EXIT SIGN, SINGLE SIDED, GREEN, 230V AC, 136 X 303 X 62 MM |  | 2024-02-12 |  |  |  | EACH | 0 | [17 empty] | From DPW | BU | BU table | February | 2024
66 | 2024-02-12 | 30 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 | 5975-60-V00-0480 | JUNCTION BOX, w/ BLANK SIDE, 100 X 100 X 50 MM | 53938 | 2024-02-12 | 2024-02-14 | CLOSE | 3 | EACH | 3 | 12 | 36 | 21117 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14897 | 4 | 2024-02-15 | APPR | 2024-02-15 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 | COMP | 2024-02-19 | 3.00 |  | BU | BU table | February | 2024
66 | 2024-02-12 | 30 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 53938 | 2024-02-12 | 2024-02-14 | CLOSE | 2 | ROLL | 1 | 92.02 | 92.02 | 21117 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14897 | 3 | 2024-02-15 | APPR | 2024-02-15 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | February | 2024
66 | 2024-02-12 | 30 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 53937 | 2024-02-12 | 2024-02-14 | CLOSE | 1 | EACH | 20 | 4.3 | 86 | 21110 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14895 | 4 | 2024-02-15 | APPR | 2024-02-15 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 20.00 |  | BU | BU table | February | 2024
66 | 2024-02-12 | 30 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 | 5180-60-V00-0075 | NUT DRIVER SET, SAE, 3/16 – 9/16 INCH, 8 PIECES | 53934 | 2024-02-12 | 2024-02-14 | CLOSE | 1 | EACH | 2 | 139.86 | 279.72 | 21110 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14895 | 2 | 2024-02-15 | APPR | 2024-02-15 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-15 |  |  |  |  | BU | BU table | February | 2024
66 | 2024-02-12 | 30 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 | 5975-60-V00-0382 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, STEEL, 20MM | 53936 | 2024-02-12 | 2024-02-14 | CLOSE | 1 | EACH | 50 | 1.9 | 95 | 21117 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14897 | 1 | 2024-02-15 | APPR | 2024-02-15 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 | COMP | 2024-02-19 | 50.00 |  | BU | BU table | February | 2024
66 | 2024-02-12 | 30 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 53935 | 2024-02-12 | 2024-02-14 | CLOSE | 1 | BX | 1 | 52.45 | 52.45 | 21110 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14895 | 3 | 2024-02-15 | APPR | 2024-02-15 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | February | 2024
66 | 2024-02-12 | 30 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 | 5120-60-V00-0237 | TAPE, FISH, STEEL & POLYPROPYLENE, 1/8 X .045 INCH X 50 FEET | 53939 | 2024-02-12 | 2024-02-14 | CLOSE | 1 | EACH | 1 | 51.15 | 51.15 | 21095 | CLOSE | 2024-02-18 | 2024-02-18 | KW1-15000 | 1 | 2024-02-18 | APPR | 2024-02-18 | Visakh, Ajith - No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-31 | COMP | 2024-02-22 | 1.00 |  | BU | BU table | February | 2024
66 | 2024-02-12 | 30 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 53938 | 2024-02-12 | 2024-02-14 | CLOSE | 1 | ROLL | 1 | 145 | 145 | 21117 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14897 | 2 | 2024-02-15 | APPR | 2024-02-15 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 4120-60-V00-0009 | AIR CONDITIONER, WINDOW, EXPLOSION PROOF, 208/230 V, 60 HZ, R-410A, BTU 24,000 | 54193 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 2 | 9373.95 | 18747.9 | 21122 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14944 | 1 | 2024-02-16 | APPR | 2024-02-16 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-22 |  |  |  | Catalog completed 14 Feb 24 | BU | BU table | February | 2024
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5930-60-V00-0254 | SWITCH, DOUBLE POLE, METAL CLAD, 1 GANG, 32A | 54197 | 2024-02-14 | 2024-02-15 | CLOSE | 5 | EA | 2 | 70.38 | 140.76 |  |  |  |  | KW1-14950 | 24 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 2.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-60-V00-0528 | CONDUIT, RIGID, EMT, GALVANIZED STEEL, 1/2 INCH X 10 FEET | 54195 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 2 | 27 | 54 |  |  |  |  | KW1-14950 | 19 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 2.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-60-V00-0197 | ELBOW, ELECTRICAL CONDUIT, ½ INCH | 54197 | 2024-02-14 | 2024-02-15 | CLOSE | 4 | EA | 4 | 15.8 | 63.2 |  |  |  |  | KW1-14950 | 23 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 4.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-60-V00-0021 | BOX CONNECTOR, ELECTRICAL, RAINTIGHT, STEEL, 1/2 INCH | 54197 | 2024-02-14 | 2024-02-15 | CLOSE | 3 | EA | 10 | 5.2 | 52 |  |  |  |  | KW1-14950 | 22 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-21 | 10.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-60-V00-0382 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, STEEL, 20MM | 54197 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 10 | 2.3 | 23 |  |  |  |  | KW1-14950 | 20 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 10.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-60-V00-0237 | JUNCTION BOX, w/ KNOCKOUT, GALVANIZED STEEL, SQUARE, 4 INCHES | 54194 | 2024-02-14 | 2024-02-15 | CLOSE | 4 | EA | 2 | 24.14 | 48.28 |  |  |  |  | KW1-15098 | 3 | 2024-02-22 | APPR | 2024-02-22 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-25 07:00 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-60-V00-0629 | COVER, JUNCTION BOX, STEEL, SQUARE, FLAT, 0.063 X 4 X 4 INCHES | 54194 | 2024-02-14 | 2024-02-15 | CLOSE | 3 | EA | 2 | 6.66 | 13.32 |  |  |  |  | KW1-15100 | 20 | 2024-02-22 | APPR | 2024-02-22 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 07:00 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 54194 | 2024-02-14 | 2024-02-15 | CLOSE | 2 | EA | 1 | 16.98 | 16.98 |  |  |  |  | KW1-15098 | 2 | 2024-02-22 | APPR | 2024-02-22 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-25 07:00 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 54197 | 2024-02-14 | 2024-02-15 | CLOSE | 2 | EA | 1 | 21.11 | 21.11 |  |  |  |  | KW1-14950 | 21 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5970-01-013-9369 | TAPE, INSULATION, ELECTRICAL, RED, 3/4 X 792 INCHES | 54194 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 1 | 10.32 | 10.32 |  |  |  |  | KW1-15098 | 1 | 2024-02-22 | APPR | 2024-02-22 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-25 07:00 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 54196 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | BX | 1 | 29.4 | 29.4 |  |  |  |  | KW1-14954 | 11 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 07:00 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-05-V01-0071 | GLAND, CABLE PLASTIC, NYLON, WHITE, PG 13.5 | 54198 | 2024-02-14 | 2024-02-15 | CLOSE | 2 | EA | 2 | 0.69 | 1.38 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 14 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-60-V00-0809 | STUFFING TUBE (CABLE GLAND), POLYAMIDE, BLACK, M16 X 5-10 MM | 54198 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 2 | 3.3 | 6.6 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 13 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-04-03 07:00 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 50 | BU24-0058 | T6050 Add to TE | 9330911 | 5640-60-V00-0032 | WEATHER STRIP, DOOR, W/RUBBER BOTTOM SWEEP, 39" | 54208 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 2 | 17.4 | 34.8 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 21 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 50 | BU24-0058 | T6050 Add to TE | 9330911 | 5640-60-V00-0035 | WEATHER STRIP, DOOR, W/BRUSH, 2 X 36 INCHES | 54205 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 2 | 30.47 | 60.94 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 20 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 50 | BU24-0058 | T6050 Add to TE | 9330911 | 8040-60-V00-0027 | TAPE, ADHESIVE, POLY FOAM, OPEN CELL, BLACK, 12.7 X 19 MM X 5 METERS | 54207 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | RO | 3 | 19.8 | 59.4 |  |  |  |  | KW1-14950 | 31 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 3.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 50 | BU24-0058 | T6050 Add to TE | 9330911 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 54206 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | BX | 1 | 29.4 | 29.4 |  |  |  |  | KW1-14954 | 12 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 07:00 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 50 | BU24-0058 | T6050 Add to TE | 9330911 | 5640-60-V00-0028 | WEATHER STRIP, ADHESIVE, POLY FOAM, BLACK, 19 MM X 5 METERS | 54209 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 1 | 15 | 15 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 22 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 6210-60-V00-0094 | FIXTURE, LIGHTING, LED, RETROFIT, POLYCARBONATE, PURE WHITE, 40W | 54203 | 2024-02-14 | 2024-02-15 | CLOSE | 6 | EA | 16 | 242.35 | 3877.6 |  |  |  |  | KW1-14950 | 30 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 16.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 54203 | 2024-02-14 | 2024-02-15 | CLOSE | 5 | EA | 2 | 302.94 | 605.88 |  |  |  |  | KW1-14950 | 29 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 2.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 54203 | 2024-02-14 | 2024-02-15 | CLOSE | 4 | EA | 2 | 58.91 | 117.82 |  |  |  |  | KW1-14950 | 28 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 2.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 54200 | 2024-02-14 | 2024-02-15 | CLOSE | 4 | RO | 1 | 244.76 | 244.76 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15056 | 6 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-25 | 1.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 9905-60-V00-0065 | SIGN, DANGER HIGH VOLTAGE, ADHESIVE, CUSTOMIZED (Length 9X8 Width Inches) | 54199 | 2024-02-14 | 2024-02-15 | CLOSE | 2 | EA | 2 | 9.99 | 19.98 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 16 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 9905-60-V00-0066 | SIGN, DANGER, 415 VOLTS , 5 X 3-3/4 INCHES | 54200 | 2024-02-14 | 2024-02-15 | CLOSE | 3 | PG | 1 | 17.48 | 17.48 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 18 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 5930-60-V00-0254 | SWITCH, DOUBLE POLE, METAL CLAD, 1 GANG, 32A | 54203 | 2024-02-14 | 2024-02-15 | CLOSE | 3 | EA | 2 | 70.38 | 140.76 |  |  |  |  | KW1-14950 | 27 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 2.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 6210-60-V00-0115 | LIGHT UNIT, EMERGENCY, EXIT, 60 HZ, 3 WATT | 54204 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 1 | 186.03 | 186.03 |  |  |  |  | KW1-15019 | 2 | 2024-02-20 | APPR | 2024-02-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 6850-60-V00-0025 | CLEANING COMPOUND,SOLVENT, CONTACT, COLORLESS, 11OZ | 54201 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 2 | 90.91 | 181.82 |  |  |  |  | KW1-15019 | 1 | 2024-02-20 | APPR | 2024-02-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 54203 | 2024-02-14 | 2024-02-15 | CLOSE | 2 | EA | 4 | 260.02 | 1040.08 |  |  |  |  | KW1-14950 | 26 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 4.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 5120-05-V00-0014 | CUTTER, CABLE/WIRE, HAND OPERATED, ALLOY STEEL, 140MM | 54202 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 2 | 64.3 | 128.6 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 19 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-04-04 07:00 | COMP | 2024-03-07 | 2.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 6625-60-V00-0093 | SCREW DRIVER / NUT DRIVER, HEAVY DUTY, MULTI-BIT | 54199 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 2 | 74.93 | 149.86 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 15 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 8020-00-245-4519 | BRUSH, PAINT, BRISTLES, FLAT, 4 INCHES | 54203 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 2 | 14.9 | 29.8 |  |  |  |  | KW1-14950 | 25 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-22 | 2.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 5305-60-V00-0001 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 54200 | 2024-02-14 | 2024-02-15 | CLOSE | 2 | BX | 1 | 19.31 | 19.31 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15057 | 4 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 6350-60-V00-0102 | ALARM, SMOKE, AUTOMATIC, PLASTIC | 54200 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 4 | 28.97 | 115.88 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 17 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 4.00 |  | BU | BU table | February | 2024
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 54230 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EACH | 3 | 27.31 | 81.93 | 21184 | CLOSE | 2024-02-17 |  | KW1-14967 | 56 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-02 | COMP | 2024-02-20 | 3.00 |  | BU | BU table | February | 2024
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 54233 | 2024-02-14 | 2024-02-15 | CLOSE | 4 | ROLL | 1 | 92.02 | 92.02 | 21184 | CLOSE | 2024-02-17 |  | KW1-14967 | 60 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-02 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
68 | 2024-02-14 | 40 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 54242 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EACH | 6 | 4.3 | 25.8 | 21182 | CLOSE | 2024-02-17 |  | KW1-14963 | 28 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-20 | 6.00 |  | BU | BU table | February | 2024
68 | 2024-02-14 | 40 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 5975-60-V00-0382 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, STEEL, 20MM | 54243 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EACH | 12 | 2.3 | 27.6 |  |  |  |  | KW1-15019 | 3 | 2024-02-20 | APPR | 2024-02-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-24 | 12.00 |  | BU | BU table | February | 2024
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 54288 | 2024-02-14 | 2024-02-19 | CLOSE | 1 | EACH | 14 | 4.3 | 60.2 | 21337 | CLOSE | 2024-02-22 |  | KW1-15079 | 11 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 | COMP | 2024-02-24 | 14.00 |  | BU | BU table | February | 2024
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 5975-60-V00-0382 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, STEEL, 20MM | 54289 | 2024-02-14 | 2024-02-19 | CLOSE | 1 | EACH | 38 | 2.3 | 87.4 | 21341 | CLOSE | 2024-02-22 |  | KW1-15084 | 21 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-02-24 | 38.00 |  | BU | BU table | February | 2024
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 5210-01-626-3065 | DISTANCE MEASURER, LASER, STANLEY, 100’ RANGE, TLM99 | 54234 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EACH | 1 | 127.75 | 127.75 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 24 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-04-04 07:00 |  |  |  |  | BU | BU table | February | 2024
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 54231 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | BX | 1 | 52.45 | 52.45 | 21182 | CLOSE | 2024-02-17 |  | KW1-14963 | 27 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 6145-60-V00-0158 | WIRE, ELECTRICAL, RED, 1 CORE, 2.5 MM² | 54233 | 2024-02-14 | 2024-02-15 | CLOSE | 3 | ROLL | 1 | 57 | 57 | 21184 | CLOSE | 2024-02-17 |  | KW1-14967 | 59 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-02 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 6145-60-V00-0151 | WIRE, ELECTRICAL, BLACK 1 CORE, 2.5 MM² | 54233 | 2024-02-14 | 2024-02-15 | CLOSE | 2 | ROLL | 1 | 65 | 65 | 21184 | CLOSE | 2024-02-17 |  | KW1-14967 | 58 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-02 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 54232 | 2024-02-14 | 2024-02-15 | CLOSE | 2 | ROLL | 1 | 64.5 | 64.5 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15057 | 5 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 5120-60-V00-0110 | SCREW DRIVER, BLACK, SET, 7 PIECES | 54232 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EACH | 2 | 144.3 | 288.6 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 23 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-04-04 07:00 |  |  |  |  | BU | BU table | February | 2024
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 54233 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | PG | 1 | 26.93 | 26.93 | 21184 | CLOSE | 2024-02-17 |  | KW1-14967 | 57 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-02 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W |  | 2024-02-14 |  |  |  | EA | 2 | [17 empty] | From DPW | BU | BU table | February | 2024
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 6145-60-V00-0158 | WIRE, ELECTRICAL, RED, 1 CORE, 2.5 MM² | 54269 | 2024-02-14 | 2024-02-19 | CLOSE | 5 | RO | 1 | 57 | 57 | 21341 | CLOSE | 2024-02-22 |  | KW1-15084 | 20 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 6145-60-V00-0151 | WIRE, ELECTRICAL, BLACK 1 CORE, 2.5 MM² | 54269 | 2024-02-14 | 2024-02-19 | CLOSE | 4 | RO | 1 | 65 | 65 | 21341 | CLOSE | 2024-02-22 |  | KW1-15084 | 19 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 54268 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | RO | 1 | 64.5 | 64.5 |  |  |  |  | KW1-14954 | 14 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 07:00 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 54267 | 2024-02-14 | 2024-02-15 | CLOSE | 3 | EA | 2 | 26.62 | 53.24 |  |  |  |  | KW1-14950 | 34 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 2.00 |  | BU | BU table | February | 2024
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5975-60-V00-0487 | COUPLING, ELECTRICAL CONDUIT, w/ SCREW, Â½ INCH | 54269 | 2024-02-14 | 2024-02-19 | CLOSE | 3 | EA | 20 | 5 | 100 | 21341 | CLOSE | 2024-02-22 |  | KW1-15084 | 18 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-02-24 | 20.00 |  | BU | BU table | February | 2024
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5975-60-V00-0483 | BOX CONNECTOR, ELECTRICAL, ZINC DIE CAST, 1/2 INCH | 54267 | 2024-02-14 | 2024-02-15 | CLOSE | 2 | EA | 10 | 3.9 | 39 |  |  |  |  | KW1-14950 | 33 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 10.00 |  | BU | BU table | February | 2024
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5345-60-V00-0017 | WHEEL, ABRASIVE (CUTTING DISK), METAL CUTTING, 180 X 22.23 X 3 MM | 54270 | 2024-02-14 | 2024-02-19 | CLOSE | 4 | EA | 10 | 3.61 | 36.1 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 23 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-04-11 |  |  |  |  | BU | BU table | February | 2024
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5975-60-V00-0467 | STRAP, TIE DOWN, ELECTRICAL COMPONENT, NYLON 6.6, BLACK, 12.2 X 0.374 INCHES | 54265 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | PG | 1 | 232.11 | 232.11 |  |  |  |  | KW1-14950 | 32 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5305-60-V00-0001 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 54267 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | PG | 1 | 18.83 | 18.83 |  |  |  |  | KW1-14954 | 13 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 07:00 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5975-60-V00-0066 | CONDUIT, METAL, RIGID, GALVANIZED STEEL, 1/2 INCH X 10 FEET | 54269 | 2024-02-14 | 2024-02-19 | CLOSE | 2 | EA | 20 | 11.77 | 235.4 | 21341 | CLOSE | 2024-02-22 |  | KW1-15084 | 17 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-02-24 | 20.00 |  | BU | BU table | February | 2024
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5925-60-V00-0105 | CIRCUIT BREAKER, MCB, 240 V, 10 A | 54270 | 2024-02-14 | 2024-02-19 | CLOSE | 3 | EA | 1 | 14 | 14 | 21782 | CLOSE | 2024-03-01 | 2024-02-24 | KW1-15326 | 1 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-06 | 1.00 |  | BU | BU table | February | 2024
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5120-60-V00-0158 | BIT, SCREWDRIVER, STEEL, #2 PHILLIPS, 1 INCH, 30 PIECES | 54270 | 2024-02-14 | 2024-02-19 | CLOSE | 2 | PG | 1 | 25.58 | 25.58 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 27 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-28 | COMP | 2024-03-05 | 1.00 |  | BU | BU table | February | 2024
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5120-60-V00-0159 | HOLDER, SCREWDRIVER BIT, HEX, STEEL, 1/4 X 3 INCHES | 54266 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 10 | 27.27 | 272.7 | 21292 | CLOSE | 2024-02-23 | 2024-02-21 | KW1-15138 | 7 | 2024-02-23 | APPR | 2024-02-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL-IRTEKAZ NATIONAL GEN.TRDG.C | 2024-03-22 07:00 | COMP | 2024-02-29 | 10.00 |  | BU | BU table | February | 2024
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 54269 | 2024-02-14 | 2024-02-19 | CLOSE | 1 | PG | 1 | 26.93 | 26.93 | 21341 | CLOSE | 2024-02-22 |  | KW1-15084 | 16 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5120-60-V00-0238 | TAPE, FISH, STEEL & PLASTIC, 1/8 X 12 INCHES X 250 FEET | 54270 | 2024-02-14 | 2024-02-19 | CLOSE | 1 | EA | 1 | 151.29 | 151.29 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 26 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-04-11 | COMP | 2024-03-10 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4710-60-V00-0055 | PIPE, PLASTIC, DRAINAGE, ORANGE, SINGLE SOCKET, 110 MM X 6 METERS | 54414 | 2024-02-17 | 2024-02-19 | CLOSE | 6 | EA | 3 | 47.85 | 143.55 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 16 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-05 | 3.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0964 | COUPLING, SEWAGE, w/RUBBER GASKET, PVC, ORANGE, 4 INCHES | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 20 | EA | 7 | 13.1 | 91.7 |  |  |  |  | KW1-15107 | 19 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 7.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4510-60-V00-0096 | TRAP, BOTTLE, ADJUSTABLE INLET, w/FLEXIBLE HOSE, 1-1/2 INCHES | 54412 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 2 | 21.1 | 42.2 | 21312 | CLOSE | 2024-02-21 | 2024-02-21 | KW1-15049 | 2 | 2024-02-21 | APPR | 2024-02-21 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-05 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0458 | ELBOW, PIPE, SOCKET X SPIGOT, 45°, PVC, ORANGE, 110MM | 54404 | 2024-02-17 |  |  | 4 | EA | 2 | [18 empty] | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0970 | ELBOW, PRESSURE FITTINGS, PVC, STANDARD, 90 °, SPIGOT X SOCKET, ORANGE, 110 MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 19 | EA | 3 | 12.4 | 37.2 |  |  |  |  | KW1-15107 | 18 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 3.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0644 | REDUCER, PIPE, PVC, ORANGE, 50 X 110MM | 54407 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 2 | 9.16 | 18.32 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 25 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4820-60-V00-0227 | VALVE, ANGLE, 1/2 X 1/2 INCHES | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 18 | EA | 4 | 17.3 | 69.2 |  |  |  |  | KW1-15107 | 17 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 4.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4820-60-V00-0229 | VALVE, BALL, BRASS, PN25, RED, 3/4 INCH | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 17 | EA | 2 | 15.6 | 31.2 |  |  |  |  | KW1-15107 | 16 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0973 | TEE, PIPE, SEWER AND DRAIN FITTINGS, PVC, SCH-80, ORANGE, 110 MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 16 | EA | 1 | 49.3 | 49.3 |  |  |  |  | KW1-15107 | 15 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-26 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0847 | WYE, PIPE, SEWAGE, 45 °, UPVC, ORANGE, 110MM | 54410 | 2024-02-17 | 2024-02-19 | CLOSE | 3 | EA | 2 | 11.4 | 22.8 | 21336 | CLOSE | 2024-02-22 |  | KW1-15077 | 12 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-03-31 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0943 | UNION, PIPE, SOCKET X SOCKET, SCH 40, CPVC, OFF-WHITE, 25 MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 15 | EA | 2 | 10 | 20 |  |  |  |  | KW1-15107 | 14 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4510-60-V00-0211 | SINK, COMMERCIAL, TWO COMPARTMENT, W/LEGS AND DRAINBOARD, STAINLESS STEEL, 17 X 17 X 12 INCHES | 54414 | 2024-02-17 | 2024-02-19 | CLOSE | 5 | EA | 1 | 665.73 | 665.73 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 15 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-28 |  |  |  |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0929 | TEE, PIPE, SOCKET X SOCKET X SOCKET, SCH-80, CPVC, OFF-WHITE, 25 MM | 54408 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 5 | 7.83 | 39.15 | 21336 | CLOSE | 2024-02-22 |  | KW1-15077 | 13 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-03-31 | COMP | 2024-02-24 | 5.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4410-60-V00-0003 | HEATER, WATER, ELECTRIC, 8 BAR, 220-240V, 2000W, 50 LITERS | 54404 | 2024-02-17 |  |  | 1 | EA | 1 | [18 empty] | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4510-60-V00-0028 | COWL, VENTILATION, UPVC, GRAY, 50MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 14 | EA | 1 | 16.2 | 16.2 |  |  |  |  | KW1-15107 | 13 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0819 | COUPLING, WASTE, SINK, PLASTIC, 1-1/2 INCHES | 54407 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | EA | 6 | 17.32 | 103.92 | 21337 | CLOSE | 2024-02-22 |  | KW1-15079 | 12 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 | COMP | 2024-02-24 | 6.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4710-60-V00-0164 | PIPE, PLASTIC, PVC, GRAY, 1-1/2 INCHES X 6 METERS | 54409 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 2 | 42.46 | 84.92 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 19 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4510-60-V00-0040 | FAUCET, SINGLE, SWIVEL TUBULAR, WALL MOUNTED, CHROME, 1/2 INCH | 54410 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 1 | 231.7 | 231.7 | 21336 | CLOSE | 2024-02-22 |  | KW1-15077 | 11 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-03-31 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0754 | ADAPTER, PRESSURE FITTINGS, MALE, CPVC, STANDARD, SOCKET X MIPT, PN16, OFF-WHITE, 25 MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 13 | EA | 4 | 3.2 | 12.8 |  |  |  |  | KW1-15107 | 12 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 4.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0850 | ELBOW, CPVC, SOCKET X SOCKET, SCH 40, OFF-WHITE, 25 MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 12 | EA | 14 | 3.6 | 50.4 |  |  |  |  | KW1-15107 | 11 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 14.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4720-60-V00-0266 | HOSE, METALLIC, FLEXIBLE, DOUBLE NUT, STAINLESS STEEL BRAIDED, 1/2 INCH X 1-1/2 FEET |  | 2024-02-17 |  |  |  | EA | 4 | [18 empty] | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 9150-60-V00-0050 | LUBRICANT, PIPE JOINT, 32 FL OUNCES | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 11 | EA | 1 | 43.6 | 43.6 |  |  |  |  | KW1-15107 | 10 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 8040-60-V00-0040 | CEMENT, HEAVY BODIED, CPVC, ORANGE, 16 OZ | 54412 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | CN | 1 | 18.2 | 18.2 | 21312 | CLOSE | 2024-02-21 | 2024-02-21 | KW1-15049 | 1 | 2024-02-21 | APPR | 2024-02-21 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-05 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 8040-01-307-0504 | ADHESIVE, CEMENT, PVC, MEDIUM BODIED, CLEAR, 16 OZ | 54414 | 2024-02-17 | 2024-02-19 | CLOSE | 4 | CN | 1 | 36.62 | 36.62 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 8 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-04-11 | COMP | 2024-03-05 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 50 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-05-V01-0706 | ELBOW, PIPE, 90 DEGREE, UPVC, SOCKET, 50MM |  | 2024-02-17 |  |  |  | EA | 4 | [18 empty] | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0871 | ELBOW, PVC, 45 DEGREE, SCH-40, GRAY, 1-1/2 INCH | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 10 | EA | 3 | 9.81 | 29.43 |  |  |  |  | KW1-15107 | 9 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 3.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0829 | COUPLING, UPVC, SCH-40, GRAY, 50 MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 9 | EA | 4 | 9.5 | 38 |  |  |  |  | KW1-15107 | 8 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 4.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 7105-60-V00-0019 | MIRROR, GLASS, ROUND, WALL MOUNTED, WHITE, 50 CM | 54405 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 1 | 19.65 | 19.65 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 22 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-05 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4710-60-V00-0108 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 8 | EA | 10 | 18.6 | 186 |  |  |  |  | KW1-15107 | 7 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 10.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0810 | CLAMP, PIPE, CPVC, BEIGE, 25 MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 7 | EA | 20 | 0.9 | 18 |  |  |  |  | KW1-15107 | 6 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 20.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4720-60-V00-0266 | HOSE, METALLIC, FLEXIBLE, DOUBLE NUT, STAINLESS STEEL BRAIDED, 1/2 INCH X 1-1/2 FEET |  | 2024-02-17 |  |  |  | EA | 4 | [18 empty] | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0863 | ELBOW, PRESSURE FITTINGS, CPVC, BRASS, REDUCTION, 90 °, SOCKET X FIPT, SCH- 40, OFF-WHITE, 25 x 20 MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 6 | EA | 4 | 14.8 | 59.2 |  |  |  |  | KW1-15107 | 5 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 4.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0763 | ADAPTER, PRESSURE FITTINGS, FEMALE, CPVC, REDUCTION, SOCKET X FIPT, SCH- 40, OFF-WHITE, 3/4 X 1/2 INCH | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 5 | EA | 4 | 24.2 | 96.8 |  |  |  |  | KW1-15107 | 4 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 4.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0834 | COUPLING, CPVC, SCH-40, TAN, 25 MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 4 | EA | 6 | 5 | 30 |  |  |  |  | KW1-15107 | 3 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 6.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 8030-09-V00-0010 | TAPE, ANTISEIZING, (TEFLON), PTFE, WHITE, 43 FEET X 1/2 INCHES | 54414 | 2024-02-17 | 2024-02-19 | CLOSE | 3 | EA | 5 | 1.34 | 6.7 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 14 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-28 | COMP | 2024-03-05 | 5.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5130-60-V00-0135 | BLADE, HOLE SAW, BI-METAL, 3/4 INCH | 54414 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 1 | 38.94 | 38.94 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 13 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-28 |  |  |  |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5130-60-V00-0139 | BLADE, HOLE SAW, BI-METAL, 1 INCHES | 54406 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | EA | 1 | 26.31 | 26.31 | 21337 | CLOSE | 2024-02-22 |  | KW1-15079 | 9 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 |  |  |  |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5306-60-V00-0073 | BOLT, MACHINE, HEX HEAD, COARSE THREAD, STEEL, 1/2 X 5 INCHES | 54404 | 2024-02-17 | 2024-02-19 | CLOSE | 3 | EA | 10 | 3.16 | 31.6 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 20 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-05 | 10.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-01-241-8789 | TRAP, DRAINAGE PIPE, SOCKET, PLASTIC, 1-1/2 INCHES | 54413 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | EA | 2 | 58.5 | 117 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15027 | 1 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-03 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4510-60-V00-0029 | DRAIN, FLOOR, COVER, UPVC, BEIGE, 160/110MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 3 | EA | 1 | 11.19 | 11.19 |  |  |  |  | KW1-15105 | 1 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0734 | WYE, TRUE, PIPE, BRANCH, UPVC, 45 DEG, 50 MM | 54404 | 2024-02-17 |  |  | 2 | EA | 1 | [18 empty] | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4510-60-V00-0027 | DRAIN, FLOOR, TRAP, MINI, 2 WAY, UPVC, GRAY, 4 X 2 INCHES | 54410 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | EA | 1 | 23.2 | 23.2 | 21336 | CLOSE | 2024-02-22 |  | KW1-15077 | 10 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-03-31 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4240-60-V00-0150 | TAPE, WARNING, UNDERGROUND, CAUTION BURIED WATER LINE BELOW, BLUE & BLACK, 6 INCHES X 1000 FEET | 54409 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | RO | 1 | 230.1 | 230.1 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 18 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 |  |  |  |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 9905-60-V00-0064 | TAPE, BARRICADE, "CAUTION BURIED SEWER LINE BELOW", GREEN, 3 INCHES | 54414 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | RO | 1 | 254.1 | 254.1 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 12 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-04-11 |  |  |  |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 9905-01-282-2285 | TAPE, FLAGGING (BARRICADE TAPE), CAUTION DO NOT ENTER, POLYETHYLENE, YELLOW, 3 INCH X 1000 FEET | 54408 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | RO | 1 | 90.91 | 90.91 | 21337 | CLOSE | 2024-02-22 |  | KW1-15079 | 10 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5620-60-V00-0013 | CONCRETE BLOCK, READYMADE, AAC, WHITE, 600 X 200 X 100 MM | 54405 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | EA | 30 | 12.82 | 384.6 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 21 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-05 | 30.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0917 | BUSHING, PIPE, REDUCER, SPIGOT X SOCKET, UPVC, GRAY, 2 X 1-1/2 INCHES | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 1 | 4.5 | 4.5 |  |  |  |  | KW1-15107 | 2 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0106 | PLUG, PIPE, PVC, ORANGE, 110MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | EA | 1 | 13.1 | 13.1 |  |  |  |  | KW1-15107 | 1 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 6145-60-V00-0163 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORE, 4 MM² | 54421 | 2024-02-17 | 2024-02-19 | CLOSE | 4 | RO | 1 | 249 | 249 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 8 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 54421 | 2024-02-17 | 2024-02-19 | CLOSE | 3 | EA | 1 | 52 | 52 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 7 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5930-60-V00-0254 | SWITCH, DOUBLE POLE, METAL CLAD, 1 GANG, 32A | 54421 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 1 | 70.38 | 70.38 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 6 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5925-60-V00-0051 | CIRCUIT BREAKER, MINIATURE, 1 POLE, 230/400V, 20A | 54418 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | EA | 1 | 139.69 | 139.69 | 21341 | CLOSE | 2024-02-22 |  | KW1-15084 | 15 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-31 |  |  |  |  | BU | BU table | February | 2024
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5975-60-V00-0097 | CONDUIT, METAL, RIGID, STEEL, ZINC, 3/4 INCH X 3 MTR | 54416 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | EA | 6 | 22.2 | 133.2 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 10 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-05 | 6.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5975-60-V00-0009 | BOX CONNECTOR, ELECTRICAL, LIQUID-TIGHT CONDUIT, ZINC, 3/4 INCH | 54415 | 2024-02-17 | 2024-02-19 | CLOSE | 4 | EA | 4 | 153.18 | 612.72 | 21341 | CLOSE | 2024-02-22 |  | KW1-15084 | 14 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-02-24 | 4.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5975-60-V00-0090 | COUPLING, ELECTRICAL CONDUIT, COMPRESSION, ZINC DIE CAST, 3/4 INCH | 54415 | 2024-02-17 | 2024-02-19 | CLOSE | 3 | EA | 10 | 19.98 | 199.8 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 9 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-05 | 10.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5975-60-V00-0203 | ELBOW, ELECTRICAL CONDUIT, ZINC PLATED, 3/4 INCH | 54415 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 6 | 30.64 | 183.84 | 21341 | CLOSE | 2024-02-22 |  | KW1-15084 | 13 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-02-24 | 6.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 54421 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | RO | 2 | 21.11 | 42.22 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 5 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5970-01-013-9369 | TAPE, INSULATION, ELECTRICAL, RED, 3/4 X 792 INCHES | 54419 | 2024-02-17 | 2024-02-19 | CLOSE | 3 | RO | 2 | 10.1 | 20.2 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 3 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 54419 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | RO | 3 | 16.83 | 50.49 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 2 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 3.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5975-60-V00-0079 | CLAMP, ELECTRICAL, CONDUIT, w/ BOLT, STEEL, 3/4 INCH | 54415 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | PG | 1 | 115.38 | 115.38 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 17 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-05 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5975-60-V00-0379 | CLAMP, ELECTRICAL, CONDUIT, 2 HOLE, GALVANIZED STEEL, 3/4 INCH | 54419 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | EA | 10 | 2.5 | 25 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 1 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 10.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5305-60-V00-0002 | SCREW, SELF DRILLING, PHILIPS, MODIFIED TRUSS HEAD, #8 X 1-1/2 INCHES | 54417 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | BX | 1 | 29.97 | 29.97 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15027 | 2 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-05 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5305-60-V00-0182 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATE, #8 X 1-1/4 INCHES | 54420 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | BX | 1 | 29.2 | 29.2 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15027 | 3 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-05 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-1750 | TRAP, DRAINAGE PIPE (P-TRAP), POLYPROPYLENE, WHITE, 1-1/2 INCHES |  | 2024-02-29 |  |  |  | EA | 5 | [18 empty] | BU | BU table | February | 2024
71 | 2024-02-12 |  | BU24-0076 | Replace floor in female shower trailer 16A |  |  |  | PRINPRG | [23 empty] | Project Cancelled | BU | BU table | February | 2024
72 | 2024-02-18 | 30 | BU24-0167 | Install Security Bars Z2 Trailer2028 | 9653621 | 5306-60-V00-0100 | BOLT, CARRIAGE w/HEX NUT, STEEL, ZINC PLATED, 10M X 4-1/2 INCHES | 54781 | 2024-02-20 | 2024-02-24 | CLOSE | 1 | EA | 16 | 3.14 | 50.24 | 21739 | CLOSE | 2024-03-02 | 2024-03-02 | KW1-15364 | 7 | 2024-03-02 | APPR | 2024-03-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-03-16 | COMP | 2024-03-05 | 16.00 |  | BU | BU table | February | 2024
72 | 2024-02-18 | 30 | BU24-0167 | Install Security Bars Z2 Trailer2028 | 9653621 | 5133-60-V00-0072 | DRILL, TWIST, (BIT), METAL, 10MM | 54780 | 2024-02-20 | 2024-02-24 | CLOSE | 1 | EA | 2 | 8.12 | 16.24 | 21739 | CLOSE | 2024-03-02 | 2024-03-02 | KW1-15364 | 6 | 2024-03-02 | APPR | 2024-03-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-03-16 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024
73 | 1900-03-18 | 30 | BU24-0165 | Emplace Gravel Z8 PAT Site9 | 9722236 | 5610-60-V00-0009 | GRAVEL (CUSTOMIZED) | 54615 | 2024-02-18 |  | CAN | 1 | CZ | 120 | 96.57 | 11588.4 | [15 empty] | CANCELLED | BU | BU table | March | 1900
73 | 2024-02-18 | 30 | BU24-0165 | Emplace Gravel Z8 PAT Site9 | 9722236 | 5610-60-V00-0010 | GATCH AND GRAVEL, MIXED, CUBIC METER | 54547 | 2024-02-18 |  | CAN | 1 | CZ | 91 | 56.5 | 5141.5 | [15 empty] | CANCELLED | BU | BU table | February | 2024
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 54532 | 2024-02-18 | 2024-02-20 | CLOSE | 4 | EA | 2 | 10.1 | 20.2 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 13 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 54531 | 2024-02-18 | 2024-02-19 | CLOSE | 3 | EA | 10 | 4.3 | 43 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15027 | 8 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-05 | COMP | 2024-02-24 | 10.00 |  | BU | BU table | February | 2024
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 6145-60-V00-0136 | WIRE, ELECTRICAL, RED, 1 CORE, 4MM² | 54530 | 2024-02-18 | 2024-02-19 | CLOSE | 6 | RO | 1 | 91.58 | 91.58 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15028 | 5 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-05 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 6145-60-V00-0154 | WIRE, ELECTRICAL, BLACK, 1 CORE, 4MM² | 54530 | 2024-02-18 | 2024-02-19 | CLOSE | 5 | RO | 1 | 91.58 | 91.58 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15028 | 4 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-05 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 6145-60-V00-0143 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4MM² | 54530 | 2024-02-18 | 2024-02-19 | CLOSE | 4 | RO | 1 | 91.58 | 91.58 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15028 | 3 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-05 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5345-60-V00-0017 | WHEEL, ABRASIVE (CUTTING DISK), METAL CUTTING, 180 X 22.23 X 3 MM | 54533 | 2024-02-18 | 2024-02-19 | CLOSE | 2 | EA | 10 | 3.61 | 36.1 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 7 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-28 |  |  |  |  | BU | BU table | February | 2024
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5935-60-V00-0167 | CONNECTOR, WIRE, RED, 18 -10 AWG | 54532 | 2024-02-18 | 2024-02-20 | CLOSE | 3 | PG | 1 | 23.3 | 23.3 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 12 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5975-60-V00-0460 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, GALVANIZED STEEL, 3/4 INCHES | 54530 | 2024-02-18 | 2024-02-19 | CLOSE | 3 | PG | 10 | 2.16 | 21.6 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15028 | 2 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-05 | COMP | 2024-02-24 | 10.00 |  | BU | BU table | February | 2024
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5305-60-V00-0001 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 54530 | 2024-02-18 | 2024-02-19 | CLOSE | 2 | PG | 1 | 19.31 | 19.31 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15027 | 5 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-05 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 54532 | 2024-02-18 | 2024-02-20 | CLOSE | 2 | BX | 1 | 92 | 92 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 11 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 54532 | 2024-02-18 | 2024-02-20 | CLOSE | 1 | EA | 2 | 27 | 54 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 10 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5970-60-V00-0043 | TAPE, INSULATION, ELECTRICAL, SUPER 33 +,VINYL, BLACK, 3/4" X 66' | 54530 | 2024-02-18 | 2024-02-19 | CLOSE | 1 | EA | 1 | 14.32 | 14.32 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15028 | 1 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-05 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5120-60-V00-0105 | BIT, SCREWDRIVER, HEXAGONAL, PHILLIPS, #2 X 1/4 X 1 INCHES | 54533 | 2024-02-18 | 2024-02-19 | CLOSE | 1 | PG | 2 | 8 | 16 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 6 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-04-11 |  |  |  |  | BU | BU table | February | 2024
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5130-01-473-9387 | HOLDER, SCREWDRIVER BIT, STEEL, 6 INCHES | 54529 | 2024-02-18 | 2024-02-19 | CLOSE | 1 | EA | 2 | 35.9 | 71.8 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15027 | 4 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-05 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5120-60-V00-0111 | SCREW DRIVER / NUT DRIVER, HEAVY DUTY, MULTI-BIT | 54531 | 2024-02-18 | 2024-02-19 | CLOSE | 2 | EA | 1 | 24.7 | 24.7 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15027 | 7 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-05 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5120-60-V00-0193 | NUTDRIVER SET, HEX SOCKET, MAGNETIC, CHROME VANADIUM STEEL, 4 PIECES | 54531 | 2024-02-18 | 2024-02-19 | CLOSE | 1 | SE | 2 | 24.7 | 49.4 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15027 | 6 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-05 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 5530-00-618-8073 | PLYWOOD, CONSTRUCTION, 3/4 INCH X 4 X 8 FEET | 54793 | 2024-02-21 | 2024-02-24 | CLOSE | 7 | SH | 15 | 47 | 705 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 15 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-10 | COMP | 2024-02-27 | 15.00 |  | BU | BU table | February | 2024
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 5530-60-V00-0010 | PLYWOOD, CONSTRUCTION, MARINE GRADE, 3/4 INCH X 8 X 4 FEET | 54793 | 2024-02-21 | 2024-02-24 | CLOSE | 6 | SH | 15 | 61.61 | 924.15 | 21455 | CLOSE | 2024-02-29 | 2024-02-27 | KW1-15285 | 2 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-10 | COMP | 2024-03-04 | 15.00 |  | BU | BU table | February | 2024
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 5510-60-V00-0011 | LUMBER, HEAT TREATED, IPPC, 4 X 4 INCHES X 16 FEET | 54794 | 2024-02-21 |  |  | 1 | EA | 35 | [18 empty] | BU | BU table | February | 2024
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 5510-60-V00-0013 | LUMBER, HEAT TREATED, IPPC, 2 X 4 INCHES, 16 FEET | 54791 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 10 | 27.64 | 276.4 | 21739 | CLOSE | 2024-03-02 | 2024-03-02 | KW1-15364 | 9 | 2024-03-02 | APPR | 2024-03-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-03-16 | COMP | 2024-03-05 | 10.00 |  | BU | BU table | February | 2024
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 5510-01-433-1371 | LUMBER, SOFTWOOD, 2 X 6 INCHES X 16 FEET | 54789 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 15 | 30.64 | 459.6 | 21739 | CLOSE | 2024-03-02 | 2024-03-02 | KW1-15364 | 8 | 2024-03-02 | APPR | 2024-03-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-03-16 | COMP | 2024-03-05 | 15.00 |  | BU | BU table | February | 2024
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 54793 | 2024-02-21 | 2024-02-24 | CLOSE | 5 | BX | 20 | 19.81 | 396.2 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 14 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-10 | COMP | 2024-02-27 | 20.00 |  | BU | BU table | February | 2024
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 5305-60-V00-0169 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 3 INCHES | 54793 | 2024-02-21 | 2024-02-24 | CLOSE | 4 | BX | 8 | 30.97 | 247.76 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 13 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-17 | COMP | 2024-02-27 | 8.00 |  | BU | BU table | February | 2024
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 7210-60-V00-0059 | FLOOR COVERING, VINYL RESIN, 3 MM X 40 FEET | 54793 | 2024-02-21 | 2024-02-24 | CLOSE | 3 | RO | 1 | 722.61 | 722.61 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 12 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-10 | COMP | 2024-03-06 | 1.00 |  | BU | BU table | February | 2024
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 8040-00-273-8713 | ADHESIVE, FLOORING, WHITE, 1 GL | 54795 | 2024-02-21 | 2024-02-24 | CLOSE | 3 | GL | 3 | 185.7 | 557.1 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 16 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 3.00 |  | BU | BU table | February | 2024
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 5640-60-V00-0038 | STRIP, ALUMINIUM, 3MM X 1-1/2 INCHES X 12FEET | 54793 | 2024-02-21 | 2024-02-24 | CLOSE | 2 | EA | 5 | 44.96 | 224.8 | 21455 | CLOSE | 2024-02-29 | 2024-02-27 | KW1-15285 | 1 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-10 | COMP | 2024-03-04 | 5.00 |  | BU | BU table | February | 2024
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 54793 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 15 | 45.4 | 681 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 11 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-10 | COMP | 2024-02-27 | 15.00 |  | BU | BU table | February | 2024
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 54795 | 2024-02-21 | 2024-02-24 | CLOSE | 2 | BX | 1 | 143.19 | 143.19 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 15 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-29 | 1.00 |  | BU | BU table | February | 2024
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 54795 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 5 | 13.9 | 69.5 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 14 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 5.00 |  | BU | BU table | February | 2024
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 6515-60-V00-0015 | GLOVES, EXAM, DISPOSABLE, NITRILE, PURPLE, X-LARGE | 54790 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 1 | 49.95 | 49.95 | 21736 | CLOSE | 2024-02-29 |  | KW1-15290 | 4 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-15 | COMP | 2024-03-03 | 1.00 |  | BU | BU table | February | 2024
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 3405-60-V00-0008 | BLADE, RECIPROCATING SAW, METAL, STRAIGHT, 14/18 TPI, 8 X 1 INCHES | 54792 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 3 | 33.3 | 99.9 | 21739 | CLOSE | 2024-03-02 | 2024-03-02 | KW1-15364 | 2 | 2024-03-02 | APPR | 2024-03-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-03-30 | COMP | 2024-03-05 | 3.00 |  | BU | BU table | February | 2024
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 5530-00-618-8073 | PLYWOOD, CONSTRUCTION, 3/4 INCH X 4 X 8 FEET | 54815 | 2024-02-21 | 2024-02-24 | CLOSE | 7 | SH | 15 | 47.45 | 711.75 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 10 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-10 | COMP | 2024-02-27 | 15.00 |  | BU | BU table | February | 2024
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 5530-60-V00-0010 | PLYWOOD, CONSTRUCTION, MARINE GRADE, 3/4 INCH X 8 X 4 FEET | 54815 | 2024-02-21 | 2024-02-24 | CLOSE | 6 | SH | 15 | 61.61 | 924.15 | 21455 | CLOSE | 2024-02-29 | 2024-02-27 | KW1-15285 | 4 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-10 | COMP | 2024-03-04 | 15.00 |  | BU | BU table | February | 2024
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 5510-60-V00-0011 | LUMBER, HEAT TREATED, IPPC, 4 X 4 INCHES X 16 FEET | 54816 | 2024-02-21 |  |  | 1 | EA | 35 | [18 empty] | BU | BU table | February | 2024
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 5510-60-V00-0013 | LUMBER, HEAT TREATED, IPPC, 2 X 4 INCHES, 16 FEET | 54813 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 10 | 27.64 | 276.4 | 21739 | CLOSE | 2024-03-02 | 2024-03-02 | KW1-15364 | 11 | 2024-03-02 | APPR | 2024-03-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-03-16 | COMP | 2024-03-05 | 10.00 |  | BU | BU table | February | 2024
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 5510-01-433-1371 | LUMBER, SOFTWOOD, 2 X 6 INCHES X 16 FEET | 54811 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 15 | 30.64 | 459.6 | 21739 | CLOSE | 2024-03-02 | 2024-03-02 | KW1-15364 | 10 | 2024-03-02 | APPR | 2024-03-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-03-16 | COMP | 2024-03-05 | 15.00 |  | BU | BU table | February | 2024
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 54815 | 2024-02-21 | 2024-02-24 | CLOSE | 5 | BX | 20 | 19.81 | 396.2 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 9 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-10 | COMP | 2024-02-27 | 20.00 |  | BU | BU table | February | 2024
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 5305-60-V00-0169 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 3 INCHES-( | 54815 | 2024-02-21 | 2024-02-24 | CLOSE | 4 | BX | 8 | 30.97 | 247.76 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 8 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-17 | COMP | 2024-02-27 | 8.00 |  | BU | BU table | February | 2024
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 7210-60-V00-0059 | FLOOR COVERING, VINYL RESIN, 3 MM X 40 FEET | 54815 | 2024-02-21 | 2024-02-24 | CLOSE | 3 | RO | 1 | 722.61 | 722.61 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 7 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-10 | COMP | 2024-03-06 | 1.00 |  | BU | BU table | February | 2024
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 8040-00-273-8713 | ADHESIVE, FLOORING, WHITE,( | 54817 | 2024-02-21 | 2024-02-24 | CLOSE | 3 | GL | 3 | 185.7 | 557.1 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 13 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 3.00 |  | BU | BU table | February | 2024
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 5640-60-V00-0038 | STRIP, ALUMINIUM, 3MM X 1-1/2 INCHES X 12FEET | 54815 | 2024-02-21 | 2024-02-24 | CLOSE | 2 | EA | 5 | 44.96 | 224.8 | 21455 | CLOSE | 2024-02-29 | 2024-02-27 | KW1-15285 | 3 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-10 | COMP | 2024-03-04 | 5.00 |  | BU | BU table | February | 2024
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 54815 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 15 | 45.4 | 681 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 6 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-10 | COMP | 2024-02-27 | 15.00 |  | BU | BU table | February | 2024
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 54817 | 2024-02-21 | 2024-02-24 | CLOSE | 2 | BX | 1 | 142 | 142 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 12 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-29 | 1.00 |  | BU | BU table | February | 2024
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 54817 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 5 | 13.9 | 69.5 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 11 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 5.00 |  | BU | BU table | February | 2024
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 6515-60-V00-0015 | GLOVES, EXAM, DISPOSABLE, NITRILE, PURPLE, X-LARGE | 54812 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 1 | 49.95 | 49.95 | 21736 | CLOSE | 2024-02-29 |  | KW1-15290 | 5 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-15 | COMP | 2024-03-03 | 1.00 |  | BU | BU table | February | 2024
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 3405-60-V00-0008 | BLADE, RECIPROCATING SAW, METAL, STRAIGHT, 14/18 TPI, 8 X 1 INCHES | 54814 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 3 | 33.3 | 99.9 | 21739 | CLOSE | 2024-03-02 | 2024-03-02 | KW1-15364 | 12 | 2024-03-02 | APPR | 2024-03-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-03-30 |  |  |  |  | BU | BU table | February | 2024
77 | 2024-02-21 | 30 | BU24-0175 | Paint Floor Lines Z3 VLAM005 | 9790969 | 8010-60-V00-0067 | PAINT, TRAFFIC, GLOSS, YELLOW, 16 LITERS | 54832 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | CN | 6 | 188.84 | 1133.04 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 10 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 6.00 |  | BU | BU table | February | 2024
77 | 2024-02-21 | 30 | BU24-0175 | Paint Floor Lines Z3 VLAM005 | 9790969 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 54834 | 2024-02-21 | 2024-02-24 | CLOSE | 3 | EA | 10 | 29 | 290 | 21463 | CLOSE | 2024-02-25 |  | KW1-15178 | 4 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 10.00 |  | BU | BU table | February | 2024
77 | 2024-02-21 | 30 | BU24-0175 | Paint Floor Lines Z3 VLAM005 | 9790969 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 54834 | 2024-02-21 | 2024-02-24 | CLOSE | 2 | EA | 5 | 13.9 | 69.5 | 21463 | CLOSE | 2024-02-25 |  | KW1-15178 | 3 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 5.00 |  | BU | BU table | February | 2024
77 | 2024-02-21 | 30 | BU24-0175 | Paint Floor Lines Z3 VLAM005 | 9790969 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 54834 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 10 | 2.4 | 24 | 21463 | CLOSE | 2024-02-25 |  | KW1-15178 | 2 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 10.00 |  | BU | BU table | February | 2024
77 | 2024-02-21 | 30 | BU24-0175 | Paint Floor Lines Z3 VLAM005 | 9790969 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 54833 | 2024-02-21 | 2024-02-24 | CLOSE | 2 | EA | 10 | 14.6 | 146 |  |  |  |  | KW1-15232 | 2 | 2024-02-27 | APPR | 2024-02-27 | Reghuraman, Karthik -Vectrus -GSD -No Export | MARATHON INC TRADING LLC | 2024-03-31 07:00 | COMP | 2024-02-29 | 10.00 |  | BU | BU table | February | 2024
77 | 2024-02-21 | 30 | BU24-0175 | Paint Floor Lines Z3 VLAM005 | 9790969 | 7510-00-266-6710 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 54833 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 20 | 8 | 160 |  |  |  |  | KW1-15232 | 1 | 2024-02-27 | APPR | 2024-02-27 | Reghuraman, Karthik -Vectrus -GSD -No Export | MARATHON INC TRADING LLC | 2024-03-12 07:00 | COMP | 2024-02-29 | 20.00 |  | BU | BU table | February | 2024
77 | 2024-02-21 | 30 | BU24-0175 | Paint Floor Lines Z3 VLAM005 | 9790969 | 6515-60-V00-0015 | GLOVES, EXAM, DISPOSABLE, NITRILE, PURPLE, X-LARGE | 54831 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | BX | 1 | 49.95 | 49.95 | 21736 | CLOSE | 2024-02-29 |  | KW1-15290 | 6 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-15 | COMP | 2024-03-03 | 1.00 |  | BU | BU table | February | 2024
78 | 2024-02-21 | 30 | BU24-0143 | Install Overhead Lights B9501AB | 9360741 | 5925-60-V00-0267 | CIRCUIT BREAKER, MINIATURE, 1 POLE, 230-400V, 10A | 54838 | 2024-02-21 | 2024-02-24 | CLOSE | 3 | EA | 2 | 11.63 | 23.26 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 9 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 2.00 |  | BU | BU table | February | 2024
78 | 2024-02-21 | 30 | BU24-0143 | Install Overhead Lights B9501AB | 9360741 | 6210-60-V00-0094 | FIXTURE, LIGHTING, LED, RETROFIT, POLYCARBONATE, PURE WHITE, 40W | 54838 | 2024-02-21 | 2024-02-24 | CLOSE | 2 | EA | 9 | 242.35 | 2181.15 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 8 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 9.00 |  | BU | BU table | February | 2024
78 | 2024-02-21 | 30 | BU24-0143 | Install Overhead Lights B9501AB | 9360741 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 54838 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | ROLL | 1 | 145.35 | 145.35 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 7 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 1.00 |  | BU | BU table | February | 2024
79 | 2024-02-21 | 30 | BU24-0172 | (TT404) NEED TO FIX DAMAGE FLOOR | 9790884 | 8010-00-597-7856 | VARNISH, OIL, GLOSS, CLEAR, 1 GL | 54841 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | CN | 6 | 247.6 | 1485.6 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 6 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 |  |  |  |  | BU | BU table | February | 2024
79 | 2024-02-21 | 30 | BU24-0172 | (TT404) NEED TO FIX DAMAGE FLOOR | 9790884 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 54842 | 2024-02-21 | 2024-02-24 | CLOSE | 3 | EA | 6 | 29 | 174 | 21463 | CLOSE | 2024-02-25 |  | KW1-15178 | 7 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 6.00 |  | BU | BU table | February | 2024
79 | 2024-02-21 | 30 | BU24-0172 | (TT404) NEED TO FIX DAMAGE FLOOR | 9790884 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 54842 | 2024-02-21 | 2024-02-24 | CLOSE | 2 | EA | 10 | 13.99 | 139.9 | 21463 | CLOSE | 2024-02-25 |  | KW1-15178 | 6 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 10.00 |  | BU | BU table | February | 2024
79 | 2024-02-21 | 30 | BU24-0172 | (TT404) NEED TO FIX DAMAGE FLOOR | 9790884 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 54842 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 10 | 2.4 | 24 | 21463 | CLOSE | 2024-02-25 |  | KW1-15178 | 5 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 10.00 |  | BU | BU table | February | 2024
79 | 2024-02-21 | 30 | BU24-0172 | (TT404) NEED TO FIX DAMAGE FLOOR | 9790884 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 54840 | 2024-02-21 | 2024-02-24 | CLOSE | 2 | EA | 10 | 14.6 | 146 |  |  |  |  | KW1-15232 | 4 | 2024-02-27 | APPR | 2024-02-27 | Reghuraman, Karthik -Vectrus -GSD -No Export | MARATHON INC TRADING LLC | 2024-03-31 07:00 | COMP | 2024-02-29 | 10.00 |  | BU | BU table | February | 2024
79 | 2024-02-21 | 30 | BU24-0172 | (TT404) NEED TO FIX DAMAGE FLOOR | 9790884 | 7510-00-266-6710 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 54840 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 20 | 8 | 160 |  |  |  |  | KW1-15232 | 3 | 2024-02-27 | APPR | 2024-02-27 | Reghuraman, Karthik -Vectrus -GSD -No Export | MARATHON INC TRADING LLC | 2024-03-12 07:00 | COMP | 2024-02-29 | 20.00 |  | BU | BU table | February | 2024
79 | 2024-02-21 | 30 | BU24-0172 | (TT404) NEED TO FIX DAMAGE FLOOR | 9790884 | 6515-60-V00-0015 | GLOVES, EXAM, DISPOSABLE, NITRILE, PURPLE, X-LARGE | 54839 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | BX | 1 | 49.95 | 49.95 | 21579 | CLOSE | 2024-03-01 |  | KW1-15331 | 1 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-09 07:00 | COMP | 2024-03-05 | 1.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5340-60-V00-0505 | RAIN GUARD, DOOR, ALUMINUM, 236.22 X 4 INCHES | 55566 | 2024-02-28 | 2024-02-29 | CLOSE | 3 | EA | 2 | 53.63 | 107.26 | 21797 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15336 | 2 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MARATHON INC TRADING LLC | 2024-04-12 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 55565 | 2024-02-28 | 2024-02-29 | CLOSE | 2 | BX | 1 | 29.37 | 29.37 |  |  |  |  | KW1-15346 | 5 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5610-60-V00-0001 | CEMENT, MASONRY, (MORTAR MIX), TYPE- N, 60 LB | 55565 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | BG | 1 | 26.4 | 26.4 |  |  |  |  | KW1-15346 | 4 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5340-60-V00-0481 | HINGE, DOOR, STAINLESS STEEL, 3 MM X 3-1/2 X 4 INCHES | 55568 | 2024-02-28 | 2024-02-29 | CLOSE | 4 | EA | 1 | 29.9 | 29.9 |  |  |  |  | KW1-15346 | 9 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5620-60-V00-0043 | CONCRETE SPLASH BLOCK | 55568 | 2024-02-28 | 2024-02-29 | CLOSE | 3 | EA | 4 | 79.2 | 316.8 |  |  |  |  | KW1-15346 | 8 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 4.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 55569 | 2024-02-28 | 2024-02-29 | CLOSE | 4 | BX | 1 | 142 | 142 |  |  |  |  | KW1-15340 | 12 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-22 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 8010-60-V00-0095 | PRIMER, COATING, RED OXIDE, LIQUID, 3.78 TO 4 LITERS | 55569 | 2024-02-28 | 2024-02-29 | CLOSE | 3 | CN | 1 | 41.3 | 41.3 |  |  |  |  | KW1-15340 | 10 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 8010-60-V00-0028 | PAINT, ENAMEL, GLOSS, DESERT SAND, 3.6 LITER | 55569 | 2024-02-28 | 2024-02-29 | CLOSE | 5 | CN | 1 | 39.6 | 39.6 |  |  |  |  | KW1-15340 | 9 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 55567 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | EA | 2 | 14.6 | 29.2 | 21797 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15336 | 3 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MARATHON INC TRADING LLC | 2024-04-20 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 55569 | 2024-02-28 | 2024-02-29 | CLOSE | 2 | EA | 2 | 29 | 58 |  |  |  |  | KW1-15340 | 11 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 7210-60-V00-0059 | FLOOR COVERING, VINYL RESIN, 3 MM X 40 FEET | 55568 | 2024-02-28 | 2024-02-29 | CLOSE | 2 | RL | 1 | 716.1 | 716.1 |  |  |  |  | KW1-15346 | 7 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 |  |  |  |  | BU | BU table | February | 2024
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 55568 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | EA | 12 | 45.4 | 544.8 |  |  |  |  | KW1-15346 | 6 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 12.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 8040-60-V00-0027 | TAPE, ADHESIVE, POLY FOAM, OPEN CELL, BLACK, 12.7 X 19 MM X 5 METERS | 55566 | 2024-02-28 | 2024-02-29 | CLOSE | 2 | RO | 2 | 19.8 | 39.6 | 21802 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15339 | 1 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5640-60-V00-0032 | WEATHER STRIP, DOOR, W/RUBBER BOTTOM SWEEP, 39" | 55564 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | EA | 2 | 16.17 | 32.34 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 13 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-09 07:00 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5640-60-V00-0035 | WEATHER STRIP, DOOR, W/BRUSH, 2 X 36 INCHES | 55563 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | EA | 2 | 53.3 | 106.6 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 12 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-09 07:00 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 8040-00-273-8713 | ADHESIVE, FLOORING, WHITE, 1 GL | 55569 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | GL | 4 | 185.7 | 742.8 |  |  |  |  | KW1-15340 | 13 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 4.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5110-60-V00-0077 | KNIFE, PUTTY, 3 INCHES | 55566 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | EA | 3 | 11.55 | 34.65 |  |  |  |  | KW1-15338 | 1 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 3.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 40 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 4730-60-V00-0869 | ELBOW, PIPE, SCH-40, SOCKET X SOCKET, 90°, PVC, GRAY, 63 MM | 55573 | 2024-02-28 | 2024-02-29 | CLOSE | 3 | EA | 8 | 4.3 | 34.4 |  |  |  |  | KW1-15346 | 12 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 8.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 40 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 4710-60-V00-0103 | PIPE, PLASTIC, SCH-40, UPVC, GRAY, 2 INCHES | 55573 | 2024-02-28 | 2024-02-29 | CLOSE | 2 | EA | 1 | 31.4 | 31.4 |  |  |  |  | KW1-15346 | 11 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 40 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 4730-60-V00-0428 | ELBOW, PIPE, SOCKET X SOCKET, 45 °, PVC, GRAY, 63 MM | 55573 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | EA | 4 | 24.6 | 98.4 |  |  |  |  | KW1-15346 | 10 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 4.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 40 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 8040-60-V00-0040 | CEMENT, HEAVY BODIED, CPVC, ORANGE, 16 OZ | 55574 | 2024-02-28 | 2024-02-29 | CLOSE | 2 | EA | 1 | 18.2 | 18.2 |  |  |  |  | KW1-15340 | 14 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 40 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 7930-60-V00-0046 | CLEANER, PVC/CPVC, CLEAR, 8 FL OUNCES | 55572 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | EA | 1 | 21.65 | 21.65 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 14 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-09 07:00 | COMP | 2024-03-05 | 1.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 40 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 4510-60-V00-0132 | STRAP, METAL | 55574 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | EA | 1 | 73.9 | 73.9 |  |  |  |  | KW1-15340 | 1 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 40 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5610-60-V00-0009 | GRAVEL (CUSTOMIZED) | 55654 | 2024-02-28 | 2024-03-03 | CLOSE | 1 | CZ | 1 | 94.25 | 94.25 | 22027 | CLOSE | 2024-03-08 | 2024-03-06 | KW1-15482 | 10 | 2024-03-08 | APPR | 2024-03-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-15 07:00 |  |  |  |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 6145-60-V00-0142 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4 MM ² | 55593 | 2024-02-28 | 2024-03-01 | CLOSE | 3 | MT | 25 | 65.51 | 1637.75 |  |  |  |  | KW1-15347 | 5 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-09 07:00 | COMP | 2024-03-04 | 25.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 6145-60-V00-0139 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 6 MM ² | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 10 | YD | 25 | 28.1 | 702.5 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 11 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 25.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0421 | LUG, TERMINAL, ROUND TYPE, ONE-HOLE, 6MM² X 6MM | 55595 | 2024-02-28 | 2024-03-01 | CLOSE | 3 | PG | 1 | 70 | 70 |  |  |  |  | KW1-15352 | 3 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0425 | LUG, TERMINAL, ROUND TYPE, ONE-HOLE, 10MM X M6 | 55592 | 2024-02-28 | 2024-03-01 | CLOSE | 1 | EA | 10 | 6.93 | 69.3 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 1 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-04-12 | COMP | 2024-03-04 | 10.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-00-727-5153 | STRAP, TIE DOWN, ELECTRICAL COMPONENTS, 3.9 INCHES | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 9 | HD | 1 | 81.2 | 81.2 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 10 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-01-223-8533 | STRAP, TIE DOWN, ELECTRICAL COMPONENTS, PLASTIC POLYAMIDE, 0.1 X 8 INCHES | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 8 | PG | 1 | 66.48 | 66.48 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 9 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 7510-01-490-7265 | TAPE, LABELING, BLACK ON WHITE, 1/2 INCH X 26 FEET | 55595 | 2024-02-28 | 2024-03-01 | CLOSE | 2 | EA | 1 | 29.7 | 29.7 |  |  |  |  | KW1-15354 | 1 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MARATHON INC TRADING LLC | 2024-03-15 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 7 | EA | 10 | 3.5 | 35 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 8 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 10.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0511 | GLAND, ELECTRICAL CONDUIT, BRASS, BW, w/ EARTH TAG, 25 MM | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 6 | EA | 2 | 8 | 16 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 7 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0128 | TRAY, CABLE, STRAIGHT, MEDIUM DUTY, GALVANIZED STEEL, 450 MM X 3 METERS | 55597 | 2024-02-28 | 2024-03-01 | APPR | 2 | MT | 4 | 77.55 | 310.2 | 21808 | SENT | 2024-03-08 | 2024-03-03 | [12 empty] | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0108 | RACEWAY, METALLIC, GALVANISED STEEL, 150 X 100 MM, 10 FEET | 55591 | 2024-02-28 | 2024-02-29 | CLOSE | 2 | EA | 3 | 503.25 | 1509.75 |  |  |  |  | KW1-15347 | 4 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-04-30 07:00 |  |  |  |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5940-60-V00-0077 | TERMINAL STRIP, GROUNDING, 12 WAY, PLASTIC, WHITE, 16 MM ², 30A | 55594 | 2024-02-28 | 2024-03-01 | CLOSE | 1 | EA | 5 | 23.1 | 115.5 |  |  |  |  | KW1-15352 | 1 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-22 |  |  |  |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0480 | JUNCTION BOX, w/ BLANK SIDE, 100 X 100 X 50 MM | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 5 | EA | 3 | 12 | 36 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 6 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 3.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0477 | JUNCTION BOX, CIRCULAR, 3-WAY, GALVANIZED MALLEABLE IRON, 20 X 20 X 25 MM | 55591 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | EA | 3 | 44.55 | 133.65 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 15 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-09 07:00 | COMP | 2024-03-09 | 3.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5970-01-013-9369 | TAPE, INSULATION, ELECTRICAL, RED, 3/4 X 792 INCHES | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 4 | RL | 2 | 10.1 | 20.2 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 5 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 3 | RL | 2 | 21.11 | 42.22 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 4 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5970-60-v00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 55595 | 2024-02-28 | 2024-03-01 | CLOSE | 1 | RO | 2 | 16.5 | 33 |  |  |  |  | KW1-15352 | 2 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 4240-60-V00-0054 | TAPE, BARRICADE, "CAUTION BURIED ELECTRIC LINE BELOW", 3 INCHES X 1000 FEET | 55593 | 2024-02-28 | 2024-03-01 | CLOSE | 2 | RO | 2 | 239.75 | 479.5 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 17 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-09 07:00 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0209 | RACEWAY, METALLIC, GALVANIZED STEEL, 2 X 2 INCHES X 10 FEET | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 2 | EA | 2 | 56.21 | 112.42 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 3 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0161 | RACEWAY, NON-METALLIC (CABLE TRUNKING), UPVC, WHITE, 50 X 50MM X 3 METER 12 | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 1 | EA | 2 | 25.25 | 50.5 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 2 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 4210-60-V00-0189 | EXTINGUISHER, FIRE, ABC DRY CHEMICAL W/ WALL HOOK, 10 LBS | 55593 | 2024-02-28 | 2024-03-01 | CLOSE | 1 | EA | 1 | 274.73 | 274.73 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 16 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-04-30 07:00 |  |  |  |  | BU | BU table | February | 2024
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 7125-09-V00-0027 | CABINET, FIRE EXTINGUISHER, SURFACE MOUNT, POLYSTYRENE, ACRYLIC, 20 LBS | 55597 | 2024-02-28 | 2024-03-01 | APPR | 1 | EA | 2 | 93.83 | 187.66 | 21808 | SENT | 2024-03-08 | 2024-03-03 | KW1-15472 | 1 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-04-19 |  |  |  |  | BU | BU table | February | 2024
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5975-60-V00-0391 | SOCKET, PLUG-IN ELECTRONIC COMPONENT, OUTLET, SHUTTERED, 2 GANG, 15A, 127V | 55476 | 2024-02-27 | 2024-02-29 | CLOSE | 3 | EA | 6 | 42.5 | 255 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 8 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-15 07:00 | COMP | 2024-03-05 | 6.00 |  | BU | BU table | February | 2024
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5975-60-V00-0208 | BOX, METAL CLAD, SURFACE MOUNT, 2 GANG, 20MM | 55480 | 2024-02-27 | 2024-02-29 | CLOSE | 7 | EA | 6 | 11.02 | 66.12 |  |  |  |  | KW1-15340 | 4 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 6.00 |  | BU | BU table | February | 2024
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5975-60-V00-0254 | COVER, JUNCTION BOX, BLANKING PLATE, STEEL, 1 GANG, GRAY, 79 X 79 X 42 MM | 55480 | 2024-02-27 | 2024-02-29 | CLOSE | 6 | EA | 10 | 6.27 | 62.7 |  |  |  |  | KW1-15340 | 5 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 10.00 |  | BU | BU table | February | 2024
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 6145-60-V00-0136 | WIRE, ELECTRICAL, RED, 1 CORE, 4MM² | 55480 | 2024-02-27 | 2024-02-29 | CLOSE | 5 | RO | 1 | 90.56 | 90.56 |  |  |  |  | KW1-15340 | 6 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 6145-60-V00-0154 | WIRE, ELECTRICAL, BLACK, 1 CORE, 4MM² | 55480 | 2024-02-27 | 2024-02-29 | CLOSE | 4 | RO | 1 | 90.56 | 90.56 |  |  |  |  | KW1-15340 | 7 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 6145-60-V00-0143 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4MM² | 55478 | 2024-02-27 | 2024-02-29 | CLOSE | 2 | RO | 1 | 90 | 90 | 21792 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15330 | 2 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5975-60-V00-0743 | BOX CONNECTOR, ELECTRICAL, CONDUIT, SET SCREW, STEEL, 3/4 INCH | 55476 | 2024-02-27 | 2024-02-29 | CLOSE | 2 | EA | 30 | 17.16 | 514.8 |  |  |  |  | KW1-15347 | 2 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 07:00 |  |  |  |  | BU | BU table | February | 2024
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5975-60-V00-0376 | COUPLING, CONDUIT, w/ SET SCREW, STEEL, 3/4 INCH | 55476 | 2024-02-27 | 2024-02-29 | CLOSE | 1 | EA | 5 | 1.95 | 9.75 |  |  |  |  | KW1-15347 | 1 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-22 07:00 | COMP | 2024-03-04 | 5.00 |  | BU | BU table | February | 2024
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5975-00-178-1217 | CONDUIT, RIGID, EMT, GALVANIZED STEEL, 3/4" INCH X 10 FEET | 55478 | 2024-02-27 | 2024-02-29 | CLOSE | 1 | EA | 10 | 14.9 | 149 | 21792 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15330 | 1 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-03-04 | 10.00 |  | BU | BU table | February | 2024
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5133-60-V00-0002 | DRILL, MULTI-STEP, (BIT), TITANIUM, 4 PIECES | 55477 | 2024-02-27 | 2024-02-29 | CLOSE | 2 | SE | 2 | 287.1 | 574.2 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15419 | 1 | 2024-03-05 | APPR | 2024-03-05 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-12 07:00 |  |  |  |  | BU | BU table | February | 2024
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 8040-01-024-6988 | SUPER GLUE, INSTANT ADHESIVE, 3500PSI, CLEAR, 20G | 55477 | 2024-02-27 | 2024-02-29 | CLOSE | 1 | EA | 5 | 108.57 | 542.85 |  |  |  |  | KW1-15347 | 3 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-04-30 07:00 |  |  |  |  | BU | BU table | February | 2024
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5935-60-V00-0167 | CONNECTOR, WIRE, RED, 18 -10 AWG | 55480 | 2024-02-27 | 2024-02-29 | CLOSE | 3 | PG | 2 | 25.3 | 50.6 |  |  |  |  | KW1-15340 | 2 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5975-00-111-3208 | STRAP, TIE DOWN, ELECTRICAL COMPONENTS, PLASTIC, NATURAL, 0.146 X 0.055 X 4.680 INCHES | 55480 | 2024-02-27 | 2024-02-29 | CLOSE | 2 | HD | 20 | 1.31 | 26.2 |  |  |  |  | KW1-15340 | 3 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 20.00 |  | BU | BU table | February | 2024
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 6150-60-V00-0012 | REEL, CABLE, 4 WAY, 50 METERS, 13A | 55480 | 2024-02-27 | 2024-02-29 | CLOSE | 1 | EA | 2 | 230.62 | 461.24 |  |  |  |  | KW1-15340 | 8 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5305-60-V00-0002 | SCREW, SELF DRILLING, PHILIPS, MODIFIED TRUSS HEAD, #8 X 1-1/2 INCHES | 55479 | 2024-02-27 | 2024-02-29 | CLOSE | 1 | BX | 1 | 29.5 | 29.5 |  |  |  |  | KW1-15346 | 2 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 5307-60-V00-0021 | STUD, DRYWALL FRAME, U-CHANNEL, GALVANIZED STEEL, 3 X 1-1/4 INCHES X 12 FEET | 55474 | 2024-02-27 | 2024-02-29 | CLOSE | 5 | EA | 2 | 6.34 | 12.68 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 7 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-09 07:00 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 5305-60-V00-0220 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, STEEL, #6 X 2 INCHES | 55469 | 2024-02-27 | 2024-02-28 | CLOSE | 3 | BX | 1 | 52 | 52 | 21682 | CLOSE | 2024-03-01 | 2024-02-29 | KW1-15335 | 8 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2024-03-09 07:00 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 5640-60-V00-0048 | DRYWALL SHEET, (GYPSUM BOARD), 4 X 8 FEET X 1/2 INCH | 55474 | 2024-02-27 | 2024-02-29 | CLOSE | 4 | EA | 2 | 19.1 | 38.2 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 6 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-09 07:00 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 5305-60-V00-0157 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, COARSE THREAD, #7 X 1-3/8 INCHES 1000pc/box | 55469 | 2024-02-27 | 2024-02-28 | CLOSE | 2 | BX | 1 | 23.1 | 23.1 | 21682 | CLOSE | 2024-03-01 | 2024-02-29 | KW1-15335 | 7 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2024-03-09 07:00 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 5640-60-V00-0044 | TAPE, SELF ADHESIVE, DRYWALL JOINT, FIBERGLASS, 2 INCHES X 300 FEET | 55470 | 2024-02-27 | 2024-02-28 | CLOSE | 1 | EA | 1 | 18.2 | 18.2 | 21682 | CLOSE | 2024-03-01 | 2024-02-29 | KW1-15335 | 9 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2024-03-09 07:00 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 55474 | 2024-02-27 | 2024-02-29 | CLOSE | 3 | CN | 1 | 37 | 37 |  |  |  |  | KW1-15349 | 3 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 07:00 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 7510-00-680-2395 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 55469 | 2024-02-27 | 2024-02-28 | CLOSE | 1 | RO | 1 | 12.67 | 12.67 | 21682 | CLOSE | 2024-03-01 | 2024-02-29 | KW1-15335 | 6 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2024-03-09 07:00 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 5350-60-V00-0007 | PAPER, ABRASIVE (SANDPAPER), 120 GRIT, 9 X 11 INCHES | 55474 | 2024-02-27 | 2024-02-29 | CLOSE | 2 | EA | 10 | 4.2 | 42 |  |  |  |  | KW1-15349 | 2 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 07:00 | COMP | 2024-03-04 | 10.00 |  | BU | BU table | February | 2024
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 8010-60-V00-0241 | PRIMER, PAINT, LATEX, INTERIOR, WATERBASED, WHITE, 5 GALLON | 55474 | 2024-02-27 | 2024-02-29 | CLOSE | 1 | CN | 1 | 55.08 | 55.08 |  |  |  |  | KW1-15349 | 1 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-23 07:00 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 8010-60-V00-0130 | PAINT, LATEX, MATT, WHITE, 1 GL (3.2 TO 3.6 LT) | 55475 | 2024-02-27 | 2024-02-29 | CLOSE | 4 | CN | 1 | 42.2 | 42.2 | 21790 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15329 | 4 | 2024-03-02 | APPR | 2024-03-02 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-03-07 | 1.00 |  | BU | BU table | February | 2024
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 8010-60-V00-0028 | PAINT, ENAMEL, GLOSS, DESERT SAND, 3.6 LITER | 55475 | 2024-02-27 | 2024-02-29 | CLOSE | 3 | CN | 1 | 39.6 | 39.6 | 21790 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15329 | 3 | 2024-03-02 | APPR | 2024-03-02 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 55473 | 2024-02-27 | 2024-02-29 | CLOSE | 1 | EA | 2 | 14.6 | 29.2 | 21797 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15336 | 1 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MARATHON INC TRADING LLC | 2024-04-20 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 55475 | 2024-02-27 | 2024-02-29 | CLOSE | 2 | EA | 2 | 13.9 | 27.8 | 21790 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15329 | 2 | 2024-03-02 | APPR | 2024-03-02 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUAR | 55475 | 2024-02-27 | 2024-02-29 | CLOSE | 1 | EA | 2 | 29 | 58 | 21790 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15329 | 1 | 2024-03-02 | APPR | 2024-03-02 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 5680-09-V00-0001 | CORNER BEAD, QUICKSILVER, METAL, 8 FEET X 1-1/4 INCHES | 55472 | 2024-02-27 | 2024-02-29 | CLOSE | 1 | ea | 2 | 8.42 | 16.84 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 5 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-04-30 07:00 |  |  |  |  | BU | BU table | February | 2024
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 8415-01-492-0179 | GLOVES, DISPOSABLE, LATEX FREE, NITRILE, MEDIUM | 55471 | 2024-02-27 | 2024-02-28 | CLOSE | 1 | BX | 1 | 18.48 | 18.48 |  |  |  |  | KW1-15265 | 1 | 2024-02-28 | APPR | 2024-02-28 | Narayana Kutty Pillai, Nisha - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-05-31 | COMP | 2024-03-02 | 1.00 |  | BU | BU table | February | 2024
83 | 2024-02-24 |  | BU24-0177 | Replace Electrical Cable Z1 B103 |  |  |  | PRINPRG | [23 empty] | CATALOG INPRG | BU | BU table | February | 2024
84 | 2024-02-29 | 50 | BU23-223 | TI Deficiency Repairs Zone6 TT6078 - C to TDP | 7562117 | 5340-60-V00-0213 | VERTICAL ROD EXIT DEVICE, SURFACE, 1-1/2 HOUR FIRE-LISTED, SATIN STAINLESS STEEL, LHR | 55705 | 2024-02-29 | 2024-03-03 | CLOSE | 1 | EA | 1 | 2046 | 2046 | 21896 | SENT | 2024-03-08 | 2024-03-05 | KW1-15486 | 3 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-04-30 |  |  |  |  | BU | BU table | February | 2024
84 | 2024-02-29 | 70 | BU23-223 | TI Deficiency Repairs Zone6 TT6078 - C to TDP | 7562117 | 5340-60-V00-0213 | VERTICAL ROD EXIT DEVICE, SURFACE, 1-1/2 HOUR FIRE-LISTED, SATIN STAINLESS STEEL, LHR | 55697 | 2024-02-29 | 2024-03-03 | CLOSE | 1 | EA | 1 | 2046 | 2046 | 21896 | SENT | 2024-03-08 | 2024-03-05 | KW1-15486 | 1 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-04-30 |  |  |  |  | BU | BU table | February | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5660-60-V00-0033 | FENCE, GALVANIZED STEEL, CHAIN LINK MESH, 50 x 10 FEET | 56039 | 2024-03-04 | 2024-03-07 | APPR | 13 | RL | 1 | 500.6 | 500.6 |  |  |  |  | KW1-15459 | 16 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 |  |  |  |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5650-60-V01-0003 | C-STUD RUNNER, STEEL, 0.0366IN X 1¼" X 3" X 12FT | 56039 | 2024-03-04 | 2024-03-07 | APPR | 12 | EA | 14 | 6.3 | 88.2 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5307-60-V00-0021 | STUD, DRYWALL FRAME, U-CHANNEL, GALVANIZED STEEL, 3 X 1-1/4 INCHES X 12 FEET | 56034 | 2024-03-04 | 2024-03-07 | APPR | 2 | EA | 14 | 6.27 | 87.78 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5640-60-V00-0048 | DRYWALL SHEET, (GYPSUM BOARD), 4 X 8 FEET X 1/2 INCH | 56034 | 2024-03-04 | 2024-03-07 | APPR | 1 | EA | 15 | 19.1 | 286.5 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5340-05-V00-0095 | HINGE, BUTT, CABINET, PIANO, STEEL, 1-1/2 X 12 INCHES | 56041 | 2024-03-04 | 2024-03-07 | APPR | 5 | EA | 2 | 14.79 | 29.58 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 56039 | 2024-03-04 | 2024-03-07 | APPR | 11 | BX | 2 | 19.6 | 39.2 |  |  |  |  | KW1-15459 | 15 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 2.00 |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STAINLESS STEEL, 10 X 3/4 INCHES 100pc / bx | 56039 | 2024-03-04 | 2024-03-07 | APPR | 1 | BX | 3 | 29.4 | 88.2 |  |  |  |  | KW1-15459 | 6 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 3.00 |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 56039 | 2024-03-04 | 2024-03-07 | APPR | 10 | CN | 1 | 37 | 37 |  |  |  |  | KW1-15459 | 14 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 1.00 |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5640-60-V00-0044 | TAPE, SELF ADHESIVE, DRYWALL JOINT, FIBERGLASS, 2 INCHES X 300 FEET | 56035 | 2024-03-04 | 2024-03-07 | APPR | 1 | EA | 2 | 18.48 | 36.96 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8010-60-V00-0006 | PAINT, LATEX, MATT, OFF-WHITE, 3.2 LITER | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 10 | CN | 2 | 44 | 88 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 9 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 9 | EA | 4 | 29 | 116 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 8 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 8 | EA | 2 | 13.9 | 27.8 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 7 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8020-00-682-6489 | COVER, PAINT ROLLER, ACRYLIC, 0.375 X 7 INCHES | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 7 | EA | 3 | 14.2 | 42.6 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 6 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-04-30 |  |  |  |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 56038 | 2024-03-04 | 2024-03-07 | CLOSE | 2 | EA | 4 | 14.6 | 58.4 | 22161 | CLOSE | 2024-03-07 |  | KW1-15460 | 2 | 2024-03-07 | APPR | 2024-03-07 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-04-18 |  |  |  |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 7510-00-266-6710 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 56038 | 2024-03-04 | 2024-03-07 | CLOSE | 1 | EA | 2 | 8 | 16 | 22161 | CLOSE | 2024-03-07 |  | KW1-15460 | 1 | 2024-03-07 | APPR | 2024-03-07 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 56039 | 2024-03-04 | 2024-03-07 | APPR | 9 | ea | 8 | 45.4 | 363.2 |  |  |  |  | KW1-15459 | 13 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 8.00 |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8030-01-075-1156 | CAULKING COMPOUND, CARTRIDGE, WHITE, 10 OZ | 56039 | 2024-03-04 | 2024-03-07 | APPR | 8 | ea | 10 | 14.9 | 149 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5335-60-V00-0001 | WIRE MESH, GALVANIZED STEEL, 21 GAGE, 4 X 50 FEET | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 6 | rool | 1 | 39.7 | 39.7 | 22149 | CLOSE | 2024-03-07 |  | KW1-15453 | 2 | 2024-03-07 | APPR | 2024-03-07 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 56037 | 2024-03-04 | 2024-03-07 | CLOSE | 1 | bx | 1 | 19.47 | 19.47 | 22164 | CLOSE | 2024-03-07 |  | KW1-15462 | 1 | 2024-03-09 | APPR | 2024-03-09 | Santhumayor, Santhosh - Vectrus - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-04-30 |  |  |  |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8010-60-V00-0089 | PRIMER COATING, WHITE, 1 GL | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 5 | gal | 2 | 41.3 | 82.6 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 5 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5130-60-V00-0123 | WHEEL, ABRASIVE, ALUMINUM OXIDE, 12,225 RPM, 5 X 1/16 X 7/8 INCHES | 56039 | 2024-03-04 | 2024-03-07 | APPR | 7 | EA | 6 | 15 | 90 |  |  |  |  | KW1-15459 | 12 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 6.00 |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5130-60-V00-0134 | BIT, SCREWDRIVER, (POWER BIT), PHILLIPS, STEEL, #2 X 2 INCHES | 56039 | 2024-03-04 | 2024-03-07 | APPR | 6 | pg | 1 | 14.8 | 14.8 |  |  |  |  | KW1-15459 | 11 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 1.00 |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5350-60-V00-0007 | PAPER, ABRASIVE (SANDPAPER), 120 GRIT, 9 X 11 INCHES | 56039 | 2024-03-04 | 2024-03-07 | APPR | 5 | ea | 10 | 4.2 | 42 |  |  |  |  | KW1-15459 | 10 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 10.00 |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5680-60-V01-0002 | CORNER BEAD, STAINLESS STEEL, 25 MM X2.5 METER | 56033 | 2024-03-04 | 2024-03-07 | APPR | 3 | ea | 10 | 108.9 | 1089 | 22173 | SENT | 2024-03-07 | 2024-03-10 | [12 empty] | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5130-60-V00-0125 | DISK, ABRASIVE, SANDING, HOOK AND LOOP, 220 GRIT, 8 HOLE, 5 INCHES-DUSTLESS HOOK AND LOOP SANDING DISC | 56039 | 2024-03-04 | 2024-03-07 | APPR | 4 | bx | 1 | 45.7 | 45.7 |  |  |  |  | KW1-15459 | 9 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 1.00 |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 4710-05-V00-0007 | TUBE, RECTANGULAR, STEEL, 3 X 1-1/2 X 1/8 INCHES x 20ft | 56033 | 2024-03-04 | 2024-03-07 | APPR | 2 | ea | 4 | 41.25 | 165 | 22173 | SENT | 2024-03-07 | 2024-03-10 | [12 empty] | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5306-60-V00-0100 | CARRIAGE BOLT 8M X 4 1/4" WITH NUT AND WASHER SQUARE NECK | 56036 | 2024-03-04 | 2024-03-07 | APPR | 1 | ea | 20 | 3.63 | 72.6 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5340-60-V00-0116 | LOCK, FLUSH, CABINET AND DRAWER, STEEL, GOLD, 1.8 X 1.3 INCHES | 56041 | 2024-03-04 | 2024-03-07 | APPR | 4 | ea | 1 | 13.2 | 13.2 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GL | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 4 | GAL | 1 | 54.6 | 54.6 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 4 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8010-00-297-0584 | PAINT, ENAMEL, SEMIPAINT, ENAMEL, SEMIGLOSPAINT, ENAMEL, SEMIGLOSS, WHITE, 1 GLS, WHITE, 1 GLGLOSS, WHITE, 1 GL | 56062 | 2024-03-04 | 2024-03-07 | APPR | 1 | GAL | 1 | 41.53 | 41.53 | 22172 | SENT | 2024-03-07 | 2024-03-10 | [12 empty] | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8010-60-V00-0124 | PRIMER, RED OXIDE, OIL BASED, RED, 1 GL | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 3 | gal | 1 | 41.4 | 41.4 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 3 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 2 | EA | 3 | 12.4 | 37.2 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 2 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8020-01-317-2854 | COVER, PAINT ROLLER, POLYESTER FIBER, 3 INCHES | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 1 | EA | 3 | 6.6 | 19.8 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 1 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5305-05-V00-0020 | SCREW, SELF DRILLING, HEX HEAD, w/NEOPRENE WASHER, STAINLESS STEEL, #10 X 1-1/2 INCHES | 56041 | 2024-03-04 | 2024-03-07 | APPR | 2 | EA | 50 | 0.7 | 35 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5305-60-V00-0167 | SCREW, HEX WASHER HEAD, STEEL, #14 X 3 INCHES | 56039 | 2024-03-04 | 2024-03-07 | APPR | 3 | bx | 32 | 35.6 | 1139.2 |  |  |  |  | KW1-15459 | 8 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 32.00 |  | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5133-05-V01-0089 | DRILL BIT, CARBIDE, TIPPED, SAND BLAST, 12 MM | 56041 | 2024-03-04 | 2024-03-07 | APPR | 1 | EA | 2 | 22.1 | 44.2 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 4240-60-V00-0043 | MASK, N95, PARTICULATE RESPIRATOR, 10EA/BOX, WHITE | 56033 | 2024-03-04 | 2024-03-07 | APPR | 1 | bx | 1 | 53.46 | 53.46 | 22173 | SENT | 2024-03-07 | 2024-03-10 | [12 empty] | BU | BU table | March | 2024
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5305-60-V00-0022 | MATERIAL: STAINLESS STEELSIZE: #10SCREW LENGTH: 1-1/2 INCHESHEAD STYLE: TRUSS HEADDRIVE TYPE: PHILLIPSUNIT OF MEASURE: PACKAGE (CONTAINS 100 EACH) | 56039 | 2024-03-04 | 2024-03-07 | APPR | 2 | pg | 1 | 44.9 | 44.9 |  |  |  |  | KW1-15459 | 7 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 1.00 |  | BU | BU table | March | 2024
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 5130-60-V00-0122 | WHEEL ABRASIVE, ALUMINIUM OXIDE, 4 X 1/16 X 5/8 INCHES | 56045 | 2024-03-04 | 2024-03-07 | APPR | 1 | EA | 10 | 19.8 | 198 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [11 empty] | CATALOG INPRG | BU | BU table | March | 2024
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 5345-60-V00-0019 | DISK, FLAP, ABRASIVE, 60 GRIT, ZIRCONIA, 4-1/2 X 7/8 INCHES | 56047 | 2024-03-04 | 2024-03-07 | CLOSE | 2 | EA | 15 | 12.8 | 192 |  |  |  |  | KW1-15459 | 20 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 15.00 |  | BU | BU table | March | 2024
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 9150-01-418-9008 | LUBRICATING OIL, UTILITY, 11 OZ. | 56046 | 2024-03-04 | 2024-03-07 | APPR | 3 | EA | 3 | 23.3 | 69.9 | 22172 | SENT | 2024-03-07 | 2024-03-10 | [12 empty] | BU | BU table | March | 2024
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 8010-60-V00-0095 | PRIMER, COATING, RED OXIDE, LIQUID, 3.78 TO 4 LITERS | 56048 | 2024-03-04 | 2024-03-07 | CLOSE | 5 | GL | 6 | 41.3 | 247.8 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 14 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 8010-60-V00-0028 | PAINT, ENAMEL, GLOSS, DESERT SAND, 3.6 LITER | 56048 | 2024-03-04 | 2024-03-07 | CLOSE | 4 | EA | 10 | 39.6 | 396 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 13 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 56044 | 2024-03-04 | 2024-03-07 | CLOSE | 1 | bx | 2 | 19.47 | 38.94 | 22164 | CLOSE | 2024-03-07 |  | KW1-15462 | 3 | 2024-03-09 | APPR | 2024-03-09 | Santhumayor, Santhosh - Vectrus - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-04-30 |  |  |  |  | BU | BU table | March | 2024
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 56046 | 2024-03-04 | 2024-03-07 | APPR | 2 | EA | 8 | 14.6 | 116.8 | 22161 | CLOSE | 2024-03-07 |  | KW1-15460 | 4 | 2024-03-07 | APPR | 2024-03-07 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-04-18 |  |  |  |  | BU | BU table | March | 2024
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 5120-60-V00-0328 | NUTDRIVER SET, MAGNETIC, 3 PIECES | 56047 | 2024-03-04 | 2024-03-07 | CLOSE | 1 | ea | 4 | 24.1 | 96.4 |  |  |  |  | KW1-15459 | 19 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 4.00 |  | BU | BU table | March | 2024
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 5305-60-V00-0090 | SCREW, SELF-DRILLING, STEEL, w/ RUBBER WASHER, #14 X 1 INCH | 56046 | 2024-03-04 | 2024-03-07 | APPR | 1 | PK | 15 | 23.5 | 352.5 | 22172 | SENT | 2024-03-07 | 2024-03-10 | [12 empty] | BU | BU table | March | 2024
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 56048 | 2024-03-04 | 2024-03-07 | CLOSE | 3 | EA | 4 | 12.4 | 49.6 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 12 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 8020-01-317-2854 | COVER, PAINT ROLLER, POLYESTER FIBER, 3 INCHES | 56048 | 2024-03-04 | 2024-03-07 | CLOSE | 2 | EA | 12 | 6.6 | 79.2 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 11 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 56048 | 2024-03-04 | 2024-03-07 | CLOSE | 1 | EA | 4 | 29 | 116 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 10 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 8030-60-V00-0008 | SEALING COMPOUND, GUTTER & SEAM, WHITE, 10 OZ. | 56043 | 2024-03-04 | 2024-03-07 | CLOSE | 2 | ea | 12 | 23.1 | 277.2 |  |  |  |  | KW1-15459 | 18 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 12.00 |  | BU | BU table | March | 2024
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 5130-60-V00-0101 | GRINDER, ELECTRIC, PORTABLE, ANGLE, RPM 800, 20 V | 56043 | 2024-03-04 | 2024-03-07 | CLOSE | 1 | EA | 1 | 1205.49 | 1205.49 |  |  |  |  | KW1-15459 | 17 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 1.00 |  | BU | BU table | March | 2024
86 | 2024-03-04 | 50 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 9515-60-V00-0008 | SHEET, METAL, CORRUGATED, 4 X 14 FEET | 56069 | 2024-03-04 | 2024-03-07 | APPR | 1 | EA | 33 | 37.95 | 1252.35 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
86 | 2024-03-04 | 50 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 9515-60-V00-0004 | SHEET, METAL, CORRUGATED, 1 X 3 METER | 56070 | 2024-03-04 | 2024-03-07 | APPR | 1 | EA | 24 | 21.47 | 515.28 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 6115-60-V00-0037 | GENERATOR SET, DIESEL ENGINE, 4-CYCLE, 400V, 24 KW, 50HZ | 56512 | 2024-03-09 |  | PREFIN | 1 | EA | 2 | 14597.59 | 29195.18 | [15 empty] | Waiting Submittal approval | BU | BU table | February | 2024
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 56514 | 2024-03-09 |  | WDOAPPR | 8 | EA | 4 | 302.94 | 1211.76 | [16 empty] | BU | BU table | February | 2024
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 56514 | 2024-03-09 |  | WDOAPPR | 7 | EA | 4 | 58.91 | 235.64 | [16 empty] | BU | BU table | February | 2024
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 6145-60-V00-0119 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 25 MM² | 56514 | 2024-03-09 |  | WDOAPPR | 6 | MR | 30 | 26.5 | 795 | [16 empty] | BU | BU table | February | 2024
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM ² | 56514 | 2024-03-09 |  | WDOAPPR | 5 | YD | 35 | 242.58 | 242.58 | [16 empty] | BU | BU table | February | 2024
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 5940-60-V00-0016 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 16 MM² | 56513 | 2024-03-09 |  | WDOAPPR | 1 | EA | 10 | 5 | 50 | [16 empty] | BU | BU table | February | 2024
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 5975-60-V00-0512 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, CW, BRASS, 32 MM | 56514 | 2024-03-09 |  | WDOAPPR | 4 | KT | 2 | 25.5 | 51 | [16 empty] | BU | BU table | February | 2024
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 5940-60-V00-0017 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 25 MM² | 56514 | 2024-03-09 |  | WDOAPPR | 3 | EA | 10 | 5 | 50 | [16 empty] | BU | BU table | February | 2024
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 56514 | 2024-03-09 |  | WDOAPPR | 2 | YD | 35 | 163 | 163 | [16 empty] | BU | BU table | February | 2024
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 5975-60-V00-0209 | RACEWAY, METALLIC, GALVANIZED STEEL, 2 X 2 INCHES X 10 FEET | 56514 | 2024-03-09 |  | WDOAPPR | 1 | EA | 1 | 56.21 | 56.21 | [16 empty] | BU | BU table | February | 2024
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 5975-60-V00-0793 | TRAY, CABLE, STRAIGHT, MEDIUM DUTY, GALVANIZED STEEL, 450 MM X 3 METERS | 56511 | 2024-03-09 |  | WDOAPPR | 1 | EA | 1 | 55.09 | 55.09 | [16 empty] | BU | BU table | February | 2024
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 6115-60-V00-0037 | GENERATOR SET, DIESEL ENGINE, 4-CYCLE, 400V, 24 KW, 50HZ | 56508 | 2024-03-09 |  | PREFIN | 1 | EA | 2 | 14597.6 | 29195.2 | [16 empty] | BU | BU table | February | 2024
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 56510 | 2024-03-09 |  | WDOAPPR | 8 | EA | 4 | 302.94 | 1211.76 | [16 empty] | BU | BU table | February | 2024
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 56510 | 2024-03-09 |  | WDOAPPR | 7 | EA | 4 | 58.91 | 235.64 | [16 empty] | BU | BU table | February | 2024
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 6145-60-V00-0119 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 25 MM² | 56510 | 2024-03-09 |  | WDOAPPR | 6 | MR | 30 | 26.5 | 795 | [16 empty] | BU | BU table | February | 2024
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM ² | 56510 | 2024-03-09 |  | WDOAPPR | 5 | YD | 35 | 242.58 | 242.58 | [16 empty] | BU | BU table | February | 2024
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 5940-60-V00-0016 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 16 MM² | 56509 | 2024-03-09 |  | WDOAPPR | 1 | EA | 10 | 5 | 50 | [16 empty] | BU | BU table | February | 2024
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 5975-60-V00-0512 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, CW, BRASS, 32 MM | 56510 | 2024-03-09 |  | WDOAPPR | 4 | KT | 2 | 25.5 | 51 | [16 empty] | BU | BU table | February | 2024
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 5940-60-V00-0017 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 25 MM² | 56510 | 2024-03-09 |  | WDOAPPR | 3 | EA | 10 | 5 | 50 | [16 empty] | BU | BU table | February | 2024
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 56510 | 2024-03-09 |  | WDOAPPR | 2 | YD | 35 | 163 | 163 | [16 empty] | BU | BU table | February | 2024
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 5975-60-V00-0209 | RACEWAY, METALLIC, GALVANIZED STEEL, 2 X 2 INCHES X 10 FEET | 56510 | 2024-03-09 |  | WDOAPPR | 1 | EA | 1 | 56.21 | 56.21 | [16 empty] | BU | BU table | February | 2024
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 5975-60-V00-0793 | RACEWAY, METALLIC, (CABLE TRAY), MEDIUM DUTY, HOT-DIP GALVANIZED, 1.20 X 50 X 3000 X 450 MM | 56507 | 2024-03-09 |  | WDOAPPR | 1 | EA | 1 | 55.09 | 55.09 | [16 empty] | BU | BU table | February | 2024
89 | 2024-03-04 | 30 | BU24-0179 | 4 New Cipher Locks TT301 | 9966783 | 5340-60-V00-0429 | LOCK SET, MECHANICAL, PUSH BUTTON, RIGHT HAND, 2-3/4 INCHES | 56124 | 2024-03-05 | 2024-03-07 | CLOSE | 3 | EA | 2 | 602.6 | 1205.2 | 22149 | CLOSE | 2024-03-07 |  | KW1-15453 | 5 | 2024-03-07 | APPR | 2024-03-07 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-21 | COMP | 2024-03-10 | 2.00 |  | BU | BU table | March | 2024
89 | 2024-03-04 | 30 | BU24-0179 | 4 New Cipher Locks TT301 | 9966783 | 5340-60-V00-0171 | LOCK SET, RIM, PUSHBUTTON, LHR, 5 INCHES | 56124 | 2024-03-05 | 2024-03-07 | CLOSE | 2 | EA | 2 | 751.4 | 1502.8 | 22149 | CLOSE | 2024-03-07 |  | KW1-15453 | 4 | 2024-03-07 | APPR | 2024-03-07 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-21 | COMP | 2024-03-10 | 2.00 |  | BU | BU table | March | 2024
89 | 2024-03-04 | 30 | BU24-0179 | 4 New Cipher Locks TT301 | 9966783 | 5340-60-V00-0169 | LOCK SET, MORTISE, RIM EXIT DEVICE, KEY OUTSIDE UNLOCKS/LOCKS TRIM | 56124 | 2024-03-05 | 2024-03-07 | CLOSE | 1 | EA | 2 | 2227.5 | 4455 | 22149 | CLOSE | 2024-03-07 |  | KW1-15453 | 3 | 2024-03-07 | APPR | 2024-03-07 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-21 | COMP | 2024-03-10 | 2.00 |  | BU | BU table | March | 2024
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 9905-60-V00-0065 | SIGN, DANGER HIGH VOLTAGE, ADHESIVE, CUSTOMIZED (Length 9X8 Width Inches) | 56188 | 2024-03-05 | 2024-03-07 | APPR | 1 | EA | 1 | 9.75 | 9.75 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 9905-60-V00-0066 | SIGN, DANGER, 415 VOLTS , 5 X 3-3/4 INCHES | 56156 | 2024-03-05 | 2024-03-07 | APPR | 1 | PG | 1 | 17.06 | 17.06 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 11 | EA | 1 | 302.94 | 302.94 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 25 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 10 | EA | 1 | 58.91 | 58.91 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 24 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 9 | EA | 1 | 146.47 | 146.47 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 23 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 56144 | 2024-03-05 |  |  | 8 | RO | 2 | [18 empty] | BU | BU table | March | 2024
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 7 | EA | 6 | 3.26 | 19.56 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 21 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 6 | RO | 1 | 92.02 | 92.02 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 20 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 | COMP | 2024-03-10 | 1.00 |  | BU | BU table | March | 2024
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 5975-60-V00-0480 | JUNCTION BOX, w/ BLANK SIDE, 100 X 100 X 50 MM | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 5 | EA | 1 | 12 | 12 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 19 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6145-60-V00-0101 | CABLE, POWER, ELECTRICAL, H07RN-F, BLACK, 3 CORE, 4 MM² | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 4 | MR | 20 | 13.5 | 270 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 18 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6145-60-V00-0128 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 10 MM ² | 56143 | 2024-03-05 | 2024-03-07 | CLOSE | 1 | RL | 1 | 26 | 26 |  |  |  |  | KW1-15455 | 2 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | MARATHON INC TRADING LLC | 2024-03-31 07:00 |  |  |  |  | BU | BU table | March | 2024
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 5975-60-V00-0299 | PLATE, ELECTRICAL GROUNDING (BUS BAR), 20 HOLES, COPPER, TIN-PLATED, 19-3/8 X 1 X 3/16 INCHES | 56141 | 2024-03-05 | 2024-03-07 | CLOSE | 1 | KT | 1 | 273.24 | 273.24 |  |  |  |  | KW1-15457 | 1 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-14 07:00 |  |  |  |  | BU | BU table | March | 2024
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 3 | EA | 1 | 260.02 | 260.02 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 17 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6210-60-V00-0094 | FIXTURE, LIGHTING, LED, RETROFIT, POLYCARBONATE, PURE WHITE, 40W | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 2 | EA | 2 | 242.35 | 484.7 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 16 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6210-60-V00-0040 | FIXTURE, LIGHTING, LED, WALL PACK, 5000K, 100-277 VAC, 30W | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 1 | EA | 1 | 142.6 | 142.6 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 15 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6130-60-V00-0097 | BATTERY, EMERGENCY LED DRIVER, 50/60HZ, 15W, 100-277V | 56142 | 2024-03-05 | 2024-03-07 | APPR | 1 | EA | 1 | 117.81 | 117.81 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6625-60-V00-0093 | TESTER, SOCKET, THREE, FLAT, PRONG, 220V, 13A | 56155 | 2024-03-05 | 2024-03-07 | APPR | 1 | EA | 1 | 211.79 | 211.79 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6625-60-V00-0049 | TESTER, VOLTAGE, W/FLASHLIGHT, 12-1000V | 56154 | 2024-03-05 | 2024-03-07 | APPR | 1 | EA | 1 | 169.99 | 169.99 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 30 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 8030-60-V00-0008 | SEALING COMPOUND, GUTTER & SEAM, WHITE, 10 OZ. | 56364 | 2024-03-07 | 2024-03-09 | CLOSE | 1 | CS | 24 | 23.1 | 554.4 | 22249 | CLOSE | 2024-03-10 |  | KW1-15519 | 6 | 2024-03-10 | APPR | 2024-03-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-24 |  |  |  |  | BU | BU table | March | 2024
91 | 2024-03-07 | 30 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 56366 | 2024-03-09 | 2024-03-09 | CLOSE | 3 | BX | 1 | 141.9 | 141.9 |  |  |  |  | KW1-15508 | 3 | 2024-03-09 | APPR | 2024-03-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-16 07:00 |  |  |  |  | BU | BU table | March | 2024
91 | 2024-03-07 | 30 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 9330-60-V00-0016 | SHEET, ACRYLIC, WHITE, 48 X 96 X 0.250 INCHES | 56366 | 2024-03-09 | 2024-03-09 | CLOSE | 2 | SH | 1 | 181.5 | 181.5 |  |  |  |  | KW1-15508 | 2 | 2024-03-09 | APPR | 2024-03-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-16 07:00 |  |  |  |  | BU | BU table | March | 2024
91 | 2024-03-07 | 30 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 8010-01-331-6107 | PAINT, ENAMEL, GLOSS, SPRAY, BLACK, 11 OZ | 56366 | 2024-03-09 | 2024-03-09 | CLOSE | 1 | PT | 3 | 57.5 | 172.5 |  |  |  |  | KW1-15508 | 1 | 2024-03-09 | APPR | 2024-03-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-16 07:00 |  |  |  |  | BU | BU table | March | 2024
91 | 2024-03-07 | 30 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 56365 | 2024-03-09 | 2024-03-09 | CLOSE | 1 | BX | 1 | 29.4 | 29.4 |  |  |  |  | KW1-15509 | 5 | 2024-03-09 | APPR | 2024-03-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-16 07:00 |  |  |  |  | BU | BU table | March | 2024
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 9905-60-V00-0065 | SIGN, DANGER HIGH VOLTAGE, ADHESIVE, CUSTOMIZED (Length 9X8 Width Inches) | 56459 | 2024-03-09 | 2024-03-09 | APPR | 1 | EA | 1 | 9.9 | 9.9 | 22252 | SENT | 2024-03-10 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 9905-60-V00-0066 | SIGN, DANGER, 415 VOLTS , 5 X 3-3/4 INCHES | 56462 | 2024-03-09 |  | WDOAPPR | 1 | PG | 1 | 17.33 | 17.33 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 56464 | 2024-03-09 |  | WDOAPPR | 9 | EA | 1 | 302.94 | 302.94 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 56464 | 2024-03-09 |  | WDOAPPR | 8 | EA | 1 | 58.91 | 58.91 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 |  | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 6625-60-V01-0056 | TESTER, SOCKET, 230V, 50Hz, RCD 30mA, SM300 |  | 2024-03-09 |  |  |  | EA | 1 | [17 empty] | Waiting AHJ approval | BU | BU table | March | 2024
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5975-60-V00-0531 | PROTECTOR, ELECTRICAL CABLE, PVC, WHITE, 1 INCH X 9 FEET | 56464 | 2024-03-09 |  | WDOAPPR | 7 | EA | 5 | 11.83 | 59.15 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 56464 | 2024-03-09 |  | WDOAPPR | 6 | EA | 1 | 260.02 | 260.02 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 56464 | 2024-03-09 |  |  | 5 | RO | 1 | [18 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 56464 | 2024-03-09 |  | WDOAPPR | 4 | EA | 6 | 3.7 | 22.2 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5120-01-428-8497 | SCREWDRIVER SET, FLAT TIP AND CROSS TIP, 8 PIECES | 56461 | 2024-03-09 | 2024-03-09 | CLOSE | 1 | SE | 1 | 94.71 | 94.71 |  |  |  |  | KW1-15509 | 11 | 2024-03-09 | APPR | 2024-03-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-16 07:00 |  |  |  |  | BU | BU table | March | 2024
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 6625-60-V00-0093 | TESTER, SOCKET, W/ BEEPER, RCD, 250 V, 50 HZ | 56460 | 2024-03-09 | 2024-03-09 | APPR | 1 | EA | 3 | 74.25 | 222.75 | 22252 | SENT | 2024-03-10 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5975-60-V00-0480 | JUNCTION BOX, w/ BLANK SIDE, 100 X 100 X 50 MM | 56464 | 2024-03-09 |  | WDOAPPR | 3 | EA | 3 | 13.1 | 39.3 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 6145-60-V00-0101 | CABLE, POWER, ELECTRICAL, H07RN-F, BLACK, 3 CORE, 4 MM² | 56464 | 2024-03-09 |  | WDOAPPR | 2 | MR | 20 | 12.75 | 255 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 6145-60-V00-0128 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 10 MM ² | 56463 | 2024-03-09 |  | WDOAPPR | 1 | RL | 1 | 26 | 26 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 6210-60-V00-0021 | FIXTURE, LIGHTING, LED, SAFETY AND EXIT SIGN, SINGLE SIDED, GREEN, 230V AC, 136 X 303 X 62 MM | 56464 | 2024-03-09 |  | WDOAPPR | 1 | EA | 1 | 639.54 | 639.54 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 4130-60-V00-0288 | TAPE, WRAP, INSULATION, 3 INCHES X 150 FEET | 56471 | 2024-03-09 |  | WDOAPPR | 2 | RO | 1 | 32 | 32 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5970-60-V00-0037 | TAPE, INSULATION, ELECTRICAL, WHITE, 19MM X 20M | 56468 | 2024-03-09 |  | WDOAPPR | 1 | RO | 1 | 21.45 | 21.45 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 56472 | 2024-03-09 |  | WDOAPPR | 6 | RO | 1 | 92 | 92 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 6145-60-V00-0139 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 6 MM ² | 56472 | 2024-03-09 |  | WDOAPPR | 5 | RO | 1 | 28.1 | 28.1 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5975-60-V00-0421 | LUG, TERMINAL, ROUND TYPE, ONE-HOLE, 6 X 6 MM | 56472 | 2024-03-09 |  | WDOAPPR | 4 | PG | 1 | 51.82 | 51.82 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 |  | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5306-35-V00-0001 | ASSORTMENT KIT, BOLTS AND NUTS, 375PCS |  | 2024-03-09 |  |  |  | KT | 1 | [17 empty] | Waiting catalog | BU | BU table | March | 2024
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 56472 | 2024-03-09 |  | WDOAPPR | 3 | EA | 1 | 52 | 52 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5975-60-V00-0505 | STUFFING TUBE (CABLE GLAND), PG16, POLYAMIDE, GRAY, 9 -14 MM | 56472 | 2024-03-09 |  | WDOAPPR | 2 | EA | 4 | 2.96 | 11.84 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 4730-60-V00-0594 | C-CLAMP W/ RUBBER, GALVANIZED STEEL, 2 INCHES | 56470 | 2024-03-09 |  | WDOAPPR | 2 | EA | 4 | 9.4 | 37.6 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 4710-60-V00-0110 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 56470 | 2024-03-09 |  | WDOAPPR | 1 | EA | 1 | 17.5 | 17.5 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 4130-60-V00-0137 | MOUNTING BASE, AIR-CONDITIONER, POLYPROPYLENE, IVORY, 17 X 3 X 5.12 INCHES | 56471 | 2024-03-09 |  | WDOAPPR | 1 | PG | 1 | 68 | 68 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 8030-60-V00-0053 | FOAM, CONSTRUCTION, CREAM, 700ML | 56472 | 2024-03-09 |  | WDOAPPR | 1 | EA | 1 | 19.5 | 19.5 | [16 empty] | BU | BU table | March | 2024
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 6350-60-V00-0102 | ALARM, SMOKE, AUTOMATIC, PLASTIC | 56469 | 2024-03-09 |  | WDOAPPR | 1 | EA | 1 | 28.71 | 28.71 | [16 empty] | BU | BU table | March | 2024
92 | 2024-03-09 | 40 | BU24-0143 | Install Overhead Lights B9501AB | 9360741 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 56500 | 2024-03-09 |  | WDOAPPR | 2 | EA | 3 | 260.02 | 780.06 | [15 empty] | Additional material request | BU | BU table | March | 2024
92 | 2024-03-09 | 40 | BU24-0143 | Install Overhead Lights B9501AB | 9360741 | 5306-60-V00-0117 | BOLT, TOGGLE, ROUND HEAD, BRASS, 3/16 X 2-1/2 INCHES | 56501 | 2024-03-09 |  | WDOAPPR | 1 | EA | 30 | 1.49 | 44.7 | [16 empty] | BU | BU table | March | 2024
92 | 2024-03-09 | 40 | BU24-0143 | Install Overhead Lights B9501AB | 9360741 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 56500 | 2024-03-09 |  | WDOAPPR | 1 | EA | 10 | 27 | 270 | [16 empty] | BU | BU table | March | 2024
93 | 2024-03-10 |  | BU24-0129 | Relocate Retention Pond RP6002 |  |  |  | PRINPRG | [24 empty] | BU | BU table | March | 2024

## AJ Fabrication PR
NO. OF PROJECTS | BOM Received date | TASK | PROJECT# | PROJECT DESCRIPTION | WO# | CATALOG | Item # | PR # | PR REQUESTED DATE | PR APPROVED DATE | PR Cur. Status | PR Line # | Unit of Issue | Order Qty. | Unit Cost | Ext. Cost (Line Cost) | RFQ # | RFQ Status | RFQ Status Date | RFQ Due Date | PO # | PO Line # | PO Award Date | PO Status | PO Status Date | Buyer | Vendor | Vendor Date (EDD) | Delivery Status | Delivery Date | Recv. Qty | Remarks | Color Code list | table | month | year
1 | 2022-05-13 |  | AJ21-0177 | BLDG 540 Hanel Lean-Lift Power Panel and Equipment Installation | 1194736 | FABRICATION | FABRICATION POWER DFISTRIBUTION PANEL 12 way | 32165 | 2022-05-13 | 2022-05-13 |  | 1 | EA | 1 | [6 empty] | LCVKW0302S | 1 | [5 empty] | 2022-08-17 | COMP | 2022-08-21 | 1 | Vendor Submittal approved 5 July 22 | AJ | Fab table | May | 2022
2 | 2022-05-16 |  | AJ22-0074 | MP23LM2 | 1234123 | FABRICATION | FABRICATION PANEL, POWER DISTRIBUTION , 8WAY , 415V, 63AMPS, 3PHASE | 32198 | 2022-05-16 | 2022-05-16 |  | 2 | EA | 1 | [6 empty] | LCVKW0313S | 2 | [5 empty] | 2022-07-15 | COMP | 2022-07-21 | 1 |  | AJ | Fab table | May | 2022
3 | 2022-05-26 |  | AJ22-0081 | RLB T6044 Relocation and Modification | 1368335 | FABRICATION | FABRICATION PANEL WITH DISCONNECT SWITCH | 32698 | 2022-05-26 | 2022-05-26 |  | 2 | AY | 2 | [6 empty] | LCVKW0312S | N/A | [5 empty] | 2022-07-15 | COMP | 2022-07-22 | 2 |  | AJ | Fab table | May | 2022
3 | 2022-06-01 |  | AJ22-0081 | RLB T6044 Relocation and Modification | 1368335 | FABRICATION | FABRICATION DOOR WITH FRAME | 32848 | 2022-06-01 | 2022-06-01 |  | 1 | AY | 11 | [6 empty] | LCVKW0320S | N/A | [5 empty] | 2022-07-28 | COMP | 2022-08-01 | 11 | Materials Recived | AJ | Fab table | June | 2022
4 | 2022-06-23 |  | AJ22-0044 | Replace 65 Street Light Heads | 2238765 | FABRICATION | FABRICATION OF LIGHT POLE BRACKET ASPER THE DRAWING, SOUTH ABRAMS, FABRICATION OF BRACKET ASPER THE DRAWING, | 33968 | 2022-06-23 | 2022-06-23 |  | 1 | EA | 63 | [6 empty] | LCVKW0341S | 1 | [5 empty] | 2022-10-15 | COMP | 2022-10-15 | 63 |  | AJ | Fab table | June | 2022
5 | 2022-07-07 |  | AJ22-0067 | T725 Power Outlets and Equipment Install | 2141547 | FABRICATION | FABRICATION PANEL (INDOOR PANEL), 32A 1POLE RCBO-1EA, 25A 1 POLE RCBO -3EA, 20A 1 POLE RCBO-6EA,16A 1 POLE RCBO-2EA | 34654 | 2022-07-07 | 2022-07-08 |  | 1 | AY | 1 | [6 empty] | LCVKW0350S | 1 | [5 empty] | 2022-09-16 | COMP | 2022-09-16 | 1 | Vendor Submittal approved 20 Aug 22 | AJ | Fab table | July | 2022
6 | 2022-07-28 |  | AJ22-0265 | Joint Portal Shield Biological Detection Sensor | 2671164 | FABRICATION | FABRICATION, OUTDOOR PANEL AND 40A MCCB 3 POLE BREAKER WITH STAND | 35777 | 2022-07-28 | 2022-08-04 |  | 1 | AY | 3 | [6 empty] | LCVKW0357S | 1 | [5 empty] | 2022-09-30 | COMP | 2022-09-30 | 3 |  | AJ | Fab table | July | 2022
7 | 2022-08-31 |  | AJ22-0105 | T340 Security Features Install | 2621467 | FABRICATION | SINGLE WOODEN DOOR, SOLID WOODEN DOOR THICKNESS IS 1-3/4” (3'X7') WITH GYPSUM BOARD METAL FRAME(FABRICATION SERVICES) | 37171 | 2022-08-31 | 2022-09-10 |  | 1 | EA | 8 | [6 empty] | LCVKW0390S | 1 | [5 empty] | 2022-10-18 |  |  |  |  | AJ | Fab table | August | 2022
7 | 2022-08-31 |  | AJ22-0105 | T340 Security Features Install | 2621467 | FABRICATION | DOUBLE DOOR, SOLID WOODEN DOOR THICKNESS IS 1-3/4”(6'X7') (WOODEN) WITH GYPSUM BOARD METAL FRAME(FABRICATION SERVICES) | 37171 | 2022-08-31 | 2022-09-10 |  | 2 | EA | 1 | [6 empty] | LCVKW0390S | 2 | [5 empty] | 2022-10-18 |  |  |  |  | AJ | Fab table | August | 2022
7 | 2022-08-31 |  | AJ22-0105 | T340 Security Features Install | 2621467 | FABRICATION | WINDOWS SECURITY ALUMINIUM BAR FOR EXTERNAL WINDOWS(4'X3'5.5") (FABRICATION SERVICES) | 37171 | 2022-08-31 | 2022-09-10 |  | 3 | EA | 22 | [6 empty] | LCVKW0390S | 3 | [5 empty] | 2022-10-18 |  |  |  |  | AJ | Fab table | August | 2022
7 | 2022-08-31 |  | AJ22-0105 | T340 Security Features Install | 2621467 | FABRICATION | WINDOWS SECURITY ALUMINIUM BAR FOR EXTERNAL DOOR WINDOWS WITH FLEXI GLASS (1'X1'4") (FABRICATION SERVICES) | 37171 | 2022-08-31 | 2022-09-10 |  | 4 | EA | 5 | [6 empty] | LCVKW0390S | 4 | [5 empty] | 2022-10-18 |  |  |  |  | AJ | Fab table | August | 2022
8 | 2022-09-18 |  | AJ22-0137 | Vectrus Tent 1 Relocation | 2238613 | FABRICATION | FABRICATION OF 2 NEW 90-DEGREE ELBOW TRANSITION DUCTS | 37556 | 2022-09-18 | 2022-09-21 |  | 1 | AY | 2 | [6 empty] | LCKW0404S | [6 empty] | 2022-10-11 | COMP | 2022-10-30 | 2 |  | AJ | Fab table | September | 2022
9 | 2022-09-18 |  | AJ22-0138 | Vectrus Tent 2 Relocation | 2238650 | FABRICATION | FABRICATION OF 2 NEW 90-DEGREE ELBOW TRANSITION DUCTS | 37558 | 2022-09-18 | 2022-09-21 |  | 1 | EA | 2 | [6 empty] | LCKW0404S | [6 empty] | 2022-10-11 | COMP | 2022-10-30 | 2 | 2 | AJ | Fab table | September | 2022
10 | 2022-09-18 |  | AJ22-0139 | Vectrus Tent 3 Relocation | 2238605 | FABRICATION | FABRICATION OF 2 NEW 90-DEGREE ELBOW TRANSITION DUCTS | 37559 | 2022-09-18 | 2022-09-21 |  | 1 | EA | 2 | [6 empty] | LCKW0404S | [6 empty] | 2022-10-11 | COMP | 2022-10-01 | 2 |  | AJ | Fab table | September | 2022
11 | 2022-09-18 |  | AJ22-0140 | Vectrus Tent 4 Relocation | 2238683 | FABRICATION | FABRICATION OF 2 NEW 90-DEGREE ELBOW TRANSITION DUCTS | 37560 | 2022-09-18 | 2022-09-21 |  | 1 | EA | 2 | [6 empty] | LCKW0404S | [6 empty] | 2022-10-11 | COMP | 2022-10-01 | 2 |  | AJ | Fab table | September | 2022
12 | 2022-09-18 |  | AJ22-0141 | Vectrus Tent 5 Relocation | 2238643 | FABRICATION | FABRICATION OF 2 NEW 90-DEGREE ELBOW TRANSITION DUCTS | 37561 | 2022-09-18 | 2022-09-21 |  | 1 | EA | 2 | [6 empty] | LCKW0404S | [6 empty] | 2022-10-11 | COMP | 2022-10-11 | 2 |  | AJ | Fab table | September | 2022
13 | 2022-09-18 |  | AJ22-0142 | Vectrus Tent 6 Relocation | 2238633 | FABRICATION | FABRICATION OF 2 NEW 90-DEGREE ELBOW TRANSITION DUCTS | 37554 | 2022-09-18 | 2022-09-21 |  | 1 | EA | 2 | [6 empty] | LCKW0404S | [6 empty] | 2022-10-11 | COMP | 2022-10-11 | 2 |  | AJ | Fab table | September | 2022
14 | 2022-09-18 |  | AJ22-0143 | Vectrus Tent 7 Relocation | 2539656 | FABRICATION | FABRICATION OF 2 NEW 90-DEGREE ELBOW TRANSITION DUCTS | 37555 | 2022-09-18 | 2022-09-21 |  | 1 | EA | 2 | [6 empty] | LCKW0404S | [6 empty] | 2022-10-11 | COMP | 2022-10-11 | 2 |  | AJ | Fab table | September | 2022
15 | 2022-09-29 |  | AJ22-0145 | Z7 Utility Infrastructure-Power Generation | 2219753 | FABRICATION | MDP (OUTDOOR): AIR CIRCUIT BREAKERS(ACB) 1250A, BRANCH: 3Px160A, 6EA , 3Px 300A, 1EA, 3Px 63A, 1EA, SPARE BLANK 2EA, W/ STAND | 45822 | 2022-09-29 | CANCELLED |  |  | EA | 1 | [18 empty] | AJ | Fab table | September | 2022
15 | 2022-09-29 |  | AJ22-0145 | Z7 Utility Infrastructure-Power Generation | 2219753 | FABRICATION | DISCONNECT SWITCH(OUTDOOR): 4Px100A W/ STAND | 45822 | 2022-09-29 | 2023-05-10 |  | 1 | EA | 4 | [6 empty] | LCVKW0637S | [11 empty] | AJ | Fab table | September | 2022
15 | 2022-09-29 |  | AJ22-0145 | Z7 Utility Infrastructure-Power Generation | 2219753 | FABRICATION | DISCONNECT SWITCH(OUTDOOR): 4Px63A W/ STAND | 45822 | 2022-09-29 | 2023-05-10 |  | 2 | EA | 1 | [6 empty] | LCVKW0637S | [11 empty] | AJ | Fab table | September | 2022
15 | 2022-09-29 |  | AJ22-0145 | Z7 Utility Infrastructure-Power Generation | 2219753 | FABRICATION | MANUAL TRANSFER SWITCH, MTS (OUTDOOR) 4Px2000A, W/ STAND | 45822 | 2022-09-29 | 2023-05-10 |  | 3 | EA | 1 | [6 empty] | LCVKW0637S | [11 empty] | AJ | Fab table | September | 2022
16 | 2022-10-05 |  | AJ22-0156 | RMOs Motor Pool 19 | 2854733 | FABRICATION | FABRICATION, 8 WAY PANEL, MCB, IP54 APPROVED SUBMITTAL VIA TRANSMITTAL # AJ220156-LCV-ELE-MTL-0001 DATED 2022-09-15 | 38064 | 2022-10-05 | 2022-10-05 |  |  | AY | 1 | [6 empty] | PO KW1-6993 | [6 empty] | 2023-01-31 |  |  |  |  | AJ | Fab table | October | 2022
17 | 2022-11-22 |  | AJ22-0248 | ZONE 1 B209 | 2969436 | FABRICATION | FABRICATION, DISTRIBUTION BOARD (DB-220/415V ), FABRICATION, DISTRIBUTION BOARD ( DB-120/230V ) | 39709 | 2022-11-22 | 2022-11-23 |  |  | AY | 1 | [18 empty] | AJ | Fab table | November | 2022
18 | 2023-01-19 |  | AJ22-0135 | Replace 65 Street Light Heads | 238765 | FABRICATION | FABRICATION OF BRACKET ASPER THE DRAWING, ALUMINUM TAPERED ELLIPTICAL BRACKET (4 FEET LENGTH) (PATTON BLVD) ( INCLUDING ALL THE NUTS, BOLTS, SCREWS AND WASHER | 41504 | 2023-01-19 | 2023-01-21 |  | 1 | AY | 27 | [6 empty] | LCVKW0522S | [6 empty] | 2023-03-08 | COMP | 2023-04-04 | 1 |  | AJ | Fab table | January | 2023
19 | 2023-03-12 |  | AJ22-0143, | Vectrus Tent 7 Relocation |  | FABRICATION | FABRICATION OF SOLID CORE WOOD DOORS AND METAL ,FRAMES, SARGENT PUSH BARS (CATALOG: 5340-60-V00-0169 ) SARGENT LEVER DOOR HANDLE | 44110 | 2023-03-12 | 2023-03-28 |  |  | AY | 2 | [18 empty] | AJ | Fab table | March | 2023
20 | 2023-03-16 |  | AJ23-0089 | B314 Backup Power Connection |  | FABRICATION | FABRICATION, MSB-2 WAYS ( INCOMER 250A) , APPROVED SUBMITTAL VIA TRANSMITTAL # AJ230089-LCV-ELE-DSN-0001 | 43694 | 2023-03-16 | 2023-03-16 |  |  | AY | 1 | [6 empty] | LCVKW0574S | 1 | [10 empty] | AJ | Fab table | March | 2023
21 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak | 5434294 | FABRICATION | READY MADE CONCRETE MIX (4000 PSI) CONCRETE STRENGTH (TYPE-K-300-4000PSI) | 44816 | 2023-04-13 | 2023-04-17 |  | 1 | CUM | 5 | [18 empty] | AJ | Fab table | April | 2023
23 | 2023-04-16 |  | AJ23-0413 | Z6 Patton Pipe Repair | 2874083 | FABRICATION | READY MADE CONCRETE MIX (4000 PSI) CONCRETE STRENGTH (TYPE-K-300-4000PSI) | 44798 | 2023-04-16 | 2023-04-16 |  | 1 | CUM | 6 | [18 empty] | AJ | Fab table | April | 2023
26 | 2023-05-30 |  | AJ23-0467 | FSLIDs Container Power Connection | 4982395 | FABRICATION | FABRICATION PANEL, DISTRIBUTION BOARD IP-65, 120V,40A,60HZ 10ka | 46730 | 2023-05-30 | 2023-05-31 |  |  | AY | 1 | [18 empty] | AJ | Fab table | May | 2023
26 | 2023-06-06 |  | AJ23-0467 | Warehouse 532 Power for Four Lift Storage Systems | 5967149 | FABRICATION | FABRICATION, PANEL (MAIN BREAKER-63A 3 POLE MCCB SUB BREAKERS 30MA 20A 3 POLE MCB (4EA) TWO SPACE INDOOR DB PANEL) | 48005 | 2023-06-06 | 2023-07-06 |  |  | AY | 2 | [6 empty] | LCVKW0681S | [11 empty] | AJ | Fab table | June | 2023
26 | 2023-07-26 |  | AJ23-0467 | Electrical Outlets | 424782 | FABRICATION | FABRICATION, POWER OUTLETS STAND (METAL HOLLOW) (20"x12"x4") SEE ATTACHED DRAWING | 48795 | 2023-07-26 | 2023-07-26 |  |  | AY | 2 | [18 empty] | AJ | Fab table | July | 2023
27 | 2023-09-10 |  | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | FABRICATION | FABRICATION, SERVICES METAL STAIR 1.5M WIDTH X 1.84M DEPTH AND 1M HEIGTH HANDRAIL, STEEL PLATE LANDING WITH DIAMOND GRATING FABRICATION SERVICES ALUMINUM SLIDING WINDOW WITH FRAME 100X120CM WITH SECONDARY SLIDING MESH PROCESSED BY (BUYER) PROMISED SHIPPING DATE Are these items ITAR controlled? METAL DOOR KNOCK OUT TYPE FRAME, JAMB LIP OPENING 12CM, DOOR LEAF PANEL 4.5 CM X 86CM X 202CM W/ HINGES,PUSH BAR MORTISE TYPE LEVER HANDLE, LEFT HAND REVERSE PRIMERED AND PAINTED TAN COLOR SMOOTH FINISH. (VENDOR SITE VISIT REQUIRED) FABRICATION SERVICE SIGN BOARDS T5802 (FABRICATION SERVICE) METAL STAND,CARRIER OUTDOOR SPLIT UNIT.SIZE:39.5" L X 19" W X 12" H (2"X2" ANGLE BAR THICKNESS 5MM) (SEE ATTACHED FABRICATION SOW AND DRAWINGS) | 50407 | 2023-09-10 |  |  | 1 | AY | 15 | [18 empty] | AJ | Fab table | September | 2023
28 | 2023-09-13 |  | AJ23-0366 | TI Repairs | 7162722 | FABRICATION | FABRICATION ITEMS | 50407 | 2023-09-13 | 2023-09-13 |  |  | AY | 15 | [18 empty] | AJ | Fab table | September | 2023
30 | 2023-10-22 |  | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | FABRICATION | FABRICATION PANEL, DB APPROVED SUBMITTAL VIA TRANSMITTAL# AJ230508-LCV-ELE-MTL- 0001 | 52073 | 2023-10-22 |  |  | 1 | AY | 1 | [18 empty] | AJ | Fab table | October | 2023
31 | 2023-11-01 |  | AJ22-0135 | Install Smart Electric Meters | 8018616 | FABRICATION | FABRICATION, SCHNEIDER ELECTRIC (SE)FABRICATION, NEMA 4X CUSTOM ENCLOSURE, EACH WITH (1) INSTALLED PM5563 METER. THE ENCLOSURE TO INCLUDE THE FOLLOWING:PM5563 RD METER, FACTORY ASSEMBLED (WIRED) NEMA 4X ENCLOSURE, POWER SUPPLY,CONTROL POWER TRANSFORMER, FIBER MEDIA CONVERTER FUSE BLOCKS PROTECTION. (SEE ATTACHED APPROVED 4025) | 52595 | 2023-11-01 | 2023-11-08 |  |  | AY | 1 | [18 empty] | AJ | Fab table | November | 2023
33 | 2023-11-02 |  | AJ22-0135 | Relocation of Building 370 from Z1 to Z7(IMD) | 7116535 | FABRICATION | FABRICATION PANEL, DB APPROVED SUBMITTAL VIA TRANSMITTAL# AJ230467-LCV-ELE-DSN- 0001 | 52514 | 2023-11-02 | 2023-11-06 |  |  | AY | 1 | [18 empty] | AJ | Fab table | November | 2023
33 | 2023-11-02 |  | AJ22-0135 | Replacement of Isolator Panel and Suction Pumps B169 Z1 | 7641976 | FABRICATION | FABRICATION CONTROL PANEL, APPROVED SUBMITTAL VIA TRANSMITTAL# AJ230726-LCVGEN- MTL-0001 | 52516 | 2023-11-02 | 2023-11-06 |  |  | AY | 1 | [18 empty] | AJ | Fab table | November | 2023
33 | 2023-11-02 |  | AJ22-0135 | CT Scanner Site Prep and Installation | 7922463 | FABRICATION | READY MADE CONCRETE MIX (4000 PSI) CONCRETE STRENGTH (TYPE-K-300-4000PSI) | 52448 | 2023-11-02 | 2023-11-02 |  |  | CUBIC | 8 | [18 empty] | AJ | Fab table | November | 2023
34 | 2023-11-26 |  | AJ22-0551 | Provide electrical connection for CCTV installation for 17 buildings | 7249685 | FABRICATION | DB (DISTRIBUTION PANEL) APPROVED SUBMITTAL VIA TRANSMITTAL# AJ220551-LCV-ELEDSN- 0001 (SEE ATTCHED APPROVED SUBMITTAL) | 53320 | 2023-11-26 | 2023-12-01 |  |  | LT | 1 | [6 empty] | LCVKW0923S | 1 |  |  |  |  | AL NISF ELECTRICAL CO WLL | 2024-01-21 |  |  |  | CANCELLED | AJ | Fab table | November | 2023
34 | 2023-11-26 |  | AJ22-0551 | Provide electrical connection for CCTV installation for 17 buildings | 7249685 | FABRICATION | FABRICATION, SPD BOX IP65 8 x 6 x 6in (HxWxD) (SEE ATTACHED DRAWING) | 53320 | 2023-11-26 | 2023-12-01 |  |  | LT | 1 | [6 empty] | LCVKW0923S | 2 |  |  |  |  | AL NISF ELECTRICAL CO WLL | 2024-01-21 |  |  |  | CANCELLED | AJ | Fab table | November | 2023
34 | 2023-11-26 |  | AJ22-0551 | Provide electrical connection for CCTV installation for 17 buildings | 7249685 | FABRICATION | FABRICATION, STAND (SEE ATTACHED DRAWING) | 53320 | 2023-11-26 | 2023-12-01 |  |  | LT | 12 | [6 empty] | LCVKW0925S | 3 |  |  |  |  | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-21 |  |  |  | CANCELLED | AJ | Fab table | November | 2023
35 | 2023-12-13 |  | AJ23-0512 | CLVB RLB Upgrade | 8139100 | FABRICATION | FABRICATION, PANEL (DB) , APPROVED SUBMITTAL VIA TRANSMITTAL# AJ230512-LCV-ELEDSN- 0001.01 | 54010 | 2023-12-13 | 2023-12-17 |  | 1 | LT | 1 | 1148 | 1148 |  |  |  |  | LCVKW0950S | 1 |  |  |  |  | AL NISF ELECTRICAL CO WLL |  | COMP | 2024-02-10 |  |  | AJ | Fab table | December | 2023
36 | 2023-12-13 |  | AJ23-0536 | Electrical & Carpentry B1005 Z6, | 8379855 | FABRICATION | FABRICATION, PANEL MDB , APPROVED SUBMITTAL VIA TRANSMITTAL# AJ230536-LCV-ELEMTL- 0001 | 54009 | 2023-12-13 | 2023-12-17 |  | 1 | LT | 1 | 4430 | 4430 |  |  |  |  | LCVKW0949S | [5 empty] | AL NISF ELECTRICAL CO WLL | 2023-01-21 | COMP |  |  | Delivery completed | AJ | Fab table | December | 2023
36 | 2023-12-13 |  | AJ23-0536 | Electrical & Carpentry B1005 Z6, | 8379855 | FABRICATION | FABRICATION, OUTDOOR OUTLET STAND (SEE ATTCHED DRAWING) | 54009 | 2023-12-13 | 2023-12-17 |  | 2 | LT | 6 | 179 | 1074 |  |  |  |  | LCVKW0949S | [5 empty] | AL NISF ELECTRICAL CO WLL | 2024-02-15 |  |  |  |  | AJ | Fab table | December | 2023
40 | 2023-12-19 |  | AJ21-0011 | 43 Electrical Meter Installation, | 5171089 | FABRICATION | FABRICATION, SCHNEIDER ELECTRIC (SE)FABRICATION, SCHNEIDER ELECTRIC (SE) NEMA 4X CUSTOM ENCLOSURE, EACH | 54208 | 2023-12-19 | 2023-12-21 |  | 1 | LT | 33 | 221970.87 | 221970.87 |  |  |  |  | LCVKW0657S | 1 | 2024-02-05 |  |  |  | Schneider | 2024-05-02 |  |  |  | IFS PR COMPLETED | AJ | Fab table | December | 2023
41 | 2023-12-19 |  | AJ21-0011 | 43 Electrical Meter Installation, | 5171089 | FABRICATION | CURRENT TRANSFORMER (CT) | 54208 | 2023-12-19 | 2023-12-21 |  | 2 | LT | 99 | 31747.47 | 31747.47 |  |  |  |  | LCVKW0657S | 2 | 2024-02-05 |  |  |  | Schneider | 2024-05-02 |  |  |  | IFS PR COMPLETED | AJ | Fab table | December | 2023
44 | 2023-12-12 |  | AJ23-0788 | Replace electrical panel for TT7011 | 7996575 | FABRICATION | FABRICATION, PANEL MDB , APPROVED SUBMITTAL VIA TRANSMITTAL# AJ230788-LCV-ELEDSN- 0001 | 54414 | 2023-12-12 | 2023-12-31 |  | 1 | LT | 1 | 4317.1 | 4317.1 |  |  |  |  | LCVKW0983 | [5 empty] | AL NISF ELECTRICAL CO WLL | 2024-02-15 | COMP | 2024-02-10 |  | IFS PR COMPLETED | AJ | Fab table | December | 2023
46 | 2023-11-01 |  | AJ23-0726 | Replacement of Isolator Panel and Suction Pumps | 7641976 | FABRICATION | FABRICATION CONTROL PANEL, APPROVED SUBMITTAL VIA TRANSMITTAL# AJ230726-LCVGEN- MTL-0001 | 52516 | 2023-11-02 | 2023-11-06 |  | 1 | LT | 1 | 4929 | 4929 |  |  |  |  | LCVKW0885S | [5 empty] | AL NISF ELECTRICAL CO WLL | 2024-01-21 | COMP |  |  | Delivery completed | AJ | Fab table | November | 2023
47 | 2023-11-12 |  | AJ22-0465 | Zone 7 Fire Station 4 Refer Power Connection | 7116535 | FABRICATION | FDP (FINAL DISTRIBUTION PANEL) APPROVED SUBMITTAL VIA TRANSMITTAL# AJ220465-LCVELE- MTL-0001 (SEE ATTCHED APPROVED SUBMITTAL) | 52715 | 2023-11-12 | 2023-11-12 |  | 1 | LT | 1 | 2300.31 | 2300.31 |  |  |  |  | LCVKW0903S | [5 empty] | AL NISF ELECTRICAL CO WLL | 2024-01-21 | COMP | 2024-02-21 |  | IFS PR COMPLETED | AJ | Fab table | November | 2023
48 | 2023-12-29 |  | AJ24-0065 | Zone 2 B505 ASG 511 Connection to Support ASG 014 | 8038045 | FABRICATION | MTS-2000A | 55085 | 2024-01-20 | 2024-01-22 |  | 1 | LT | 1 | 10437.9 | 10437.9 |  |  |  |  | LCVKW1014S | [5 empty] | AL NISF ELECTRICAL CO WLL | 2024-02-29 | COMP | 2024-02-10 |  | IFS PR COMPLETED | AJ | Fab table | December | 2023
49 | 2024-01-03 |  | AJ23-0512 | CLVB RLB Upgrade | 8139100 | FABRICATION | MDB | 55228 | 2024-01-20 | 2024-01-24 |  | 1 | LT | 1 | 1750.85 | 1750.85 |  |  |  |  | LCVKW1029S | [5 empty] | AL NISF ELECTRICAL CO WLL | 2024-02-21 | COMP | 2024-02-21 |  | IFS PR COMPLETED | AJ | Fab table | January | 2024
50 | 2024-01-31 |  | AJ24-0202 | Z7 CRSP Yard SS812 Elec Repairs |  | FABRICATION | LDB | [24 empty] | Vendor submittal received 1 Feb | AJ | Fab table | January | 2024
51 | 2024-02-14 |  | AJ24-0203 | MAIN FEEDER CABLE DAMAGED NEED TO REPLACE |  | FABRICATION | MSB 100A , 4 WAYS 415/240V 100A 50H | PWD-ELEC-PANEL-PWO-AJ24-0203-4065.1 | 2024-03-05 |  |  | 1 | LT | 1 | 2211 | 2211 | [16 empty] | AJ | Fab table | February | 2024
52 | 2024-02-29 |  | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | FABRICATION | DB-1, INDOOR IP 42, Main 63A |  |  |  |  | 1 | AY | [18 empty] | Vendor Suibmittal received 3Mar24 | AJ | Fab table | February | 2024
52 | 2024-02-29 |  | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | FABRICATION | DB-2, INDOOR IP 42, Main 80A |  |  |  |  | 1 | AY | [19 empty] | AJ | Fab table | February | 2024
52 | 2024-02-29 |  | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | FABRICATION | BUS BAR FABRICATION (AJ MDP 1600A )https://www.bahra-electric.com/Products/Busbars.aspx |  |  |  |  | 1 | AY | [19 empty] | AJ | Fab table | February | 2024
53 | 2024-02-14 |  | AJ23-0551 | SPOD T5 Refurbishment | 6443145 | FABRICATION | MDP PANEL 125A 6 WAYS |  |  |  |  | 1 | AY | [18 empty] | Vewndor submittal received 14 Feb | AJ | Fab table | February | 2024

## BU Fabrication PR
NO. OF PROJECTS | BOM Received date | TASK | PROJECT# | PROJECT DESCRIPTION | WO# | CATALOG | Item # | PR # | PR REQUESTED DATE | PR APPROVED DATE | PR Cur. Status | PR Line # | Unit of Issue | Order Qty. | Unit Cost | Ext. Cost (Line Cost) | RFQ # | RFQ Status | RFQ Status Date | RFQ Due Date | PO # | PO Line # | PO Award Date | PO Status | PO Status Date | Buyer | Vendor | Vendor Date (EDD) | Delivery Status | Delivery Date | Recv. Qty | Remarks | Color Code list | table | month | year
1 | 2023-12-16 |  | BU24-0095 | Install Vestibule Doors Z5 Pad21 TT14 | 8563372 | FABRICATION | FABRICATE METAL DOOR WITH METAL FRAME, CYPHER LOCK, PANIC BAR AND DOOR CLOSURE (SEE ATTCHED DRAWING AND SOW ) | 54270 | 2023-12-16 | 2023-12-24 | CLOSE | 1 | LT | 2 | 5224.66 | 10449.32 |  |  |  |  | LCVKW0995S | 1 | 2024-01-16 | APPR |  | SHIJO | EGYKUW | 2024-02-29 | COMP | 2024-03-05 | 1 | Rev-1 EDD March 10 | BU | Fab table | December | 2023
2 | 2023-12-16 |  | BU24-0096 | Install Vestibule Doors Z5 Pad21 TT09 | 8564095 | FABRICATION | FABRICATE METAL DOOR WITH METAL FRAME, CYPHER LOCK, PANIC BAR AND DOOR CLOSURE (SEE ATTCHED DRAWING AND SOW ) | 54279 | 2023-12-16 | 2023-12-24 | CLOSE | 1 | LT | 2 | 5224.66 | 10449.32 |  |  |  |  | LCVKW0995S | 1 | 2024-01-16 | APPR |  | SHIJO | EGYKUW | 2024-02-29 | COMP | 2024-03-05 | 1 | Rev-1 EDD March 10 | BU | Fab table | December | 2023
3 | 2023-12-19 |  | BU22-0007 | Install 50 Electrical Meters | 4103915 | FABRICATION | FABRICATION, SCHNEIDER ELECTRIC (SE)FABRICATION, SCHNEIDER ELECTRIC (SE) NEMA 4X CUSTOM ENCLOSURE, EACH | 54209 | 2023-12-19 | 2023-12-21 | APPR | 1 | LT | 40 | 269055.6 | 269055.6 |  |  |  |  | LCVKW0657S | 1 | 2024-02-05 | APPR |  | ROJAS | Schneider | 2024-05-02 |  |  |  | IFS PR COMPLETED | BU | Fab table | December | 2023
4 | 2023-12-19 |  | BU22-0007 | Install 50 Electrical Meters | 4103915 | FABRICATION | CURRENT TRANSFORMER (CT) | 54209 | 2023-12-19 | 2023-12-21 | APPR | 1 | LT | 120 | 17274.27 | 17274.27 |  |  |  |  | LCVKW0657S | 2 | 45327 | APPR |  | ROJAS | Schneider | 2024-05-02 |  |  |  | IFS PR COMPLETED | BU | Fab table | December | 2023
5 | 2023-12-24 |  | BU24-0093 | Change Door Z1 B100 RM127 | 8564196 | FABRICATION | FABRICATE METAL DOOR WITH CIPHER LOCK AS PER APPROVED DESIGN. INCLUDES PANICPUSH BAR, SARGENT HEAVY DUTY DOOR CLOSER AND CIPHER LOCK | 54415 | 2023-12-25 | 2023-12-31 | CLOSE | 1 | LT | 1 | 4052.91 | 4052.91 |  |  |  |  | LCVKW0995S | 1 | 2024-01-16 | APPR |  | SHIJO | EGYKUW | 2024-02-16 | COMP | 2024-03-05 | 1 | Rev-1 EDD March 10 | BU | Fab table | December | 2023
6 | 2024-01-07 |  | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | FABRICATION | Wooden door w/ 10cm frame x 90 x 210Cm pre painted w/ hinges,door locks lever type and thumblatch, sargeant locks, rigth hand (Lock set, mortise, 8205 series, office/entry, 2-3/4 inches ; manufacturer: sargent) | 54848 | 2024-01-14 | 2024-01-14 | APPR | 1 | AY | 2 | 2640 | 5280 |  |  |  |  | LCVKW1002S | 1 | 2024-01-18 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-18 | COMP | 2024-02-07 |  |  | BU | Fab table | January | 2024
7 | 2024-01-07 |  | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | FABRICATION | Wooden door w/ 10cm frame x 100 x 210Cm pre- painted w/ hinges,door locks lever type and thumblatch, sargeant locks, rigth hand (Lock set, mortise, 8205 series, office/entry, 2-3/4 inches ; manufacturer: sargent) | 54848 | 2024-01-14 | 2024-01-14 | APPR | 2 | AY | 1 | 2640 | 2640 |  |  |  |  | LCVKW1002S | 2 | 2024-01-18 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-18 | COMP | 2024-02-07 |  |  | BU | Fab table | January | 2024
8 | 2024-01-08 |  | BU23-0193 | Z2 TT2071 Build Out | 6871039 | FABRICATION | DB (DISTRIBUTION PANEL) | 55258 | 2024-01-24 | 2024-01-25 | APPR | 1 | AY | 1 | 2333.1 | 2333.1 |  |  |  |  | LCVKW1029S | 1 | 2024-02-04 | APPR |  | SHIJO | AL NISF ELECTRICAL CO WLL | 2023-03-15 |  |  |  | IFS PR COMPLETED | BU | Fab table | January | 2024
9 | 2024-01-09 |  | BU24-0066 | Repair Sunshade Z3 SS3081 | 8293539 | FABRICATION | FABRICATION WITH MATERIALS OF FRAME AND CANVAS REPAIR (require vendor visit) | 55206 | 2024-01-23 | 2024-01-24 | APPR | 1 | AY | 1 | 15000 | 15000 |  |  |  |  | LCVKW1021S | 1 | 2024-01-29 | APPR |  | SHIJO | GULF PIONEER COMPANY LLC | 2024-02-28 | COMP |  |  |  | BU | Fab table | January | 2024
10 | 2024-01-09 |  | BU24-0064 | Rev1 Repair Sunshade Z3 SS3082 | 8687667 | FABRICATION | FABRICATION WITH MATERIALS OF FRAME AND CANVAS REPAIR (require vendor visit) | 55203 | 2024-01-23 | 2024-01-24 | APPR | 2 | AY | 1 | 16000 | 16000 |  |  |  |  | LCVKW1021S | 2 | 2024-01-29 | APPR |  | SHIJO | GULF PIONEER COMPANY LLC | 2024-02-28 | COMP |  |  |  | BU | Fab table | January | 2024
11 | 2024-01-16 |  | BU24-0048 | New Signs ASP Z8 T8000 | 8418200 | FABRICATION | Sign stand 2" x 2" squre tube 84" heigth, 6ft base frame 2" x 3" squre tube with 8 hole 4 hole each side, 1 1/4" diameter for anchor rod. Pls see attached file. (Primed and painted tan color) | 54993 | 2024-01-17 | 2024-01-18 | APPR | 1 | LT | 20 | 645 | 12900 |  |  |  |  | LCVKW1011S | 1 | 2024-01-24 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-24 | COMP | 2024-02-18 |  | IFS PR COMPLETED | BU | Fab table | January | 2024
13 | 2024-01-16 |  | BU24-0048 | New Signs ASP Z8 T8000 | 8418200 | FABRICATION | Steel rod pointed tip 1' diameter 24" length 2" x 2" square head. | 54993 | 2024-01-17 | 2024-01-18 | APPR | 2 | LT | 125 | 30 | 3750 |  |  |  |  | LCVKW1011S | 2 | 2024-01-24 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-24 | COMP | 2024-02-18 |  | IFS PR COMPLETED | BU | Fab table | January | 2024
12 | 2024-01-27 |  | BU24-0059 | Add T132 to TE | 8528915 | FABRICATION | consumer distribution panel indoor | 56192 | 2024-02-14 | 2024-02-17 | APPR | 2 | LT | 1 | 1914 | 3828 |  |  |  |  | LCVKW1098S | 1 | 2024-03-04 |  |  |  | AL NISF ELECTRICAL CO WLL | 2024-03-30 |  |  |  |  | BU | Fab table | January | 2024
13 | 2024-01-27 |  | BU24-0059 | Add T132 to TE | 8528915 | FABRICATION | Fabrication of single leaf wooden door with wooden frame, Door closer and Lock set cylindrical mortise (see attached drawing) | 56192 | 2024-02-14 | 2024-02-17 | APPR | 1 | EA | 2 | 541 | 541 |  |  |  |  | LCVKW1092S | 2 | 2024-03-04 |  |  |  | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | January | 2024
14 | 2024-01-31 |  | BU23-0366 | Connect to MDP Z5 Pad16 TT516 | 8528982 | FABRICATION | FABRICATION, PANEL (DB) DISTRIBUTION BOARD, APPROVED SUBMITTAL VIA TRANSMITTAL # BU230366-LCV-ELE-DSN-0001 (SEE ATTCHED SUBMITTAL | 55610 | 2024-01-31 | 2024-02-01 | APPR | 1 | LT | 1 | 2123.72 | 2123.72 |  |  |  |  | LCVKW1073S | 1 | 2024-02-13 | APPR |  | SHIJO | AL NISF ELECTRICAL CO WLL | 2024-03-13 | COMP | 2024-02-21 |  | IFS PR COMPLETED | BU | Fab table | January | 2024
15 | 2024-02-07 |  | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | FABRICATION | Wooden door 10cm frame, 90x210Cm, hinges, primed and painted smooth finish, LEFTT hand, (required vendor visit to match the exisitimg door design and color) | 55973 | 2024-02-10 | 2024-02-11 | APPR | 1 | LT | 5 | 1255 | 6275 |  |  |  |  | LCVKW1078S | 1 | 2024-02-17 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 | COMP | 2024-03-02 | 5 |  | BU | Fab table | February | 2024
15 | 2024-02-07 |  | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | FABRICATION | Wooden door 10cm frame, 90x210Cm, hinges, primed and painted smooth finish, RIGTH hand, (required vendor visit to match the exisitimg door design and color) | 55973 | 2024-02-10 | 2024-02-11 | APPR | 2 | LT | 5 | 1255 | 6275 |  |  |  |  | LCVKW1078S | 2 | 2024-02-17 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 | COMP | 2024-03-02 | 5 |  | BU | Fab table | February | 2024
15 | 2024-02-07 |  | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | FABRICATION | BAR, METAL, FLAT, GALVANIZE STEEL, 1/4 X 1-1/2 INCHES X 20 FEET WITH 18SQMM HOLE 1FT APART | 55973 | 2024-02-10 | 2024-02-11 | APPR | 3 | LT | 30 | 73 | 2190 |  |  |  |  | LCVKW1078S | 3 | 2024-02-17 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024
16 | 2024-02-07 |  | BU24-0050 | ARTC TT614 Vestibule | 9487106 | FABRICATION | PPGI ROOF SHEET BOX PROFILE,28 GAUGE- COLOR : BEIGE, SIZE 1.8 M X 1 M | 56189 | 2024-02-13 | 2024-02-17 | APPR | 1 | LT | 6 | 16 | 96 |  |  |  |  | LCVKW1089S | 1 | 2024-02-27 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024
16 | 2024-02-07 |  | BU24-0050 | ARTC TT614 Vestibule | 9487106 | FABRICATION | PPGI WALL SHEET BOX PROFILE,28 GAUGE- COLOR : BEIGE, SIZE 2.25 M X 1.15 M | 56189 | 2024-02-13 | 2024-02-17 | APPR | 2 | LT | 16 | 25 | 400 |  |  |  |  | LCVKW1089S | 2 | 2024-02-27 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024
16 | 2024-02-07 |  | BU24-0050 | ARTC TT614 Vestibule | 9487106 | FABRICATION | RIDGE - COLOR : BEIGE, SIZE 2.40 M X 0.035 MM | 56189 | 2024-02-13 | 2024-02-17 | APPR | 3 | LT | 4 | 122 | 488 |  |  |  |  | LCVKW1089S | 3 | 2024-02-27 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024
16 | 2024-02-07 |  | BU24-0050 | ARTC TT614 Vestibule | 9487106 | FABRICATION | FLASHING - COLOR : BEIGE, SIZE 2.40 M X 0.035 MM | 56189 | 2024-02-13 | 2024-02-17 | APPR | 4 | LT | 10 | 122 | 1220 |  |  |  |  | LCVKW1089S | 4 | 2024-02-27 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024
16 | 2024-02-07 |  | BU24-0050 | ARTC TT614 Vestibule | 9487106 | FABRICATION | METAL DOOR WITH FRAME INCLUDING ACCESSORIES (KABA CIPHER LOCK , SARGENT DOOR CLOSER ,SARGENT PUSH BAR LOCK , DOOR HINGES) | 56189 | 2024-02-13 | 2024-02-17 | APPR | 5 | LT | 2 | 6435 | 12870 |  |  |  |  | LCVKW1089S | 5 | 2024-02-27 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024
17 | 2024-02-07 |  | BU24-0051 | ARTC TT615 Vestibule | 9487373 | FABRICATION | PPGI ROOF SHEET BOX PROFILE,28 GAUGE- COLOR : BEIGE, SIZE 1.8 M X 1 M | 56190 | 2024-02-13 | 2024-02-17 | APPR | 1 | EA | 6 | 16 | 96 |  |  |  |  | LCVKW1090S | 1 | 45349 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024
17 | 2024-02-07 |  | BU24-0051 | ARTC TT615 Vestibule | 9487373 | FABRICATION | PPGI WALL SHEET BOX PROFILE,28 GAUGE- COLOR : BEIGE, SIZE 2.25 M X 1.15 M | 56190 | 2024-02-13 | 2024-02-17 | APPR | 2 | EA | 16 | 25 | 400 |  |  |  |  | LCVKW1090S | 2 | 45349 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024
17 | 2024-02-07 |  | BU24-0051 | ARTC TT615 Vestibule | 9487373 | FABRICATION | RIDGE - COLOR : BEIGE, SIZE 2.40 M X 0.035 MM | 56190 | 2024-02-13 | 2024-02-17 | APPR | 3 | EA | 4 | 122 | 488 |  |  |  |  | LCVKW1090S | 3 | 45349 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024
17 | 2024-02-07 |  | BU24-0051 | ARTC TT615 Vestibule | 9487373 | FABRICATION | FLASHING - COLOR : BEIGE, SIZE 2.40 M X 0.035 MM | 56190 | 2024-02-13 | 2024-02-17 | APPR | 4 | EA | 10 | 122 | 1220 |  |  |  |  | LCVKW1090S | 4 | 45349 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024
17 | 2024-02-07 |  | BU24-0051 | ARTC TT615 Vestibule | 9487373 | FABRICATION | METAL DOOR WITH FRAME INCLOODING ,ACCESSORIES (KABA CIPHER LOCK , SARGENT DOOR CLOSER ,SARGENT PUSH BAR LOCK , DOOR HINGES) | 56190 | 2024-02-13 | 2024-02-17 | APPR | 5 | LOT | 2 | 6435 | 12870 |  |  |  |  | LCVKW1090S | 5 | 45349 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024
18 | 2024-02-18 |  | BU24-0167 | Install Security Bars Z2 Trailer2028 | 9653621 | FABRICATION | FABRICATED WINDOW GRILL WITH A HEIGHT OF 118 CM AND A WIDTH OF 98 CM USING A 4CM X 6MM FLAT BAR FRAME, WITH A DIMENSION OF | 56329 | 2024-02-21 | 2024-02-21 | APPR | 1 | LT | 2 | 280.5 | 280.5 | [10 empty] | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  | Verbal Award | BU | Fab table | February | 2024
19 | 2024-03-02 |  | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS |  | Fabrication | BAR, METAL, FLAT, GALVANIZE STEEL, 1/4 X 1-1/2 INCHES X 20 FEET WITH 18SQMM HOLE 1FT APART) | 56856 | 2024-03-05 | 2024-03-05 | APPR | 1 | LT | 8 | 73 | 584 | [16 empty] | BU | Fab table | March | 2024
20 | 2024-02-24 |  | BU24-0174 | Correct TI deficiencies ECP1 Breakroom |  | Fabrication | FABRICATION OF WINDOW SCREEN ( height -95.5cm, width-79.5) | PRINPRG |  |  |  |  | EA | 2 | [18 empty] | BU | Fab table | February | 2024
21 | 2024-02-20 |  | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | Fabrication | Testing and Commissioning by Supplier/SME | PRINPRG |  |  |  |  | LOT | 1 | [18 empty] | BU | BU table | December | 2023
22 | 2024-02-20 |  | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | Fabrication | Testing and Commissioning by Supplier/SME | PRINPRG |  |  |  |  | LOT | 1 | [18 empty] | BU | Fab table | February | 2024

## AJ Subcon PR
NO. OF PROJECTS | BOM Received date | TASK | PROJECT# | PROJECT DESCRIPTION | WO# | CATALOG | Item # | PR # | PR REQUESTED DATE | PR APPROVED DATE | PR Cur. Status | PR Line # | Unit of Issue | Order Qty. | Unit Cost | Ext. Cost (Line Cost) | RFQ # | RFQ Status | RFQ Status Date | RFQ Due Date | PO # | PO Line # | PO Award Date | PO Status | PO Status Date | Buyer | Vendor | Vendor Date (EDD) | Delivery Status | Delivery Date | Recv. Qty | Remarks | Color Code list | table | month | year
2 | 2022-10-02 |  | AJ22-0241 | Building 5723 TT PKAC Replacement | 2647953 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 38225 | 2022-10-02 | 2022-10-11 | [22 empty] | AJ | Sub table | October | 2022
3 | 2022-10-03 |  | AJ22-0218 | Interlock Concrete Pavers for Walking Area at Camp Arifjan. | 2647953 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 38173 | 2022-10-03 | 2022-10-08 | [22 empty] | AJ | Sub table | October | 2022
5 | 2022-10-10 |  | AJ22-0392 | ILU Repair Set 4 | 3326596 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 38641 | 2022-10-10 | 2022-10-26 | [22 empty] | AJ | Sub table | October | 2022
6 | 2022-10-10 |  | AJ22-0234 | ILU Repair Set 1 | 3296566 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 38640 | 2022-10-10 | 2022-10-26 | [22 empty] | AJ | Sub table | October | 2022
7 | 2022-10-11 |  | AJ22-0042 | B6075 MTS Replace | 2624592 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 38638 | 2022-10-11 | 2022-10-22 | [22 empty] | AJ | Sub table | October | 2022
8 | 2022-10-15 |  | AJ22-0175 | Bldg. 224 Steam Generator 1 Replacement | 2873774 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39353 | 2022-10-15 | 2022-11-13 | [22 empty] | AJ | Sub table | October | 2022
10 | 2022-10-17 |  | AJ21-0002 | APS-5 Medical Warehouse Bldg. 4009 | 195272 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39424 | 2022-10-17 | 2022-11-15 | [22 empty] | AJ | Sub table | October | 2022
11 | 2022-10-17 |  | AJ22-0352 | Hazardous Waste Material Removal in Lot 59 | 3054100 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39621 | 2022-10-17 | 2022-11-21 | [22 empty] | AJ | Sub table | October | 2022
12 | 2022-10-17 |  | AJ22-0335 | Bldg.205 Substation 5 Cleaning & Maintenance | 3055849 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39620 | 2022-10-17 | 2022-11-21 | [22 empty] | AJ | Sub table | October | 2022
13 | 2022-10-17 |  | AJ22-0174 | B224 Chiller Water Pump Replacement | 2539650 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39259 | 2022-10-17 | 2022-11-09 | [22 empty] | AJ | Sub table | October | 2022
14 | 2022-10-17 |  | AJ22-0336 | Z1 B165 Cleaning and Maintenance | 3055853 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39654 | 2022-10-17 | 2022-11-22 | [22 empty] | AJ | Sub table | October | 2022
15 | 2022-10-17 |  | AJ22-0354 | Z7 Lot 32 Debris Removal | 3054121 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39264 | 2022-10-17 | 2022-11-09 | [22 empty] | AJ | Sub table | October | 2022
16 | 2022-10-18 |  | AJ22-0353 | Z7 Clearing EOD Training Site | 2453547 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39352 | 2022-10-18 | 2022-11-13 | [22 empty] | AJ | Sub table | October | 2022
18 | 2022-10-19 |  | AJ21-0038 | BLDG 1131 Office Buildout | 2504223 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39622 | 2022-10-19 | 2022-11-21 | [22 empty] | AJ | Sub table | October | 2022
19 | 2022-10-20 |  | AJ22-0236 | ILU Repair Set 3 | 3326587 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39354 | 2022-10-20 | 2022-11-13 | [22 empty] | AJ | Sub table | October | 2022
20 | 2022-10-22 |  | AJ22-0393 | ILU Repair Set 5 | 3326604 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39349 | 2022-10-22 | 2022-11-13 | [22 empty] | AJ | Sub table | October | 2022
21 | 2022-10-22 |  | AJ22-0394 | ILU Repair Set 6 | 3326608 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39350 | 2022-10-22 | 2022-11-13 | [22 empty] | AJ | Sub table | October | 2022
22 | 2022-10-23 |  | AJ22-0176 | BLDG 224 Steam Generator Replacement | 2873763 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39261 | 2022-10-23 | 2022-11-09 | [22 empty] | AJ | Sub table | October | 2022
23 | 2022-10-26 |  | AJ22-0177 | Bldg. 224 Steam Generator 3 Replacement | 2873756 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39262 | 2022-10-26 | 2022-11-09 | [22 empty] | AJ | Sub table | October | 2022
25 | 2022-10-27 |  | AJ22-0146 | B507 Fire Hardening | 2671555 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39050 | 2022-10-27 | 2022-11-03 | [22 empty] | AJ | Sub table | October | 2022
26 | 2022-10-27 |  | AJ22-0147 | Utilities ASP500 Tie-in | 2147424 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39048 | 2022-10-27 | 2022-11-03 | [22 empty] | AJ | Sub table | October | 2022
27 | 2022-10-29 |  | AJ22-0235 | ILU Repair Set 2 | 3296610 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 38960 | 2022-10-29 | 2022-11-01 | [22 empty] | AJ | Sub table | October | 2022
29 | 2022-11-03 |  | AJ22-0534 | Care and Preservation Facility |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39049 | 2022-11-03 | 2022-11-03 | [22 empty] | AJ | Sub table | November | 2022
30 | 2022-11-06 |  | AJ22-0407 | Z6 Senior Pods Shower Replacement | 3270986 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39265 | 2022-11-06 | 2022-11-09 | [22 empty] | AJ | Sub table | November | 2022
31 | 2022-11-06 |  | AJ22-0409 | Z6 Senior Pods Female Shower | 3270589 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39256 | 2022-11-06 | 2022-11-09 | [22 empty] | AJ | Sub table | November | 2022
32 | 2022-11-06 |  | AJ22-0407 | Z6 Senior Pods Shower Replacement | 3270986 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39265 | 2022-11-06 | 2022-11-09 | [22 empty] | AJ | Sub table | November | 2022
33 | 2022-11-08 |  | AJ22-0333 | Substation 3 Cleaning & Maintenance Zone 1-Bldg 121 | 3137625 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39625 | 2022-11-08 | 2022-11-21 | [22 empty] | AJ | Sub table | November | 2022
34 | 2022-11-09 |  | AJ22-0332 | Substation 2 Cleaning & Maintenance Zone 2-Bldg 463 | 3055876 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39624 | 2022-11-09 | 2022-11-21 | [22 empty] | AJ | Sub table | November | 2022
35 | 2022-11-10 |  | AJ22-0334 | Z1 B145 Cleaning and Maintenance | 3055843 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39626 | 2022-11-10 | 2022-11-21 | [22 empty] | AJ | Sub table | November | 2022
36 | 2022-11-14 |  | AJ22-0331 | Substation 1 Cleaning & Maintenance Zone 2-Bldg 513 | 3055868 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39646 | 2022-11-14 | 2022-11-22 | [22 empty] | AJ | Sub table | November | 2022
37 | 2022-11-21 |  | AJ22-0046 | Replace HVAC System and Controls at B-306 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39903 | 2022-11-21 | 2022-11-29 | [22 empty] | AJ | Sub table | November | 2022
38 | 2022-11-21 |  | AJ22-0106 | Pipe Leak Repair At Zone 2 APS 500 Warehouse 4 | 2539713 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | PWD-PROJECT-PWO-AJ22-0106- 2325 | 2022-11-21 | [22 empty] | As per Mark The Project has been cancelled | AJ | Sub table | November | 2022
39 | 2022-11-22 |  | AJ22-0468 | Bldg.216 Chiller Efficiency Upgrade, Camp Arifjan | 3511691 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 40106 | 2022-11-22 | 2022-12-03 | [22 empty] | AJ | Sub table | November | 2022
40 | 2022-12-11 |  | AJ22-0379 | Z5 Trailer T28 Tie In | 3133125 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 46334 | 2022-12-11 | 2023-05-23 | [22 empty] | AJ | Sub table | December | 2022
41 | 2022-12-11 |  | AJ22-0232 | Z6 Repair Pipeline B544-1 | 3215439 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 48591 | 2022-12-11 | 2023-07-23 | [22 empty] | AJ | Sub table | December | 2022
43 | 2022-12-18 |  | AJ22-0359 | Z7 Relocate Tents | 3145108 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 41641 | 2022-12-18 | 2023-01-24 | [22 empty] | AJ | Sub table | December | 2022
44 | 2022-12-19 |  | AJ22-0325 | Z1 B145 Mini Splits | 3195847 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 40978 | 2022-12-19 | 2023-01-03 | [22 empty] | AJ | Sub table | December | 2022
50 | 2023-01-17 |  | AJ22-0021 | Bldg 162 PSD Control Room Remodel | 4535846 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 41583 | 2023-01-17 | 2022-01-22 | [22 empty] | AJ | Sub table | January | 2023
51 | 2023-01-21 |  | AJ22-0205 | Deconstruct RLB Pad-D, Camp Arifjan | 2035242 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 41729 | 2023-01-21 | 2023-01-25 | [22 empty] | AJ | Sub table | January | 2023
52 | 2023-01-22 |  | AJ22-0233 | Bldg B6028 Replacement of Water Pipelines | 4246289 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 42739 | 2023-01-22 | 2023-01-19 | [22 empty] | AJ | Sub table | January | 2023
54 | 2023-01-28 |  | AJ22-0534 | Care and Preservation Facility T | 3615548 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | PWD-PROJECT-PWO-AJ22-0534-3028 | 2023-01-28 | [22 empty] | PR Cancelled | AJ | Sub table | January | 2023
57 | 2023-02-13 |  | AJ22-0297 | B131 Pool Pump Room HVAC and Handrail Install | 3604408 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44881 | 2023-02-13 | 2023-04-19 | [22 empty] | AJ | Sub table | February | 2023
68 | 2023-03-14 |  | AJ22-0351 | Male Latrine Floor Tile Replacement B507 Zone 2 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 43635 | 2023-03-14 | 2023-03-15 | [22 empty] | AJ | Sub table | March | 2023
69 | 2023-03-25 |  | AJ21-0038 | BUILDING 1131 OFFICE BUILDOUT |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45127 | 2023-03-25 | 2023-04-26 | [22 empty] | AJ | Sub table | March | 2023
72 | 2023-03-29 |  | AJ22-0317 | Z6 T1022 SINK TIE IN | 3897909 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44237 | 2023-03-29 | 2023-03-30 | [22 empty] | AJ | Sub table | March | 2023
74 | 2023-04-06 |  | AJ22-0322 | BLDG 513 HVAC AND FACILITY REPAIR | 3187334 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44605 | 2023-04-06 | 2023-04-11 | [22 empty] | AJ | Sub table | April | 2023
75 | 2023-04-06 |  | AJ22-0326 | B 205 HVAC AND FACILITY REPAIR | 3196414 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44608 | 2023-04-06 | 2023-04-11 | [22 empty] | AJ | Sub table | April | 2023
76 | 2023-04-06 |  | AJ22-0324 | BLDG 121 HVAC AND FACILITY REPAIR | 3193786 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44603 | 2023-04-06 | 2023-04-11 | [22 empty] | AJ | Sub table | April | 2023
78 | 2023-04-10 |  | AJ22-0327 | B-165 HVAC AND FACILITY REPAIR | 3196067 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51577 | 2023-04-10 | 2023-10-10 | [22 empty] | AJ | Sub table | April | 2023
82 | 2023-04-16 |  | AJ23-0045 | BACKUP CONNECTION TO HOSPITAL REEFER | 4304698 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 47185 | 2023-04-16 | 2023-06-13 | [22 empty] | AJ | Sub table | April | 2023
83 | 2023-04-18 |  | AJ22-0321 | B-350 HVAC and Facility Repair at Camp Arifjan | 3196626 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45380 | 2023-04-18 | 2023-05-02 | [22 empty] | AJ | Sub table | April | 2023
85 | 2023-04-18 |  | AJ23-0134 | CARE & PRESERVATION CENTER GENERATOR SERVICE | 5685817 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45465 | 2023-04-18 | 2023-05-03 | [22 empty] | AJ | Sub table | April | 2023
87 | 2023-04-26 |  | AJ23-0090 | SPOD Fuel Generator Consolidation, Camp SPOD | 5770261 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45805 | 2023-04-26 | 2023-05-10 | [22 empty] | AJ | Sub table | April | 2023
88 | 2023-04-30 |  | AJ22-0231 | BLDG 6029 REPLACEMENT OF WATER PIPELINES | 3216160 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45803 | 2023-04-30 | 2023-05-10 | [22 empty] | AJ | Sub table | April | 2023
93 | 2023-05-06 |  | AJ23-0132 | TI FOR APS 500 WAREHOUSE |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45821 | 2023-05-06 | 2023-05-10 | [22 empty] | AJ | Sub table | May | 2023
94 | 2023-05-06 |  | AJ23-0133 | TI FOR TIP C WAREHOUSE |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45957 | 2023-05-06 | 2023-05-13 | [22 empty] | AJ | Sub table | May | 2023
96 | 2023-05-13 |  | AJ22-0222 | PAD HVAC PLACEMENT IN SENIOR PODS | 3344194 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 4623247068 | 2023-05-13 | 5/21/2023, 8Jun 23 | [22 empty] | AJ | Sub table | May | 2023
97 | 2023-05-13 |  | AJ22-0400 | CONNECT 3100T TO GRID POWER ZONE 3 | 3682675 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 46055 | 2023-05-13 | 2023-05-17 | [22 empty] | AJ | Sub table | May | 2023
100 | 2023-05-17 |  | AJ23-0006 | HVAC LIFECYCLE REPLACEMENT T-824D ZONE 7, |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 46250 | 2023-05-17 | 2023-05-21 | [22 empty] | AJ | Sub table | May | 2023
102 | 2023-05-21 |  | AJ23-0005 | HVAC LIFECYCLE REPLACEMENT T-824C ZONE 7 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 46940 | 2023-05-21 | 2023-06-06 | [22 empty] | AJ | Sub table | May | 2023
103 | 2023-05-22 |  | AJ22-0198 | Z6 TT6007 FLOOR REPAIR | 3812629 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 47193 | 2023-05-22 | 2023-06-14 | [22 empty] | AJ | Sub table | May | 2023
104 | 2023-05-22 |  | AJ22-0322 | BLDG 513 HVAC FACILITY REPAIR | 3187334 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50607 | 2023-05-22 | 2023-09-19 | [22 empty] | AJ | Sub table | May | 2023
105 | 2023-05-22 |  | AJ22-0324 | BLDG 121 HVAC FACILITY REPAIR | 3193786 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 47195 | 2023-05-22 | 2023-06-14 | [22 empty] | AJ | Sub table | May | 2023
106 | 2023-05-22 |  | AJ22-0326 | B-205 HVAC AND FACILITY REPAIR | 3196414 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 47194 | 2023-05-22 | 2023-06-14 | [22 empty] | AJ | Sub table | May | 2023
108 | 2023-05-24 |  | AJ22-0547 | UPS LIFE CYCLE REPLACEMENT BLDG 505 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 47344 | 2023-05-24 | 2023-06-19 | [22 empty] | AJ | Sub table | May | 2023
109 | 2023-05-24 |  | AJ22-0507 | RADOME POWER UPGRADE |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 48309 | 2023-05-24 | 2023-07-13 | [22 empty] | AJ | Sub table | May | 2023
112 | 2023-05-28 |  | AJ22-0497 | 5th Medical Brigade Warehouse Doors Replacement- Bldg.550 | 3682682 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 47340 | 2023-05-28 | 2023-06-19 | [22 empty] | AJ | Sub table | May | 2023
114 | 2023-06-14 |  | AJ23-0004 | INSTALL SPLIT SYSTEM AND REPLACE THERMOSTAT | 3878081 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50914 | 2023-06-14 | 2023-09-23 | [22 empty] | AJ | Sub table | June | 2023
115 | 2023-06-14 |  | AJ22-0149 | REPLACEMENT OF UDS4 CABLE | 1676813 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 48670 | 2023-06-14 | 2023-07-23 | [22 empty] | AJ | Sub table | June | 2023
120 | 2023-07-12 |  | AJ23-0574 | Electrical Panel Replacement | 6653886 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | PWD-ELECT-PWO-AJ23-0574-3193 | 2023-07-12 | [22 empty] | Send ODC 12 July 23 | AJ | Sub table | July | 2023
125 | 2023-08-28 |  | AJ22-0537 | Install 15 Smart Water Meters | 7178664 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50415 | 2023-08-28 | 2023-09-13 | [22 empty] | AJ | Sub table | August | 2023
126 | 2023-09-02 |  | AJ22-0184 | ZONE 6 BASKET BALL COURT | 1975715 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52515 | 2023-09-02 | 2023-11-06 | [22 empty] | AJ | Sub table | September | 2023
127 | 2023-09-03 |  | AJ23-0192 | KNB Wash Rack Tank Repair | 7297357 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50097 | 2023-09-03 | 2023-09-03 | [22 empty] | AJ | Sub table | September | 2023
128 | 2023-09-03 |  | AJ23-0193 | KNB Wash Rack Sand Filter System Repair | 7312848 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50099 | 2023-09-03 | 2023-09-03 | [22 empty] | AJ | Sub table | September | 2023
129 | 2023-09-03 |  | AJ22-0380 | TRAILER MOVE AND TIE-IN | 2624597 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51885 | 2023-09-03 | 2023-10-18 | [22 empty] | AJ | Sub table | September | 2023
130 | 2023-09-07 |  | AJ22-0417 | TT752B HVAC REPLACEMEN | 3682803 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 3682803 | 2023-09-07 | 2023-09-07 | [22 empty] | AJ | Sub table | September | 2023
131 | 2023-09-10 |  | AJ23-0167 | TI Deficiencies Correction | 4911390 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50414 | 2023-09-10 | 2023-09-13 | [22 empty] | AJ | Sub table | September | 2023
132 | 2023-09-10 |  | AJ23-0179 | Lower Roof Replace Z4 Building 777, | 4970059 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50412 | 2023-09-10 | 2023-09-13 | [22 empty] | AJ | Sub table | September | 2023
134 | 2023-09-17 |  | AJ23-0306 | Bldg.134 PX Roof Repair |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50927 | 2023-09-17 | 2023-09-25 | [22 empty] | AJ | Sub table | September | 2023
135 | 2023-09-17 |  | AJ22-0123 | HVAC THERMOSTAT IN KDOC | 1567044 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50599 | 2023-09-17 | 2023-09-19 | [22 empty] | AJ | Sub table | September | 2023
136 | 2023-09-17 |  | AJ22-0055 | REPLACE THE YARD RADIATION DETECTORS AT DLA | 7527758 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51355 | 2023-09-17 | 2023-10-04 | [22 empty] | AJ | Sub table | September | 2023
137 | 2023-09-19 |  | AJ20-0135 | Military Working Dog |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52652 | 2023-09-19 | 2023-11-08 | [22 empty] | AJ | Sub table | September | 2023
138 | 2023-09-19 |  | AJ22-0378 | Solar Light Set | 7584104 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52634 | 2023-09-19 | 2023-11-09 | [22 empty] | AJ | Sub table | September | 2023
139 | 2023-09-19 |  | AJ22-0406 | RELOCATION OF POWER PANEL AND GENERATOR IN Z6 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52636 | 2023-09-19 | 2023-11-09 | [22 empty] | AJ | Sub table | September | 2023
140 | 2023-09-20 |  | AJ22-0004 | ECP-1 Access Road Repair | 7584064 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52258 | 2023-09-20 | 26ODC23 | [22 empty] | AJ | Sub table | September | 2023
141 | 2023-09-26 |  | AJ23-0007 | HVAC Lifecycle Replacement | 3898188 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52403 | 2023-09-26 | 2023-11-01 | [22 empty] | AJ | Sub table | September | 2023
143 | 2023-09-27 |  | AJ22-0199 | Replacement of the Solid State Frequency Converte | 2024951 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51888 | 2023-09-27 | 2023-10-19 | [22 empty] | AJ | Sub table | September | 2023
144 | 2023-09-28 |  | AJ23-0258 | RP6000 MARCENT New Trenching and Culverts |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52705 | 2023-09-28 | 2023-11-11 | [21 empty] | Resend to Contracts 6 Nov 23 | AJ | Sub table | September | 2023
145 | 2023-10-02 |  | AJ21-0038 | Office Buildout1131 | 2504223 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52245 | 2023-10-02 | 2043-01-14 | [22 empty] | AJ | Sub table | October | 2023
146 | 2023-10-03 |  | AJ23-0101 | DFAC Locker Rebuild | 4515922 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51361 | 2023-10-03 | 2023-10-04 | [22 empty] | AJ | Sub table | October | 2023
147 | 2023-10-03 |  | AJ22-0323 | HVAC and Facility Light Fixture Repair, | 2324497 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51359 | 2023-10-03 | 2023-10-04 | [22 empty] | AJ | Sub table | October | 2023
152 | 2023-10-09 |  | AJ23-0668 | Irrigation and Landscaping Zone 1 & 4 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52388 | 2023-10-09 | 2023-10-31 | [22 empty] | AJ | Sub table | October | 2023
154 | 2023-10-11 |  | AJ22-0536 | Remove existing asphalt road to subbase to be repaired. | 3790651 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51868 | 2023-10-11 | 2023-10-18 | [22 empty] | AJ | Sub table | October | 2023
157 | 2023-10-14 |  | AJ23-0268 | Walker Road Culvert Z2 | 7874945 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52495 | 2023-10-14 | 2023-11-04 | [22 empty] | AJ | Sub table | October | 2023
159 | 2023-10-16 |  | AJ23-0437 | TFCF Training Trailer Electrical Upgrades Z4 | 7995997 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52416 | 2023-10-16 | 2023-11-01 | [22 empty] | AJ | Sub table | October | 2023
161 | 2023-10-16 |  | AJ23-0079 | TT1004 Chapel Refurbishment Z6 | 7986313 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52413 | 2023-10-16 | 2023-11-01 | [22 empty] | AJ | Sub table | October | 2023
162 | 2023-10-16 |  | AJ23-0532 | T6526 NEW DOOR AND CIPHER LOCKS Z6 | 7975040 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52414 | 2023-10-16 | 2023-11-01 | [22 empty] | AJ | Sub table | October | 2023
163 | 2023-10-16 |  | AJ23-0598 | PAHP Flight Line Fence | 7973212 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52496 | 2023-10-16 | 2023-11-04 | [22 empty] | AJ | Sub table | October | 2023
164 | 2023-10-17 |  | AJ22-0390 | Renovate room 115 of Building 300 Zone 1, | 3444456 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52334 | 2023-10-17 | 2023-10-30 | [22 empty] | AJ | Sub table | October | 2023
165 | 2023-10-17 |  | AJ22-0546 | TT755 Grid Connection, | 8024236 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52134 | 2023-10-17 | 2023-10-24 | [22 empty] | AJ | Sub table | October | 2023
167 | 2023-10-18 |  | AJ23-0245 | T1000 Structural Assessment Z2 | 8019766 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52378 | 2023-10-18 | 2023-10-31 | [22 empty] | AJ | Sub table | October | 2023
169 | 2023-10-22 |  | AJ23-0481 | B505 HVAC Replacement | 7813302 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52316 | 2023-10-22 | 2023-10-28 | [22 empty] | AJ | Sub table | October | 2023
170 | 2023-10-22 |  | AJ23-0482 | B506 HVAC Replacement | 7814 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52317 | 2023-10-22 | 2023-10-28 | [22 empty] | AJ | Sub table | October | 2023
171 | 2023-10-22 |  | AJ23-0425 | B507 HVAC Replacement | 7815289 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52129 | 2023-10-22 | 2023-10-24 | [22 empty] | AJ | Sub table | October | 2023
172 | 2023-10-23 |  | AJ22-0549 | Zone 1 Curb Construction Phase 2 | 7815713 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52160 | 2023-10-23 | 2023-10-24 | [22 empty] | AJ | Sub table | October | 2023
173 | 2023-10-23 |  | AJ22-0073 | Lot 39 Perimeter Fence | 7815937 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52310 | 2023-10-23 | 2023-10-28 | [22 empty] | AJ | Sub table | October | 2023
174 | 2023-10-23 |  | AJ23-0166 | Zone 1 Sidewalk Construction | 7817685 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52309 | 2023-10-23 | 2023-10-28 | [22 empty] | AJ | Sub table | October | 2023
175 | 2023-10-24 |  | AJ23-0493 | Trailer LDN3 Floor Repairs Z6 | 3527965 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52358 | 2023-10-24 | 2023-10-30 | [22 empty] | AJ | Sub table | October | 2023
176 | 2023-10-24 |  | AJ22-0240 | ZONE 6 SOFTBALL SCORE BOARD | 8084482 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52329 | 2023-10-24 | 2023-10-28 | [22 empty] | AJ | Sub table | October | 2023
177 | 2023-10-24 |  | AJ23-0172 | MOTOR POOL 17 COMPOUND POWER CONSOLIDATION | 8013745 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52661 | 2023-10-24 | 2023-11-09 | [22 empty] | AJ | Sub table | October | 2023
178 | 2023-10-24 |  | AJ23-0442 | ADA Generator Power Consolidation Z5 | 8017222 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52410 | 2023-10-24 | 2023-11-01 | [22 empty] | AJ | Sub table | October | 2023
179 | 2023-10-24 |  | AJ23-0579 | PAT Entrance Gate and Fence Install Z5 | 8094857 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52714 | 2023-10-24 | 2023-11-13 | [22 empty] | AJ | Sub table | October | 2023
180 | 2023-10-24 |  | AJ23-0300 | B148 Chapel Acoustic Z1 | 5233949 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52321 | 2023-10-24 | 2023-10-28 | [22 empty] | AJ | Sub table | October | 2023
182 | 2023-10-25 |  | AJ23-0260 | Storm Water Drainage | 8110777 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52319 | 2023-10-25 | 2023-10-28 | [22 empty] | AJ | Sub table | October | 2023
183 | 2023-10-29 |  | AJ23-0225 | CARE AND PRESERVATION STORM CHANNEL | 8095088 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52665 | 2023-10-29 | 2023-11-09 | [22 empty] | AJ | Sub table | October | 2023
185 | 2023-11-01 |  | AJ23-0068 | B224 Fire Protection Assessment Z1 | 8111216 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52579 | 2023-11-01 | 2023-11-07 | [22 empty] | AJ | Sub table | November | 2023
188 | 2023-11-06 |  | AJ22-0474 | Bldg 3029 PKCA Replacement | 5337653 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52656 | 2023-11-06 | [23 empty] | AJ | Sub table | November | 2023
189 | 2023-11-07 |  | AJ22-0524 | B134 POST OFFICE PAINTING Z1 | 3527959 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 53321 | 2023-11-07 | 2023-12-01 | [22 empty] | AJ | Sub table | November | 2023
190 | 2023-11-07 |  | AJ22-0505 | Replace the flooring for Building T438 | 3804265 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52752 | 2023-11-07 | 2023-11-15 | [22 empty] | AJ | Sub table | November | 2023
191 | 2023-11-08 |  | AJ22-0399 | MOVE T2003 AND POWER TIE-IN | 7267384 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52751 | 2023-11-08 | 2023-11-15 | [22 empty] | AJ | Sub table | November | 2023
194 | 2023-11-17 |  | AJ23-0260 | Zone 1 T115 Storm Water Drainage, | 8110777 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52319 | 2023-11-17 | 2023-10-28 | [18 empty] | COMP |  |  |  | AJ | Sub table | November | 2023
195 | 2023-11-24 |  | AJ23-0645 | Z4 TT752D PKAC4481 Life Cycle Replacement | 6602085 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54372 | 2023-11-24 | 2023-12-28 |  | 1 | LT | 1 | 25000 | 25000 | [12 empty] | COMP |  |  |  | AJ | Sub table | November | 2023
196 | 2023-11-24 |  | AJ22-0189 | Replace Feeder Cable, | 3878015 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54016 | 2023-11-24 | 2023-12-17 |  | 1 | LT | 1 | 46770 | 46770 | [12 empty] | COMP |  |  |  | AJ | Sub table | November | 2023
197 | 2023-11-24 |  | AJ22-0190 | B450 Vent and Duct cleaning | 1850088 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54287 | 2023-11-24 | 2023-12-25 |  | 1 | LT | 1 | 11870 | 11870 | [12 empty] | COMP |  |  |  | AJ | Sub table | November | 2023
198 | 2023-11-27 |  | AJ23-0502 | RP2002 Modifications Z2 | 8389198 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 53316 | 2023-11-27 | 2023-12-01 | [18 empty] | COMP |  |  |  | AJ | Sub table | November | 2023
202 | 2023-12-06 |  | AJ22-0475 | TTHV5 PKAC Replacemen | 5337643 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54018 | 2023-12-06 | 2023-12-17 |  | 1 | LT | 1 | 29950 | 29950 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023
203 | 2023-12-06 |  | AJ22-0371 | CHILLER REPAIR (SN 12A101231) | 2564193 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54344 | 2023-12-06 | 2023-12-27 |  | 1 | [16 empty] | COMP |  |  |  | AJ | Sub table | December | 2023
204 | 2023-12-06 |  | AJ22-0530 | CFLCC Repair | 4515912 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54022 | 2023-12-06 | 2023-12-17 |  | 1 | LT | 1 | 52412 | 52412 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023
205 | 2023-12-07 |  | AJ23-0450 | Zone 1 Pool Pump House | 5847348 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54023 | 2023-12-07 | 2023-12-17 |  | 1 | LT | 1 | 50338 | 50338 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023
206 | 2023-12-07 |  | AJ23-0237 | Zone 2 Coalition Village Kitchen | 5424135 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54024 | 2023-12-07 | 2023-12-17 |  | 1 | LT | 1 | 49830 | 49830 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023
207 | 2023-12-07 |  | AJ23-0040 | Rock or something for Welcome Sign_ Zone 4, | 4170764 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54375 | 2023-12-07 | 2023-12-28 |  | 1 | LT | 1 | 16600 | 16600 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023
209 | 2023-12-10 |  | AJ23-0241 | Life Cycle Replacement | 5720168 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54011 | 2023-12-10 | 2023-12-17 |  | 1 | LT | 1 | 100000 | 10000 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023
210 | 2023-12-10 |  | AJ23-0619 | Sink Booster Heater Installation | 6768439 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54021 | 2023-12-10 | 2023-12-17 |  | 1 | LT | 1 | 48589 | 48589 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023
211 | 2023-12-11 |  | AJ23-0243 | Z6 Life Cycle Replacement 0609L | 5712915 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54369 | 2023-12-11 | 2023-12-28 |  | 1 | LT | 1 | 100000 | 100000 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023
212 | 2023-12-11 |  | AJ23-0242 | Life Cycle Replacement | 5720130 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54370 | 2023-12-11 | 2023-12-28 |  | 1 | LT | 1 | 100000 | 100000 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023
215 | 2023-12-17 |  | AJ23-0252 | Plumbing Correction | 5790685 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54378 | 2023-12-17 | 2023-12-28 |  | 1 | LT | 1 | 13703 | 13703 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023
216 | 2023-12-20 |  | AJ22-0110 | Sunshade Relocate Z7 | 2642514 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54367 | 2023-12-20 | 2023-12-28 |  | 1 | LT | 1 | 25584 | 25584 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023
217 | 2023-12-17 |  | AJ23-0606 | Z5 New Grounding Points on PAHP | 6679341 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54289 | 2023-12-17 | 2023-12-27 |  | 1 | LT | 1 | 27038 | 27038 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023
218 | 2023-12-19 |  | AJ22-0267 | Zone 6 Post Office Truck Lift Repair | 2232451 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54502 | 2023-12-19 | 2023-01-06 | COMP | 1 | LT | 1 | 18412 | 18412 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023
219 | 2023-12-19 |  | AJ23-0510 | CLM 1 Reskin | 6043651 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54603 | 2023-12-19 | 2024-01-06 | COMP | 1 | LT | 1 | 73100 | 73100 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023
220 | 2023-12-19 |  | AJ23-0610 | SPOD T70 Female Latrine Renovations | 6417910 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54292 | 2023-12-19 | 2023-12-25 | COMP | 1 | LT | 1 | 38000 | 38000 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023
221 | 2023-12-19 |  | AJ23-0676 | Sink Booster Heater Installation | 6768274 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54290 | 2023-12-19 | 2023-12-25 | COMP | 1 | LT | 1 | 27820 | 27820 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023
223 | 2023-12-20 |  | AJ22-0168 | SS812 Sunshade Replace | 2635682 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54280 | 2023-12-19 | 2023-12-24 | COMP | 1 | LT | 1 | 41008 | 41008 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023
225 | 2023-12-06 |  | AJ23-0593 | B777 ATS and Emergency Light, Zine 4 | 8675931 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54286 | 2023-12-24 | 2023-12-25 | COMP | 1 | LT | 1 | 39000 | 39000 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023
226 | 2023-12-23 |  | AJ23-0492 | ARCENT CMD Group Foyer Work |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54615 | 2023-12-23 | 2024-01-08 | COMP | 1 | LT | 1 | 14553 | 14553 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023
227 | 2023-12-23 |  | AJ23-0240 | Z6 Life Cycle Replacement 1404E and 1402W | 8084482 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54493 | 2023-12-23 | 2024-01-04 | COMP | 1 | LT | 1 | 100000 | 100000 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023
228 | 2023-12-23 |  | AJ23-0611 | SPOD T73 Male Latrine Renovations |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54610 | 2023-12-23 | 2024-01-07 | COMP | 1 | LT | 1 | 52585 | 52585 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023
229 | 2023-12-16 |  | AJ22-0120 | T1084 Outside Stairs Broken | 8810536 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54291 | 2023-12-24 | 2023-12-25 | COMP | 1 | LT | 1 | 10689.28 | 10689.28 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023
230 | 2023-12-26 |  | AJ23-0496 | ECP2 RMU2-4A-4 Replacement | 6007449 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54497 | 2023-12-26 | 2024-01-04 | COMP | 1 | LT | 1 | 49000 | 49000 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023
231 | 2023-12-26 |  | AJ23-0468 | T6207 Roof Replacement | 5903790 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54501 | 2023-12-26 | 2024-01-04 | COMP | 1 | LT | 1 | 34857 | 34857 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023
232 | 2023-12-26 |  | AJ23-0469 | T6206 Roof Replacement | 5904257 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55069 | 2024-01-20 | 2024-01-04 | COMP | 1 | LT | 1 | 34857 | 34857 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023
234 | 2023-01-03 |  | AJ23-0666 | DFAC Lockers Rebuild, Zone 2, Camp Arifjan, Kuwait | 6653617 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54608 | 2023-01-04 | 2023-01-07 | COMP | 1 | LT | 1 | 24896 | 24896 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2023
235 | 2024-01-03 |  | AJ23-0470 | Z6 T6208 Roof Replacement | 5904437 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54609 | 2023-01-04 | 2023-01-07 | COMP | 1 | LT | 1 | 32857 | 32857 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
238 | 2024-01-06 |  | AJ23-0723 | New Concrete Pad Zone 3 Camp Arifjan, Kuwait | 9069828, | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54843 | 2024-01-11 | 2024-01-14 | COMP | 1 | LT | 1 | 35462 | 35462 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
239 | 2024-01-07 |  | AJ23-0667 | DFAC Lockers Rebuild, Zone 6, Camp Arifjan, Kuwait | 6653596 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54844 | 2024-01-11 | 2024-01-14 | COMP | 1 | LT | 1 | 15601 | 15601 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
240 | 2024-01-09 |  | AJ23-0472 | T6204 Roof Replacement | 5904246 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54838 | 2024-01-11 | 2024-01-13 | COMP | 1 | LT | 1 | 32857.11 | 32857.11 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
241 | 2024-01-09 |  | AJ23-0750 | Repair HVAC in B216 Basement, S3 section | 7324760 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54839 | 2024-01-11 | 2024-01-13 | COMP | 1 | LT | 1 | 53817 | 53817 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
242 | 2024-01-09 |  | AJ23-0475 | T6201 Roof Replacement | 5904456 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54837 | 2024-01-11 | 2024-01-13 |  | 1 | LT | 1 | 32857.11 | 32857.11 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
243 | 2024-01-09 |  | AJ23-0420 | UDS 1-4A/1 Transformer Replacement Zone 2 Camp Arifjan, Kuwait | 5600909 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55083 | 2024-01-11 | 2024-01-22 | COMP | 1 | LT | 1 | 125780 | 125780 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
244 | 2024-01-09 |  | AJ23-0473 | T6203 Roof Replacement | 5904228 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54847 | 2024-01-11 | 2024-01-14 | COMP | 1 | LT | 1 | 32857.11 | 32857.11 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
245 | 2024-01-09 |  | AJ23-0474 | T6202 Roof Replacement | 5904297 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54841 | 2024-01-11 | 2024-01-13 | COMP | 1 | LT | 1 | 32857.11 | 32857.11 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
246 | 2024-01-09 |  | AJ23-0471 | T6205 Roof Replacement | 5904289 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54840 | 2024-01-11 | 2024-01-13 | COMP | 1 | LT | 1 | 32857 | 32857 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
247 | 2024-01-17 |  | AJ23-0699 | B224-BMS Preventive Maintenance Assessment, Camp Arifjan |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55070 | 2024-01-20 | 2024-01-20 | COMP | 1 | LT | 1 | 8620 | 8620 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
248 | 2024-01-17 |  | AJ23-0229 | Z6 Motor Pool 19 Power Consolidation |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55105 | 2024-01-20 | 2024-01-22 | COMP | 1 | LT | 1 | 69135 | 69135 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
249 | 2024-01-20 |  | AJ24-0170 | B229 Breaker and Breaker Frame Repair by Replacement, Camp Arifjan, Kuwait |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55084 | 2024-01-20 | 2024-01-22 | COMP | 1 | LT | 1 | 78500 | 78500 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
250 | 2024-01-20 |  | AJ22-0258 | B462 HVAC Replacement | 9117358 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55684 | 2024-01-22 | 2024-02-04 | COMP | 1 | LT | 1 | $ 1 03,492.00 | $ 1 03,492.00 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
251 | 2024-01-24 |  | AJ22-0179 | Z1 Repair LV Side at SS-6 | 9242132 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55790 | 2024-01-27 | 28jna24 | COMP | 1 | LT | 1 | 3800 | 3800 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
252 | 2024-01-27 |  | AJ23-0566 | Z3 ASP Magazine Concrete Remediations | 6669326 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55500 | 2024-01-29 | 2024-01-30 | COMP | 1 | LT | 1 | 114000 | 114000 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
253 | 2024-01-27 |  | AJ23-0423 | Zone 1-B229 HVAC Circuit on Backup Power, Camp Arifjan |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55680 | 2024-01-29 | 2024-02-03 | COMP | 1 | LT | 1 | 42140 | 42140 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
254 | 2024-01-27 |  | AJ23-0584 | Street Sign Refurbishment |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55547 | 2024-01-29 | 2024-01-31 | COMP | 1 | LT | 1 | 28170 | 28170 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
255 | 2024-01-27 |  | AJ23-0701 | Signal Radio Park Privacy Screen & Gate Removal |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55572 | 2024-01-29 | 2023-02-01 | COMP | 1 | LT | 1 | 34640 | 34640 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
256 | 2024-01-27 |  | AJ21-0097 | Recycling Fence Center Z7, Arifjan (PPR VEC-23-0400-KUW0 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55368 | 2024-01-27 |  |  | 1 | LT | 1 | 1 75,000.00 | 1 75,000.00 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
257 | 2024-01-28 |  | AJ22-0266 | B134 Post Office Truck Lift Repair, Zone 1, Camp Arifjan |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55967 | 2024-01-31 | 2024-02-10 | COMP | 1 | LT | 1 | 1 8,064.00 | 1 8,064.00 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024
258 | 2024-02-03 |  | AJ23-0093 | Z6 DFAC Prime Power Connection |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55682 | 2024-02-03 | 2024-02-04 |  | 1 | LT | 1 | 105,44 | 105,44 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | February | 2024
259 | 2024-02-04 |  | AJ24-0022 | KNB Wash Rack Add Gravel, Compact and Grade |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55683 | 2024-02-04 | 2024-02-04 |  | 1 | LT | 1 | 28100 | 28100 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | February | 2024
260 | 2024-02-04 |  | AJ22-0300 | Bldg.224 Tank Monitoring System Replacement, Camp Arifjan |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55966 | 2024-02-07 | 2024-02-10 | COMP | 1 | LT | 1 | 34802 | 34802 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | February | 2024
261 | 2024-02-10 |  | AJ23-0250 | RP8002 Expansion |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55977 | 2024-02-10 | 2024-02-11 |  | 1 | LT | 1 | 1 34,235.00 | 1 34,235.00 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | February | 2024
262 | 2024-02-10 |  | AJ23-0219 | Z2 B532 Door Frame Replacement |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55972 | 2024-02-10 | 2024-02-11 | COMP | 1 | LT | 1 | 1 0,750.00 | 1 0,750.00 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | February | 2024
263 | 2024-02-10 |  | AJ23-0751 | Z1 B144 REPLACE HVAC UNITS |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55975 | 2024-02-10 | 2024-02-11 | COMP | 1 | LT | 1 | 120150 | 120150 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | February | 2024
264 | 2024-02-10 |  | AJ23-0143 | Secure Exposed Overhead Electrical Cable |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55982 | 2024-02-10 | 2024-02-11 | COMP | 1 | LT | 1 | 1 4,220.00 | 1 4,220.00 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | February | 2024
265 | 2024-02-10 |  | AJ24‐0009 | SPOD CHAIN‐LINK FENCE REPAIRS |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55974 | 2024-02-10 | 2024-02-11 | COMP | 1 | LT | 1 | 1 32,000.00 | 1 32,000.00 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | February | 2024
266 | 2024-02-12 |  | AJ23-0238 | T758 Fence Inserts Zone 4, Camp Arifjan |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56193 | 2024-02-13 | 2024-02-18 | COMP | 1 | LT | 1 | 16969 | 16969 | [12 empty] | COMP |  |  | Sent signature Mark 13 Feb | AJ | Sub table | February | 2024
267 | 2024-02-13 |  | AJ23-0740 | REPLACEMENT/INSTALLATION HVAC UNIT B179 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56061 | 2024-02-13 | 2024-02-13 | COMP | 1 | LT | 1 | 70000 | 70000 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | February | 2024
268 | 2024-02-17 |  | AJ23-0079 | TT1004 Chapel Refurb Z6 AJ23-0079 | 7986313 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56201 | 2024-02-18 | 2024-02-19 | COMP | [17 empty] | COMP |  |  |  | AJ | Sub table | February | 2024
269 | 2024-02-17 |  | AJ23-0620 | T504D Cage Wall Installation |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56204 | 2024-02-18 | 2024-02-19 | COMP | 1 | LT | 1 | 7794 | 7794 | [12 empty] | COMP |  |  |  | AJ | Sub table | February | 2024
270 | 2024-02-17 |  | AJ23-0247 | Z1 TT1700 Additional Exit Doors | 9705833 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56203 | 2024-02-18 | 2024-02-19 | COMP | 1 | LT | 1 | 23350 | 23350 | [12 empty] | COMP |  |  |  | AJ | Sub table | February | 2024
271 | 2024-02-19 |  | AJ23-0376 | KNB T1 Repairs CT-14, KNB, Kuwait |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56304 | 2024-02-19 | 2024-02-21 | COMP | 1 | LT | 1 | 2 1,900.00 | [13 empty] | COMP |  |  |  | AJ | Sub table | February | 2024
272 | 2024-02-24 |  | AJ23-0378 | KNB T1 Repairs T-411, KNB, Kuwait |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56655 | 2024-02-29 | 2024-02-29 | COMP | 1 | LT | 1 | 73930 | [13 empty] | COMP |  |  |  | AJ | Sub table | February | 2024
273 | 2024-02-22 |  | AJ23-0494 | TT5000 Electrical Work |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56654 | 2024-02-29 | 2024-02-29 | COMP | 1 | LT | 1 | 135150 | [13 empty] | COMP |  |  |  | AJ | Sub table | February | 2024
274 | 2024-02-24 |  | AJ21-0051 | Bldg. 222 Security Hardening_ Zone 1 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56660 | 2024-02-29 | 2024-02-29 |  | 1 | LT | 1 | 47000 | [13 empty] | COMP |  |  |  | AJ | Sub table | February | 2024
275 | 2024-02-20 |  | AJ23-0254 | Off-Post Trench RP8002 CAKU |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56770 | 2024-02-29 | 2024-03-03 | COMP | 1 | LT | 1 | 91600 | [13 empty] | COMP |  |  |  | AJ | Sub table | February | 2024
276 | 2024-02-13 |  | AJ23-0439 | Wash Rack Area Light Poles & Lighting KNB Camp Arifjan, Kuwait |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56768 | 2024-03-02 | 2024-03-03 | COMP | 1 | LT | 1 | [14 empty] | COMP |  |  |  | AJ | Sub table | February | 2024
277 | 2024-03-02 |  | AJ24-0050 | TI Corrections - Fire Protection |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56899 | 2024-03-03 |  | COMP | 1 | LT | 1 | 98500 | [13 empty] | COMP |  |  |  | AJ | Sub table | March | 2024
278 | 2024-03-02 |  | AJ23-0767 | B179 EDOC and Optometry Sun Shade |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56775 | 2024-03-03 | 2024-04-03 | COMP | 1 | LT | 1 | 31290 | [13 empty] | COMP |  |  |  | AJ | Sub table | March | 2024
279 | 2024-03-02 |  | AJ23-0380 | KNB T1 Repairs T-413 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56777 | 2024-03-03 | 2024-03-03 |  | 1 | LT | 1 | 78950 | [13 empty] | COMP |  |  |  | AJ | Sub table | March | 2024
280 | 2024-03-02 |  | AJ23-0382 | KNB T1 Repairs T-415 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56776 | 2024-03-03 | 2024-03-03 |  | 1 | LT | 1 | 110372 | [13 empty] | COMP |  |  |  | AJ | Sub table | March | 2024

## BU Subcon PR
NO. OF PROJECTS | BOM Received date | TASK | PROJECT# | PROJECT DESCRIPTION | WO# | CATALOG | Item # | PR # | PR REQUESTED DATE | PR APPROVED DATE | PR Cur. Status | PR Line # | Unit of Issue | Order Qty. | Unit Cost | Ext. Cost (Line Cost) | RFQ # | RFQ Status | RFQ Status Date | RFQ Due Date | PO # | PO Line # | PO Award Date | PO Status | PO Status Date | Buyer | Vendor | Vendor Date (EDD) | Delivery Status | Delivery Date | Recv. Qty | Remarks | Color Code list | table | month | year
4 | 2022-10-06 |  | BU22-036 | Install HVAC in TT-526 | 1898690 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 38223 | 2022-10-06 | 2022-10-11 | [22 empty] | BU | Sub table | October | 2022
17 | 2022-10-19 |  | BU22-039 | installation of Bird Prevention Mesh for SS1070, | 3296468 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 38502 | 2022-10-19 | 2022-10-19 | [22 empty] | BU | Sub table | October | 2022
24 | 2022-10-27 |  | BU22-032 | TT-4053 Multi-Purpose Ctr. Renovation | 3812648 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39110 | 2022-10-27 | 2022-11-05 | [22 empty] | BU | Sub table | October | 2022
42 | 2022-12-17 |  | BU22-027 | GS-3001 to Kcrossing | 2883768 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 40943 | 2022-12-17 | 2022-12-31 | [22 empty] | BU | Sub table | December | 2022
45 | 2022-12-20 |  | BU22-120 | Sanitary and Domestic Water Line Connection to New CAB HQ BLDG | 4322143 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 41068 | 2022-12-20 | 2023-01-05 | [22 empty] | BU | Sub table | December | 2022
46 | 2022-12-21 |  | BU22-069 | URC RANGE 6 MPMG, TOWER MOVEMENT AND PERMANENT POWER | 4369560 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 41835 | 2022-12-21 | 2023-01-28 | [22 empty] | BU | Sub table | December | 2022
47 | 2022-12-21 |  | BU22-045 | CAB HQ Roof Repairs | 4369511 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 40967 | 2022-12-21 | 2022-12-31 | [22 empty] | BU | Sub table | December | 2022
48 | 2022-12-24 |  | BU22-049 | Lightening Protection for ARTC RVTT Cover | 4369515 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 41366 | 2022-12-24 | 2023-01-14 | [22 empty] | BU | Sub table | December | 2022
49 | 2023-01-04 |  | BU22-048 | Dental Clinic Upgrades | 4369536 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 41267 | 2023-01-04 | 2022-12-12 | [22 empty] | BU | Sub table | January | 2023
53 | 2023-01-28 |  | BU22-039 | SS-1070 Bird Netting CO1 | 3296468 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 41996 | 2023-01-28 | 2023-02-02 | [22 empty] | BU | Sub table | January | 2023
55 | 2023-02-06 |  | BU23-0023 | FS-Lids Prep & Stair for Stacked Container | 4140138 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 42402 | 2023-02-06 | 2023-02-12 | [22 empty] | BU | Sub table | February | 2023
56 | 2023-02-09 |  | BU22-070 | ARF Control Tower Relocation | 2481790 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 42406 | 2023-02-09 | 2023-02-13 | [22 empty] | BU | Sub table | February | 2023
58 | 2023-02-15 |  | BU22-041 | PAD 9 ROOF REPAIR | 2238889 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 42586 | 2023-02-15 | 2023-02-16 | [22 empty] | BU | Sub table | February | 2023
63 | 2023-03-04 |  | BU22-064 | Bird Netting for MWD Small Exercise Yard Bldg. SS-110 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 43336 | 2023-03-04 | 2023-03-07 | [22 empty] | BU | Sub table | March | 2023
64 | 2023-03-12 |  | BU22-089 | Vet Clinic Sanitation Sink |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 43619 | 2023-03-12 | 2023-03-15 | [22 empty] | BU | Sub table | March | 2023
65 | 2023-03-12 |  | BU22-057 | BIRD NETTING FOR ARTC BLDG 606 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 43614 | 2023-03-12 | 2023-03-15 | [22 empty] | BU | Sub table | March | 2023
66 | 2023-03-12 |  | BU22-065 | BIRD NETTING FOR HAZMAT FACILITY SS2087 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 43615 | 2023-03-12 | 2023-03-15 | [22 empty] | BU | Sub table | March | 2023
67 | 2023-03-14 |  | BU22-0110 | WIDENING FOR NORTH AND SOUTH PERIMETER GATES |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 43673 | 2023-03-14 | 2023-03-16 | [22 empty] | BU | Sub table | March | 2023
70 | 2023-03-25 |  | BU22-047 | ULZ HANGAR 11 WATER SYSTEM |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44046 | 2023-03-25 | 2023-03-27 | [22 empty] | BU | Sub table | March | 2023
71 | 2023-03-28 |  | BU22-066 | Dual Containment, Concrete Pad for SS2087 | 2423847 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44156 | 2023-03-28 | 2023-03-29 | [22 empty] | BU | Sub table | March | 2023
73 | 2023-04-05 |  | BU22-0028 | REPLACE BREAKER PANEL OFF SUB STATION 6 | 5337607 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44416 | 2023-04-05 | 2023-04-05 | [22 empty] | BU | Sub table | April | 2023
77 | 2023-04-08 |  | BU22-069 | Range 6 MPMG Tower Relocation at Camp Buehring | 2481682 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44610 | 2023-04-08 | 2023-04-11 | [22 empty] | BU | Sub table | April | 2023
79 | 2023-04-10 |  | BU22-038 | B-503 INSTALLATION OF HVAC UNITS AND DUCT WORK | 1961070 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44590 | 2023-04-10 | 2023-04-11 | [22 empty] | BU | Sub table | April | 2023
80 | 2023-04-10 |  | BU22-031 | PAD 16 POWER CABLE REPLACEMENT | 1302592 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44611 | 2023-04-10 | 2023-04-11 | [22 empty] | BU | Sub table | April | 2023
81 | 2023-04-16 |  | BU22-0105 | GRIT BUILDING UTILIZATION PROJECT, T-4010 & TT-402 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44969 | 2023-04-16 | 2023-04-25 |  | 1 | RO | 4 | [18 empty] | BU | Sub table | April | 2023
84 | 2023-04-18 |  | BU22-066 | Dual Containment, Concrete Pad for SS2087 at Camp Buehring | 2423847 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44156 | 2023-04-18 | 2023-04-29 | [22 empty] | BU | Sub table | April | 2023
89 | 2023-05-01 |  | BU22-062 | URC RANGE 4 SRGC MACHINE GUN POSITIONS | 5772162 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45466 | 2023-05-01 | 2023-05-03 | [22 empty] | BU | Sub table | May | 2023
90 | 2023-05-02 |  | BU23-030 | INSTALL SIDING TO RVTT SHELTER AREA | 5766601 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45382 | 2023-05-02 | 2023-05-03 | [22 empty] | BU | Sub table | May | 2023
91 | 2023-05-02 |  | BU23-032 | ARTC BLDG 605 PARKING COVER SIDING | 5768075 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45384 | 2023-05-02 | 2023-05-03 | [22 empty] | BU | Sub table | May | 2023
92 | 2023-05-02 |  | BU23-029 | PRIVACY FENCING FOR ARTC TRAINING AREA | 5767438 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45385 | 2023-05-02 | 2023-05-03 | [22 empty] | BU | Sub table | May | 2023
95 | 2023-05-11 |  | BU23-0102 | Provide Generator at IPBC Range at Camp Buehring |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45958 | 2023-05-11 | 2023-05-13 | [22 empty] | BU | Sub table | May | 2023
98 | 2023-05-16 |  | BU23-0166 | ECP BIRD NETTING Z2, CAMP BUEHRING |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | PWD PROJECT-PWO-BU23-0166-3136 | 2023-05-16 | [22 empty] | Send ODC | BU | Sub table | May | 2023
99 | 2023-05-16 |  | BU23-0143 | K-CROSSING MOTORIZED GATE REPAIR |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | PWD PROJECT-PWO-BU23-0143-3136.1 | 2023-05-16 | [22 empty] | Send ODC | BU | Sub table | May | 2023
101 | 2023-05-20 |  | BU22-0066 |  |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 46251 | 2023-05-20 | [23 empty] | BU | Sub table | May | 2023
107 | 2023-05-23 |  | BU23-0111 | Remediation of flooding in the ARTC |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | PWD-PROJECT-PWO-BU23-0111-3143 | 2023-05-23 | [22 empty] | Send DPW 23 May 23 | BU | Sub table | May | 2023
110 | 2023-05-24 |  | BU23-0094 | Lockers and Sunshades at Camp Buehring |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | PWD-PROJECT-PWO-BU23-0094-3144.3 | 2023-05-24 | [22 empty] | Pending NTP | BU | Sub table | May | 2023
111 | 2023-05-24 |  | BU22-0055 | Range 6 MRF Tower Temperature Control Modification, Camp Buehring |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 48419 | 2023-05-24 | 2023-07-18 | [22 empty] | BU | Sub table | May | 2023
113 | 2023-06-03 |  | BU23-0077 | SHOOT HOUSE LEAD REMEDIATION |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 48233 | 2023-06-03 | 2023-07-12 | [22 empty] | BU | Sub table | June | 2023
116 | 2023-06-15 |  | BU23-0206 | Lease Generators for Weather Shelters A and B on ULZ, | 5616366 | SUBCON PR | LEASE OF GENSET 250KVA, 60 HZ WITH FUEL TANK AND CONTAINMENT TRAY INCLUDING INSTALLATION AND PERIODIC MAINTENANCE (POP 06 MONTHS) | 47347 | 2023-06-15 | 2023-06-19 | [22 empty] | BU | Sub table | June | 2023
117 | 2023-06-19 |  | BU22-0109 | Install Personnel Gate with Cipher lock into EOD Fence, |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 47378 | 2023-06-19 | 2023-06-21 | [22 empty] | BU | Sub table | June | 2023
118 | 2023-06-22 |  | BU23-0175 | REPLACE DAMAGED ROOF PANELS |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 47967 | 2023-06-22 | 2023-07-05 | [22 empty] | BU | Sub table | June | 2023
119 | 2023-06-24 |  | BU23-0166 | INSTALL BIRD NETTING IN ECP1 | 5286014 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 47968 | 2023-06-24 | 2023-07-05 | [22 empty] | BU | Sub table | June | 2023
121 | 2023-07-15 |  | BU23-0094 | LOCKERS AND SUNSHADE, |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | IFS PR 48687 | 2023-07-15 | 2023-08-01 | [22 empty] | BU | Sub table | July | 2023
122 | 2023-07-26 |  | BU23-0143 | MOTORIZED GATE REPAIR | 6767855 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 48927 | 2023-07-26 | 2023-07-31 | [22 empty] | BU | Sub table | July | 2023
123 | 2023-07-26 |  | BU23-0182 | GENERATORS WEATHER SHELTERS A AND B | 6871999 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 48926 | 2023-07-26 | 2023-07-31 | [22 empty] | BU | Sub table | July | 2023
124 | 2023-08-07 |  | BU23-0123 | Replace Manual Transfer Switch (MTS) for Substation | 6903875 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 49403 | 2023-08-07 | 2023-08-15 | [22 empty] | BU | Sub table | August | 2023
133 | 2023-09-11 |  | BU23-0029 | CO-01 Privacy Fencing for ARTC Training Area |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50292 | 2023-09-11 | 2023-09-11 | [22 empty] | BU | Sub table | September | 2023
142 | 2023-09-26 |  | BU23-0232 | RUHQ Electrical Connection to SS-3 | 6328865 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51208 | 2023-09-26 | 2023-10-10 | [22 empty] | BU | Sub table | September | 2023
148 | 2023-10-03 |  | BU22-0031 | PAD 16 Power and MTS |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51357 | 2023-10-03 | 2023-10-10 | [22 empty] | BU | Sub table | October | 2023
149 | 2023-10-03 |  | BU23-0192 | Stair Access for Drone Defense Zone5 Tower13 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51574 | 2023-10-03 | 2023-10-11 | [22 empty] | BU | Sub table | October | 2023
150 | 2023-10-04 |  | BU23-0306 | Install Fire System Z4 TT4053 | 6589884 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51492 | 2023-10-04 | 2023-10-08 | [22 empty] | BU | Sub table | October | 2023
151 | 2023-10-09 |  | BU22-0045 | Car Ports |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51502 | 2023-10-09 | 2023-10-09 | [22 empty] | BU | Sub table | October | 2023
153 | 2023-10-11 |  | BU23-0372 | PROVIDE LEASED GENERATOR TO RUHQ | 7382193 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52529 | 2023-10-11 | 2023-11-06 | [22 empty] | BU | Sub table | October | 2023
155 | 2023-10-14 |  | BU23-0262 | NSTALLATION OF NEW ATS IN FS BLDG. 103 , C | 6231156 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51923 | 2023-10-14 | 2023-10-19 | [22 empty] | BU | Sub table | October | 2023
156 | 2023-10-14 |  | BU23-0281 | CAB HQ Emergency Power Generator, | 6408129 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51922 | 2023-10-14 | 2023-10-19 | [22 empty] | BU | Sub table | October | 2023
158 | 2023-10-14 |  | BU23-0183 | Asphalt Binder Capa Pads | 7874910 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51924 | 2023-10-14 | 2023-10-19 | [22 empty] | BU | Sub table | October | 2023
160 | 2023-10-16 |  | BU22-0105 | GRIT Building Utilization Project, |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51891 | 2023-10-16 | 2023-10-19 | [22 empty] | BU | Sub table | October | 2023
166 | 2023-10-17 |  | BU23-0351 | Secondary Fence Installation Zone 6, | 7221399 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52063 | 2023-10-17 | 2023-10-21 | [22 empty] | BU | Sub table | October | 2023
168 | 2023-10-19 |  | BU23-0233 | ULZ Install Grounding Points at Aircraft Parking Pads, | 5876978 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52161 | 2023-10-19 | 2023-10-24 | [22 empty] | BU | Sub table | October | 2023
181 | 2023-10-25 |  | BU22-048 | CO#1 DENTAL CLINIC UPGRADES CAMP BUEHRING, KUWAIT | 4369536 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52247 | 2023-10-25 | 2023-10-26 | [22 empty] | BU | Sub table | October | 2023
184 | 2023-10-31 |  | BU23-0279 | BU23-0279 RUHQ Emergency Power Generation Installation, Camp Buehring $64,633.00 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52497 | 2023-10-31 | 2023-11-04 | [22 empty] | BU | Sub table | October | 2023
186 | 2023-11-05 |  | BU23-0350 | REPLACE DOORS Z6 B6016 | 7221392 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52750 | 2023-11-05 | 2023-11-15 | [22 empty] | BU | Sub table | November | 2023
187 | 2023-11-05 |  | BU23-0353 | 0353 Install Privacy Netting Z6 B6016 | 7221404 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52692 | 2023-11-05 | 2023-11-09 | [22 empty] | BU | Sub table | November | 2023
192 | 2023-11-08 |  | BU23-0124 | Engineer Village Power Consolidation | 5375966 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 53084 | 2023-11-08 | 2023-11-23 | [22 empty] | BU | Sub table | November | 2023
193 | 2023-11-08 |  | BU23-0353 | B6016 & B2017 PERIMETER FENCE PRIVACY NETTING | 8236743 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52692 | 2023-11-08 | 2023-11-09 | [22 empty] | BU | Sub table | November | 2023
199 | 2023-12-02 |  | BU23-0193 | Build out Zone 2 TT 2071 into office space | 6871039 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 53561 | 2023-12-02 | 2023-12-06 | [18 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023
200 | 2023-12-04 |  | BU23-249 | DENTAL CLINIC CABINETS AND COUNTERTOP ZONE 2, | 8528611 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54008 | 2023-12-04 | 2023-12-17 |  | 1 | LT | 1 | 35000 | 35000 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023
201 | 2023-12-06 |  | BU23-0264 | Install Manual Transfer Switch Z2 TP2 | 8449225 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54017 | 2023-12-06 | 2023-12-17 |  | 1 | LT | 1 | 15000 | 15000 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023
208 | 2023-12-10 |  | BU23-0205 | Connect Sanitary Water Lines Z5 RUHQ B5999 | 8689493 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54014 | 2023-12-10 | 2023-12-24 |  | 1 | LT | 1 | 53314 | 53314 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023
213 | 2023-12-11 |  | BU23-0314 | Replacement of Water Filling Railing Zone 3, | 6665414 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54030 | 2023-12-11 | 2023-12-17 |  | 1 | LT | 1 | 27435 | 27435 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023
214 | 2023-12-17 |  | BU23-0375 | Deconstruct Facility Z6 TT7-3 TT7-9 | 8781713 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54377 | 2023-12-17 | 2023-12-28 |  | 1 | LT | 1 | 5688 | 5688 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023
222 | 2023-12-20 |  | BU23-0160 | Replace Manual Transfer Switch | 5203390 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54494 | 2023-12-19 | 2023-01-04 | COMP | 1 | LT | 1 | 75600 | 75600 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023
224 | 2023-12-19 |  | BU23-0208 | B6015 Relocation | 5616330 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54291 | 2023-12-19 | 2023-12-27 | COMP | 1 | LT | 1 | 47800 | 47800 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023
233 | 2023-12-27 |  | BU23-0357 | TT1051 Deconstruction Tent | 7249582 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54611 | 2023-12-27 | 2024-01-07 | COMP | 1 | LT | 1 | 9000 | 9000 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023
236 | 2023-12-31 |  | BU23-0373 | Deconstruct Z8 T2032 | 8948486 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54612 | 2023-01-06 | 2024-01-07 | COMP | 1 | LT | 1 | 6240 | 6240 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023
237 | 2023-12-31 |  | BU23-0338 | Emplace Furniture Z5 B5999 | 8944194 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54725 | 2023-01-06 | 2024-01-11 | COMP | 1 | LT | 1 | 80500 | 80500 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023
238 | 2024-01-28 |  | BU23-0368 | Connect Cable from Hangar 9 (TT9600) at ESS-14 | 7335344 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55549 | 2024-01-31 | 2024-01-31 | COMP | 1 | LT | 1 | 16150 | 16150 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | January | 2024
239 | 2024-02-07 |  | BU23-0275 | TT403 Sunshade Replacement Phase 1 | 6874479 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55968 | 2024-02-07 | 2024-02-10 | COMP | 1 | LT | 1 | 87500 | 87500 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | February | 2024
240 | 2024-02-21 |  | BU23-0221 | Install Electrical Outlets FP-C to TDP | 9805359 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56589 | 2024-02-21 | 2024-02-28 | COMP | 1 | LT | 1 | 59530 | 59530 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | February | 2024
241 | 2024-03-03 |  | BU24-0060 | Install Fencing Gates Z3 TT307 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 57046 | 2024-03-04 | 2024-03-09 | COMP | 1 | LT | 1 | 1 4,725.00 | [13 empty] | COMP |  |  |  | BU | Sub table | March | 2024
242 | 2024-03-02 |  | BU20-0026A | Automated Record Fire (ARF) Sunshade Range 4, Camp Buehring |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 57043 | 2024-03-05 | 2024-03-09 |  | 1 | LT | 1 | 101400 | [13 empty] | COMP |  |  |  | BU | Sub table | March | 2024
243 | 2024-03-02 |  | BU20-0026B | SRGC Sunshade Construction Range 4, Camp Buehring, Kuwait |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 57044 | 2024-03-05 | 2024-03-09 |  | 1 | LT | 1 | 154764 | [13 empty] | COMP |  |  |  | BU | Sub table | March | 2024
244 | 2024-03-05 |  | BU24-0012 | Fix Def Solar Lights |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 57053 | 2024-03-05 |  |  | 1 | LT | 1 | 41500 | [13 empty] | comp |  |  |  | BU | Sub table | March | 2024
245 | 2024-03-09 |  | BU24-0006 | Connect HAZMAT and Pest Control Facilities to ESS-14 CAMP Buehring, Kuwait |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | PRINPRG |  |  |  | 1 | LT | 1 | 102000 | [17 empty] | BU | Sub table | March | 2024
246 | 2024-03-09 |  | BU23-0379 | Correct TI Deficiencies for ESS 14TO18 Zone -1,2 Camp Buehring |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | PRINPRG |  |  |  | 1 | LT | 1 | 32700 | [17 empty] | BU | Sub table | March | 2024
247 | [32 empty] | #VALUE! | FALSE | January | 1900
248 | [32 empty] | #VALUE! | FALSE | January | 1900
249 | [32 empty] | #VALUE! | FALSE | January | 1900
250 | [32 empty] | #VALUE! | FALSE | January | 1900
251 | [32 empty] | #VALUE! | FALSE | January | 1900
252 | [32 empty] | #VALUE! | FALSE | January | 1900

## Dashboard info
NO. OF PROJECTS | NO_OF_PROJECTS | BOM Received date | PROJECT# | PROJECT DESCRIPTION | WO# | PR # | PR REQUESTED DATE | PR APPROVED DATE | PO # | Vendor Date (EDD) | Delivery Status | Name | color
73 | 1 | 1900-03-18 | BU24-0165 | Emplace Gravel Z8 PAT Site9 | 9722236 | 54615 | 2024-02-18 |  |  |  |  | MM_BU | MM_AJ
1 | 2 | 2022-05-13 | AJ21-0177 | BLDG 540 Hanel Lean-Lift Power Panel and Equipment Installation | 1194736 | 32165 | 2022-05-13 | 2022-05-13 | LCVKW0302S | 2022-08-17 | COMP | AJ_Fabrication | MM_BU
2 | 3 | 2022-05-16 | AJ22-0074 | MP23LM2 | 1234123 | 32198 | 2022-05-16 | 2022-05-16 | LCVKW0313S | 2022-07-15 | COMP | AJ_Fabrication | Fabrication
3 | 4 | 2022-05-26 | AJ22-0081 | RLB T6044 Relocation and Modification | 1368335 | 32698 | 2022-05-26 | 2022-05-26 | LCVKW0312S | 2022-07-15 | COMP | AJ_Fabrication | Subcon_PR
5 | 5 | 2022-07-07 | AJ22-0067 | T725 Power Outlets and Equipment Install | 2141547 | 34654 | 2022-07-07 | 2022-07-08 | LCVKW0350S | 2022-09-16 | COMP | AJ_Fabrication
6 | 6 | 2022-07-28 | AJ22-0265 | Joint Portal Shield Biological Detection Sensor | 2671164 | 35777 | 2022-07-28 | 2022-08-04 | LCVKW0357S | 2022-09-30 | COMP | AJ_Fabrication | comp
7 | 7 | 2022-08-31 | AJ22-0105 | T340 Security Features Install | 2621467 | 37171 | 2022-08-31 | 2022-09-10 | LCVKW0390S | 2022-10-18 |  | AJ_Fabrication
1 | 8 | 2022-09-10 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 17049 | 2022-09-10 | 2022-09-21 | KW1-5620 | 2022-11-17 | COMP | MM_AJ
8 | 9 | 2022-09-18 | AJ22-0137 | Vectrus Tent 1 Relocation | 2238613 | 37556 | 2022-09-18 | 2022-09-21 | LCKW0404S | 2022-10-11 | COMP | AJ_Fabrication
9 | 10 | 2022-09-18 | AJ22-0138 | Vectrus Tent 2 Relocation | 2238650 | 37558 | 2022-09-18 | 2022-09-21 | LCKW0404S | 2022-10-11 | COMP | AJ_Fabrication
10 | 11 | 2022-09-18 | AJ22-0139 | Vectrus Tent 3 Relocation | 2238605 | 37559 | 2022-09-18 | 2022-09-21 | LCKW0404S | 2022-10-11 | COMP | AJ_Fabrication
11 | 12 | 2022-09-18 | AJ22-0140 | Vectrus Tent 4 Relocation | 2238683 | 37560 | 2022-09-18 | 2022-09-21 | LCKW0404S | 2022-10-11 | COMP | AJ_Fabrication
12 | 13 | 2022-09-18 | AJ22-0141 | Vectrus Tent 5 Relocation | 2238643 | 37561 | 2022-09-18 | 2022-09-21 | LCKW0404S | 2022-10-11 | COMP | AJ_Fabrication
13 | 14 | 2022-09-18 | AJ22-0142 | Vectrus Tent 6 Relocation | 2238633 | 37554 | 2022-09-18 | 2022-09-21 | LCKW0404S | 2022-10-11 | COMP | AJ_Fabrication
14 | 15 | 2022-09-18 | AJ22-0143 | Vectrus Tent 7 Relocation | 2539656 | 37555 | 2022-09-18 | 2022-09-21 | LCKW0404S | 2022-10-11 | COMP | AJ_Fabrication
15 | 16 | 2022-09-29 | AJ22-0145 | Z7 Utility Infrastructure-Power Generation | 2219753 | 45822 | 2022-09-29 | CANCELLED |  |  |  | AJ_Fabrication
2 | 17 | 2022-10-02 | AJ22-0241 | Building 5723 TT PKAC Replacement | 2647953 | 38225 | 2022-10-02 | 2022-10-11 |  |  |  | AJ_Subcon_PR
3 | 18 | 2022-10-03 | AJ22-0218 | Interlock Concrete Pavers for Walking Area at Camp Arifjan. | 2647953 | 38173 | 2022-10-03 | 2022-10-08 |  |  |  | AJ_Subcon_PR
16 | 19 | 2022-10-05 | AJ22-0156 | RMOs Motor Pool 19 | 2854733 | 38064 | 2022-10-05 | 2022-10-05 | PO KW1-6993 | 2023-01-31 |  | AJ_Fabrication
4 | 20 | 2022-10-06 | BU22-036 | Install HVAC in TT-526 | 1898690 | 38223 | 2022-10-06 | 2022-10-11 |  |  |  | BU_Subcon_PR
5 | 21 | 2022-10-10 | AJ22-0392 | ILU Repair Set 4 | 3326596 | 38641 | 2022-10-10 | 2022-10-26 |  |  |  | AJ_Subcon_PR
6 | 22 | 2022-10-10 | AJ22-0234 | ILU Repair Set 1 | 3296566 | 38640 | 2022-10-10 | 2022-10-26 |  |  |  | AJ_Subcon_PR
7 | 23 | 2022-10-11 | AJ22-0042 | B6075 MTS Replace | 2624592 | 38638 | 2022-10-11 | 2022-10-22 |  |  |  | AJ_Subcon_PR
8 | 24 | 2022-10-15 | AJ22-0175 | Bldg. 224 Steam Generator 1 Replacement | 2873774 | 39353 | 2022-10-15 | 2022-11-13 |  |  |  | AJ_Subcon_PR
10 | 25 | 2022-10-17 | AJ21-0002 | APS-5 Medical Warehouse Bldg. 4009 | 195272 | 39424 | 2022-10-17 | 2022-11-15 |  |  |  | AJ_Subcon_PR
11 | 26 | 2022-10-17 | AJ22-0352 | Hazardous Waste Material Removal in Lot 59 | 3054100 | 39621 | 2022-10-17 | 2022-11-21 |  |  |  | AJ_Subcon_PR
12 | 27 | 2022-10-17 | AJ22-0335 | Bldg.205 Substation 5 Cleaning & Maintenance | 3055849 | 39620 | 2022-10-17 | 2022-11-21 |  |  |  | AJ_Subcon_PR
13 | 28 | 2022-10-17 | AJ22-0174 | B224 Chiller Water Pump Replacement | 2539650 | 39259 | 2022-10-17 | 2022-11-09 |  |  |  | AJ_Subcon_PR
14 | 29 | 2022-10-17 | AJ22-0336 | Z1 B165 Cleaning and Maintenance | 3055853 | 39654 | 2022-10-17 | 2022-11-22 |  |  |  | AJ_Subcon_PR
15 | 30 | 2022-10-17 | AJ22-0354 | Z7 Lot 32 Debris Removal | 3054121 | 39264 | 2022-10-17 | 2022-11-09 |  |  |  | AJ_Subcon_PR
16 | 31 | 2022-10-18 | AJ22-0353 | Z7 Clearing EOD Training Site | 2453547 | 39352 | 2022-10-18 | 2022-11-13 |  |  |  | AJ_Subcon_PR
17 | 32 | 2022-10-19 | BU22-039 | installation of Bird Prevention Mesh for SS1070, | 3296468 | 38502 | 2022-10-19 | 2022-10-19 |  |  |  | BU_Subcon_PR
19 | 33 | 2022-10-20 | AJ22-0236 | ILU Repair Set 3 | 3326587 | 39354 | 2022-10-20 | 2022-11-13 |  |  |  | AJ_Subcon_PR
20 | 34 | 2022-10-22 | AJ22-0393 | ILU Repair Set 5 | 3326604 | 39349 | 2022-10-22 | 2022-11-13 |  |  |  | AJ_Subcon_PR
21 | 35 | 2022-10-22 | AJ22-0394 | ILU Repair Set 6 | 3326608 | 39350 | 2022-10-22 | 2022-11-13 |  |  |  | AJ_Subcon_PR
22 | 36 | 2022-10-23 | AJ22-0176 | BLDG 224 Steam Generator Replacement | 2873763 | 39261 | 2022-10-23 | 2022-11-09 |  |  |  | AJ_Subcon_PR
23 | 37 | 2022-10-26 | AJ22-0177 | Bldg. 224 Steam Generator 3 Replacement | 2873756 | 39262 | 2022-10-26 | 2022-11-09 |  |  |  | AJ_Subcon_PR
25 | 38 | 2022-10-27 | AJ22-0146 | B507 Fire Hardening | 2671555 | 39050 | 2022-10-27 | 2022-11-03 |  |  |  | AJ_Subcon_PR
26 | 39 | 2022-10-27 | AJ22-0147 | Utilities ASP500 Tie-in | 2147424 | 39048 | 2022-10-27 | 2022-11-03 |  |  |  | AJ_Subcon_PR
24 | 40 | 2022-10-27 | BU22-032 | TT-4053 Multi-Purpose Ctr. Renovation | 3812648 | 39110 | 2022-10-27 | 2022-11-05 |  |  |  | BU_Subcon_PR
27 | 41 | 2022-10-29 | AJ22-0235 | ILU Repair Set 2 | 3296610 | 38960 | 2022-10-29 | 2022-11-01 |  |  |  | AJ_Subcon_PR
29 | 42 | 2022-11-03 | AJ22-0534 | Care and Preservation Facility |  | 39049 | 2022-11-03 | 2022-11-03 |  |  |  | AJ_Subcon_PR
30 | 43 | 2022-11-06 | AJ22-0407 | Z6 Senior Pods Shower Replacement | 3270986 | 39265 | 2022-11-06 | 2022-11-09 |  |  |  | AJ_Subcon_PR
31 | 44 | 2022-11-06 | AJ22-0409 | Z6 Senior Pods Female Shower | 3270589 | 39256 | 2022-11-06 | 2022-11-09 |  |  |  | AJ_Subcon_PR
33 | 45 | 2022-11-08 | AJ22-0333 | Substation 3 Cleaning & Maintenance Zone 1-Bldg 121 | 3137625 | 39625 | 2022-11-08 | 2022-11-21 |  |  |  | AJ_Subcon_PR
34 | 46 | 2022-11-09 | AJ22-0332 | Substation 2 Cleaning & Maintenance Zone 2-Bldg 463 | 3055876 | 39624 | 2022-11-09 | 2022-11-21 |  |  |  | AJ_Subcon_PR
35 | 47 | 2022-11-10 | AJ22-0334 | Z1 B145 Cleaning and Maintenance | 3055843 | 39626 | 2022-11-10 | 2022-11-21 |  |  |  | AJ_Subcon_PR
36 | 48 | 2022-11-14 | AJ22-0331 | Substation 1 Cleaning & Maintenance Zone 2-Bldg 513 | 3055868 | 39646 | 2022-11-14 | 2022-11-22 |  |  |  | AJ_Subcon_PR
37 | 49 | 2022-11-21 | AJ22-0046 | Replace HVAC System and Controls at B-306 |  | 39903 | 2022-11-21 | 2022-11-29 |  |  |  | AJ_Subcon_PR
38 | 50 | 2022-11-21 | AJ22-0106 | Pipe Leak Repair At Zone 2 APS 500 Warehouse 4 | 2539713 | PWD-PROJECT-PWO-AJ22-0106- 2325 | 2022-11-21 |  |  |  |  | AJ_Subcon_PR
17 | 51 | 2022-11-22 | AJ22-0248 | ZONE 1 B209 | 2969436 | 39709 | 2022-11-22 | 2022-11-23 |  |  |  | AJ_Fabrication
39 | 52 | 2022-11-22 | AJ22-0468 | Bldg.216 Chiller Efficiency Upgrade, Camp Arifjan | 3511691 | 40106 | 2022-11-22 | 2022-12-03 |  |  |  | AJ_Subcon_PR
40 | 53 | 2022-12-11 | AJ22-0379 | Z5 Trailer T28 Tie In | 3133125 | 46334 | 2022-12-11 | 2023-05-23 |  |  |  | AJ_Subcon_PR
41 | 54 | 2022-12-11 | AJ22-0232 | Z6 Repair Pipeline B544-1 | 3215439 | 48591 | 2022-12-11 | 2023-07-23 |  |  |  | AJ_Subcon_PR
42 | 55 | 2022-12-17 | BU22-027 | GS-3001 to Kcrossing | 2883768 | 40943 | 2022-12-17 | 2022-12-31 |  |  |  | BU_Subcon_PR
43 | 56 | 2022-12-18 | AJ22-0359 | Z7 Relocate Tents | 3145108 | 41641 | 2022-12-18 | 2023-01-24 |  |  |  | AJ_Subcon_PR
44 | 57 | 2022-12-19 | AJ22-0325 | Z1 B145 Mini Splits | 3195847 | 40978 | 2022-12-19 | 2023-01-03 |  |  |  | AJ_Subcon_PR
45 | 58 | 2022-12-20 | BU22-120 | Sanitary and Domestic Water Line Connection to New CAB HQ BLDG | 4322143 | 41068 | 2022-12-20 | 2023-01-05 |  |  |  | BU_Subcon_PR
46 | 59 | 2022-12-21 | BU22-069 | URC RANGE 6 MPMG, TOWER MOVEMENT AND PERMANENT POWER | 4369560 | 41835 | 2022-12-21 | 2023-01-28 |  |  |  | BU_Subcon_PR
47 | 60 | 2022-12-21 | BU22-045 | CAB HQ Roof Repairs | 4369511 | 40967 | 2022-12-21 | 2022-12-31 |  |  |  | BU_Subcon_PR
48 | 61 | 2022-12-24 | BU22-049 | Lightening Protection for ARTC RVTT Cover | 4369515 | 41366 | 2022-12-24 | 2023-01-14 |  |  |  | BU_Subcon_PR
234 | 62 | 2023-01-03 | AJ23-0666 | DFAC Lockers Rebuild, Zone 2, Camp Arifjan, Kuwait | 6653617 | 54608 | 2023-01-04 | 2023-01-07 |  |  | COMP | AJ_Subcon_PR
49 | 63 | 2023-01-04 | BU22-048 | Dental Clinic Upgrades | 4369536 | 41267 | 2023-01-04 | 2022-12-12 |  |  |  | BU_Subcon_PR
2 | 64 | 2023-01-14 | AJ22-0135 | T357 Relocation | 2141526 | 25435 | 2023-01-14 | 2023-01-15 | KW1-7626 | 2023-02-11 | COMP | MM_AJ
50 | 65 | 2023-01-17 | AJ22-0021 | Bldg 162 PSD Control Room Remodel | 4535846 | 41583 | 2023-01-17 | 2022-01-22 |  |  |  | AJ_Subcon_PR
52 | 66 | 2023-01-22 | AJ22-0233 | Bldg B6028 Replacement of Water Pipelines | 4246289 | 42739 | 2023-01-22 | 2023-01-19 |  |  |  | AJ_Subcon_PR
55 | 67 | 2023-02-06 | BU23-0023 | FS-Lids Prep & Stair for Stacked Container | 4140138 | 42402 | 2023-02-06 | 2023-02-12 |  |  |  | BU_Subcon_PR
56 | 68 | 2023-02-09 | BU22-070 | ARF Control Tower Relocation | 2481790 | 42406 | 2023-02-09 | 2023-02-13 |  |  |  | BU_Subcon_PR
3 | 69 | 2023-02-11 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 27260 | 2023-02-11 | 2023-02-12 | KW1-8005 | 2023-04-30 | COMP | MM_AJ
57 | 70 | 2023-02-13 | AJ22-0297 | B131 Pool Pump Room HVAC and Handrail Install | 3604408 | 44881 | 2023-02-13 | 2023-04-19 |  |  |  | AJ_Subcon_PR
58 | 71 | 2023-02-15 | BU22-041 | PAD 9 ROOF REPAIR | 2238889 | 42586 | 2023-02-15 | 2023-02-16 |  |  |  | BU_Subcon_PR
63 | 72 | 2023-03-04 | BU22-064 | Bird Netting for MWD Small Exercise Yard Bldg. SS-110 |  | 43336 | 2023-03-04 | 2023-03-07 |  |  |  | BU_Subcon_PR
19 | 73 | 2023-03-12 | AJ22-0143, | Vectrus Tent 7 Relocation |  | 44110 | 2023-03-12 | 2023-03-28 |  |  |  | AJ_Fabrication
64 | 74 | 2023-03-12 | BU22-089 | Vet Clinic Sanitation Sink |  | 43619 | 2023-03-12 | 2023-03-15 |  |  |  | BU_Subcon_PR
65 | 75 | 2023-03-12 | BU22-057 | BIRD NETTING FOR ARTC BLDG 606 |  | 43614 | 2023-03-12 | 2023-03-15 |  |  |  | BU_Subcon_PR
66 | 76 | 2023-03-12 | BU22-065 | BIRD NETTING FOR HAZMAT FACILITY SS2087 |  | 43615 | 2023-03-12 | 2023-03-15 |  |  |  | BU_Subcon_PR
68 | 77 | 2023-03-14 | AJ22-0351 | Male Latrine Floor Tile Replacement B507 Zone 2 |  | 43635 | 2023-03-14 | 2023-03-15 |  |  |  | AJ_Subcon_PR
67 | 78 | 2023-03-14 | BU22-0110 | WIDENING FOR NORTH AND SOUTH PERIMETER GATES |  | 43673 | 2023-03-14 | 2023-03-16 |  |  |  | BU_Subcon_PR
20 | 79 | 2023-03-16 | AJ23-0089 | B314 Backup Power Connection |  | 43694 | 2023-03-16 | 2023-03-16 | LCVKW0574S |  |  | AJ_Fabrication
5 | 80 | 2023-03-25 | AJ22-0136 | T353 Relocation | 2141524 | 30405 | 2023-03-25 | 2023-03-26 | KW1-8897 | 2023-06-29 | COMP | MM_AJ
70 | 81 | 2023-03-25 | BU22-047 | ULZ HANGAR 11 WATER SYSTEM |  | 44046 | 2023-03-25 | 2023-03-27 |  |  |  | BU_Subcon_PR
71 | 82 | 2023-03-28 | BU22-066 | Dual Containment, Concrete Pad for SS2087 | 2423847 | 44156 | 2023-03-28 | 2023-03-29 |  |  |  | BU_Subcon_PR
72 | 83 | 2023-03-29 | AJ22-0317 | Z6 T1022 SINK TIE IN | 3897909 | 44237 | 2023-03-29 | 2023-03-30 |  |  |  | AJ_Subcon_PR
73 | 84 | 2023-04-05 | BU22-0028 | REPLACE BREAKER PANEL OFF SUB STATION 6 | 5337607 | 44416 | 2023-04-05 | 2023-04-05 |  |  |  | BU_Subcon_PR
76 | 85 | 2023-04-06 | AJ22-0324 | BLDG 121 HVAC AND FACILITY REPAIR | 3193786 | 44603 | 2023-04-06 | 2023-04-11 |  |  |  | AJ_Subcon_PR
78 | 86 | 2023-04-10 | AJ22-0327 | B-165 HVAC AND FACILITY REPAIR | 3196067 | 51577 | 2023-04-10 | 2023-10-10 |  |  |  | AJ_Subcon_PR
79 | 87 | 2023-04-10 | BU22-038 | B-503 INSTALLATION OF HVAC UNITS AND DUCT WORK | 1961070 | 44590 | 2023-04-10 | 2023-04-11 |  |  |  | BU_Subcon_PR
80 | 88 | 2023-04-10 | BU22-031 | PAD 16 POWER CABLE REPLACEMENT | 1302592 | 44611 | 2023-04-10 | 2023-04-11 |  |  |  | BU_Subcon_PR
6 | 89 | 2023-04-13 | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 31564 | 2023-04-13 | 2023-04-15 | KW1-9067 | 2023-04-23 07:00 | COMP | MM_AJ
23 | 90 | 2023-04-16 | AJ23-0413 | Z6 Patton Pipe Repair | 2874083 | 44798 | 2023-04-16 | 2023-04-16 |  |  |  | AJ_Fabrication
82 | 91 | 2023-04-16 | AJ23-0045 | BACKUP CONNECTION TO HOSPITAL REEFER | 4304698 | 47185 | 2023-04-16 | 2023-06-13 |  |  |  | AJ_Subcon_PR
81 | 92 | 2023-04-16 | BU22-0105 | GRIT BUILDING UTILIZATION PROJECT, T-4010 & TT-402 |  | 44969 | 2023-04-16 | 2023-04-25 |  |  |  | BU_Subcon_PR
83 | 93 | 2023-04-18 | AJ22-0321 | B-350 HVAC and Facility Repair at Camp Arifjan | 3196626 | 45380 | 2023-04-18 | 2023-05-02 |  |  |  | AJ_Subcon_PR
85 | 94 | 2023-04-18 | AJ23-0134 | CARE & PRESERVATION CENTER GENERATOR SERVICE | 5685817 | 45465 | 2023-04-18 | 2023-05-03 |  |  |  | AJ_Subcon_PR
84 | 95 | 2023-04-18 | BU22-066 | Dual Containment, Concrete Pad for SS2087 at Camp Buehring | 2423847 | 44156 | 2023-04-18 | 2023-04-29 |  |  |  | BU_Subcon_PR
87 | 96 | 2023-04-26 | AJ23-0090 | SPOD Fuel Generator Consolidation, Camp SPOD | 5770261 | 45805 | 2023-04-26 | 2023-05-10 |  |  |  | AJ_Subcon_PR
7 | 97 | 2023-04-29 | AJ22-0044 | T357 Relocation | 2141526 | 32769 | 2023-04-29 | 2023-05-03 | KW1-9404 | 2023-05-14 07:00 | COMP | MM_AJ
9 | 98 | 2023-04-29 | AJ22-0205 | T357 Relocation | 2141526 | 32772 | 2023-04-29 | 2023-05-03 | KW1-9404 | 2023-05-14 07:00 | COMP | MM_AJ
88 | 99 | 2023-04-30 | AJ22-0231 | BLDG 6029 REPLACEMENT OF WATER PIPELINES | 3216160 | 45803 | 2023-04-30 | 2023-05-10 |  |  |  | AJ_Subcon_PR
89 | 100 | 2023-05-01 | BU22-062 | URC RANGE 4 SRGC MACHINE GUN POSITIONS | 5772162 | 45466 | 2023-05-01 | 2023-05-03 |  |  |  | BU_Subcon_PR
90 | 101 | 2023-05-02 | BU23-030 | INSTALL SIDING TO RVTT SHELTER AREA | 5766601 | 45382 | 2023-05-02 | 2023-05-03 |  |  |  | BU_Subcon_PR
91 | 102 | 2023-05-02 | BU23-032 | ARTC BLDG 605 PARKING COVER SIDING | 5768075 | 45384 | 2023-05-02 | 2023-05-03 |  |  |  | BU_Subcon_PR
92 | 103 | 2023-05-02 | BU23-029 | PRIVACY FENCING FOR ARTC TRAINING AREA | 5767438 | 45385 | 2023-05-02 | 2023-05-03 |  |  |  | BU_Subcon_PR
93 | 104 | 2023-05-06 | AJ23-0132 | TI FOR APS 500 WAREHOUSE |  | 45821 | 2023-05-06 | 2023-05-10 |  |  |  | AJ_Subcon_PR
94 | 105 | 2023-05-06 | AJ23-0133 | TI FOR TIP C WAREHOUSE |  | 45957 | 2023-05-06 | 2023-05-13 |  |  |  | AJ_Subcon_PR
11 | 106 | 2023-05-10 | AJ22-0417 | Z1 Pool Water Leak Assessment | 5171089 | 33483 | 2023-05-10 | 2023-05-28 | KW1-9736 | 2023-06-10 | COMP | MM_AJ
12 | 107 | 2023-05-10 | AJ22-0536 | T357 Relocation | 5171089 | 33483 | 2023-05-10 | 2023-05-28 | KW1-9736 | 2023-06-10 | COMP | MM_AJ
13 | 108 | 2023-05-10 | AJ23-0193 | 43 Electrical Meter Installation | 5171089 | 33483 | 2023-05-10 | 2023-05-28 | KW1-9736 | 2023-07-25 | COMP | MM_AJ
14 | 109 | 2023-05-10 | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 33483 | 2023-05-10 | 2023-05-28 | KW1-9736 | 2023-06-10 | COMP | MM_AJ
95 | 110 | 2023-05-11 | BU23-0102 | Provide Generator at IPBC Range at Camp Buehring |  | 45958 | 2023-05-11 | 2023-05-13 |  |  |  | BU_Subcon_PR
15 | 111 | 2023-05-13 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 33618 | 2023-05-13 | 2023-05-20 | KW1-9700 | 2023-06-03 | COMP | MM_AJ
98 | 112 | 2023-05-16 | BU23-0166 | ECP BIRD NETTING Z2, CAMP BUEHRING |  | PWD PROJECT-PWO-BU23-0166-3136 | 2023-05-16 |  |  |  |  | BU_Subcon_PR
99 | 113 | 2023-05-16 | BU23-0143 | K-CROSSING MOTORIZED GATE REPAIR |  | PWD PROJECT-PWO-BU23-0143-3136.1 | 2023-05-16 |  |  |  |  | BU_Subcon_PR
101 | 114 | 2023-05-20 | BU22-0066 |  |  | 46251 | 2023-05-20 |  |  |  |  | BU_Subcon_PR
107 | 115 | 2023-05-23 | BU23-0111 | Remediation of flooding in the ARTC |  | PWD-PROJECT-PWO-BU23-0111-3143 | 2023-05-23 |  |  |  |  | BU_Subcon_PR
109 | 116 | 2023-05-24 | AJ22-0507 | RADOME POWER UPGRADE |  | 48309 | 2023-05-24 | 2023-07-13 |  |  |  | AJ_Subcon_PR
110 | 117 | 2023-05-24 | BU23-0094 | Lockers and Sunshades at Camp Buehring |  | PWD-PROJECT-PWO-BU23-0094-3144.3 | 2023-05-24 |  |  |  |  | BU_Subcon_PR
111 | 118 | 2023-05-24 | BU22-0055 | Range 6 MRF Tower Temperature Control Modification, Camp Buehring |  | 48419 | 2023-05-24 | 2023-07-18 |  |  |  | BU_Subcon_PR
113 | 119 | 2023-06-03 | BU23-0077 | SHOOT HOUSE LEAD REMEDIATION |  | 48233 | 2023-06-03 | 2023-07-12 |  |  |  | BU_Subcon_PR
116 | 120 | 2023-06-15 | BU23-0206 | Lease Generators for Weather Shelters A and B on ULZ, | 5616366 | 47347 | 2023-06-15 | 2023-06-19 |  |  |  | BU_Subcon_PR
117 | 121 | 2023-06-19 | BU22-0109 | Install Personnel Gate with Cipher lock into EOD Fence, |  | 47378 | 2023-06-19 | 2023-06-21 |  |  |  | BU_Subcon_PR
118 | 122 | 2023-06-22 | BU23-0175 | REPLACE DAMAGED ROOF PANELS |  | 47967 | 2023-06-22 | 2023-07-05 |  |  |  | BU_Subcon_PR
121 | 123 | 2023-07-15 | BU23-0094 | LOCKERS AND SUNSHADE, |  | IFS PR 48687 | 2023-07-15 | 2023-08-01 |  |  |  | BU_Subcon_PR
123 | 124 | 2023-07-26 | BU23-0182 | GENERATORS WEATHER SHELTERS A AND B | 6871999 | 48926 | 2023-07-26 | 2023-07-31 |  |  |  | BU_Subcon_PR
124 | 125 | 2023-08-07 | BU23-0123 | Replace Manual Transfer Switch (MTS) for Substation | 6903875 | 49403 | 2023-08-07 | 2023-08-15 |  |  |  | BU_Subcon_PR
24 | 126 | 2023-08-16 | AJ21-0038 | Z7 Relocation of Building 370 | 5876937 | 40097 | 2023-08-16 | 2023-08-21 | KW1-11171 | 2023-09-03 03:00 | COMP | MM_AJ
25 | 127 | 2023-08-16 | AJ22-0004 | Z7 Relocation of Building 370 | 5876937 | 40097 | 2023-08-16 | 2023-08-21 | KW1-11171 | 2023-09-03 03:00 | COMP | MM_AJ
26 | 128 | 2023-08-16 | AJ22-0073 | Z7 Relocation of Building 370 | 5876937 | 40097 | 2023-08-16 | 2023-08-21 | KW1-11171 | 2023-09-03 03:00 | COMP | MM_AJ
27 | 129 | 2023-08-16 | AJ22-0123 | Z7 Relocation of Building 370 | 5876937 | 40097 | 2023-08-16 | 2023-08-21 | KW1-11171 | 2023-09-03 03:00 | COMP | MM_AJ
28 | 130 | 2023-08-16 | AJ22-0149 | Z7 Relocation of Building 370 | 5876937 | 40097 | 2023-08-16 | 2023-08-21 | KW1-11171 | 2023-09-03 03:00 | COMP | MM_AJ
29 | 131 | 2023-08-16 | AJ22-0184 | Z7 Relocation of Building 370 | 5876937 | 40097 | 2023-08-16 | 2023-08-21 | KW1-11171 | 2023-09-03 03:00 | COMP | MM_AJ
30 | 132 | 2023-08-16 | AJ22-0222 | Z7 Relocation of Building 370 | 5876937 | 40058 | 2023-08-16 | 2023-08-20 | KW1-11206 | 2023-09-03 | COMP | MM_AJ
31 | 133 | 2023-08-16 | AJ22-0322 | Z7 Relocation of Building 370 | 5876937 | 40058 | 2023-08-16 | 2023-08-20 | KW1-11206 | 2023-09-03 | COMP | MM_AJ
32 | 134 | 2023-08-16 | AJ22-0323 | Z7 Relocation of Building 370 | 5876937 | 40097 | 2023-08-16 | 2023-08-21 | KW1-11171 | 2023-09-03 03:00 | COMP | MM_AJ
33 | 135 | 2023-08-16 | AJ22-0326 | Z7 Relocation of Building 370 | 5876937 | 40055 | 2023-08-16 | 2023-08-20 | KW1-11204 | 2023-09-03 | COMP | MM_AJ
34 | 136 | 2023-08-16 | AJ22-0390 | Z7 Relocation of Building 370 | 5876937 | 40098 | 2023-08-16 | 2023-08-20 | KW1-11204 | 2023-09-03 | COMP | MM_AJ
35 | 137 | 2023-08-16 | AJ22-0547 | Z7 Relocation of Building 370 | 5876937 | 40057 | 2023-08-16 | 2023-08-20 | KW1-11206 | 2023-10-22 | COMP | MM_AJ
36 | 138 | 2023-08-16 | AJ23-0006 | Z7 Relocation of Building 370 | 5876937 | 40059 | 2023-08-16 | 2023-08-20 | KW1-11206 | 2023-09-03 | COMP | MM_AJ
37 | 139 | 2023-08-16 | AJ23-0079 | Z7 Relocation of Building 370 | 5876937 | 40058, 40100 | 2023-08-16 | 2023-08-20 | KW1-11206 | 2023-09-03 | COMP | MM_AJ
38 | 140 | 2023-08-16 | AJ23-0172 | Z7 Relocation of Building 370 | 5876937 | 40097 | 2023-08-16 | 2023-08-21 | KW1-11171 | 2023-09-03 03:00 | COMP | MM_AJ
39 | 141 | 2023-08-16 | AJ23-0300 | Z7 Relocation of Building 370 | 5876937 | 40100 | 2023-08-16 | 2023-08-20 | KW1-11204 | 2023-09-03 | COMP | MM_AJ
40 | 142 | 2023-08-16 | AJ23-0365 | Z7 Relocation of Building 370 | 5876937 | 40097 | 2023-08-16 | 2023-08-21 | KW1-11171 | 2023-09-03 03:00 | COMP | MM_AJ
42 | 143 | 2023-08-16 | AJ23-0493 | Z7 Relocation of Building 370 | 5876937 | 40097 | 2023-08-16 | 2023-08-21 | KW1-11171 |  | COMP | MM_AJ
43 | 144 | 2023-08-16 | AJ23-0499 | Z7 Relocation of Building 370 | 5876937 | 40102 | 2023-08-16 | 2023-08-21 | KW1-11171 | 2023-09-03 03:00 | COMP | MM_AJ
44 | 145 | 2023-08-16 | AJ23-0540 | Z7 Relocation of Building 370 | 5876937 | 40097 | 2023-08-16 | 2023-08-21 | KW1-11171 | 2023-09-03 03:00 | COMP | MM_AJ
45 | 146 | 2023-08-16 | AJ23-0563 | Z7 Relocation of Building 370 | 5876937 | 40101 | 2023-08-16 | 2023-08-20 | KW1-11204 | 2023-09-03 | COMP | MM_AJ
47 | 147 | 2023-08-17 | AJ22-0400 | REPLACE WOODEN DOOR WITH METAL DOOR | 7177768 | 49519 | 2023-08-17 | 2023-08-19 |  |  |  | MM_AJ
49 | 148 | 2023-08-27 | AJ23-0508 | T357 Relocation | 2141526 | 40852 | 2023-08-27 | 2023-08-29 | KW1-11331 | 2023-12-16 | COMP | MM_AJ
51 | 149 | 2023-08-28 | AJ22-0189 | T357 Relocation | 2141526 | 40887 | 2023-08-28 | 2023-09-02 | KW1-11386 | 2023-09-17 | COMP | MM_AJ
52 | 150 | 2023-08-28 | AJ22-0240 | T357 Relocation | 2141526 | 40882 | 2023-08-28 | 2023-09-02 | KW1-11429 | 2023-09-19 | COMP | MM_AJ
53 | 151 | 2023-08-28 | AJ22-0380 | T357 Relocation | 2141526 | 40876 | 2023-08-28 | 2023-09-02 | KW1-11427 | 2023-09-19 | COMP | MM_AJ
54 | 152 | 2023-08-28 | AJ22-0406 | T357 Relocation | 2141526 | 40879 | 2023-08-28 | 2023-09-02 | KW1-11425 | 2023-09-19 | COMP | MM_AJ
55 | 153 | 2023-08-28 | AJ22-0455 | T357 Relocation | 2141526 | 40876 | 2023-08-28 | 2023-09-02 | KW1-11427 | 2023-09-19 | COMP | MM_AJ
56 | 154 | 2023-08-28 | AJ22-0465 | T357 Relocation | 2141526 | 40885 | 2023-08-28 | 2023-09-02 | KW1-11427 | 2023-09-19 | COMP | MM_AJ
57 | 155 | 2023-08-28 | AJ22-0497 | T357 Relocation | 2141526 | 40880 | 2023-08-28 | 2023-09-02 | KW1-11429 | 2023-09-19 | COMP | MM_AJ
58 | 156 | 2023-08-28 | AJ22-0524 | T357 Relocation | 2141526 | 40879 | 2023-08-28 | 2023-09-02 | KW1-11425 | 2023-09-19 | COMP | MM_AJ
59 | 157 | 2023-08-28 | AJ22-0549 | T357 Relocation | 2141526 | 40879 | 2023-08-28 | 2023-09-02 | KW1-11425 | 2023-09-19 | COMP | MM_AJ
60 | 158 | 2023-08-28 | AJ23-0004 | T357 Relocation | 2141526 | 40882 | 2023-08-28 | 2023-09-02 | KW1-11429 | 2023-09-19 | COMP | MM_AJ
61 | 159 | 2023-08-28 | AJ23-0005 | T357 Relocation | 2141526 | 40878 | 2023-08-28 | 2023-09-02 | KW1-11425 | 2023-09-19 | COMP | MM_AJ
62 | 160 | 2023-08-28 | AJ23-0007 | T357 Relocation | 2141526 | 40880 | 2023-08-28 | 2023-09-02 | KW1-11429 | 2023-09-19 | COMP | MM_AJ
63 | 161 | 2023-08-28 | AJ23-0068 | T357 Relocation | 2141526 | 40886 | 2023-08-28 | 2023-09-02 | KW1-11427 | 2023-09-19 | COMP | MM_AJ
64 | 162 | 2023-08-28 | AJ23-0101 | T357 Relocation | 2141526 | 40876 | 2023-08-28 | 2023-09-02 | KW1-11427 | 2023-09-19 | COMP | MM_AJ
65 | 163 | 2023-08-28 | AJ23-0166 | T357 Relocation | 2141526 | 40877 | 2023-08-28 | 2023-09-02 | KW1-11427 | 2023-09-19 | COMP | MM_AJ
66 | 164 | 2023-08-28 | AJ23-0179 | T357 Relocation | 2141526 | 40882 | 2023-08-28 | 2023-09-02 | KW1-11429 | 2023-09-19 | COMP | MM_AJ
67 | 165 | 2023-08-28 | AJ23-0225 | T357 Relocation | 2141526 | 40881 | 2023-08-28 | 2023-09-10 | KW1-11708 | 2023-09-29 | COMP | MM_AJ
68 | 166 | 2023-08-28 | AJ23-0258 | T357 Relocation | 2141526 | 40884 | 2023-08-28 | 2023-09-02 | KW1-11429 | 2023-09-19 | COMP | MM_AJ
69 | 167 | 2023-08-28 | AJ23-0260 | T357 Relocation | 2141526 | 40887 | 2023-08-28 | 2023-09-02 | KW1-11386 | 2023-09-17 | COMP | MM_AJ
70 | 168 | 2023-08-28 | AJ23-0268 | T357 Relocation | 2141526 | 40884 | 2023-08-28 | 2023-09-02 | KW1-11429 | 2023-09-19 | COMP | MM_AJ
71 | 169 | 2023-08-28 | AJ23-0337 | T357 Relocation | 2141526 | 40884 | 2023-08-28 | 2023-09-02 | KW1-11429 | 2023-09-19 | COMP | MM_AJ
72 | 170 | 2023-08-28 | AJ23-0467 | T357 Relocation | 2141526 | 40882 | 2023-08-28 | 2023-09-02 | KW1-11429 | 2023-09-19 | COMP | MM_AJ
73 | 171 | 2023-08-28 | AJ23-0482 | T357 Relocation | 2141526 | 40883 | 2023-08-28 | 2023-09-02 | KW1-11386 | 2023-09-17 | COMP | MM_AJ
75 | 172 | 2023-08-28 | AJ23-0574 | T357 Relocation | 2141526 | 40879 | 2023-08-28 | 2023-09-02 | KW1-11425 | 2023-09-19 | COMP | MM_AJ
76 | 173 | 2023-08-28 | AJ23-0579 | T357 Relocation | 2141526 | 40887 | 2023-08-28 | 2023-09-02 | KW1-11386 | 2023-09-17 | COMP | MM_AJ
77 | 174 | 2023-08-28 | AJ23-0598 | T357 Relocation | 2141526 | 40882 | 2023-08-28 | 2023-09-02 | KW1-11429 | 2023-09-19 | COMP | MM_AJ
78 | 175 | 2023-08-28 | AJ23-0668 | T357 Relocation | 2141526 | 40879 | 2023-08-28 | 2023-09-02 | KW1-11425 | 2023-09-19 | COMP | MM_AJ
79 | 176 | 2023-08-28 | AJ23-0782 | T357 Relocation | 2141526 | 40879 | 2023-08-28 | 2023-09-02 | KW1-11425 | 2023-09-19 | COMP | MM_AJ
80 | 177 | 2023-08-28 | BU23-0193 | T357 Relocation | 2141526 | 40881 | 2023-08-28 | 2023-09-10 | KW1-11708 | 2023-09-29 | COMP | MM_AJ
81 | 178 | 2023-08-28 | BU23-0353 | T357 Relocation | 2141526 | 40885 | 2023-08-28 | 2023-09-02 | KW1-11427 | 2023-09-19 | COMP | MM_AJ
125 | 179 | 2023-08-28 | AJ22-0537 | Install 15 Smart Water Meters | 7178664 | 50415 | 2023-08-28 | 2023-09-13 |  |  |  | AJ_Subcon_PR
83 | 180 | 2023-08-31 | AJ22-0371 | T357 Relocation | 2141526 | 41138 | 2023-08-31 | 2023-09-02 | KW1-11386 | 2023-09-17 | COMP | MM_AJ
84 | 181 | 2023-08-31 | AJ22-0475 | T357 Relocation | 2141526 | 41143 | 2023-08-31 | 2023-09-02 | KW1-11386 | 2023-09-17 | COMP | MM_AJ
85 | 182 | 2023-08-31 | AJ23-0040 | T357 Relocation | 2141526 | 41140 | 2023-08-31 | 2023-09-02 | KW1-11451 | 2023-09-20 | COMP | MM_AJ
86 | 183 | 2023-08-31 | AJ23-0450 | T357 Relocation | 2141526 | 41138 | 2023-08-31 | 2023-09-02 | KW1-11386 | 2023-09-17 | COMP | MM_AJ
87 | 184 | 2023-08-31 | BU23-0264 | T357 Relocation | 2141526 | 41144 | 2023-08-31 | 2023-09-02 | KW1-11386 | 2023-09-17 | COMP | MM_AJ
88 |  | 2023-08-31 |  | T357 Relocation | 2141526 | 41146 | 2023-08-31 | 2023-09-02 | KW1-11451 | 2023-09-20 | COMP | MM_AJ
127 | 185 | 2023-09-03 | AJ23-0192 | KNB Wash Rack Tank Repair | 7297357 | 50097 | 2023-09-03 | 2023-09-03 |  |  |  | AJ_Subcon_PR
90 | 186 | 2023-09-07 | AJ22-0198 | Replacing The Main Distribution Panel | 6669460 | 50205 | 2023-09-07 | 2023-09-07 |  |  |  | MM_AJ
91 | 187 | 2023-09-07 | BU23-0372 | 43 Electrical Meter Installation | 2141526 | 50213 | 2023-09-07 | 2023-09-07 |  |  |  | MM_AJ
131 | 188 | 2023-09-10 | AJ23-0167 | TI Deficiencies Correction | 4911390 | 50414 | 2023-09-10 | 2023-09-13 |  |  |  | AJ_Subcon_PR
133 | 189 | 2023-09-11 | BU23-0029 | CO-01 Privacy Fencing for ARTC Training Area |  | 50292 | 2023-09-11 | 2023-09-11 |  |  |  | BU_Subcon_PR
96 | 190 | 2023-09-12 | AJ23-0747 | Technical Inspection Repairs, T5802 | 7162722 | 42166 | 2023-09-12 | 2023-09-17 | KW1-11867 | 2023-09-30 | COMP | MM_AJ
28 | 191 | 2023-09-13 | AJ23-0366 | TI Repairs | 7162722 | 50407 | 2023-09-13 | 2023-09-13 |  |  |  | AJ_Fabrication
134 | 192 | 2023-09-17 | AJ23-0306 | Bldg.134 PX Roof Repair |  | 50927 | 2023-09-17 | 2023-09-25 |  |  |  | AJ_Subcon_PR
136 | 193 | 2023-09-17 | AJ22-0055 | REPLACE THE YARD RADIATION DETECTORS AT DLA | 7527758 | 51355 | 2023-09-17 | 2023-10-04 |  |  |  | AJ_Subcon_PR
137 | 194 | 2023-09-19 | AJ20-0135 | Military Working Dog |  | 52652 | 2023-09-19 | 2023-11-08 |  |  |  | AJ_Subcon_PR
138 | 195 | 2023-09-19 | AJ22-0378 | Solar Light Set | 7584104 | 52634 | 2023-09-19 | 2023-11-09 |  |  |  | AJ_Subcon_PR
142 | 196 | 2023-09-26 | BU23-0232 | RUHQ Electrical Connection to SS-3 | 6328865 | 51208 | 2023-09-26 | 2023-10-10 |  |  |  | BU_Subcon_PR
143 | 197 | 2023-09-27 | AJ22-0199 | Replacement of the Solid State Frequency Converte | 2024951 | 51888 | 2023-09-27 | 2023-10-19 |  |  |  | AJ_Subcon_PR
148 | 198 | 2023-10-03 | BU22-0031 | PAD 16 Power and MTS |  | 51357 | 2023-10-03 | 2023-10-10 |  |  |  | BU_Subcon_PR
149 | 199 | 2023-10-03 | BU23-0192 | Stair Access for Drone Defense Zone5 Tower13 |  | 51574 | 2023-10-03 | 2023-10-11 |  |  |  | BU_Subcon_PR
150 | 200 | 2023-10-04 | BU23-0306 | Install Fire System Z4 TT4053 | 6589884 | 51492 | 2023-10-04 | 2023-10-08 |  |  |  | BU_Subcon_PR
151 | 201 | 2023-10-09 | BU22-0045 | Car Ports |  | 51502 | 2023-10-09 | 2023-10-09 |  |  |  | BU_Subcon_PR
155 | 202 | 2023-10-14 | BU23-0262 | NSTALLATION OF NEW ATS IN FS BLDG. 103 , C | 6231156 | 51923 | 2023-10-14 | 2023-10-19 |  |  |  | BU_Subcon_PR
156 | 203 | 2023-10-14 | BU23-0281 | CAB HQ Emergency Power Generator, | 6408129 | 51922 | 2023-10-14 | 2023-10-19 |  |  |  | BU_Subcon_PR
158 | 204 | 2023-10-14 | BU23-0183 | Asphalt Binder Capa Pads | 7874910 | 51924 | 2023-10-14 | 2023-10-19 |  |  |  | BU_Subcon_PR
159 | 205 | 2023-10-16 | AJ23-0437 | TFCF Training Trailer Electrical Upgrades Z4 | 7995997 | 52416 | 2023-10-16 | 2023-11-01 |  |  |  | AJ_Subcon_PR
162 | 206 | 2023-10-16 | AJ23-0532 | T6526 NEW DOOR AND CIPHER LOCKS Z6 | 7975040 | 52414 | 2023-10-16 | 2023-11-01 |  |  |  | AJ_Subcon_PR
160 | 207 | 2023-10-16 | BU22-0105 | GRIT Building Utilization Project, |  | 51891 | 2023-10-16 | 2023-10-19 |  |  |  | BU_Subcon_PR
165 | 208 | 2023-10-17 | AJ22-0546 | TT755 Grid Connection, | 8024236 | 52134 | 2023-10-17 | 2023-10-24 |  |  |  | AJ_Subcon_PR
166 | 209 | 2023-10-17 | BU23-0351 | Secondary Fence Installation Zone 6, | 7221399 | 52063 | 2023-10-17 | 2023-10-21 |  |  |  | BU_Subcon_PR
167 | 210 | 2023-10-18 | AJ23-0245 | T1000 Structural Assessment Z2 | 8019766 | 52378 | 2023-10-18 | 2023-10-31 |  |  |  | AJ_Subcon_PR
168 | 211 | 2023-10-19 | BU23-0233 | ULZ Install Grounding Points at Aircraft Parking Pads, | 5876978 | 52161 | 2023-10-19 | 2023-10-24 |  |  |  | BU_Subcon_PR
169 | 212 | 2023-10-22 | AJ23-0481 | B505 HVAC Replacement | 7813302 | 52316 | 2023-10-22 | 2023-10-28 |  |  |  | AJ_Subcon_PR
171 | 213 | 2023-10-22 | AJ23-0425 | B507 HVAC Replacement | 7815289 | 52129 | 2023-10-22 | 2023-10-24 |  |  |  | AJ_Subcon_PR
178 | 214 | 2023-10-24 | AJ23-0442 | ADA Generator Power Consolidation Z5 | 8017222 | 52410 | 2023-10-24 | 2023-11-01 |  |  |  | AJ_Subcon_PR
184 | 215 | 2023-10-31 | BU23-0279 | BU23-0279 RUHQ Emergency Power Generation Installation, Camp Buehring $64,633.00 |  | 52497 | 2023-10-31 | 2023-11-04 |  |  |  | BU_Subcon_PR
46 | 216 | 2023-11-01 | AJ23-0726 | Replacement of Isolator Panel and Suction Pumps | 7641976 | 52516 | 2023-11-02 | 2023-11-06 | LCVKW0885S | 2024-01-21 | COMP | AJ_Fabrication
186 | 217 | 2023-11-05 | BU23-0350 | REPLACE DOORS Z6 B6016 | 7221392 | 52750 | 2023-11-05 | 2023-11-15 |  |  |  | BU_Subcon_PR
188 | 218 | 2023-11-06 | AJ22-0474 | Bldg 3029 PKCA Replacement | 5337653 | 52656 | 2023-11-06 |  |  |  |  | AJ_Subcon_PR
190 | 219 | 2023-11-07 | AJ22-0505 | Replace the flooring for Building T438 | 3804265 | 52752 | 2023-11-07 | 2023-11-15 |  |  |  | AJ_Subcon_PR
191 | 220 | 2023-11-08 | AJ22-0399 | MOVE T2003 AND POWER TIE-IN | 7267384 | 52751 | 2023-11-08 | 2023-11-15 |  |  |  | AJ_Subcon_PR
192 | 221 | 2023-11-08 | BU23-0124 | Engineer Village Power Consolidation | 5375966 | 53084 | 2023-11-08 | 2023-11-23 |  |  |  | BU_Subcon_PR
193 | 222 | 2023-11-08 | BU23-0353 | B6016 & B2017 PERIMETER FENCE PRIVACY NETTING | 8236743 | 52692 | 2023-11-08 | 2023-11-09 |  |  |  | BU_Subcon_PR
195 | 223 | 2023-11-24 | AJ23-0645 | Z4 TT752D PKAC4481 Life Cycle Replacement | 6602085 | 54372 | 2023-11-24 | 2023-12-28 |  |  | COMP | AJ_Subcon_PR
197 | 224 | 2023-11-24 | AJ22-0190 | B450 Vent and Duct cleaning | 1850088 | 54287 | 2023-11-24 | 2023-12-25 |  |  | COMP | AJ_Subcon_PR
34 | 225 | 2023-11-26 | AJ22-0551 | Provide electrical connection for CCTV installation for 17 buildings | 7249685 | 53320 | 2023-11-26 | 2023-12-01 | LCVKW0923S | 2024-01-21 |  | AJ_Fabrication
49 | 226 | 2023-11-27 | BU23-0310 | Install New Emergency Shower | 6872738 | 42734 | 2023-09-19 | 2023-12-30 | KW1-14163 | 2024-01-24 03:00 | COMP | MM_BU
198 | 227 | 2023-11-27 | AJ23-0502 | RP2002 Modifications Z2 | 8389198 | 53316 | 2023-11-27 | 2023-12-01 |  |  | COMP | AJ_Subcon_PR
10 | 228 | 2023-12-03 | BU24-0087 | Install Circuit Breakers Z8 TT803 | 8565458 | 48795 | 2023-12-03 | 2023-12-07 | KW1-13609 | 2023-12-20 | COMP | MM_BU
1 | 229 | 2023-12-04 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 48879 | 2023-12-04 | 2023-12-11 | KW1-13841 | 2024-01-24 | COMP | MM_BU
2 | 230 | 2023-12-04 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 48882 | 2023-12-04 | 2023-12-11 | KW1-13841 | 2024-01-24 | COMP | MM_BU
200 | 231 | 2023-12-04 | BU23-249 | DENTAL CLINIC CABINETS AND COUNTERTOP ZONE 2, | 8528611 | 54008 | 2023-12-04 | 2023-12-17 |  |  | COMP | BU_Subcon_PR
3 | 232 | 2023-12-04 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 48938 | 2023-12-05 | 2023-12-11 | KW1-13840 | 2024-01-24 | COMP | MM_BU
204 | 233 | 2023-12-06 | AJ22-0530 | CFLCC Repair | 4515912 | 54022 | 2023-12-06 | 2023-12-17 |  |  | COMP | AJ_Subcon_PR
225 | 234 | 2023-12-06 | AJ23-0593 | B777 ATS and Emergency Light, Zine 4 | 8675931 | 54286 | 2023-12-24 | 2023-12-25 |  |  | COMP | AJ_Subcon_PR
206 | 235 | 2023-12-07 | AJ23-0237 | Zone 2 Coalition Village Kitchen | 5424135 | 54024 | 2023-12-07 | 2023-12-17 |  |  | COMP | AJ_Subcon_PR
209 | 236 | 2023-12-10 | AJ23-0241 | Life Cycle Replacement | 5720168 | 54011 | 2023-12-10 | 2023-12-17 |  |  | COMP | AJ_Subcon_PR
210 | 237 | 2023-12-10 | AJ23-0619 | Sink Booster Heater Installation | 6768439 | 54021 | 2023-12-10 | 2023-12-17 |  |  | COMP | AJ_Subcon_PR
208 | 238 | 2023-12-10 | BU23-0205 | Connect Sanitary Water Lines Z5 RUHQ B5999 | 8689493 | 54014 | 2023-12-10 | 2023-12-24 |  |  | COMP | BU_Subcon_PR
211 | 239 | 2023-12-11 | AJ23-0243 | Z6 Life Cycle Replacement 0609L | 5712915 | 54369 | 2023-12-11 | 2023-12-28 |  |  | COMP | AJ_Subcon_PR
212 | 240 | 2023-12-11 | AJ23-0242 | Life Cycle Replacement | 5720130 | 54370 | 2023-12-11 | 2023-12-28 |  |  | COMP | AJ_Subcon_PR
213 | 241 | 2023-12-11 | BU23-0314 | Replacement of Water Filling Railing Zone 3, | 6665414 | 54030 | 2023-12-11 | 2023-12-17 |  |  | COMP | BU_Subcon_PR
44 | 242 | 2023-12-12 | AJ23-0788 | Replace electrical panel for TT7011 | 7996575 | 54414 | 2023-12-12 | 2023-12-31 | LCVKW0983 | 2024-02-15 | COMP | AJ_Fabrication
7 | 243 | 2023-12-13 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 49482 | 2023-12-13 | 2023-12-15 | KW1-13913 | 2024-02-28 | COMP | MM_BU
8 | 244 | 2023-12-13 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 49470 | 2023-12-13 | 2023-12-15 | KW1-13777 | 2024-01-31 | COMP | MM_BU
9 | 245 | 2023-12-13 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 49587 | 2023-12-13 | 2023-12-15 | KW1-13913 | 2024-01-13 | COMP | MM_BU
11 | 246 | 2023-12-13 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 49486 | 2023-12-13 | 2023-12-15 | KW1-13776 | 2024-01-10 | COMP | MM_BU
12 | 247 | 2023-12-13 | BU24-0097 | Install Exit Lights Z2 B211 | 8564897 | 48798 | 2023-12-13 | 2023-12-06 | KW1-13557 | 2023-12-13 | COMP | MM_BU
13 | 248 | 2023-12-13 | BU24-0098 | Install Exit Signs Basewide | 8570569 | 49511 | 2023-12-13 | 2023-12-16 | KW1-13775 | 2024-01-10 | COMP | MM_BU
14 | 249 | 2023-12-13 | BU24-0107 | Install Electrical Outlet FBF T008 | 8674569 | 49517 | 2023-12-13 | 2023-12-15 | KW1-13775 | 2024-01-10 | COMP | MM_BU
35 | 250 | 2023-12-13 | AJ23-0512 | CLVB RLB Upgrade | 8139100 | 54010 | 2023-12-13 | 2023-12-17 | LCVKW0950S |  | COMP | AJ_Fabrication
36 | 251 | 2023-12-13 | AJ23-0536 | Electrical & Carpentry B1005 Z6, | 8379855 | 54009 | 2023-12-13 | 2023-12-17 | LCVKW0949S | 2023-01-21 | COMP | AJ_Fabrication
115 | 252 | 2023-12-14 | AJ23-0708 | TI Repairs | 8012468 | 49621 | 2023-12-14 | 2023-12-16 | KW1-13925 | 2024-01-10 | COMP | MM_AJ
15 | 253 | 2023-12-16 | BU24-0073 | Install Covers Ring 4 Power Plant | 8530135 | 49762 | 2023-12-16 | 2023-12-16 | KW1-13925 | 2024-01-06 | COMP | MM_BU
16 | 254 | 2023-12-16 | BU24-0095 | Install Vestibule Doors Z5 Pad21 TT14 | 8563372 | 49784 | 2023-12-16 | 2023-12-19 | KW1-13903 | 2024-01-21 | COMP | MM_BU
17 | 255 | 2023-12-16 | BU24-0096 | Install Vestibule Doors Z5 Pad21 TT09 | 8564095 | 49785 | 2023-12-16 | 2023-12-19 | KW1-13903 | 2024-01-21 | COMP | MM_BU
229 | 256 | 2023-12-16 | AJ22-0120 | T1084 Outside Stairs Broken | 8810536 | 54291 | 2023-12-24 | 2023-12-25 |  |  | COMP | AJ_Subcon_PR
18 | 257 | 2023-12-17 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 49844 | 2023-12-17 | 2023-12-19 | KW1-13827 | 2023-12-30 | COMP | MM_BU
215 | 258 | 2023-12-17 | AJ23-0252 | Plumbing Correction | 5790685 | 54378 | 2023-12-17 | 2023-12-28 |  |  | COMP | AJ_Subcon_PR
217 | 259 | 2023-12-17 | AJ23-0606 | Z5 New Grounding Points on PAHP | 6679341 | 54289 | 2023-12-17 | 2023-12-27 |  |  | COMP | AJ_Subcon_PR
214 | 260 | 2023-12-17 | BU23-0375 | Deconstruct Facility Z6 TT7-3 TT7-9 | 8781713 | 54377 | 2023-12-17 | 2023-12-28 |  |  | COMP | BU_Subcon_PR
40 | 261 | 2023-12-19 | AJ21-0011 | 43 Electrical Meter Installation, | 5171089 | 54208 | 2023-12-19 | 2023-12-21 | LCVKW0657S | 2024-05-02 |  | AJ_Fabrication
3 | 262 | 2023-12-19 | BU22-0007 | Install 50 Electrical Meters | 4103915 | 54209 | 2023-12-19 | 2023-12-21 | LCVKW0657S | 2024-05-02 |  | BU_Fabrication
218 | 263 | 2023-12-19 | AJ22-0267 | Zone 6 Post Office Truck Lift Repair | 2232451 | 54502 | 2023-12-19 | 2023-01-06 |  |  | COMP | AJ_Subcon_PR
219 | 264 | 2023-12-19 | AJ23-0510 | CLM 1 Reskin | 6043651 | 54603 | 2023-12-19 | 2024-01-06 |  |  | COMP | AJ_Subcon_PR
220 | 265 | 2023-12-19 | AJ23-0610 | SPOD T70 Female Latrine Renovations | 6417910 | 54292 | 2023-12-19 | 2023-12-25 |  |  | COMP | AJ_Subcon_PR
221 | 266 | 2023-12-19 | AJ23-0676 | Sink Booster Heater Installation | 6768274 | 54290 | 2023-12-19 | 2023-12-25 |  |  | COMP | AJ_Subcon_PR
224 | 267 | 2023-12-19 | BU23-0208 | B6015 Relocation | 5616330 | 54291 | 2023-12-19 | 2023-12-27 |  |  | COMP | BU_Subcon_PR
223 | 268 | 2023-12-20 | AJ22-0168 | SS812 Sunshade Replace | 2635682 | 54280 | 2023-12-19 | 2023-12-24 |  |  | COMP | AJ_Subcon_PR
222 | 269 | 2023-12-20 | BU23-0160 | Replace Manual Transfer Switch | 5203390 | 54494 | 2023-12-19 | 2023-01-04 |  |  | COMP | BU_Subcon_PR
216 | 270 | 2023-12-20 | AJ22-0110 | Sunshade Relocate Z7 | 2642514 | 54367 | 2023-12-20 | 2023-12-28 |  |  | COMP | AJ_Subcon_PR
19 | 271 | 2023-12-21 | BU24-0027 | Service HVAC Units Z1 B1999 | 8236954 | 50183 | 2023-12-21 | 2023-12-23 | KW1-14093 | 2024-01-25 | COMP | MM_BU
20 | 272 | 2023-12-21 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 50298 | 2023-12-23 | 2023-12-23 | KW1-14124 | 2024-01-31 | COMP | MM_BU
21 | 273 | 2023-12-21 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 50426 | 2023-12-23 | 2023-12-24 | KW1-14244 | 2024-01-22 | COMP | MM_BU
226 | 274 | 2023-12-23 | AJ23-0492 | ARCENT CMD Group Foyer Work |  | 54615 | 2023-12-23 | 2024-01-08 |  |  | COMP | AJ_Subcon_PR
227 | 275 | 2023-12-23 | AJ23-0240 | Z6 Life Cycle Replacement 1404E and 1402W | 8084482 | 54493 | 2023-12-23 | 2024-01-04 |  |  | COMP | AJ_Subcon_PR
228 | 276 | 2023-12-23 | AJ23-0611 | SPOD T73 Male Latrine Renovations |  | 54610 | 2023-12-23 | 2024-01-07 |  |  | COMP | AJ_Subcon_PR
22 | 277 | 2023-12-23 | BU24-0119 | Install Electrical Outlet Z2 T2072 | 8789414 | 50469 | 2023-12-24 | 2023-12-24 | KW1-14244 | 2024-01-22 | COMP | MM_BU
5 | 278 | 2023-12-24 | BU24-0093 | Change Door Z1 B100 RM127 | 8564196 | 54415 | 2023-12-25 | 2023-12-31 | LCVKW0995S | 2024-02-16 | COMP | BU_Fabrication
230 | 279 | 2023-12-26 | AJ23-0496 | ECP2 RMU2-4A-4 Replacement | 6007449 | 54497 | 2023-12-26 | 2024-01-04 |  |  | COMP | AJ_Subcon_PR
231 | 280 | 2023-12-26 | AJ23-0468 | T6207 Roof Replacement | 5903790 | 54501 | 2023-12-26 | 2024-01-04 |  |  | COMP | AJ_Subcon_PR
232 | 281 | 2023-12-26 | AJ23-0469 | T6206 Roof Replacement | 5904257 | 55069 | 2024-01-20 | 2024-01-04 |  |  | COMP | AJ_Subcon_PR
233 | 282 | 2023-12-27 | BU23-0357 | TT1051 Deconstruction Tent | 7249582 | 54611 | 2023-12-27 | 2024-01-07 |  |  | COMP | BU_Subcon_PR
23 | 283 | 2023-12-28 | BU-24-0098 | BUH-Z3-00-TRLR3020 | 7286430 | 50798 | 2023-12-29 | 2023-12-31 | KW1-14132 | 2024-01-24 | COMP | MM_BU
48 | 284 | 2023-12-29 | AJ24-0065 | Zone 2 B505 ASG 511 Connection to Support ASG 014 | 8038045 | 55085 | 2024-01-20 | 2024-01-22 | LCVKW1014S | 2024-02-29 | COMP | AJ_Fabrication
35 | 285 | 2023-12-30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 50935 | 2023-12-30 | 2023-12-31 | KW1-14212 | 2024-01-31 | COMP | MM_BU
37 | 286 | 2023-12-30 | BU24-0112 | Install Bollards Ring 4 | 8920496 | 50950 | 2023-12-31 | 2024-01-02 | KW1-14163 | 2024-02-07 | COMP | MM_BU
36 | 287 | 2023-12-30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 51196 | 2024-01-04 | 2024-01-06 | KW1-14209 | 2024-01-31 | COMP | MM_BU
38 | 288 | 2023-12-30 | BU24-0018 | Install Generator Z2 PWD Yard - C to TDP | 8894903 | 51194 | 2024-01-04 | 2024-01-07 | KW1-14241 | 2024-03-10 |  | MM_BU
236 | 289 | 2023-12-31 | BU23-0373 | Deconstruct Z8 T2032 | 8948486 | 54612 | 2023-01-06 | 2024-01-07 |  |  | COMP | BU_Subcon_PR
237 | 290 | 2023-12-31 | BU23-0338 | Emplace Furniture Z5 B5999 | 8944194 | 54725 | 2023-01-06 | 2024-01-11 |  |  | COMP | BU_Subcon_PR
235 | 291 | 2024-01-03 | AJ23-0470 | Z6 T6208 Roof Replacement | 5904437 | 54609 | 2023-01-04 | 2023-01-07 |  |  | COMP | AJ_Subcon_PR
39 | 292 | 2024-01-03 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 51120 | 2024-01-03 | 2024-01-04 | KW1-14244 | 2024-01-22 | COMP | MM_BU
41 | 293 | 2024-01-03 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 51161 | 2024-01-04 | 2024-01-04 | KW1-14096 | 2024-01-25 | COMP | MM_BU
40 | 294 | 2024-01-03 | BU24-0103 | Fence Repair | 8873806 | 51336 | 2024-01-06 | 2024-01-07 | KW1-14089 | 2024-01-25 | COMP | MM_BU
45 | 295 | 2024-01-04 | BU24-0028 | Repair Runway Holes | 7894966 | [6 empty] | MM_BU
42 | 296 | 2024-01-06 | BU24-0081 | Replace Sandbags Bunkers Z5 BA2 | 8417604 | 51318 | 2024-01-06 | 2024-01-07 | KW1-14209 | 2024-01-31 | COMP | MM_BU
238 | 297 | 2024-01-06 | AJ23-0723 | New Concrete Pad Zone 3 Camp Arifjan, Kuwait | 9069828, | 54843 | 2024-01-11 | 2024-01-14 |  |  | COMP | AJ_Subcon_PR
44 | 298 | 2024-01-07 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 51540 | 2024-01-10 | 2024-01-10 | KW1-14437 | 2024-02-08 07:00 | COMP | MM_BU
239 | 299 | 2024-01-07 | AJ23-0667 | DFAC Lockers Rebuild, Zone 6, Camp Arifjan, Kuwait | 6653596 | 54844 | 2024-01-11 | 2024-01-14 |  |  | COMP | AJ_Subcon_PR
43 | 300 | 2024-01-07 | BU24-0015 | Replace Generator Z2 Bldg. 209 -C To TDP | 8944274 | 51875 | 2024-01-16 | 2024-01-27 | KW1-14808 | 2024-03-28 |  | MM_BU
46 | 301 | 2024-01-09 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 51598 | 2024-01-11 | 2024-01-13 |  |  |  | MM_BU
240 | 302 | 2024-01-09 | AJ23-0472 | T6204 Roof Replacement | 5904246 | 54838 | 2024-01-11 | 2024-01-13 |  |  | COMP | AJ_Subcon_PR
241 | 303 | 2024-01-09 | AJ23-0750 | Repair HVAC in B216 Basement, S3 section | 7324760 | 54839 | 2024-01-11 | 2024-01-13 |  |  | COMP | AJ_Subcon_PR
242 | 304 | 2024-01-09 | AJ23-0475 | T6201 Roof Replacement | 5904456 | 54837 | 2024-01-11 | 2024-01-13 |  |  | COMP | AJ_Subcon_PR
243 | 305 | 2024-01-09 | AJ23-0420 | UDS 1-4A/1 Transformer Replacement Zone 2 Camp Arifjan, Kuwait | 5600909 | 55083 | 2024-01-11 | 2024-01-22 |  |  | COMP | AJ_Subcon_PR
244 | 306 | 2024-01-09 | AJ23-0473 | T6203 Roof Replacement | 5904228 | 54847 | 2024-01-11 | 2024-01-14 |  |  | COMP | AJ_Subcon_PR
245 | 307 | 2024-01-09 | AJ23-0474 | T6202 Roof Replacement | 5904297 | 54841 | 2024-01-11 | 2024-01-13 |  |  | COMP | AJ_Subcon_PR
246 | 308 | 2024-01-09 | AJ23-0471 | T6205 Roof Replacement | 5904289 | 54840 | 2024-01-11 | 2024-01-13 |  |  | COMP | AJ_Subcon_PR
10 | 309 | 2024-01-09 | BU24-0064 | Rev1 Repair Sunshade Z3 SS3082 | 8687667 | 55203 | 2024-01-23 | 2024-01-24 | LCVKW1021S | 2024-02-28 | COMP | BU_Fabrication
47 | 310 | 2024-01-10 | BU23-0352 | Z6 B6016 Door Soundproofing | 7562147 | 51588 | 2024-01-10 | 2024-01-13 | KW1-14389 | 2024-03-15 | COMP | MM_BU
48 | 311 | 2024-01-15 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 51857 | 2024-01-16 | 2024-01-18 | KW1-14455 | 2024-02-11 | COMP | MM_BU
50 | 312 | 2024-01-16 | BU24-0048 | New Signs ASP Z8 T8000 | 8418200 | 51928 | 2024-01-17 | 2024-01-18 | KW1-14365 | 2024-02-05 | COMP | MM_BU
247 | 313 | 2024-01-17 | AJ23-0699 | B224-BMS Preventive Maintenance Assessment, Camp Arifjan |  | 55070 | 2024-01-20 | 2024-01-20 |  |  | COMP | AJ_Subcon_PR
248 | 314 | 2024-01-17 | AJ23-0229 | Z6 Motor Pool 19 Power Consolidation |  | 55105 | 2024-01-20 | 2024-01-22 |  |  | COMP | AJ_Subcon_PR
249 | 315 | 2024-01-20 | AJ24-0170 | B229 Breaker and Breaker Frame Repair by Replacement, Camp Arifjan, Kuwait |  | 55084 | 2024-01-20 | 2024-01-22 |  |  | COMP | AJ_Subcon_PR
250 | 316 | 2024-01-20 | AJ22-0258 | B462 HVAC Replacement | 9117358 | 55684 | 2024-01-22 | 2024-02-04 |  |  | COMP | AJ_Subcon_PR
51 | 317 | 2024-01-22 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 52341 | 2024-01-22 | 2024-01-27 | KW1-14638 | 2024-02-20 | COMP | MM_BU
52 | 318 | 2024-01-24 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 52617 | 2024-01-25 | 2024-01-29 | KW1-14578 | 2024-02-10 | COMP | MM_BU
251 | 319 | 2024-01-24 | AJ22-0179 | Z1 Repair LV Side at SS-6 | 9242132 | 55790 | 2024-01-27 | 28jna24 |  |  | COMP | AJ_Subcon_PR
53 | 320 | 2024-01-25 | BU24-0140 | Install Cypher Locks T9601 | 9223619 | 52621 | 2024-01-25 | 2024-01-27 | KW1-14578 | 2024-02-10 | COMP | MM_BU
56 | 321 | 2024-01-27 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 52744 | 2024-01-27 | 2024-01-29 | KW1-14739 | 2024-02-15 | COMP | MM_BU
256 | 322 | 2024-01-27 | AJ21-0097 | Recycling Fence Center Z7, Arifjan (PPR VEC-23-0400-KUW0 |  | 55368 | 2024-01-27 |  |  |  | COMP | AJ_Subcon_PR
252 | 323 | 2024-01-27 | AJ23-0566 | Z3 ASP Magazine Concrete Remediations | 6669326 | 55500 | 2024-01-29 | 2024-01-30 |  |  | COMP | AJ_Subcon_PR
253 | 324 | 2024-01-27 | AJ23-0423 | Zone 1-B229 HVAC Circuit on Backup Power, Camp Arifjan |  | 55680 | 2024-01-29 | 2024-02-03 |  |  | COMP | AJ_Subcon_PR
254 | 325 | 2024-01-27 | AJ23-0584 | Street Sign Refurbishment |  | 55547 | 2024-01-29 | 2024-01-31 |  |  | COMP | AJ_Subcon_PR
255 | 326 | 2024-01-27 | AJ23-0701 | Signal Radio Park Privacy Screen & Gate Removal |  | 55572 | 2024-01-29 | 2023-02-01 |  |  | COMP | AJ_Subcon_PR
257 | 327 | 2024-01-28 | AJ22-0266 | B134 Post Office Truck Lift Repair, Zone 1, Camp Arifjan |  | 55967 | 2024-01-31 | 2024-02-10 |  |  | COMP | AJ_Subcon_PR
238 | 328 | 2024-01-28 | BU23-0368 | Connect Cable from Hangar 9 (TT9600) at ESS-14 | 7335344 | 55549 | 2024-01-31 | 2024-01-31 |  |  | COMP | BU_Subcon_PR
58 | 329 | 2024-01-29 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 52943 | 2024-01-30 | 2024-01-31 | KW1-14614 | 2024-02-20 | COMP | MM_BU
54 | 330 | 2024-01-30 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 53005 | 2024-01-30 | 2024-02-01 | KW1-14634 | 2024-02-18 | COMP | MM_BU
50 | 331 | 2024-01-31 | AJ24-0202 | Z7 CRSP Yard SS812 Elec Repairs | [7 empty] | AJ_Fabrication
258 | 332 | 2024-02-03 | AJ23-0093 | Z6 DFAC Prime Power Connection |  | 55682 | 2024-02-03 | 2024-02-04 |  |  | COMP | AJ_Subcon_PR
259 | 333 | 2024-02-04 | AJ24-0022 | KNB Wash Rack Add Gravel, Compact and Grade |  | 55683 | 2024-02-04 | 2024-02-04 |  |  | COMP | AJ_Subcon_PR
260 | 334 | 2024-02-04 | AJ22-0300 | Bldg.224 Tank Monitoring System Replacement, Camp Arifjan |  | 55966 | 2024-02-07 | 2024-02-10 |  |  | COMP | AJ_Subcon_PR
59 | 335 | 2024-02-07 | BU24-0147 | T-2028 New Cipher Lock | 9522604 | 53597 | 2024-02-07 | 2024-02-10 | KW1-14886 | 2024-02-29 | COMP | MM_BU
239 | 336 | 2024-02-07 | BU23-0275 | TT403 Sunshade Replacement Phase 1 | 6874479 | 55968 | 2024-02-07 | 2024-02-10 |  |  | COMP | BU_Subcon_PR
60 | 337 | 2024-02-07 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 53647 | 2024-02-08 | 2024-02-10 | KW1-14886 | 2024-02-29 | COMP | MM_BU
61 | 338 | 2024-02-07 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 53880 | 2024-02-10 | 2024-02-12 | KW1-14917 | 2024-02-22 | COMP | MM_BU
62 | 339 | 2024-02-07 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 53785 | 2024-02-10 | 2024-02-10 | KW1-14924 | 2024-02-24 07:00 | COMP | MM_BU
63 | 340 | 2024-02-10 | BU23-0083 | Correct TI Deficiencies for FMR Tower | 5083138 | 53865 | 2024-02-10 | 2024-02-12 | KW1-15089 | 2024-03-07 | COMP | MM_BU
64 | 341 | 2024-02-10 | BU23-0031 | Correct TI Deficiencies for UDR 5 ISBC Tower | 5069515 | 53867 | 2024-02-10 | 2024-02-12 | KW1-15089 | 2024-03-07 | COMP | MM_BU
65 | 342 | 2024-02-10 | BU23-0082 | Correct TI Deficiencies for HSR Tower | 5083153 | 53868 | 2024-02-10 | 2024-02-12 | KW1-15089 | 2024-03-07 | COMP | MM_BU
261 | 343 | 2024-02-10 | AJ23-0250 | RP8002 Expansion |  | 55977 | 2024-02-10 | 2024-02-11 |  |  | COMP | AJ_Subcon_PR
262 | 344 | 2024-02-10 | AJ23-0219 | Z2 B532 Door Frame Replacement |  | 55972 | 2024-02-10 | 2024-02-11 |  |  | COMP | AJ_Subcon_PR
263 | 345 | 2024-02-10 | AJ23-0751 | Z1 B144 REPLACE HVAC UNITS |  | 55975 | 2024-02-10 | 2024-02-11 |  |  | COMP | AJ_Subcon_PR
264 | 346 | 2024-02-10 | AJ23-0143 | Secure Exposed Overhead Electrical Cable |  | 55982 | 2024-02-10 | 2024-02-11 |  |  | COMP | AJ_Subcon_PR
265 | 347 | 2024-02-10 | AJ24‐0009 | SPOD CHAIN‐LINK FENCE REPAIRS |  | 55974 | 2024-02-10 | 2024-02-11 |  |  | COMP | AJ_Subcon_PR
66 | 348 | 2024-02-12 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 |  | 2024-02-12 |  |  |  |  | MM_BU
266 | 349 | 2024-02-12 | AJ23-0238 | T758 Fence Inserts Zone 4, Camp Arifjan |  | 56193 | 2024-02-13 | 2024-02-18 |  |  | COMP | AJ_Subcon_PR
67 | 350 | 2024-02-12 | BU24-0058 | T6050 Add to TE | 9330911 | 54193 | 2024-02-14 | 2024-02-15 | KW1-14944 | 2024-03-22 |  | MM_BU
71 | 351 | 2024-02-12 | BU24-0076 | Replace floor in female shower trailer 16A |  | PRINPRG | [5 empty] | MM_BU
267 | 352 | 2024-02-13 | AJ23-0740 | REPLACEMENT/INSTALLATION HVAC UNIT B179 |  | 56061 | 2024-02-13 | 2024-02-13 |  |  | COMP | AJ_Subcon_PR
276 | 353 | 2024-02-13 | AJ23-0439 | Wash Rack Area Light Poles & Lighting KNB Camp Arifjan, Kuwait |  | 56768 | 2024-03-02 | 2024-03-03 |  |  | COMP | AJ_Subcon_PR
68 | 354 | 2024-02-14 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 54230 | 2024-02-14 | 2024-02-15 | KW1-14967 | 2024-03-02 | COMP | MM_BU
69 | 355 | 2024-02-14 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 |  | 2024-02-14 |  |  |  |  | MM_BU
51 | 356 | 2024-02-14 | AJ24-0203 | MAIN FEEDER CABLE DAMAGED NEED TO REPLACE |  | PWD-ELEC-PANEL-PWO-AJ24-0203-4065.1 | 2024-03-05 |  |  |  |  | AJ_Fabrication
53 | 357 | 2024-02-14 | AJ23-0551 | SPOD T5 Refurbishment | 6443145 | [6 empty] | AJ_Fabrication
70 | 358 | 2024-02-15 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 54414 | 2024-02-17 | 2024-02-19 | KW1-15278 | 2024-03-10 | COMP | MM_BU
269 | 359 | 2024-02-17 | AJ23-0620 | T504D Cage Wall Installation |  | 56204 | 2024-02-18 | 2024-02-19 |  |  | COMP | AJ_Subcon_PR
270 | 360 | 2024-02-17 | AJ23-0247 | Z1 TT1700 Additional Exit Doors | 9705833 | 56203 | 2024-02-18 | 2024-02-19 |  |  | COMP | AJ_Subcon_PR
74 | 361 | 2024-02-18 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 54532 | 2024-02-18 | 2024-02-20 | KW1-15034 | 2024-03-15 | COMP | MM_BU
72 | 362 | 2024-02-18 | BU24-0167 | Install Security Bars Z2 Trailer2028 | 9653621 | 54781 | 2024-02-20 | 2024-02-24 | KW1-15364 | 2024-03-16 | COMP | MM_BU
271 | 363 | 2024-02-19 | AJ23-0376 | KNB T1 Repairs CT-14, KNB, Kuwait |  | 56304 | 2024-02-19 | 2024-02-21 |  |  | COMP | AJ_Subcon_PR
275 | 364 | 2024-02-20 | AJ23-0254 | Off-Post Trench RP8002 CAKU |  | 56770 | 2024-02-29 | 2024-03-03 |  |  | COMP | AJ_Subcon_PR
87 | 365 | 2024-02-20 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 56512 | 2024-03-09 |  |  |  |  | MM_BU
88 | 366 | 2024-02-20 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 56508 | 2024-03-09 |  |  |  |  | MM_BU
75 | 367 | 2024-02-21 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 54793 | 2024-02-21 | 2024-02-24 | KW1-15168 | 2024-03-10 | COMP | MM_BU
76 | 368 | 2024-02-21 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 54815 | 2024-02-21 | 2024-02-24 | KW1-15168 | 2024-03-10 | COMP | MM_BU
77 | 369 | 2024-02-21 | BU24-0175 | Paint Floor Lines Z3 VLAM005 | 9790969 | 54832 | 2024-02-21 | 2024-02-24 | KW1-15166 | 2024-03-10 | COMP | MM_BU
78 | 370 | 2024-02-21 | BU24-0143 | Install Overhead Lights B9501AB | 9360741 | 54838 | 2024-02-21 | 2024-02-24 | KW1-15166 | 2024-03-10 | COMP | MM_BU
79 | 371 | 2024-02-21 | BU24-0172 | (TT404) NEED TO FIX DAMAGE FLOOR | 9790884 | 54841 | 2024-02-21 | 2024-02-24 | KW1-15166 | 2024-03-10 |  | MM_BU
240 | 372 | 2024-02-21 | BU23-0221 | Install Electrical Outlets FP-C to TDP | 9805359 | 56589 | 2024-02-21 | 2024-02-28 |  |  | COMP | BU_Subcon_PR
80 | 373 | 2024-02-21 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 55566 | 2024-02-28 | 2024-02-29 | KW1-15336 | 2024-04-12 | COMP | MM_BU
81 | 374 | 2024-02-22 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 55476 | 2024-02-27 | 2024-02-29 | KW1-15356 | 2024-03-15 07:00 | COMP | MM_BU
273 | 375 | 2024-02-22 | AJ23-0494 | TT5000 Electrical Work |  | 56654 | 2024-02-29 | 2024-02-29 |  |  | COMP | AJ_Subcon_PR
82 | 376 | 2024-02-23 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 55474 | 2024-02-27 | 2024-02-29 | KW1-15356 | 2024-03-09 07:00 | COMP | MM_BU
272 | 377 | 2024-02-24 | AJ23-0378 | KNB T1 Repairs T-411, KNB, Kuwait |  | 56655 | 2024-02-29 | 2024-02-29 |  |  | COMP | AJ_Subcon_PR
274 | 378 | 2024-02-24 | AJ21-0051 | Bldg. 222 Security Hardening_ Zone 1 |  | 56660 | 2024-02-29 | 2024-02-29 |  |  | COMP | AJ_Subcon_PR
83 | 379 | 2024-02-24 | BU24-0177 | Replace Electrical Cable Z1 B103 |  | PRINPRG | [5 empty] | MM_BU
84 | 380 | 2024-02-29 | BU23-223 | TI Deficiency Repairs Zone6 TT6078 - C to TDP | 7562117 | 55705 | 2024-02-29 | 2024-03-03 | KW1-15486 | 2024-04-30 |  | MM_BU
116 | 381 | 2024-02-29 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [6 empty] | MM_AJ
277 | 382 | 2024-03-02 | AJ24-0050 | TI Corrections - Fire Protection |  | 56899 | 2024-03-03 |  |  |  | COMP | AJ_Subcon_PR
278 | 383 | 2024-03-02 | AJ23-0767 | B179 EDOC and Optometry Sun Shade |  | 56775 | 2024-03-03 | 2024-04-03 |  |  | COMP | AJ_Subcon_PR
279 | 384 | 2024-03-02 | AJ23-0380 | KNB T1 Repairs T-413 |  | 56777 | 2024-03-03 | 2024-03-03 |  |  | COMP | AJ_Subcon_PR
280 | 385 | 2024-03-02 | AJ23-0382 | KNB T1 Repairs T-415 |  | 56776 | 2024-03-03 | 2024-03-03 |  |  | COMP | AJ_Subcon_PR
85 | 386 | 2024-03-02 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 56039 | 2024-03-04 | 2024-03-07 | KW1-15459 | 2024-04-04 07:00 |  | MM_BU
242 | 387 | 2024-03-02 | BU20-0026A | Automated Record Fire (ARF) Sunshade Range 4, Camp Buehring |  | 57043 | 2024-03-05 | 2024-03-09 |  |  | COMP | BU_Subcon_PR
243 | 388 | 2024-03-02 | BU20-0026B | SRGC Sunshade Construction Range 4, Camp Buehring, Kuwait |  | 57044 | 2024-03-05 | 2024-03-09 |  |  | COMP | BU_Subcon_PR
241 | 389 | 2024-03-03 | BU24-0060 | Install Fencing Gates Z3 TT307 |  | 57046 | 2024-03-04 | 2024-03-09 |  |  | COMP | BU_Subcon_PR
86 | 390 | 2024-03-04 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 56045 | 2024-03-04 | 2024-03-07 |  |  |  | MM_BU
89 | 391 | 2024-03-04 | BU24-0179 | 4 New Cipher Locks TT301 | 9966783 | 56124 | 2024-03-05 | 2024-03-07 | KW1-15453 | 2024-03-21 | COMP | MM_BU
90 | 392 | 2024-03-05 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 56188 | 2024-03-05 | 2024-03-07 |  |  |  | MM_BU
244 | 393 | 2024-03-05 | BU24-0012 | Fix Def Solar Lights |  | 57053 | 2024-03-05 |  |  |  | comp | BU_Subcon_PR
91 | 394 | 2024-03-07 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 56364 | 2024-03-07 | 2024-03-09 | KW1-15519 | 2024-03-24 |  | MM_BU
245 | 395 | 2024-03-09 | BU24-0006 | Connect HAZMAT and Pest Control Facilities to ESS-14 CAMP Buehring, Kuwait |  | PRINPRG | [5 empty] | BU_Subcon_PR
246 | 396 | 2024-03-09 | BU23-0379 | Correct TI Deficiencies for ESS 14TO18 Zone -1,2 Camp Buehring |  | PRINPRG | [5 empty] | BU_Subcon_PR
93 | 397 | 2024-03-10 | BU24-0129 | Relocate Retention Pond RP6002 |  | PRINPRG | [5 empty] | MM_BU

## Dashboard
|  | Total BOM Received PROJECT |  | Total Maximo PR Created in ALL |  | Total PR Created in AJ |  | Total PR Created in BU |  | Total Project material received in AJ |  | Total Project material received in BU |  | Total Project material received For ALL
|  | 2023-01-01 | 8 | 2023-01-01 | 57 | 2023-01-01 | 63 | 2023-01-01 | 2 | 2023-01-01 | 59 | 2023-01-01 | 0 | 2023-01-01 | 59
|  | 2023-02-01 | 6 | 2023-02-01 | 17 | 2023-02-01 | 2 | 2023-02-01 | 3 | 2023-02-01 | 1 | 2023-02-01 | 0 | 2023-02-01 | 16
|  | 2023-03-01 | 13 | 2023-03-01 | 21 | 2023-03-01 | 26 | 2023-03-01 | 7 | 2023-03-01 | 19 | 2023-03-01 | 0 | 2023-03-01 | 19
|  | 2023-04-01 | 20 | 2023-04-01 | 32 | 2023-04-01 | 43 | 2023-04-01 | 6 | 2023-04-01 | 32 | 2023-04-01 | 0 | 2023-04-01 | 32
|  | 2023-05-01 | 31 | 2023-05-01 | 34 | 2023-05-01 | 33 | 2023-05-01 | 11 | 2023-05-01 | 19 | 2023-05-01 | 0 | 2023-05-01 | 31
|  | 2023-06-01 | 9 | 2023-06-01 | 3 | 2023-06-01 | 6 | 2023-06-01 | 5 | 2023-06-01 | 3 | 2023-06-01 | 0 | 2023-06-01 | 3
|  | 2023-07-01 | 6 | 2023-07-01 | 4 | 2023-07-01 | 6 | 2023-07-01 | 3 | 2023-07-01 | 3 | 2023-07-01 | 0 | 2023-07-01 | 3
|  | 2023-08-01 | 63 | 2023-08-01 | 218 | 2023-08-01 | 212 | 2023-08-01 | 4 | 2023-08-01 | 195 | 2023-08-01 | 3 | 2023-08-01 | 198
|  | 2023-09-01 | 26 | 2023-09-01 | 172 | 2023-09-01 | 190 | 2023-09-01 | 3 | 2023-09-01 | 158 | 2023-09-01 | 0 | 2023-09-01 | 158
|  | 2023-10-01 | 43 | 2023-10-01 | 15 | 2023-10-01 | 43 | 2023-10-01 | 13 | 2023-10-01 | 15 | 2023-10-01 | 0 | 2023-10-01 | 15
|  | 2023-11-01 | 21 | 2023-11-01 | 74 | 2023-11-01 | 92 | 2023-11-01 | 5 | 2023-11-01 | 75 | 2023-11-01 | 1 | 2023-11-01 | 76
|  | 2023-12-01 | 71 | 2023-12-01 | 356 | 2023-12-01 | 67 | 2023-12-01 | 338 | 2023-12-01 | 64 | 2023-12-01 | 334 | 2023-12-01 | 398
|  | Total | 317 | Total | 1003 | Total | 783 | Total | 400 | Total | 643 | Total | 338 | Total | 1008
|  | Total Maximo PR Created in AJ |  | Total Maximo PR Created in BU |  | Total Fabrication PR Created in AJ |  | Total Fabrication PR Created in BU |  | Total Subcon PR Created in AJ |  | Total Subcon PR Created in BU |  | Total PO Received
|  | 2023-01-01 | 57 | 2023-01-01 | 0 | 2023-01-01 | 1 | 2023-01-01 | 0 | 2023-01-01 | 5 | 2023-01-01 | 2 | 2023-01-01 | 64
|  | 2023-02-01 | 1 | 2023-02-01 | 0 | 2023-02-01 | 0 | 2023-02-01 | 0 | 2023-02-01 | 1 | 2023-02-01 | 3 | 2023-02-01 | 21
|  | 2023-03-01 | 21 | 2023-03-01 | 0 | 2023-03-01 | 2 | 2023-03-01 | 0 | 2023-03-01 | 3 | 2023-03-01 | 7 | 2023-03-01 | 33
|  | 2023-04-01 | 32 | 2023-04-01 | 0 | 2023-04-01 | 2 | 2023-04-01 | 0 | 2023-04-01 | 9 | 2023-04-01 | 6 | 2023-04-01 | 49
|  | 2023-05-01 | 19 | 2023-05-01 | 0 | 2023-05-01 | 1 | 2023-05-01 | 0 | 2023-05-01 | 13 | 2023-05-01 | 11 | 2023-05-01 | 59
|  | 2023-06-01 | 3 | 2023-06-01 | 0 | 2023-06-01 | 1 | 2023-06-01 | 0 | 2023-06-01 | 2 | 2023-06-01 | 5 | 2023-06-01 | 11
|  | 2023-07-01 | 4 | 2023-07-01 | 0 | 2023-07-01 | 1 | 2023-07-01 | 0 | 2023-07-01 | 1 | 2023-07-01 | 3 | 2023-07-01 | 9
|  | 2023-08-01 | 211 | 2023-08-01 | 3 | 2023-08-01 | 0 | 2023-08-01 | 0 | 2023-08-01 | 1 | 2023-08-01 | 1 | 2023-08-01 | 220
|  | 2023-09-01 | 171 | 2023-09-01 | 1 | 2023-09-01 | 2 | 2023-09-01 | 0 | 2023-09-01 | 17 | 2023-09-01 | 2 | 2023-09-01 | 193
|  | 2023-10-01 | 15 | 2023-10-01 | 0 | 2023-10-01 | 1 | 2023-10-01 | 0 | 2023-10-01 | 27 | 2023-10-01 | 13 | 2023-10-01 | 56
|  | 2023-11-01 | 73 | 2023-11-01 | 1 | 2023-11-01 | 9 | 2023-11-01 | 0 | 2023-11-01 | 10 | 2023-11-01 | 4 | 2023-11-01 | 97
|  | 2023-12-01 | 34 | 2023-12-01 | 322 | 2023-12-01 | 7 | 2023-12-01 | 5 | 2023-12-01 | 26 | 2023-12-01 | 11 | 2023-12-01 | 384
|  | Total | 641 | Total | 327 | Total | 27 | Total | 5 | Total | 115 | Total | 68 | Total | 1196
AL BAYADER INTER.GROUP COMPANY |  | AL-IRTEKAZ NATIONAL GEN.TRDG.C |  | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO |  | CARRIER KUWAIT AIR CONDITIONING |  | COMMERCIAL UNITED GINCO EST. |  | CREDENCE TRADING EST. |  | EMCOR INTERNATIONAL GENERAL TRADING CO WLL |  | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST |  | GULF PIONEER COMPANY LLC |  | AL NISF ELECTRICAL CO WLL
2023-01-01 | 0 | 2023-01-01 | 0 | 2023-01-01 | 0 | 2023-01-01 | 0 | 2023-01-01 | 0 | 2023-01-01 | 0 | 2023-01-01 | 0 | 2023-01-01 | 0 | 2023-01-01 | 0 | 2023-01-01 | 0
2023-02-01 | 0 | 2023-02-01 | 0 | 2023-02-01 | 0 | 2023-02-01 | 0 | 2023-02-01 | 0 | 2023-02-01 | 0 | 2023-02-01 | 0 | 2023-02-01 | 0 | 2023-02-01 | 0 | 2023-02-01 | 0
2023-03-01 | 0 | 2023-03-01 | 0 | 2023-03-01 | 0 | 2023-03-01 | 0 | 2023-03-01 | 0 | 2023-03-01 | 0 | 2023-03-01 | 0 | 2023-03-01 | 0 | 2023-03-01 | 0 | 2023-03-01 | 0
2023-04-01 | 0 | 2023-04-01 | 0 | 2023-04-01 | 0 | 2023-04-01 | 0 | 2023-04-01 | 0 | 2023-04-01 | 0 | 2023-04-01 | 0 | 2023-04-01 | 6 | 2023-04-01 | 0 | 2023-04-01 | 0
2023-05-01 | 0 | 2023-05-01 | 0 | 2023-05-01 | 0 | 2023-05-01 | 0 | 2023-05-01 | 1 | 2023-05-01 | 0 | 2023-05-01 | 0 | 2023-05-01 | 5 | 2023-05-01 | 0 | 2023-05-01 | 0
2023-06-01 | 0 | 2023-06-01 | 0 | 2023-06-01 | 0 | 2023-06-01 | 0 | 2023-06-01 | 1 | 2023-06-01 | 0 | 2023-06-01 | 0 | 2023-06-01 | 0 | 2023-06-01 | 0 | 2023-06-01 | 0
2023-07-01 | 0 | 2023-07-01 | 0 | 2023-07-01 | 0 | 2023-07-01 | 0 | 2023-07-01 | 0 | 2023-07-01 | 0 | 2023-07-01 | 0 | 2023-07-01 | 1 | 2023-07-01 | 0 | 2023-07-01 | 0
2023-08-01 | 2 | 2023-08-01 | 0 | 2023-08-01 | 2 | 2023-08-01 | 0 | 2023-08-01 | 17 | 2023-08-01 | 22 | 2023-08-01 | 0 | 2023-08-01 | 4 | 2023-08-01 | 0 | 2023-08-01 | 0
2023-09-01 | 2 | 2023-09-01 | 4 | 2023-09-01 | 0 | 2023-09-01 | 1 | 2023-09-01 | 4 | 2023-09-01 | 6 | 2023-09-01 | 3 | 2023-09-01 | 14 | 2023-09-01 | 0 | 2023-09-01 | 0
2023-10-01 | 1 | 2023-10-01 | 0 | 2023-10-01 | 4 | 2023-10-01 | 0 | 2023-10-01 | 0 | 2023-10-01 | 3 | 2023-10-01 | 0 | 2023-10-01 | 2 | 2023-10-01 | 0 | 2023-10-01 | 0
2023-11-01 | 0 | 2023-11-01 | 0 | 2023-11-01 | 2 | 2023-11-01 | 0 | 2023-11-01 | 0 | 2023-11-01 | 0 | 2023-11-01 | 0 | 2023-11-01 | 2 | 2023-11-01 | 0 | 2023-11-01 | 4
2023-12-01 | 0 | 2023-12-01 | 0 | 2023-12-01 | 0 | 2023-12-01 | 0 | 2023-12-01 | 4 | 2023-12-01 | 0 | 2023-12-01 | 2 | 2023-12-01 | 4 | 2023-12-01 | 5 | 2023-12-01 | 5
Total | 5 | Total | 4 | Total | 8 | Total | 1 | Total | 27 | Total | 31 | Total | 5 | Total | 38 | Total | 5 | Total | 9
KASAR MARJAN CONTRACTING CO. |  | MARATHON INC TRADING LLC |  | MERIT INTERNATIONAL GENERAL TRADING CO WLL |  | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL |  | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO |  | RITAJ AL KUWAIT GENERAL TRADING CONTRACTING CO |  | TRADEX INTERNATIONAL TRADING LLC |  | UNITEC INTERNATIONAL GENERAL TRADING CO |  | MERIT INTERNATIONAL INC |  | EGYKUW
2023-01-01 | 0 | 2023-01-01 | 0 | 2023-01-01 | 0 | 2023-01-01 | 0 | 2023-01-01 | 0 | 2023-01-01 | 0 | 2023-01-01 | 0 | 2023-01-01 | 0 | 2023-01-01 | 0 | 2023-01-01 | 0
2023-02-01 | 0 | 2023-02-01 | 0 | 2023-02-01 | 11 | 2023-02-01 | 0 | 2023-02-01 | 0 | 2023-02-01 | 0 | 2023-02-01 | 0 | 2023-02-01 | 5 | 2023-02-01 | 0 | 2023-02-01 | 0
2023-03-01 | 0 | 2023-03-01 | 0 | 2023-03-01 | 18 | 2023-03-01 | 0 | 2023-03-01 | 0 | 2023-03-01 | 0 | 2023-03-01 | 0 | 2023-03-01 | 1 | 2023-03-01 | 1 | 2023-03-01 | 0
2023-04-01 | 0 | 2023-04-01 | 0 | 2023-04-01 | 0 | 2023-04-01 | 0 | 2023-04-01 | 0 | 2023-04-01 | 0 | 2023-04-01 | 0 | 2023-04-01 | 25 | 2023-04-01 | 0 | 2023-04-01 | 0
2023-05-01 | 0 | 2023-05-01 | 0 | 2023-05-01 | 24 | 2023-05-01 | 0 | 2023-05-01 | 0 | 2023-05-01 | 0 | 2023-05-01 | 0 | 2023-05-01 | 2 | 2023-05-01 | 0 | 2023-05-01 | 0
2023-06-01 | 0 | 2023-06-01 | 0 | 2023-06-01 | 0 | 2023-06-01 | 0 | 2023-06-01 | 0 | 2023-06-01 | 0 | 2023-06-01 | 0 | 2023-06-01 | 0 | 2023-06-01 | 0 | 2023-06-01 | 0
2023-07-01 | 0 | 2023-07-01 | 0 | 2023-07-01 | 0 | 2023-07-01 | 0 | 2023-07-01 | 0 | 2023-07-01 | 0 | 2023-07-01 | 0 | 2023-07-01 | 2 | 2023-07-01 | 0 | 2023-07-01 | 0
2023-08-01 | 8 | 2023-08-01 | 0 | 2023-08-01 | 114 | 2023-08-01 | 0 | 2023-08-01 | 0 | 2023-08-01 | 0 | 2023-08-01 | 0 | 2023-08-01 | 24 | 2023-08-01 | 0 | 2023-08-01 | 0
2023-09-01 | 0 | 2023-09-01 | 0 | 2023-09-01 | 41 | 2023-09-01 | 11 | 2023-09-01 | 6 | 2023-09-01 | 3 | 2023-09-01 | 0 | 2023-09-01 | 24 | 2023-09-01 | 0 | 2023-09-01 | 0
2023-10-01 | 0 | 2023-10-01 | 0 | 2023-10-01 | 4 | 2023-10-01 | 0 | 2023-10-01 | 0 | 2023-10-01 | 0 | 2023-10-01 | 0 | 2023-10-01 | 1 | 2023-10-01 | 0 | 2023-10-01 | 0
2023-11-01 | 0 | 2023-11-01 | 3 | 2023-11-01 | 16 | 2023-11-01 | 0 | 2023-11-01 | 5 | 2023-11-01 | 0 | 2023-11-01 | 1 | 2023-11-01 | 39 | 2023-11-01 | 0 | 2023-11-01 | 0
2023-12-01 | 0 | 2023-12-01 | 5 | 2023-12-01 | 244 | 2023-12-01 | 0 | 2023-12-01 | 6 | 2023-12-01 | 0 | 2023-12-01 | 2 | 2023-12-01 | 83 | 2023-12-01 | 0 | 2023-12-01 | 3
Total | 8 | Total | 8 | Total | 472 | Total | 11 | Total | 17 | Total | 3 | Total | 3 | Total | 206 | Total | 1 | Total | 3
Schneider
[8 empty] | 2023-01-01 | 0
[8 empty] | 2023-02-01 | 0
[8 empty] | 2023-03-01 | 0
[8 empty] | 2023-04-01 | 0
[8 empty] | 2023-05-01 | 0
[8 empty] | 2023-06-01 | 0
[8 empty] | 2023-07-01 | 0
[8 empty] | 2023-08-01 | 0
[8 empty] | 2023-09-01 | 0
[8 empty] | 2023-10-01 | 0
[8 empty] | 2023-11-01 | 0
[8 empty] | 2023-12-01 | 4
[8 empty] | Total | 4
|  | Total BOM Received PROJECT |  | Total Maximo PR Created in ALL |  | Total PR Created in AJ |  | Total PR Created in BU |  | Total Project material received in AJ |  | Total Project material received in BU |  | Total Project material received For ALL
|  | 2024-01-01 | 44 | 2024-01-01 | 416 | 2024-01-01 | 21 | 2024-01-01 | 427 | 2024-01-01 | 21 | 2024-01-01 | 402 | 2024-01-01 | 424
|  | 2024-02-01 | 53 | 2024-02-01 | 456 | 2024-02-01 | 20 | 2024-02-01 | 474 | 2024-02-01 | 19 | 2024-02-01 | 384 | 2024-02-01 | 403
|  | 2024-03-01 | 17 | 2024-03-01 | 110 | 2024-03-01 | 4 | 2024-03-01 | 117 | 2024-03-01 | 4 | 2024-03-01 | 22 | 2024-03-01 | 26
|  | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0
|  | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0
|  | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0
|  | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0
|  | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0
|  | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0
|  | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0
|  | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0
|  | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0
|  | Total | 114 | Total | 982 | Total | 45 | Total | 1018 | Total | 44 | Total | 808 | Total | 853
|  | Total Maximo PR Created in AJ |  | Total Maximo PR Created in BU |  | Total Fabrication PR Created in AJ |  | Total Fabrication PR Created in BU |  | Total Subcon PR Created in AJ |  | Total Subcon PR Created in BU |  | Total PO Received
|  | 2024-01-01 | 0 | 2024-01-01 | 416 | 2024-01-01 | 1 | 2024-01-01 | 10 | 2024-01-01 | 20 | 2024-01-01 | 1 | 2024-01-01 | 431
|  | 2024-02-01 | 0 | 2024-02-01 | 456 | 2024-02-01 | 1 | 2024-02-01 | 16 | 2024-02-01 | 19 | 2024-02-01 | 2 | 2024-02-01 | 606
|  | 2024-03-01 | 0 | 2024-03-01 | 110 | 2024-03-01 | 0 | 2024-03-01 | 1 | 2024-03-01 | 4 | 2024-03-01 | 6 | 2024-03-01 | 112
|  | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0
|  | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0
|  | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0
|  | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0
|  | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0
|  | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0
|  | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0
|  | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0
|  | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0
|  | Total | 0 | Total | 982 | Total | 2 | Total | 27 | Total | 43 | Total | 9 | Total | 1149
AL BAYADER INTER.GROUP COMPANY |  | AL-IRTEKAZ NATIONAL GEN.TRDG.C |  | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO |  | CARRIER KUWAIT AIR CONDITIONING |  | COMMERCIAL UNITED GINCO EST. |  | CREDENCE TRADING EST. |  | EMCOR INTERNATIONAL GENERAL TRADING CO WLL |  | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST |  | GULF PIONEER COMPANY LLC |  | AL NISF ELECTRICAL CO WLL
2024-01-01 | 4 | 2024-01-01 | 0 | 2024-01-01 | 0 | 2024-01-01 | 1 | 2024-01-01 | 1 | 2024-01-01 | 4 | 2024-01-01 | 27 | 2024-01-01 | 37 | 2024-01-01 | 2 | 2023-01-01 | 4
2024-02-01 | 26 | 2024-02-01 | 1 | 2024-02-01 | 4 | 2024-02-01 | 0 | 2024-02-01 | 8 | 2024-02-01 | 33 | 2024-02-01 | 2 | 2024-02-01 | 0 | 2024-02-01 | 0 | 2023-02-01 | 0
2024-03-01 | 0 | 2024-03-01 | 0 | 2024-03-01 | 0 | 2024-03-01 | 0 | 2024-03-01 | 0 | 2024-03-01 | 0 | 2024-03-01 | 0 | 2024-03-01 | 0 | 2024-03-01 | 0 | 2023-03-01 | 0
2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2023-04-01 | 0
2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2023-05-01 | 0
2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2023-06-01 | 0
2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2023-07-01 | 0
2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2023-08-01 | 0
2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2023-09-01 | 0
2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2023-10-01 | 0
2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2023-11-01 | 0
2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2023-12-01 | 0
Total | 30 | Total | 1 | Total | 4 | Total | 1 | Total | 9 | Total | 37 | Total | 29 | Total | 37 | Total | 2 | Total | 4
KASAR MARJAN CONTRACTING CO. |  | MARATHON INC TRADING LLC |  | MERIT INTERNATIONAL GENERAL TRADING CO WLL |  | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL |  | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO |  | RITAJ AL KUWAIT GENERAL TRADING CONTRACTING CO |  | TRADEX INTERNATIONAL TRADING LLC |  | UNITEC INTERNATIONAL GENERAL TRADING CO |  | MERIT INTERNATIONAL INC |  | EGYKUW
2024-01-01 | 0 | 2024-01-01 | 14 | 2024-01-01 | 135 | 2024-01-01 | 0 | 2024-01-01 | 70 | 2024-01-01 | 0 | 2024-01-01 | 4 | 2024-01-01 | 113 | 2024-01-01 | 0 | 2023-01-01 | 0
2024-02-01 | 0 | 2024-02-01 | 13 | 2024-02-01 | 146 | 2024-02-01 | 0 | 2024-02-01 | 75 | 2024-02-01 | 0 | 2024-02-01 | 4 | 2024-02-01 | 126 | 2024-02-01 | 0 | 2023-02-01 | 0
2024-03-01 | 0 | 2024-03-01 | 4 | 2024-03-01 | 28 | 2024-03-01 | 0 | 2024-03-01 | 0 | 2024-03-01 | 0 | 2024-03-01 | 2 | 2024-03-01 | 22 | 2024-03-01 | 0 | 2023-03-01 | 0
2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2024-04-01 | 0 | 2023-04-01 | 0
2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2024-05-01 | 0 | 2023-05-01 | 0
2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2024-06-01 | 0 | 2023-06-01 | 0
2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2024-07-01 | 0 | 2023-07-01 | 0
2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2024-08-01 | 0 | 2023-08-01 | 0
2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2024-09-01 | 0 | 2023-09-01 | 0
2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2024-10-01 | 0 | 2023-10-01 | 0
2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2024-11-01 | 0 | 2023-11-01 | 0
2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2024-12-01 | 0 | 2023-12-01 | 0
Total | 0 | Total | 31 | Total | 309 | Total | 0 | Total | 145 | Total | 0 | Total | 10 | Total | 261 | Total | 0 | Total | 0
Dashboard
Investment
TOTAL COST
397
TOTAL PROJECTS
$5,243,966
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Total Maximo PR
Total Fabrication PR
Total Subcon PR
2160
85
281
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Total BOM Received
398
Total BOM received AJ
235
Total BOM received BU
159
Total Maximo PR created in AJ
815
Total Maximo PR created in BU
1310
Total Fabrication PR created in AJ
53
Total Fabrication PR created in BU
32
Total subcon PR created in AJ
195
Total subcon PR created in BU
85
Dashboard for 2023
Total PO Received per Month 2023, for Each Vendor
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.
Total received project AJ Based on the project number
235
Total received project BU Based on the project number
159
Dashboard for 2024
Total PO Received per Month 2024, for Each Vendor
Timeline: Works in Excel 2013 or higher. Do not move or resize.
Timeline: Works in Excel 2013 or higher. Do not move or resize.

## total cost (hidden)
Sum of Ext. Cost (Line Cost)
5243966.48

## Total Pjt (hidden)
Total Project
|  | 399 | 397
Row Labels | Count of PROJECT#
AJ22-0152 | 242 | 1
AJ22-0135 | 235
AJ23-0789 | 126
AJ23-0508 | 117
BU24-0059 | 105
BU-24-0098 | 84
BU23-0193 | 69
AJ23-0467 | 66
BU23-241 | 65
BU23-270 | 64
BU24-0051 | 54
BU24-0050 | 54
BU23-0226 | 46
BU24-0117 | 42
BU24-0118 | 39
BU24-0086 | 39
BU24-0072 | 36
BU24-0174 | 34
BU24-0058 | 34
AJ23-0708 | 32
BU24-0085 | 30
AJ23-0747 | 27
BU24-0132 | 26
BU24-0005 | 26
AJ23-0122 | 26
BU23-0366 | 24
BU24-0071 | 23
BU24-0139 | 22
BU23-276 | 21
AJ22-0136 | 21
BU24-0141 | 20
BU240110 | 20
BU24-0160 | 18
UCO-P0045 | 17
BU24-0171 | 16
BU24-0151 | 16
BU24-0173 | 16
BU24-0040 | 16
BU24-0170 | 15
BU24-0168 | 15
BU24-0169 | 15
UCO23-0003 | 14
BU23-0332 | 13
BU24-0148 | 13
BU24-0022 | 13
BU24-0066 | 13
BU24-0019 | 12
BU24-0023 | 12
BU24-0020 | 11
BU24-0014 | 11
BU24-0089 | 11
BU23-0371 | 11
BU24-0021 | 11
BU24-0144 | 9
BU24-0092 | 9
BU24-0103 | 9
BU24-0119 | 7
BU24-0175 | 7
BU24-0172 | 7
BU24-0098 | 7
BU24-0028 | 6
BU24-0107 | 6
BU24-0087 | 6
BU24-0143 | 6
BU24-0015 | 5
BU24-0097 | 5
AJ23-0260 | 4
BU24-0018 | 4
AJ21-0038 | 4
AJ22-0105 | 4
AJ22-0145 | 4
AJ22-0322 | 3
BU24-0048 | 3
BU24-0179 | 3
AJ22-0551 | 3
AJ23-0079 | 3
BU24-0112 | 3
AJ22-0326 | 3
BU24-0167 | 3
AJ23-0004 | 2
AJ22-0081 | 2
AJ22-0189 | 2
AJ23-0172 | 2
AJ22-0536 | 2
AJ23-0179 | 2
AJ22-0390 | 2
AJ23-0193 | 2
AJ21-0011 | 2
AJ23-0225 | 2
AJ22-0123 | 2
AJ23-0258 | 2
BU24-0147 | 2
AJ22-0547 | 2
AJ22-0184 | 2
AJ23-0268 | 2
AJ22-0400 | 2
AJ23-0300 | 2
BU24-0096 | 2
AJ23-0450 | 2
AJ22-0407 | 2
AJ23-0482 | 2
AJ23-0007 | 2
AJ23-0493 | 2
BU24-0081 | 2
AJ23-0512 | 2
AJ22-0198 | 2
AJ23-0536 | 2
AJ22-0497 | 2
AJ23-0574 | 2
AJ22-0371 | 2
AJ23-0579 | 2
AJ22-0380 | 2
AJ23-0598 | 2
AJ23-0005 | 2
AJ22-0240 | 2
AJ22-0406 | 2
AJ22-0549 | 2
BU24-0095 | 2
BU22-039 | 2
AJ22-0073 | 2
BU22-048 | 2
BU22-0007 | 2
BU22-069 | 2
AJ22-0417 | 2
AJ22-0534 | 2
AJ23-0006 | 2
AJ22-0205 | 2
AJ23-0040 | 2
BU24-0165 | 2
AJ22-0465 | 2
AJ22-0524 | 2
AJ23-0068 | 2
BU23-0264 | 2
AJ22-0475 | 2
BU23-0353 | 2
AJ23-0101 | 2
AJ22-0323 | 2
AJ22-0004 | 2
BU23-0372 | 2
AJ23-0166 | 2
AJ22-0324 | 2
BU23-0143 | 2
AJ22-0222 | 2
AJ22-0149 | 2
BU23-223 | 2
AJ23-0668 | 2
AJ22-0044 | 2
BU23-0166 | 2
AJ23-0726 | 1
BU23-0031 | 1
AJ23-0471 | 1
AJ22-0325 | 1
AJ23-0676 | 1
AJ23-0499 | 1
BU23-0373 | 1
AJ23-0502 | 1
AJ23-0701 | 1
AJ22-0042 | 1
AJ23-0620 | 1
AJ22-0468 | 1
AJ23-0192 | 1
AJ23-0532 | 1
AJ23-0237 | 1
AJ22-0474 | 1
AJ22-0409 | 1
AJ23-0540 | 1
BU24-0140 | 1
AJ23-0563 | 1
AJ24-0022 | 1
AJ22-0248 | 1
AJ23-0238 | 1
AJ22-0327 | 1
AJ22-0021 | 1
AJ22-0505 | 1
BU24-0027 | 1
AJ23-0619 | 1
AJ23-0611 | 1
AJ23-0645 | 1
BU23-0357 | 1
AJ22-0507 | 1
AJ23-0243 | 1
AJ22-0331 | 1
AJ22-0321 | 1
AJ23-0782 | 1
AJ23-0420 | 1
BU22-0028 | 1
AJ23-0699 | 1
BU22-0031 | 1
AJ23-0566 | 1
BU22-0045 | 1
AJ22-0258 | 1
BU22-0055 | 1
AJ22-0143, | 1
BU22-0066 | 1
AJ23-0751 | 1
BU22-0105 | 1
AJ23-0425 | 1
BU22-0105 | 1
AJ22-0218 | 1
BU22-0109 | 1
AJ23-0510 | 1
BU22-0110 | 1
AJ22-0168 | 1
BU22-027 | 1
BU24-0064 | 1
BU22-031 | 1
AJ23-0492 | 1
BU22-032 | 1
AJ23-0788 | 1
BU22-036 | 1
AJ23-0468 | 1
BU22-038 | 1
AJ22-0399 | 1
AJ22-0530 | 1
AJ24-0065 | 1
BU22-041 | 1
AJ23-0666 | 1
BU22-045 | 1
AJ23-0245 | 1
BU22-047 | 1
AJ23-0667 | 1
AJ22-0332 | 1
AJ23-0750 | 1
BU22-049 | 1
AJ23-0474 | 1
BU22-057 | 1
BU23-0310 | 1
BU22-062 | 1
AJ24-0170 | 1
BU22-064 | 1
AJ22-0139 | 1
BU22-065 | 1
AJ23-0584 | 1
BU22-066 | 1
AJ21-0097 | 1
BU22-066 | 1
AJ24-0202 | 1
AJ22-0333 | 1
AJ23-0337 | 1
BU22-070 | 1
BU23-0275 | 1
AJ22-0537 | 1
AJ23-0250 | 1
AJ23-0551 | 1
AJ24‐0009 | 1
AJ22-0046 | 1
AJ22-0146 | 1
BU24-0006 | 1
AJ22-0147 | 1
AJ20-0135 | 1
AJ23-0437 | 1
BU23-0094 | 1
AJ22-0241 | 1
BU23-0094 | 1
AJ23-0481 | 1
BU23-0102 | 1
AJ23-0610 | 1
BU23-0111 | 1
BU23-0160 | 1
BU23-0123 | 1
BU23-0208 | 1
BU23-0124 | 1
AJ22-0393 | 1
AJ22-0546 | 1
AJ22-0074 | 1
AJ22-0334 | 1
AJ23-0593 | 1
AJ22-0232 | 1
AJ23-0240 | 1
BU24-0177 | 1
AJ22-0120 | 1
AJ22-0335 | 1
BU24-0093 | 1
AJ23-0494 | 1
AJ23-0496 | 1
AJ23-0254 | 1
AJ23-0469 | 1
AJ23-0439 | 1
AJ22-0394 | 1
AJ23-0767 | 1
AJ22-0106 | 1
AJ23-0382 | 1
AJ23-0241 | 1
AJ22-0156 | 1
AJ23-0242 | 1
BU20-0026B | 1
AJ21-0002 | 1
AJ22-0336 | 1
AJ23-0470 | 1
BU23-0279 | 1
BU23-0338 | 1
BU23-0281 | 1
AJ23-0723 | 1
BU23-029 | 1
AJ22-0236 | 1
BU23-030 | 1
AJ22-0235 | 1
BU23-0306 | 1
AJ23-0472 | 1
BU23-0314 | 1
AJ23-0475 | 1
BU23-032 | 1
AJ23-0473 | 1
AJ22-0177 | 1
BU23-0352 | 1
BU23-0350 | 1
AJ22-0137 | 1
BU23-0351 | 1
AJ23-0306 | 1
BU23-0353 | 1
AJ23-0229 | 1
AJ22-0351 | 1
AJ22-0138 | 1
AJ22-0352 | 1
AJ22-0179 | 1
AJ22-0353 | 1
AJ22-0140 | 1
BU23-249 | 1
AJ23-0423 | 1
AJ22-0354 | 1
AJ22-0141 | 1
AJ22-0359 | 1
BU23-0368 | 1
AJ23-0045 | 1
AJ22-0266 | 1
AJ22-0265 | 1
AJ22-0142 | 1
AJ22-0378 | 1
AJ23-0093 | 1
AJ23-0089 | 1
AJ22-0300 | 1
AJ23-0090 | 1
AJ22-0143 | 1
AJ22-0379 | 1
AJ23-0366 | 1
AJ22-0297 | 1
BU23-0083 | 1
AJ23-0132 | 1
BU23-0082 | 1
AJ22-0190 | 1
AJ23-0219 | 1
AJ23-0365 | 1
AJ23-0143 | 1
AJ22-0067 | 1
AJ23-0413 | 1
BU23-0375 | 1
AJ23-0740 | 1
AJ23-0252 | 1
AJ22-0199 | 1
BU24-0073 | 1
AJ24-0203 | 1
AJ23-0133 | 1
BU24-0076 | 1
AJ23-0134 | 1
AJ23-0247 | 1
AJ22-0317 | 1
AJ23-0442 | 1
AJ23-0167 | 1
AJ23-0376 | 1
AJ22-0392 | 1
AJ22-0231 | 1
AJ22-0110 | 1
AJ23-0467 | 1
AJ23-0606 | 1
AJ22-0455 | 1
AJ22-0267 | 1
AJ22-0233 | 1
BU23-0175 | 1
BU23-0221 | 1
BU23-0182 | 1
AJ23-0378 | 1
AJ22-0175 | 1
AJ21-0051 | 1
AJ22-0176 | 1
AJ21-0177 | 1
AJ22-0055 | 1
AJ24-0050 | 1
BU23-0205 | 1
AJ23-0380 | 1
BU23-0206 | 1
BU24-0060 | 1
BU23-0232 | 1
BU20-0026A | 1
BU23-0233 | 1
AJ22-0234 | 1
BU23-0262 | 1
BU23-0183 | 1
AJ22-0174 | 1
BU23-0192 | 1
BU22-089 | 1
BU24-0012 | 1
BU22-120 | 1
BU24-0129 | 1
BU23-0023 | 1
BU23-0379 | 1
BU23-0029 | 1
BU23-0077 | 1
(blank)
Grand Total | 2678
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## com_pjt (hidden)
count delivery
258
Row Labels | Count of Delivery Status |  |  | Completed | 255
AJ20-0135 |  |  |  | Incompleted | 142
AJ21-0002 |  | 1
AJ21-0038 | 1
AJ21-0177 | 1
AJ22-0004 | 1
AJ22-0021 |  | total comp | count
AJ22-0042 |  | 5 | 1
AJ22-0044 | 2
AJ22-0046
AJ22-0055
AJ22-0067 | 1
AJ22-0073 | 1
AJ22-0074 | 1
AJ22-0081 | 2
AJ22-0105
AJ22-0106
AJ22-0123 | 1
AJ22-0135 | 231
AJ22-0136 | 21
AJ22-0137 | 1
AJ22-0138 | 1
AJ22-0139 | 1
AJ22-0140 | 1
AJ22-0141 | 1
AJ22-0142 | 1
AJ22-0143 | 1
AJ22-0143,
AJ22-0145
AJ22-0146
AJ22-0147
AJ22-0149 | 1
AJ22-0152 | 242
AJ22-0156
AJ22-0174
AJ22-0175
AJ22-0176
AJ22-0177
AJ22-0184 | 1
AJ22-0189 | 2
AJ22-0190 | 1
AJ22-0198 | 1
AJ22-0199
AJ22-0205 | 1
AJ22-0218
AJ22-0222 | 1
AJ22-0231
AJ22-0232
AJ22-0233
AJ22-0234
AJ22-0235
AJ22-0236
AJ22-0240 | 1
AJ22-0241
AJ22-0248
AJ22-0265 | 1
AJ22-0297
AJ22-0317
AJ22-0321
AJ22-0322 | 1
AJ22-0323 | 1
AJ22-0324
AJ22-0325
AJ22-0326 | 1
AJ22-0327
AJ22-0331
AJ22-0332
AJ22-0333
AJ22-0334
AJ22-0335
AJ22-0336
AJ22-0351
AJ22-0352
AJ22-0353
AJ22-0354
AJ22-0359
AJ22-0371 | 2
AJ22-0378
AJ22-0379
AJ22-0380 | 1
AJ22-0390 | 1
AJ22-0392
AJ22-0393
AJ22-0394
AJ22-0399
AJ22-0400 | 1
AJ22-0406 | 1
AJ22-0407
AJ22-0409
AJ22-0417 | 1
AJ22-0455 | 1
AJ22-0465 | 2
AJ22-0468
AJ22-0474
AJ22-0475 | 2
AJ22-0497 | 1
AJ22-0505
AJ22-0507
AJ22-0524 | 1
AJ22-0530 | 1
AJ22-0534
AJ22-0536 | 1
AJ22-0537
AJ22-0546
AJ22-0547 | 1
AJ22-0549 | 1
AJ22-0551
AJ23-0004 | 1
AJ23-0005 | 1
AJ23-0006 | 1
AJ23-0007 | 1
AJ23-0040 | 2
AJ23-0045
AJ23-0068 | 1
AJ23-0079 | 2
AJ23-0089
AJ23-0090
AJ23-0101 | 1
AJ23-0122 | 25
AJ23-0132
AJ23-0133
AJ23-0134
AJ23-0166 | 1
AJ23-0167
AJ23-0172 | 1
AJ23-0179 | 1
AJ23-0192
AJ23-0193 | 1
AJ23-0225 | 1
AJ23-0237 | 1
AJ23-0241 | 1
AJ23-0242 | 1
AJ23-0243 | 1
AJ23-0245
AJ23-0258 | 1
AJ23-0260 | 3
AJ23-0268 | 1
AJ23-0300 | 1
AJ23-0306
AJ23-0337 | 1
AJ23-0366
AJ23-0413
AJ23-0425
AJ23-0437
AJ23-0442
AJ23-0450 | 2
AJ23-0467 | 63
AJ23-0467 | 1
AJ23-0481
AJ23-0482 | 1
AJ23-0493 | 1
AJ23-0499 | 1
AJ23-0502 | 1
AJ23-0508 | 115
AJ23-0512 | 2
AJ23-0532
AJ23-0536 | 1
AJ23-0540 | 1
AJ23-0563 | 1
AJ23-0574 | 1
AJ23-0579 | 1
AJ23-0598 | 1
AJ23-0619 | 1
AJ23-0645 | 1
AJ23-0668 | 1
AJ23-0708 | 32
AJ23-0782 | 1
BU22-0028
BU22-0031
BU22-0045
BU22-0055
BU22-0066
BU22-0105
BU22-0105
BU22-0109
BU22-0110
BU22-027
BU22-031
BU22-032
BU22-036
BU22-038
BU22-039
BU22-041
BU22-045
BU22-047
BU22-048
BU22-049
BU22-057
BU22-062
BU22-064
BU22-065
BU22-066
BU22-066
BU22-069
BU22-070
BU22-089
BU22-120
BU23-0023
BU23-0029
BU23-0077
BU23-0094
BU23-0094
BU23-0102
BU23-0111
BU23-0123
BU23-0124
BU23-0143
BU23-0166
BU23-0175
BU23-0182
BU23-0183
BU23-0192
BU23-0193 | 68
BU23-0205 | 1
BU23-0206
BU23-0232
BU23-0233
BU23-0262
BU23-0264 | 2
BU23-0279
BU23-0281
BU23-029
BU23-030
BU23-0306
BU23-0314 | 1
BU23-032
BU23-0332 | 13
BU23-0350
BU23-0351
BU23-0353
BU23-0353 | 1
BU23-0371 | 11
BU23-0372 | 1
BU23-249 | 1
BU24-0014 | 11
BU24-0020 | 11
BU24-0021 | 11
BU24-0022 | 13
BU24-0087 | 6
BU24-0089 | 11
BU24-0097 | 5
BU24-0098 | 7
BU24-0107 | 6
UCO23-0003 | 14
UCO-P0045 | 17
(blank) | 5
AJ23-0365 | 1
AJ23-0747 | 27
BU23-0375 | 1
AJ23-0252 | 1
BU24-0073 | 1
BU24-0095 | 2
BU24-0096 | 2
BU23-0366 | 24
AJ21-0011
BU22-0007
AJ22-0110 | 1
AJ23-0606 | 1
AJ22-0267 | 1
AJ23-0510 | 1
AJ23-0610 | 1
AJ23-0676 | 1
BU23-0160 | 1
AJ22-0168 | 1
BU23-0208 | 1
BU24-0027 | 1
BU24-0092 | 9
BU24-0064 | 1
BU240110 | 20
BU24-0119 | 7
AJ23-0593 | 1
AJ23-0492 | 1
AJ23-0240 | 1
AJ23-0611 | 1
AJ22-0120 | 1
AJ23-0788 | 1
BU24-0093 | 1
AJ23-0726 | 1
AJ23-0496 | 1
AJ23-0468 | 1
AJ23-0469 | 1
BU23-0357 | 1
BU-24-0098 | 84
BU24-0086 | 39
BU24-0085 | 30
BU24-0112 | 3
BU24-0018 | 4
AJ24-0065 | 1
BU23-276 | 21
BU24-0103 | 9
BU24-0005 | 26
AJ23-0666 | 1
AJ23-0470 | 1
BU23-0373 | 1
BU23-0338 | 1
BU24-0081 | 2
AJ23-0723 | 1
BU24-0015 | 5
BU24-0117 | 42
AJ23-0667 | 1
BU24-0028 | 6
BU24-0066 | 13
AJ23-0472 | 1
AJ23-0750 | 1
AJ23-0475 | 1
AJ23-0420 | 1
AJ23-0473 | 1
AJ23-0474 | 1
BU23-0352 | 1
AJ23-0471 | 1
BU24-0132 | 26
BU23-0310 | 1
BU24-0048 | 3
AJ23-0699 | 1
AJ23-0229 | 1
AJ24-0170 | 1
BU24-0139 | 22
BU24-0140 | 1
AJ22-0179 | 1
BU24-0071 | 23
BU24-0059 | 103
AJ23-0566 | 1
AJ23-0423 | 1
AJ23-0584 | 1
BU24-0072 | 36
AJ23-0701 | 1
BU23-0368 | 1
AJ21-0097 | 1
AJ22-0266 | 1
AJ22-0258 | 1
BU24-0141 | 20
AJ24-0202
AJ23-0093 | 1
AJ24-0022 | 1
AJ22-0300 | 1
BU24-0147 | 2
BU23-241 | 64
BU24-0051 | 49
BU24-0050 | 49
BU23-0275 | 1
BU23-0083 | 1
BU23-0031 | 1
BU23-0082 | 1
AJ23-0250 | 1
AJ23-0219 | 1
AJ23-0751 | 1
AJ23-0143 | 1
AJ24‐0009 | 1
BU24-0144 | 9
AJ23-0238 | 1
AJ23-0740 | 1
BU24-0058 | 34
BU24-0148 | 13
BU24-0151 | 16
AJ24-0203
BU23-270 | 64
BU24-0076 | 1
AJ23-0620 | 1
AJ23-0247 | 1
BU24-0167 | 2
BU24-0165 | 2
BU24-0171 | 16
AJ23-0376 | 1
BU24-0168 | 15
BU24-0169 | 15
BU24-0175 | 7
BU24-0143 | 6
BU24-0172 | 7
BU23-0226 | 46
BU24-0170 | 15
BU24-0173 | 16
BU24-0177 | 1
BU23-0221 | 1
BU23-223 | 2
AJ23-0378 | 1
AJ23-0494 | 1
AJ21-0051 | 1
AJ23-0254 | 1
BU24-0118 | 38
AJ23-0439 | 1
AJ24-0050 | 1
AJ23-0767 | 1
AJ23-0380 | 1
AJ23-0382 | 1
BU24-0060 | 1
AJ23-0789 | 123
BU20-0026A | 1
BU20-0026B | 1
BU24-0040 | 16
BU24-0023 | 11
BU24-0019 | 11
BU24-0179 | 3
BU24-0160 | 18
AJ23-0551
BU24-0012 | 1
BU24-0174 | 33
BU24-0129 | 1
BU24-0006
BU23-0379
Grand Total | 2439
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## cost_pjt (hidden)
Row Labels | Sum of Ext. Cost (Line Cost)
UCO23-0003 | 427998.7
UCO-P0045 | 382876.2
BU22-0007 | 286329.87
AJ21-0011 | 253718.34
AJ23-0420 | 125780
AJ23-0751 | 120150
AJ23-0566 | 114000
AJ23-0243 | 100000
AJ23-0242 | 100000
AJ23-0240 | 100000
Grand Total | 2010853.11
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## 4 tab (hidden)
Row Labels | Order Qty | Cost for
MM_AJ | 979 | 1042808.29
MM_BU | 1332 | 700221.23
AJ_Fabrication | 53 | 286316.5
BU_Fabrication | 33 | 421429.74
AJ_Subcon_PR | 195 | 2274433.72
BU_Subcon_PR | 85 | 518757
Grand Total | 2677 | 5243966.48

## po_vd (hidden)
Row Labels | Count of PO #
MERIT INTERNATIONAL INC | 1
CARRIER KUWAIT AIR CONDITIONING | 2
EGYKUW | 3
RITAJ AL KUWAIT GENERAL TRADING CONTRACTING CO | 3
Schneider | 4
AL-IRTEKAZ NATIONAL GEN.TRDG.C | 5
GULF PIONEER COMPANY LLC | 7
KASAR MARJAN CONTRACTING CO. | 8
NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 11
AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 12
TRADEX INTERNATIONAL TRADING LLC | 13
AL NISF ELECTRICAL CO WLL | 13
EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 34
AL BAYADER INTER.GROUP COMPANY | 35
COMMERCIAL UNITED GINCO EST. | 36
MARATHON INC TRADING LLC | 39
CREDENCE TRADING EST. | 68
FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 75
RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 162
(blank) | 238
UNITEC INTERNATIONAL GENERAL TRADING CO | 467
573
MERIT INTERNATIONAL GENERAL TRADING CO WLL | 781
Grand Total | 2590

## vd_cost (hidden)
Row Labels | Sum of Ext. Cost (Line Cost)
MERIT INTERNATIONAL INC | 330.52
NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 1216.24
TRADEX INTERNATIONAL TRADING LLC | 1369.09
AL-IRTEKAZ NATIONAL GEN.TRDG.C | 2311.86
RITAJ AL KUWAIT GENERAL TRADING CONTRACTING CO | 2410.48
CARRIER KUWAIT AIR CONDITIONING | 3224.4
AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 4671.29
MARATHON INC TRADING LLC | 5092.82
EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 6856.97
KASAR MARJAN CONTRACTING CO. | 7965.56
FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 14182.52
AL BAYADER INTER.GROUP COMPANY | 19147.86
EGYKUW | 24951.55
RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 33308.14
AL NISF ELECTRICAL CO WLL | 38671.98
COMMERCIAL UNITED GINCO EST. | 42876.93
GULF PIONEER COMPANY LLC | 76014.1
CREDENCE TRADING EST. | 124766.97
UNITEC INTERNATIONAL GENERAL TRADING CO | 234004.69
MERIT INTERNATIONAL GENERAL TRADING CO WLL | 388459.68
Schneider | 540048.21
876098.9
(blank) | 2795985.72
Grand Total | 5243966.48

## Bom_cou (hidden)
|  | count date | Total BOM Received
|  | 400 | 398
Row Labels | Count of BOM Received date
AJ20-0135 | 1
AJ21-0002 | 1
AJ21-0011 | 2
AJ21-0038 | 4
AJ21-0177 | 1
AJ22-0004 | 2
AJ22-0021 | 1
AJ22-0042 | 1
AJ22-0044 | 2
AJ22-0046 | 1
AJ22-0055 | 1
AJ22-0067 | 1
AJ22-0073 | 2
AJ22-0074 | 1
AJ22-0081 | 2
AJ22-0105 | 4
AJ22-0106 | 1
AJ22-0110 | 1
AJ22-0120 | 1
AJ22-0123 | 2
AJ22-0135 | 235
AJ22-0136 | 21
AJ22-0137 | 1
AJ22-0138 | 1
AJ22-0139 | 1
AJ22-0140 | 1
AJ22-0141 | 1
AJ22-0142 | 1
AJ22-0143 | 1
AJ22-0143, | 1
AJ22-0145 | 4
AJ22-0146 | 1
AJ22-0147 | 1
AJ22-0149 | 2
AJ22-0152 | 242
AJ22-0156 | 1
AJ22-0168 | 1
AJ22-0174 | 1
AJ22-0175 | 1
AJ22-0176 | 1
AJ22-0177 | 1
AJ22-0184 | 2
AJ22-0189 | 2
AJ22-0190 | 1
AJ22-0198 | 2
AJ22-0199 | 1
AJ22-0205 | 2
AJ22-0218 | 1
AJ22-0222 | 2
AJ22-0231 | 1
AJ22-0232 | 1
AJ22-0233 | 1
AJ22-0234 | 1
AJ22-0235 | 1
AJ22-0236 | 1
AJ22-0240 | 2
AJ22-0241 | 1
AJ22-0248 | 1
AJ22-0265 | 1
AJ22-0267 | 1
AJ22-0297 | 1
AJ22-0317 | 1
AJ22-0321 | 1
AJ22-0322 | 3
AJ22-0323 | 2
AJ22-0324 | 2
AJ22-0325 | 1
AJ22-0326 | 3
AJ22-0327 | 1
AJ22-0331 | 1
AJ22-0332 | 1
AJ22-0333 | 1
AJ22-0334 | 1
AJ22-0335 | 1
AJ22-0336 | 1
AJ22-0351 | 1
AJ22-0352 | 1
AJ22-0353 | 1
AJ22-0354 | 1
AJ22-0359 | 1
AJ22-0371 | 2
AJ22-0378 | 1
AJ22-0379 | 1
AJ22-0380 | 2
AJ22-0390 | 2
AJ22-0392 | 1
AJ22-0393 | 1
AJ22-0394 | 1
AJ22-0399 | 1
AJ22-0400 | 2
AJ22-0406 | 2
AJ22-0407 | 2
AJ22-0409 | 1
AJ22-0417 | 2
AJ22-0455 | 1
AJ22-0465 | 2
AJ22-0468 | 1
AJ22-0474 | 1
AJ22-0475 | 2
AJ22-0497 | 2
AJ22-0505 | 1
AJ22-0507 | 1
AJ22-0524 | 2
AJ22-0530 | 1
AJ22-0534 | 2
AJ22-0536 | 2
AJ22-0537 | 1
AJ22-0546 | 1
AJ22-0547 | 2
AJ22-0549 | 2
AJ22-0551 | 3
AJ23-0004 | 2
AJ23-0005 | 2
AJ23-0006 | 2
AJ23-0007 | 2
AJ23-0040 | 2
AJ23-0045 | 1
AJ23-0068 | 2
AJ23-0079 | 3
AJ23-0089 | 1
AJ23-0090 | 1
AJ23-0101 | 2
AJ23-0122 | 26
AJ23-0132 | 1
AJ23-0133 | 1
AJ23-0134 | 1
AJ23-0166 | 2
AJ23-0167 | 1
AJ23-0172 | 2
AJ23-0179 | 2
AJ23-0192 | 1
AJ23-0193 | 2
AJ23-0225 | 2
AJ23-0237 | 1
AJ23-0240 | 1
AJ23-0241 | 1
AJ23-0242 | 1
AJ23-0243 | 1
AJ23-0245 | 1
AJ23-0252 | 1
AJ23-0258 | 2
AJ23-0260 | 4
AJ23-0268 | 2
AJ23-0300 | 2
AJ23-0306 | 1
AJ23-0337 | 1
AJ23-0365 | 1
AJ23-0366 | 1
AJ23-0413 | 1
AJ23-0425 | 1
AJ23-0437 | 1
AJ23-0442 | 1
AJ23-0450 | 2
AJ23-0467 | 66
AJ23-0467 | 1
AJ23-0468 | 1
AJ23-0469 | 1
AJ23-0470 | 1
AJ23-0481 | 1
AJ23-0482 | 2
AJ23-0492 | 1
AJ23-0493 | 2
AJ23-0496 | 1
AJ23-0499 | 1
AJ23-0502 | 1
AJ23-0508 | 117
AJ23-0510 | 1
AJ23-0512 | 2
AJ23-0532 | 1
AJ23-0536 | 2
AJ23-0540 | 1
AJ23-0563 | 1
AJ23-0574 | 2
AJ23-0579 | 2
AJ23-0593 | 1
AJ23-0598 | 2
AJ23-0606 | 1
AJ23-0610 | 1
AJ23-0611 | 1
AJ23-0619 | 1
AJ23-0645 | 1
AJ23-0666 | 1
AJ23-0668 | 2
AJ23-0676 | 1
AJ23-0708 | 32
AJ23-0726 | 1
AJ23-0747 | 27
AJ23-0782 | 1
AJ23-0788 | 1
AJ24-0065 | 1
BU22-0007 | 2
BU22-0028 | 1
BU22-0031 | 1
BU22-0045 | 1
BU22-0055 | 1
BU22-0066 | 1
BU22-0105 | 1
BU22-0105 | 1
BU22-0109 | 1
BU22-0110 | 1
BU22-027 | 1
BU22-031 | 1
BU22-032 | 1
BU22-036 | 1
BU22-038 | 1
BU22-039 | 2
BU22-041 | 1
BU22-045 | 1
BU22-047 | 1
BU22-048 | 2
BU22-049 | 1
BU22-057 | 1
BU22-062 | 1
BU22-064 | 1
BU22-065 | 1
BU22-066 | 1
BU22-066 | 1
BU22-069 | 2
BU22-070 | 1
BU22-089 | 1
BU22-120 | 1
BU23-0023 | 1
BU23-0029 | 1
BU23-0077 | 1
BU23-0094 | 1
BU23-0094 | 1
BU23-0102 | 1
BU23-0111 | 1
BU23-0123 | 1
BU23-0124 | 1
BU23-0143 | 2
BU23-0160 | 1
BU23-0166 | 2
BU23-0175 | 1
BU23-0182 | 1
BU23-0183 | 1
BU23-0192 | 1
BU23-0193 | 69
BU23-0205 | 1
BU23-0206 | 1
BU23-0208 | 1
BU23-0232 | 1
BU23-0233 | 1
BU23-0262 | 1
BU23-0264 | 2
BU23-0279 | 1
BU23-0281 | 1
BU23-029 | 1
BU23-030 | 1
BU23-0306 | 1
BU23-0314 | 1
BU23-032 | 1
BU23-0332 | 13
BU23-0338 | 1
BU23-0350 | 1
BU23-0351 | 1
BU23-0353 | 1
BU23-0353 | 2
BU23-0357 | 1
BU23-0366 | 24
BU23-0371 | 11
BU23-0372 | 2
BU23-0373 | 1
BU23-0375 | 1
BU23-249 | 1
BU23-276 | 21
BU24-0005 | 26
BU24-0014 | 11
BU24-0018 | 4
BU24-0020 | 11
BU24-0021 | 11
BU24-0022 | 13
BU24-0027 | 1
BU24-0064 | 1
BU24-0073 | 1
BU24-0085 | 30
BU24-0086 | 39
BU24-0087 | 6
BU24-0089 | 11
BU24-0092 | 9
BU24-0093 | 1
BU24-0095 | 2
BU24-0096 | 2
BU24-0097 | 5
BU24-0098 | 7
BU-24-0098 | 84
BU24-0103 | 9
BU24-0107 | 6
BU240110 | 20
BU24-0112 | 3
BU24-0119 | 7
UCO23-0003 | 14
UCO-P0045 | 17
(blank) | 4
BU24-0081 | 2
AJ23-0723 | 1
BU24-0015 | 5
BU24-0117 | 42
AJ23-0667 | 1
BU24-0028 | 6
BU24-0066 | 13
AJ23-0472 | 1
AJ23-0750 | 1
AJ23-0475 | 1
AJ23-0420 | 1
AJ23-0473 | 1
AJ23-0474 | 1
BU23-0352 | 1
AJ23-0471 | 1
BU24-0132 | 26
BU23-0310 | 1
BU24-0048 | 3
AJ23-0699 | 1
AJ23-0229 | 1
AJ24-0170 | 1
BU24-0139 | 22
BU24-0140 | 1
AJ22-0179 | 1
BU24-0071 | 23
BU24-0059 | 105
AJ23-0566 | 1
AJ23-0423 | 1
AJ23-0584 | 1
BU24-0072 | 36
AJ23-0701 | 1
BU23-0368 | 1
AJ21-0097 | 1
AJ22-0266 | 1
AJ22-0258 | 1
BU24-0141 | 20
AJ24-0202 | 1
AJ23-0093 | 1
AJ24-0022 | 1
AJ22-0300 | 1
BU24-0147 | 2
BU23-241 | 65
BU24-0051 | 54
BU24-0050 | 54
BU23-0275 | 1
BU23-0083 | 1
BU23-0031 | 1
BU23-0082 | 1
AJ23-0250 | 1
AJ23-0219 | 1
AJ23-0751 | 1
AJ23-0143 | 1
AJ24‐0009 | 1
BU24-0144 | 9
AJ23-0238 | 1
AJ23-0740 | 1
BU24-0058 | 34
BU24-0148 | 13
BU24-0151 | 16
AJ24-0203 | 1
BU23-270 | 64
BU24-0076 | 1
AJ23-0620 | 1
AJ23-0247 | 1
BU24-0167 | 3
BU24-0165 | 2
BU24-0171 | 16
AJ23-0376 | 1
BU24-0168 | 15
BU24-0169 | 15
BU24-0175 | 7
BU24-0143 | 6
BU24-0172 | 7
BU23-0226 | 46
BU24-0170 | 15
BU24-0173 | 16
BU24-0177 | 1
BU23-0221 | 1
BU23-223 | 2
AJ23-0378 | 1
AJ23-0494 | 1
AJ21-0051 | 1
AJ23-0254 | 1
BU24-0118 | 39
AJ23-0439 | 1
AJ24-0050 | 1
AJ23-0767 | 1
AJ23-0380 | 1
AJ23-0382 | 1
BU24-0060 | 1
AJ23-0789 | 126
BU20-0026A | 1
BU20-0026B | 1
BU24-0040 | 16
BU24-0023 | 12
BU24-0019 | 12
BU24-0179 | 3
BU24-0160 | 18
AJ23-0551 | 1
BU24-0012 | 1
BU24-0174 | 34
BU24-0129 | 1
BU24-0006 | 1
BU23-0379 | 1
Grand Total | 2682
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## sb_pr (hidden)
table | Sub table | count pr | Total sub pr
|  | 1 | 281
Count of PR #
281

## mx_pr (hidden)
table | (Multiple Items) | count pr | Total maximo pr
|  | 1 | 2160
Count of PR #
2160

## mx_pr_aj (hidden)
table | (Multiple Items) | count pr | Total maximo pr aj
Color Code list | AJ | 2 | 815
Count of PR #
815

## mx_pr_bu (hidden)
table | (Multiple Items) | count pr | Total maximo pr bu
Color Code list | BU | 2 | 1310
Count of PR #
1310

## fab_pr (hidden)
table | Fab table | count pr | Total fb pr
|  | 1 | 85
Count of PR #
85

## fb_pr_aj (hidden)
table | Fab table | count pr | Total fb pr aj
Color Code list | AJ | 2 | 53
Count of PR #
53

## fb_pr_bu (hidden)
table | Fab table | count pr | Total fb pr aj
Color Code list | BU | 2 | 32
Count of PR #
32

## su_pr_aj (hidden)
table | Sub table | count pr | Total sb pr aj
Color Code list | AJ | 2 | 195
Count of PR #
195

## su_pr_bu (hidden)
table | Sub table | count pr | Total sb pr bu
Color Code list | BU | 2 | 85
Count of PR #
85

## BOM_aj_cou (hidden)
|  |  | count date | Total BOM Received aj
|  |  | 238 | 235
Color Code list | AJ
Row Labels | Count of BOM Received date
AJ20-0135 | 1 | AJ20-0135
AJ21-0002 | 1
AJ21-0011 | 2 |  |  | `
AJ21-0038 | 4
AJ21-0177 | 1
AJ22-0004 | 2
AJ22-0021 | 1
AJ22-0042 | 1
AJ22-0044 | 2
AJ22-0046 | 1
AJ22-0055 | 1
AJ22-0067 | 1
AJ22-0073 | 2
AJ22-0074 | 1
AJ22-0081 | 2
AJ22-0105 | 4
AJ22-0106 | 1
AJ22-0110 | 1
AJ22-0120 | 1
AJ22-0123 | 2
AJ22-0135 | 235
AJ22-0136 | 21
AJ22-0137 | 1
AJ22-0138 | 1
AJ22-0139 | 1
AJ22-0140 | 1
AJ22-0141 | 1
AJ22-0142 | 1
AJ22-0143 | 1
AJ22-0143, | 1
AJ22-0145 | 4
AJ22-0146 | 1
AJ22-0147 | 1
AJ22-0149 | 2
AJ22-0152 | 242
AJ22-0156 | 1
AJ22-0168 | 1
AJ22-0174 | 1
AJ22-0175 | 1
AJ22-0176 | 1
AJ22-0177 | 1
AJ22-0184 | 2
AJ22-0189 | 2
AJ22-0190 | 1
AJ22-0198 | 2
AJ22-0199 | 1
AJ22-0205 | 2
AJ22-0218 | 1
AJ22-0222 | 2
AJ22-0231 | 1
AJ22-0232 | 1
AJ22-0233 | 1
AJ22-0234 | 1
AJ22-0235 | 1
AJ22-0236 | 1
AJ22-0240 | 2
AJ22-0241 | 1
AJ22-0248 | 1
AJ22-0265 | 1
AJ22-0267 | 1
AJ22-0297 | 1
AJ22-0317 | 1
AJ22-0321 | 1
AJ22-0322 | 3
AJ22-0323 | 2
AJ22-0324 | 2
AJ22-0325 | 1
AJ22-0326 | 3
AJ22-0327 | 1
AJ22-0331 | 1
AJ22-0332 | 1
AJ22-0333 | 1
AJ22-0334 | 1
AJ22-0335 | 1
AJ22-0336 | 1
AJ22-0351 | 1
AJ22-0352 | 1
AJ22-0353 | 1
AJ22-0354 | 1
AJ22-0359 | 1
AJ22-0371 | 2
AJ22-0378 | 1
AJ22-0379 | 1
AJ22-0380 | 2
AJ22-0390 | 2
AJ22-0392 | 1
AJ22-0393 | 1
AJ22-0394 | 1
AJ22-0399 | 1
AJ22-0400 | 2
AJ22-0406 | 2
AJ22-0407 | 2
AJ22-0409 | 1
AJ22-0417 | 2
AJ22-0455 | 1
AJ22-0465 | 2
AJ22-0468 | 1
AJ22-0474 | 1
AJ22-0475 | 2
AJ22-0497 | 2
AJ22-0505 | 1
AJ22-0507 | 1
AJ22-0524 | 2
AJ22-0530 | 1
AJ22-0534 | 2
AJ22-0536 | 2
AJ22-0537 | 1
AJ22-0546 | 1
AJ22-0547 | 2
AJ22-0549 | 2
AJ22-0551 | 3
AJ23-0004 | 2
AJ23-0005 | 2
AJ23-0006 | 2
AJ23-0007 | 2
AJ23-0040 | 2
AJ23-0045 | 1
AJ23-0068 | 2
AJ23-0079 | 3
AJ23-0089 | 1
AJ23-0090 | 1
AJ23-0101 | 2
AJ23-0122 | 26
AJ23-0132 | 1
AJ23-0133 | 1
AJ23-0134 | 1
AJ23-0166 | 2
AJ23-0167 | 1
AJ23-0172 | 2
AJ23-0179 | 2
AJ23-0192 | 1
AJ23-0193 | 2
AJ23-0225 | 2
AJ23-0237 | 1
AJ23-0240 | 1
AJ23-0241 | 1
AJ23-0242 | 1
AJ23-0243 | 1
AJ23-0245 | 1
AJ23-0252 | 1
AJ23-0258 | 2
AJ23-0260 | 4
AJ23-0268 | 2
AJ23-0300 | 2
AJ23-0306 | 1
AJ23-0337 | 1
AJ23-0365 | 1
AJ23-0366 | 1
AJ23-0413 | 1
AJ23-0425 | 1
AJ23-0437 | 1
AJ23-0442 | 1
AJ23-0450 | 2
AJ23-0467 | 66
AJ23-0467 | 1
AJ23-0468 | 1
AJ23-0469 | 1
AJ23-0470 | 1
AJ23-0481 | 1
AJ23-0482 | 2
AJ23-0492 | 1
AJ23-0493 | 2
AJ23-0496 | 1
AJ23-0499 | 1
AJ23-0502 | 1
AJ23-0508 | 117
AJ23-0510 | 1
AJ23-0512 | 2
AJ23-0532 | 1
AJ23-0536 | 2
AJ23-0540 | 1
AJ23-0563 | 1
AJ23-0574 | 2
AJ23-0579 | 2
AJ23-0593 | 1
AJ23-0598 | 2
AJ23-0606 | 1
AJ23-0610 | 1
AJ23-0611 | 1
AJ23-0619 | 1
AJ23-0645 | 1
AJ23-0666 | 1
AJ23-0668 | 2
AJ23-0676 | 1
AJ23-0708 | 32
AJ23-0726 | 1
AJ23-0747 | 27
AJ23-0782 | 1
AJ23-0788 | 1
AJ24-0065 | 1
AJ23-0723 | 1
AJ23-0667 | 1
AJ23-0472 | 1
AJ23-0750 | 1
AJ23-0475 | 1
AJ23-0420 | 1
AJ23-0473 | 1
AJ23-0474 | 1
AJ23-0471 | 1
AJ23-0699 | 1
AJ23-0229 | 1
AJ24-0170 | 1
AJ22-0179 | 1
AJ23-0566 | 1
AJ23-0423 | 1
AJ23-0584 | 1
AJ23-0701 | 1
AJ22-0266 | 1
AJ22-0258 | 1
AJ24-0202 | 1
AJ23-0093 | 1
AJ24-0022 | 1
AJ22-0300 | 1
AJ23-0250 | 1
AJ23-0219 | 1
AJ23-0751 | 1
AJ23-0143 | 1
AJ24‐0009 | 1
AJ23-0238 | 1
AJ23-0740 | 1
AJ24-0203 | 1
AJ23-0620 | 1
AJ23-0247 | 1
AJ23-0376 | 1
AJ23-0378 | 1
AJ23-0494 | 1
AJ21-0051 | 1
AJ23-0254 | 1
AJ23-0439 | 1
AJ24-0050 | 1
AJ23-0767 | 1
AJ23-0380 | 1
AJ23-0382 | 1
AJ23-0789 | 126
AJ23-0551 | 1
Grand Total | 1192
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## BOM_bu_cou (hidden)
|  |  | count date | Total BOM Received bu
|  |  | 162 | 159
Color Code list | BU
Row Labels | Count of BOM Received date
BU22-0007 | 2 | BU22-0007
BU22-0028 | 1
BU22-0031 | 1
BU22-0045 | 1
BU22-0055 | 1
BU22-0066 | 1
BU22-0105 | 1
BU22-0105 | 1
BU22-0109 | 1
BU22-0110 | 1
BU22-027 | 1
BU22-031 | 1
BU22-032 | 1
BU22-036 | 1
BU22-038 | 1
BU22-039 | 2
BU22-041 | 1
BU22-045 | 1
BU22-047 | 1
BU22-048 | 2
BU22-049 | 1
BU22-057 | 1
BU22-062 | 1
BU22-064 | 1
BU22-065 | 1
BU22-066 | 1
BU22-066 | 1
BU22-069 | 2
BU22-070 | 1
BU22-089 | 1
BU22-120 | 1
BU23-0023 | 1
BU23-0029 | 1
BU23-0077 | 1
BU23-0094 | 1
BU23-0094 | 1
BU23-0102 | 1
BU23-0111 | 1
BU23-0123 | 1
BU23-0124 | 1
BU23-0143 | 2
BU23-0160 | 1
BU23-0166 | 2
BU23-0175 | 1
BU23-0182 | 1
BU23-0183 | 1
BU23-0192 | 1
BU23-0193 | 69
BU23-0205 | 1
BU23-0206 | 1
BU23-0208 | 1
BU23-0232 | 1
BU23-0233 | 1
BU23-0262 | 1
BU23-0264 | 2
BU23-0279 | 1
BU23-0281 | 1
BU23-029 | 1
BU23-030 | 1
BU23-0306 | 1
BU23-0314 | 1
BU23-032 | 1
BU23-0332 | 13
BU23-0338 | 1
BU23-0350 | 1
BU23-0351 | 1
BU23-0353 | 1
BU23-0353 | 2
BU23-0357 | 1
BU23-0366 | 24
BU23-0371 | 11
BU23-0372 | 2
BU23-0373 | 1
BU23-0375 | 1
BU23-249 | 1
BU23-276 | 21
BU24-0005 | 26
BU24-0014 | 11
BU24-0018 | 4
BU24-0020 | 11
BU24-0021 | 11
BU24-0022 | 13
BU24-0027 | 1
BU24-0064 | 1
BU24-0073 | 1
BU24-0085 | 30
BU24-0086 | 39
BU24-0087 | 6
BU24-0089 | 11
BU24-0092 | 9
BU24-0093 | 1
BU24-0095 | 2
BU24-0096 | 2
BU24-0097 | 5
BU24-0098 | 7
BU-24-0098 | 84
BU24-0103 | 9
BU24-0107 | 6
BU240110 | 20
BU24-0112 | 3
BU24-0119 | 7
BU24-0081 | 2
BU24-0015 | 5
BU24-0117 | 42
BU24-0028 | 6
BU24-0066 | 13
BU23-0352 | 1
BU24-0132 | 26
BU23-0310 | 1
BU24-0048 | 3
BU24-0139 | 22
BU24-0140 | 1
BU24-0071 | 23
BU24-0059 | 105
BU24-0072 | 36
BU23-0368 | 1
BU24-0141 | 20
BU24-0147 | 2
BU23-241 | 65
BU24-0051 | 54
BU24-0050 | 54
BU23-0275 | 1
BU23-0083 | 1
BU23-0031 | 1
BU23-0082 | 1
BU24-0144 | 9
BU24-0058 | 34
BU24-0148 | 13
BU24-0151 | 16
BU23-270 | 64
BU24-0076 | 1
BU24-0167 | 3
BU24-0165 | 2
BU24-0171 | 16
BU24-0168 | 15
BU24-0169 | 15
BU24-0175 | 7
BU24-0143 | 6
BU24-0172 | 7
BU23-0226 | 46
BU24-0170 | 15
BU24-0173 | 16
BU24-0177 | 1
BU23-0221 | 1
BU23-223 | 2
BU24-0118 | 39
BU24-0060 | 1
BU20-0026A | 1
BU20-0026B | 1
BU24-0040 | 16
BU24-0023 | 12
BU24-0019 | 12
BU24-0179 | 3
BU24-0160 | 18
BU24-0012 | 1
BU24-0174 | 34
BU24-0129 | 1
BU24-0006 | 1
BU23-0379 | 1
Grand Total | 1454
This shape represents a slicer. Slicers are supported in Excel 2010 or later. If the shape was modified in an earlier version of Excel, or if the workbook was saved in Excel 2003 or earlier, the slicer cannot be used.

## pj_aj_bu_numb (hidden)
Color Code list | AJ |  |  | Color Code list | BU
Row Labels | count PROJECT# for AJ | count | Total Received aj | Row Labels | Count of PROJECT# for BU | Count of PROJECT# for BU | Column Labels
AJ20-0135 | 1 | 238 | 235 | BU22-0007 | 2 | Row Labels | AJ | BU | UCO | (blank) | AJ | Grand Total
AJ21-0002 | 1 |  |  | BU22-0028 | 1 | AJ20-0135 | 1 |  |  |  |  | 1
AJ21-0011 | 2 |  |  | BU22-0031 | 1 | AJ21-0002 | 1 |  |  |  |  | 1
AJ21-0038 | 4 | count | Total Received bu | BU22-0045 | 1 | AJ21-0011 | 2 |  |  |  |  | 2
AJ21-0177 | 1 | 162 | 159 | BU22-0055 | 1 | AJ21-0038 | 4 |  |  |  |  | 4
AJ22-0004 | 2 |  |  | BU22-0066 | 1 | AJ21-0177 | 1 |  |  |  |  | 1
AJ22-0021 | 1 |  |  | BU22-0105 | 1 | AJ22-0004 | 2 |  |  |  |  | 2
AJ22-0042 | 1 |  |  | BU22-0105 | 1 | AJ22-0021 | 1 |  |  |  |  | 1
AJ22-0044 | 2 |  |  | BU22-0109 | 1 | AJ22-0042 | 1 |  |  |  |  | 1
AJ22-0046 | 1 |  |  | BU22-0110 | 1 | AJ22-0044 | 2 |  |  |  |  | 2
AJ22-0055 | 1 |  |  | BU22-027 | 1 | AJ22-0046 | 1 |  |  |  |  | 1
AJ22-0067 | 1 |  |  | BU22-031 | 1 | AJ22-0055 | 1 |  |  |  |  | 1
AJ22-0073 | 2 |  |  | BU22-032 | 1 | AJ22-0067 | 1 |  |  |  |  | 1
AJ22-0074 | 1 |  |  | BU22-036 | 1 | AJ22-0073 | 2 |  |  |  |  | 2
AJ22-0081 | 2 |  |  | BU22-038 | 1 | AJ22-0074 | 1 |  |  |  |  | 1
AJ22-0105 | 4 |  |  | BU22-039 | 2 | AJ22-0081 | 2 |  |  |  |  | 2
AJ22-0106 | 1 |  |  | BU22-041 | 1 | AJ22-0105 | 4 |  |  |  |  | 4
AJ22-0110 | 1 |  |  | BU22-045 | 1 | AJ22-0106 | 1 |  |  |  |  | 1
AJ22-0120 | 1 |  |  | BU22-047 | 1 | AJ22-0110 | 1 |  |  |  |  | 1
AJ22-0123 | 2 |  |  | BU22-048 | 2 | AJ22-0120 | 1 |  |  |  |  | 1
AJ22-0135 | 235 |  |  | BU22-049 | 1 | AJ22-0123 | 2 |  |  |  |  | 2
AJ22-0136 | 21 |  |  | BU22-057 | 1 | AJ22-0135 | 235 |  |  |  |  | 235
AJ22-0137 | 1 |  |  | BU22-062 | 1 | AJ22-0136 | 21 |  |  |  |  | 21
AJ22-0138 | 1 |  |  | BU22-064 | 1 | AJ22-0137 | 1 |  |  |  |  | 1
AJ22-0139 | 1 |  |  | BU22-065 | 1 | AJ22-0138 | 1 |  |  |  |  | 1
AJ22-0140 | 1 |  |  | BU22-066 | 1 | AJ22-0139 | 1 |  |  |  |  | 1
AJ22-0141 | 1 |  |  | BU22-066 | 1 | AJ22-0140 | 1 |  |  |  |  | 1
AJ22-0142 | 1 |  |  | BU22-069 | 2 | AJ22-0141 | 1 |  |  |  |  | 1
AJ22-0143 | 1 |  |  | BU22-070 | 1 | AJ22-0142 | 1 |  |  |  |  | 1
AJ22-0143, | 1 |  |  | BU22-089 | 1 | AJ22-0143 | 1 |  |  |  |  | 1
AJ22-0145 | 4 |  |  | BU22-120 | 1 | AJ22-0143, | 1 |  |  |  |  | 1
AJ22-0146 | 1 |  |  | BU23-0023 | 1 | AJ22-0145 | 4 |  |  |  |  | 4
AJ22-0147 | 1 |  |  | BU23-0029 | 1 | AJ22-0146 | 1 |  |  |  |  | 1
AJ22-0149 | 2 |  |  | BU23-0077 | 1 | AJ22-0147 | 1 |  |  |  |  | 1
AJ22-0152 | 242 |  |  | BU23-0094 | 1 | AJ22-0149 | 2 |  |  |  |  | 2
AJ22-0156 | 1 |  |  | BU23-0094 | 1 | AJ22-0152 | 242 |  |  |  |  | 242
AJ22-0168 | 1 |  |  | BU23-0102 | 1 | AJ22-0156 | 1 |  |  |  |  | 1
AJ22-0174 | 1 |  |  | BU23-0111 | 1 | AJ22-0168 | 1 |  |  |  |  | 1
AJ22-0175 | 1 |  |  | BU23-0123 | 1 | AJ22-0174 | 1 |  |  |  |  | 1
AJ22-0176 | 1 |  |  | BU23-0124 | 1 | AJ22-0175 | 1 |  |  |  |  | 1
AJ22-0177 | 1 |  |  | BU23-0143 | 2 | AJ22-0176 | 1 |  |  |  |  | 1
AJ22-0184 | 2 |  |  | BU23-0160 | 1 | AJ22-0177 | 1 |  |  |  |  | 1
AJ22-0189 | 2 |  |  | BU23-0166 | 2 | AJ22-0184 | 2 |  |  |  |  | 2
AJ22-0190 | 1 |  |  | BU23-0175 | 1 | AJ22-0189 | 2 |  |  |  |  | 2
AJ22-0198 | 2 |  |  | BU23-0182 | 1 | AJ22-0190 | 1 |  |  |  |  | 1
AJ22-0199 | 1 |  |  | BU23-0183 | 1 | AJ22-0198 | 2 |  |  |  |  | 2
AJ22-0205 | 2 |  |  | BU23-0192 | 1 | AJ22-0199 | 1 |  |  |  |  | 1
AJ22-0218 | 1 |  |  | BU23-0193 | 69 | AJ22-0205 | 2 |  |  |  |  | 2
AJ22-0222 | 2 |  |  | BU23-0205 | 1 | AJ22-0218 | 1 |  |  |  |  | 1
AJ22-0231 | 1 |  |  | BU23-0206 | 1 | AJ22-0222 | 2 |  |  |  |  | 2
AJ22-0232 | 1 |  |  | BU23-0208 | 1 | AJ22-0231 | 1 |  |  |  |  | 1
AJ22-0233 | 1 |  |  | BU23-0232 | 1 | AJ22-0232 | 1 |  |  |  |  | 1
AJ22-0234 | 1 |  |  | BU23-0233 | 1 | AJ22-0233 | 1 |  |  |  |  | 1
AJ22-0235 | 1 |  |  | BU23-0262 | 1 | AJ22-0234 | 1 |  |  |  |  | 1
AJ22-0236 | 1 |  |  | BU23-0264 | 2 | AJ22-0235 | 1 |  |  |  |  | 1
AJ22-0240 | 2 |  |  | BU23-0279 | 1 | AJ22-0236 | 1 |  |  |  |  | 1
AJ22-0241 | 1 |  |  | BU23-0281 | 1 | AJ22-0240 | 2 |  |  |  |  | 2
AJ22-0248 | 1 |  |  | BU23-029 | 1 | AJ22-0241 | 1 |  |  |  |  | 1
AJ22-0265 | 1 |  |  | BU23-030 | 1 | AJ22-0248 | 1 |  |  |  |  | 1
AJ22-0267 | 1 |  |  | BU23-0306 | 1 | AJ22-0265 | 1 |  |  |  |  | 1
AJ22-0297 | 1 |  |  | BU23-0314 | 1 | AJ22-0267 | 1 |  |  |  |  | 1
AJ22-0317 | 1 |  |  | BU23-032 | 1 | AJ22-0297 | 1 |  |  |  |  | 1
AJ22-0321 | 1 |  |  | BU23-0332 | 13 | AJ22-0317 | 1 |  |  |  |  | 1
AJ22-0322 | 3 |  |  | BU23-0338 | 1 | AJ22-0321 | 1 |  |  |  |  | 1
AJ22-0323 | 2 |  |  | BU23-0350 | 1 | AJ22-0322 | 3 |  |  |  |  | 3
AJ22-0324 | 2 |  |  | BU23-0351 | 1 | AJ22-0323 | 2 |  |  |  |  | 2
AJ22-0325 | 1 |  |  | BU23-0353 | 1 | AJ22-0324 | 2 |  |  |  |  | 2
AJ22-0326 | 3 |  |  | BU23-0353 | 2 | AJ22-0325 | 1 |  |  |  |  | 1
AJ22-0327 | 1 |  |  | BU23-0357 | 1 | AJ22-0326 | 3 |  |  |  |  | 3
AJ22-0331 | 1 |  |  | BU23-0366 | 24 | AJ22-0327 | 1 |  |  |  |  | 1
AJ22-0332 | 1 |  |  | BU23-0371 | 11 | AJ22-0331 | 1 |  |  |  |  | 1
AJ22-0333 | 1 |  |  | BU23-0372 | 2 | AJ22-0332 | 1 |  |  |  |  | 1
AJ22-0334 | 1 |  |  | BU23-0373 | 1 | AJ22-0333 | 1 |  |  |  |  | 1
AJ22-0335 | 1 |  |  | BU23-0375 | 1 | AJ22-0334 | 1 |  |  |  |  | 1
AJ22-0336 | 1 |  |  | BU23-249 | 1 | AJ22-0335 | 1 |  |  |  |  | 1
AJ22-0351 | 1 |  |  | BU23-276 | 21 | AJ22-0336 | 1 |  |  |  |  | 1
AJ22-0352 | 1 |  |  | BU24-0005 | 26 | AJ22-0351 | 1 |  |  |  |  | 1
AJ22-0353 | 1 |  |  | BU24-0014 | 11 | AJ22-0352 | 1 |  |  |  |  | 1
AJ22-0354 | 1 |  |  | BU24-0018 | 4 | AJ22-0353 | 1 |  |  |  |  | 1
AJ22-0359 | 1 |  |  | BU24-0020 | 11 | AJ22-0354 | 1 |  |  |  |  | 1
AJ22-0371 | 2 |  |  | BU24-0021 | 11 | AJ22-0359 | 1 |  |  |  |  | 1
AJ22-0378 | 1 |  |  | BU24-0022 | 13 | AJ22-0371 | 2 |  |  |  |  | 2
AJ22-0379 | 1 |  |  | BU24-0027 | 1 | AJ22-0378 | 1 |  |  |  |  | 1
AJ22-0380 | 2 |  |  | BU24-0064 | 1 | AJ22-0379 | 1 |  |  |  |  | 1
AJ22-0390 | 2 |  |  | BU24-0073 | 1 | AJ22-0380 | 2 |  |  |  |  | 2
AJ22-0392 | 1 |  |  | BU24-0085 | 30 | AJ22-0390 | 2 |  |  |  |  | 2
AJ22-0393 | 1 |  |  | BU24-0086 | 39 | AJ22-0392 | 1 |  |  |  |  | 1
AJ22-0394 | 1 |  |  | BU24-0087 | 6 | AJ22-0393 | 1 |  |  |  |  | 1
AJ22-0399 | 1 |  |  | BU24-0089 | 11 | AJ22-0394 | 1 |  |  |  |  | 1
AJ22-0400 | 2 |  |  | BU24-0092 | 9 | AJ22-0399 | 1 |  |  |  |  | 1
AJ22-0406 | 2 |  |  | BU24-0093 | 1 | AJ22-0400 | 2 |  |  |  |  | 2
AJ22-0407 | 2 |  |  | BU24-0095 | 2 | AJ22-0406 | 2 |  |  |  |  | 2
AJ22-0409 | 1 |  |  | BU24-0096 | 2 | AJ22-0407 | 2 |  |  |  |  | 2
AJ22-0417 | 2 |  |  | BU24-0097 | 5 | AJ22-0409 | 1 |  |  |  |  | 1
AJ22-0455 | 1 |  |  | BU24-0098 | 7 | AJ22-0417 | 2 |  |  |  |  | 2
AJ22-0465 | 2 |  |  | BU-24-0098 | 84 | AJ22-0455 | 1 |  |  |  |  | 1
AJ22-0468 | 1 |  |  | BU24-0103 | 9 | AJ22-0465 | 2 |  |  |  |  | 2
AJ22-0474 | 1 |  |  | BU24-0107 | 6 | AJ22-0468 | 1 |  |  |  |  | 1
AJ22-0475 | 2 |  |  | BU240110 | 20 | AJ22-0474 | 1 |  |  |  |  | 1
AJ22-0497 | 2 |  |  | BU24-0112 | 3 | AJ22-0475 | 2 |  |  |  |  | 2
AJ22-0505 | 1 |  |  | BU24-0119 | 7 | AJ22-0497 | 2 |  |  |  |  | 2
AJ22-0507 | 1 |  |  | BU24-0081 | 2 | AJ22-0505 | 1 |  |  |  |  | 1
AJ22-0524 | 2 |  |  | BU24-0015 | 5 | AJ22-0507 | 1 |  |  |  |  | 1
AJ22-0530 | 1 |  |  | BU24-0117 | 42 | AJ22-0524 | 2 |  |  |  |  | 2
AJ22-0534 | 2 |  |  | BU24-0028 | 6 | AJ22-0530 | 1 |  |  |  |  | 1
AJ22-0536 | 2 |  |  | BU24-0066 | 13 | AJ22-0534 | 2 |  |  |  |  | 2
AJ22-0537 | 1 |  |  | BU23-0352 | 1 | AJ22-0536 | 2 |  |  |  |  | 2
AJ22-0546 | 1 |  |  | BU24-0132 | 26 | AJ22-0537 | 1 |  |  |  |  | 1
AJ22-0547 | 2 |  |  | BU23-0310 | 1 | AJ22-0546 | 1 |  |  |  |  | 1
AJ22-0549 | 2 |  |  | BU24-0048 | 3 | AJ22-0547 | 2 |  |  |  |  | 2
AJ22-0551 | 3 |  |  | BU24-0139 | 22 | AJ22-0549 | 2 |  |  |  |  | 2
AJ23-0004 | 2 |  |  | BU24-0140 | 1 | AJ22-0551 | 3 |  |  |  |  | 3
AJ23-0005 | 2 |  |  | BU24-0071 | 23 | AJ23-0004 | 2 |  |  |  |  | 2
AJ23-0006 | 2 |  |  | BU24-0059 | 105 | AJ23-0005 | 2 |  |  |  |  | 2
AJ23-0007 | 2 |  |  | BU24-0072 | 36 | AJ23-0006 | 2 |  |  |  |  | 2
AJ23-0040 | 2 |  |  | BU23-0368 | 1 | AJ23-0007 | 2 |  |  |  |  | 2
AJ23-0045 | 1 |  |  | BU24-0141 | 20 | AJ23-0040 | 2 |  |  |  |  | 2
AJ23-0068 | 2 |  |  | BU24-0147 | 2 | AJ23-0045 | 1 |  |  |  |  | 1
AJ23-0079 | 3 |  |  | BU23-241 | 65 | AJ23-0068 | 2 |  |  |  |  | 2
AJ23-0089 | 1 |  |  | BU24-0051 | 54 | AJ23-0079 | 3 |  |  |  |  | 3
AJ23-0090 | 1 |  |  | BU24-0050 | 54 | AJ23-0089 | 1 |  |  |  |  | 1
AJ23-0101 | 2 |  |  | BU23-0275 | 1 | AJ23-0090 | 1 |  |  |  |  | 1
AJ23-0122 | 26 |  |  | BU23-0083 | 1 | AJ23-0101 | 2 |  |  |  |  | 2
AJ23-0132 | 1 |  |  | BU23-0031 | 1 | AJ23-0122 | 26 |  |  |  |  | 26
AJ23-0133 | 1 |  |  | BU23-0082 | 1 | AJ23-0132 | 1 |  |  |  |  | 1
AJ23-0134 | 1 |  |  | BU24-0144 | 9 | AJ23-0133 | 1 |  |  |  |  | 1
AJ23-0166 | 2 |  |  | BU24-0058 | 34 | AJ23-0134 | 1 |  |  |  |  | 1
AJ23-0167 | 1 |  |  | BU24-0148 | 13 | AJ23-0166 | 2 |  |  |  |  | 2
AJ23-0172 | 2 |  |  | BU24-0151 | 16 | AJ23-0167 | 1 |  |  |  |  | 1
AJ23-0179 | 2 |  |  | BU23-270 | 64 | AJ23-0172 | 2 |  |  |  |  | 2
AJ23-0192 | 1 |  |  | BU24-0076 | 1 | AJ23-0179 | 2 |  |  |  |  | 2
AJ23-0193 | 2 |  |  | BU24-0167 | 3 | AJ23-0192 | 1 |  |  |  |  | 1
AJ23-0225 | 2 |  |  | BU24-0165 | 2 | AJ23-0193 | 2 |  |  |  |  | 2
AJ23-0237 | 1 |  |  | BU24-0171 | 16 | AJ23-0225 | 2 |  |  |  |  | 2
AJ23-0240 | 1 |  |  | BU24-0168 | 15 | AJ23-0237 | 1 |  |  |  |  | 1
AJ23-0241 | 1 |  |  | BU24-0169 | 15 | AJ23-0240 | 1 |  |  |  |  | 1
AJ23-0242 | 1 |  |  | BU24-0175 | 7 | AJ23-0241 | 1 |  |  |  |  | 1
AJ23-0243 | 1 |  |  | BU24-0143 | 6 | AJ23-0242 | 1 |  |  |  |  | 1
AJ23-0245 | 1 |  |  | BU24-0172 | 7 | AJ23-0243 | 1 |  |  |  |  | 1
AJ23-0252 | 1 |  |  | BU23-0226 | 46 | AJ23-0245 | 1 |  |  |  |  | 1
AJ23-0258 | 2 |  |  | BU24-0170 | 15 | AJ23-0252 | 1 |  |  |  |  | 1
AJ23-0260 | 4 |  |  | BU24-0173 | 16 | AJ23-0258 | 2 |  |  |  |  | 2
AJ23-0268 | 2 |  |  | BU24-0177 | 1 | AJ23-0260 | 4 |  |  |  |  | 4
AJ23-0300 | 2 |  |  | BU23-0221 | 1 | AJ23-0268 | 2 |  |  |  |  | 2
AJ23-0306 | 1 |  |  | BU23-223 | 2 | AJ23-0300 | 2 |  |  |  |  | 2
AJ23-0337 | 1 |  |  | BU24-0118 | 39 | AJ23-0306 | 1 |  |  |  |  | 1
AJ23-0365 | 1 |  |  | BU24-0060 | 1 | AJ23-0337 | 1 |  |  |  |  | 1
AJ23-0366 | 1 |  |  | BU20-0026A | 1 | AJ23-0365 | 1 |  |  |  |  | 1
AJ23-0413 | 1 |  |  | BU20-0026B | 1 | AJ23-0366 | 1 |  |  |  |  | 1
AJ23-0425 | 1 |  |  | BU24-0040 | 16 | AJ23-0413 | 1 |  |  |  |  | 1
AJ23-0437 | 1 |  |  | BU24-0023 | 12 | AJ23-0425 | 1 |  |  |  |  | 1
AJ23-0442 | 1 |  |  | BU24-0019 | 12 | AJ23-0437 | 1 |  |  |  |  | 1
AJ23-0450 | 2 |  |  | BU24-0179 | 3 | AJ23-0442 | 1 |  |  |  |  | 1
AJ23-0467 | 66 |  |  | BU24-0160 | 18 | AJ23-0450 | 2 |  |  |  |  | 2
AJ23-0467 | 1 |  |  | BU24-0012 | 1 | AJ23-0467 | 66 |  |  |  |  | 66
AJ23-0468 | 1 |  |  | BU24-0174 | 34 | AJ23-0467 | 1 |  |  |  |  | 1
AJ23-0469 | 1 |  |  | BU24-0129 | 1 | AJ23-0468 | 1 |  |  |  |  | 1
AJ23-0470 | 1 |  |  | BU24-0006 | 1 | AJ23-0469 | 1 |  |  |  |  | 1
AJ23-0481 | 1 |  |  | BU23-0379 | 1 | AJ23-0470 | 1 |  |  |  |  | 1
AJ23-0482 | 2 |  |  | Grand Total | 1454 | AJ23-0481 | 1 |  |  |  |  | 1
AJ23-0492 | 1 |  |  |  |  | AJ23-0482 | 2 |  |  |  |  | 2
AJ23-0493 | 2 |  |  |  |  | AJ23-0492 | 1 |  |  |  |  | 1
AJ23-0496 | 1 |  |  |  |  | AJ23-0493 | 2 |  |  |  |  | 2
AJ23-0499 | 1 |  |  |  |  | AJ23-0496 | 1 |  |  |  |  | 1
AJ23-0502 | 1 |  |  |  |  | AJ23-0499 | 1 |  |  |  |  | 1
AJ23-0508 | 117 |  |  |  |  | AJ23-0502 | 1 |  |  |  |  | 1
AJ23-0510 | 1 |  |  |  |  | AJ23-0508 | 117 |  |  |  |  | 117
AJ23-0512 | 2 |  |  |  |  | AJ23-0510 | 1 |  |  |  |  | 1
AJ23-0532 | 1 |  |  |  |  | AJ23-0512 | 2 |  |  |  |  | 2
AJ23-0536 | 2 |  |  |  |  | AJ23-0532 | 1 |  |  |  |  | 1
AJ23-0540 | 1 |  |  |  |  | AJ23-0536 | 2 |  |  |  |  | 2
AJ23-0563 | 1 |  |  |  |  | AJ23-0540 | 1 |  |  |  |  | 1
AJ23-0574 | 2 |  |  |  |  | AJ23-0563 | 1 |  |  |  |  | 1
AJ23-0579 | 2 |  |  |  |  | AJ23-0574 | 2 |  |  |  |  | 2
AJ23-0593 | 1 |  |  |  |  | AJ23-0579 | 2 |  |  |  |  | 2
AJ23-0598 | 2 |  |  |  |  | AJ23-0593 | 1 |  |  |  |  | 1
AJ23-0606 | 1 |  |  |  |  | AJ23-0598 | 2 |  |  |  |  | 2
AJ23-0610 | 1 |  |  |  |  | AJ23-0606 | 1 |  |  |  |  | 1
AJ23-0611 | 1 |  |  |  |  | AJ23-0610 | 1 |  |  |  |  | 1
AJ23-0619 | 1 |  |  |  |  | AJ23-0611 | 1 |  |  |  |  | 1
AJ23-0645 | 1 |  |  |  |  | AJ23-0619 | 1 |  |  |  |  | 1
AJ23-0666 | 1 |  |  |  |  | AJ23-0645 | 1 |  |  |  |  | 1
AJ23-0668 | 2 |  |  |  |  | AJ23-0666 | 1 |  |  |  |  | 1
AJ23-0676 | 1 |  |  |  |  | AJ23-0668 | 2 |  |  |  |  | 2
AJ23-0708 | 32 |  |  |  |  | AJ23-0676 | 1 |  |  |  |  | 1
AJ23-0726 | 1 |  |  |  |  | AJ23-0708 | 32 |  |  |  |  | 32
AJ23-0747 | 27 |  |  |  |  | AJ23-0726 | 1 |  |  |  |  | 1
AJ23-0782 | 1 |  |  |  |  | AJ23-0747 | 27 |  |  |  |  | 27
AJ23-0788 | 1 |  |  |  |  | AJ23-0782 | 1 |  |  |  |  | 1
AJ24-0065 | 1 |  |  |  |  | AJ23-0788 | 1 |  |  |  |  | 1
AJ23-0723 | 1 |  |  |  |  | AJ24-0065 | 1 |  |  |  |  | 1
AJ23-0667 | 1 |  |  |  |  | BU22-0007 |  | 2 |  |  |  | 2
AJ23-0472 | 1 |  |  |  |  | BU22-0028 |  | 1 |  |  |  | 1
AJ23-0750 | 1 |  |  |  |  | BU22-0031 |  | 1 |  |  |  | 1
AJ23-0475 | 1 |  |  |  |  | BU22-0045 |  | 1 |  |  |  | 1
AJ23-0420 | 1 |  |  |  |  | BU22-0055 |  | 1 |  |  |  | 1
AJ23-0473 | 1 |  |  |  |  | BU22-0066 |  | 1 |  |  |  | 1
AJ23-0474 | 1 |  |  |  |  | BU22-0105 |  | 1 |  |  |  | 1
AJ23-0471 | 1 |  |  |  |  | BU22-0105 |  | 1 |  |  |  | 1
AJ23-0699 | 1 |  |  |  |  | BU22-0109 |  | 1 |  |  |  | 1
AJ23-0229 | 1 |  |  |  |  | BU22-0110 |  | 1 |  |  |  | 1
AJ24-0170 | 1 |  |  |  |  | BU22-027 |  | 1 |  |  |  | 1
AJ22-0179 | 1 |  |  |  |  | BU22-031 |  | 1 |  |  |  | 1
AJ23-0566 | 1 |  |  |  |  | BU22-032 |  | 1 |  |  |  | 1
AJ23-0423 | 1 |  |  |  |  | BU22-036 |  | 1 |  |  |  | 1
AJ23-0584 | 1 |  |  |  |  | BU22-038 |  | 1 |  |  |  | 1
AJ23-0701 | 1 |  |  |  |  | BU22-039 |  | 2 |  |  |  | 2
AJ22-0266 | 1 |  |  |  |  | BU22-041 |  | 1 |  |  |  | 1
AJ22-0258 | 1 |  |  |  |  | BU22-045 |  | 1 |  |  |  | 1
AJ24-0202 | 1 |  |  |  |  | BU22-047 |  | 1 |  |  |  | 1
AJ23-0093 | 1 |  |  |  |  | BU22-048 |  | 2 |  |  |  | 2
AJ24-0022 | 1 |  |  |  |  | BU22-049 |  | 1 |  |  |  | 1
AJ22-0300 | 1 |  |  |  |  | BU22-057 |  | 1 |  |  |  | 1
AJ23-0250 | 1 |  |  |  |  | BU22-062 |  | 1 |  |  |  | 1
AJ23-0219 | 1 |  |  |  |  | BU22-064 |  | 1 |  |  |  | 1
AJ23-0751 | 1 |  |  |  |  | BU22-065 |  | 1 |  |  |  | 1
AJ23-0143 | 1 |  |  |  |  | BU22-066 |  | 1 |  |  |  | 1
AJ24‐0009 | 1 |  |  |  |  | BU22-066 |  | 1 |  |  |  | 1
AJ23-0238 | 1 |  |  |  |  | BU22-069 |  | 2 |  |  |  | 2
AJ23-0740 | 1 |  |  |  |  | BU22-070 |  | 1 |  |  |  | 1
AJ24-0203 | 1 |  |  |  |  | BU22-089 |  | 1 |  |  |  | 1
AJ23-0620 | 1 |  |  |  |  | BU22-120 |  | 1 |  |  |  | 1
AJ23-0247 | 1 |  |  |  |  | BU23-0023 |  | 1 |  |  |  | 1
AJ23-0376 | 1 |  |  |  |  | BU23-0029 |  | 1 |  |  |  | 1
AJ23-0378 | 1 |  |  |  |  | BU23-0077 |  | 1 |  |  |  | 1
AJ23-0494 | 1 |  |  |  |  | BU23-0094 |  | 1 |  |  |  | 1
AJ21-0051 | 1 |  |  |  |  | BU23-0094 |  | 1 |  |  |  | 1
AJ23-0254 | 1 |  |  |  |  | BU23-0102 |  | 1 |  |  |  | 1
AJ23-0439 | 1 |  |  |  |  | BU23-0111 |  | 1 |  |  |  | 1
AJ24-0050 | 1 |  |  |  |  | BU23-0123 |  | 1 |  |  |  | 1
AJ23-0767 | 1 |  |  |  |  | BU23-0124 |  | 1 |  |  |  | 1
AJ23-0380 | 1 |  |  |  |  | BU23-0143 |  | 2 |  |  |  | 2
AJ23-0382 | 1 |  |  |  |  | BU23-0160 |  | 1 |  |  |  | 1
AJ23-0789 | 126 |  |  |  |  | BU23-0166 |  | 2 |  |  |  | 2
AJ23-0551 | 1 |  |  |  |  | BU23-0175 |  | 1 |  |  |  | 1
Grand Total | 1192 |  |  |  |  | BU23-0182 |  | 1 |  |  |  | 1
[6 empty] | BU23-0183 |  | 1 |  |  |  | 1
[6 empty] | BU23-0192 |  | 1 |  |  |  | 1
[6 empty] | BU23-0193 |  | 69 |  |  |  | 69
[6 empty] | BU23-0205 |  | 1 |  |  |  | 1
[6 empty] | BU23-0206 |  | 1 |  |  |  | 1
[6 empty] | BU23-0208 |  | 1 |  |  |  | 1
[6 empty] | BU23-0232 |  | 1 |  |  |  | 1
[6 empty] | BU23-0233 |  | 1 |  |  |  | 1
[6 empty] | BU23-0262 |  | 1 |  |  |  | 1
[6 empty] | BU23-0264 |  | 2 |  |  |  | 2
[6 empty] | BU23-0279 |  | 1 |  |  |  | 1
[6 empty] | BU23-0281 |  | 1 |  |  |  | 1
[6 empty] | BU23-029 |  | 1 |  |  |  | 1
[6 empty] | BU23-030 |  | 1 |  |  |  | 1
[6 empty] | BU23-0306 |  | 1 |  |  |  | 1
[6 empty] | BU23-0314 |  | 1 |  |  |  | 1
[6 empty] | BU23-032 |  | 1 |  |  |  | 1
[6 empty] | BU23-0332 |  | 13 |  |  |  | 13
[6 empty] | BU23-0338 |  | 1 |  |  |  | 1
[6 empty] | BU23-0350 |  | 1 |  |  |  | 1
[6 empty] | BU23-0351 |  | 1 |  |  |  | 1
[6 empty] | BU23-0353 |  | 1 |  |  |  | 1
[6 empty] | BU23-0353 |  | 2 |  |  |  | 2
[6 empty] | BU23-0357 |  | 1 |  |  |  | 1
[6 empty] | BU23-0366 |  | 24 |  |  |  | 24
[6 empty] | BU23-0371 |  | 11 |  |  |  | 11
[6 empty] | BU23-0372 |  | 2 |  |  |  | 2
[6 empty] | BU23-0373 |  | 1 |  |  |  | 1
[6 empty] | BU23-0375 |  | 1 |  |  |  | 1
[6 empty] | BU23-249 |  | 1 |  |  |  | 1
[6 empty] | BU23-276 |  | 21 |  |  |  | 21
[6 empty] | BU24-0005 |  | 26 |  |  |  | 26
[6 empty] | BU24-0014 |  | 11 |  |  |  | 11
[6 empty] | BU24-0018 |  | 4 |  |  |  | 4
[6 empty] | BU24-0020 |  | 11 |  |  |  | 11
[6 empty] | BU24-0021 |  | 11 |  |  |  | 11
[6 empty] | BU24-0022 |  | 13 |  |  |  | 13
[6 empty] | BU24-0027 |  | 1 |  |  |  | 1
[6 empty] | BU24-0064 |  | 1 |  |  |  | 1
[6 empty] | BU24-0073 |  | 1 |  |  |  | 1
[6 empty] | BU24-0085 |  | 30 |  |  |  | 30
[6 empty] | BU24-0086 |  | 39 |  |  |  | 39
[6 empty] | BU24-0087 |  | 6 |  |  |  | 6
[6 empty] | BU24-0089 |  | 11 |  |  |  | 11
[6 empty] | BU24-0092 |  | 9 |  |  |  | 9
[6 empty] | BU24-0093 |  | 1 |  |  |  | 1
[6 empty] | BU24-0095 |  | 2 |  |  |  | 2
[6 empty] | BU24-0096 |  | 2 |  |  |  | 2
[6 empty] | BU24-0097 |  | 5 |  |  |  | 5
[6 empty] | BU24-0098 |  | 7 |  |  |  | 7
[6 empty] | BU-24-0098 |  | 84 |  |  |  | 84
[6 empty] | BU24-0103 |  | 9 |  |  |  | 9
[6 empty] | BU24-0107 |  | 6 |  |  |  | 6
[6 empty] | BU240110 |  | 20 |  |  |  | 20
[6 empty] | BU24-0112 |  | 3 |  |  |  | 3
[6 empty] | BU24-0119 |  | 7 |  |  |  | 7
[6 empty] | UCO23-0003 |  |  | 14 |  |  | 14
[6 empty] | UCO-P0045 |  |  | 17 |  |  | 17
(blank)
[6 empty] | BU24-0081 |  | 2 |  |  |  | 2
[6 empty] | AJ23-0723 | 1 |  |  |  |  | 1
[6 empty] | BU24-0015 |  | 5 |  |  |  | 5
[6 empty] | BU24-0117 |  | 42 |  |  |  | 42
[6 empty] | AJ23-0667 | 1 |  |  |  |  | 1
[6 empty] | BU24-0028 |  | 6 |  |  |  | 6
[6 empty] | BU24-0066 |  | 13 |  |  |  | 13
[6 empty] | AJ23-0472 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0750 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0475 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0420 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0473 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0474 | 1 |  |  |  |  | 1
[6 empty] | BU23-0352 |  | 1 |  |  |  | 1
[6 empty] | AJ23-0471 | 1 |  |  |  |  | 1
[6 empty] | BU24-0132 |  | 26 |  |  |  | 26
[6 empty] | BU23-0310 |  | 1 |  |  |  | 1
[6 empty] | BU24-0048 |  | 3 |  |  |  | 3
[6 empty] | AJ23-0699 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0229 | 1 |  |  |  |  | 1
[6 empty] | AJ24-0170 | 1 |  |  |  |  | 1
[6 empty] | BU24-0139 |  | 22 |  |  |  | 22
[6 empty] | BU24-0140 |  | 1 |  |  |  | 1
[6 empty] | AJ22-0179 | 1 |  |  |  |  | 1
[6 empty] | BU24-0071 |  | 23 |  |  |  | 23
[6 empty] | BU24-0059 |  | 105 |  |  |  | 105
[6 empty] | AJ23-0566 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0423 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0584 | 1 |  |  |  |  | 1
[6 empty] | BU24-0072 |  | 36 |  |  |  | 36
[6 empty] | AJ23-0701 | 1 |  |  |  |  | 1
[6 empty] | BU23-0368 |  | 1 |  |  |  | 1
[6 empty] | AJ21-0097 |  |  |  |  | 1 | 1
[6 empty] | AJ22-0266 | 1 |  |  |  |  | 1
[6 empty] | AJ22-0258 | 1 |  |  |  |  | 1
[6 empty] | BU24-0141 |  | 20 |  |  |  | 20
[6 empty] | AJ24-0202 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0093 | 1 |  |  |  |  | 1
[6 empty] | AJ24-0022 | 1 |  |  |  |  | 1
[6 empty] | AJ22-0300 | 1 |  |  |  |  | 1
[6 empty] | BU24-0147 |  | 2 |  |  |  | 2
[6 empty] | BU23-241 |  | 65 |  |  |  | 65
[6 empty] | BU24-0051 |  | 54 |  |  |  | 54
[6 empty] | BU24-0050 |  | 54 |  |  |  | 54
[6 empty] | BU23-0275 |  | 1 |  |  |  | 1
[6 empty] | BU23-0083 |  | 1 |  |  |  | 1
[6 empty] | BU23-0031 |  | 1 |  |  |  | 1
[6 empty] | BU23-0082 |  | 1 |  |  |  | 1
[6 empty] | AJ23-0250 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0219 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0751 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0143 | 1 |  |  |  |  | 1
[6 empty] | AJ24‐0009 | 1 |  |  |  |  | 1
[6 empty] | BU24-0144 |  | 9 |  |  |  | 9
[6 empty] | AJ23-0238 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0740 | 1 |  |  |  |  | 1
[6 empty] | BU24-0058 |  | 34 |  |  |  | 34
[6 empty] | BU24-0148 |  | 13 |  |  |  | 13
[6 empty] | BU24-0151 |  | 16 |  |  |  | 16
[6 empty] | AJ24-0203 | 1 |  |  |  |  | 1
[6 empty] | BU23-270 |  | 64 |  |  |  | 64
[6 empty] | BU24-0076 |  | 1 |  |  |  | 1
[6 empty] | AJ23-0620 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0247 | 1 |  |  |  |  | 1
[6 empty] | BU24-0167 |  | 3 |  |  |  | 3
[6 empty] | BU24-0165 |  | 2 |  |  |  | 2
[6 empty] | BU24-0171 |  | 16 |  |  |  | 16
[6 empty] | AJ23-0376 | 1 |  |  |  |  | 1
[6 empty] | BU24-0168 |  | 15 |  |  |  | 15
[6 empty] | BU24-0169 |  | 15 |  |  |  | 15
[6 empty] | BU24-0175 |  | 7 |  |  |  | 7
[6 empty] | BU24-0143 |  | 6 |  |  |  | 6
[6 empty] | BU24-0172 |  | 7 |  |  |  | 7
[6 empty] | BU23-0226 |  | 46 |  |  |  | 46
[6 empty] | BU24-0170 |  | 15 |  |  |  | 15
[6 empty] | BU24-0173 |  | 16 |  |  |  | 16
[6 empty] | BU24-0177 |  | 1 |  |  |  | 1
[6 empty] | BU23-0221 |  | 1 |  |  |  | 1
[6 empty] | BU23-223 |  | 2 |  |  |  | 2
[6 empty] | AJ23-0378 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0494 | 1 |  |  |  |  | 1
[6 empty] | AJ21-0051 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0254 | 1 |  |  |  |  | 1
[6 empty] | BU24-0118 |  | 39 |  |  |  | 39
[6 empty] | AJ23-0439 | 1 |  |  |  |  | 1
[6 empty] | AJ24-0050 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0767 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0380 | 1 |  |  |  |  | 1
[6 empty] | AJ23-0382 | 1 |  |  |  |  | 1
[6 empty] | BU24-0060 |  | 1 |  |  |  | 1
[6 empty] | AJ23-0789 | 126 |  |  |  |  | 126
[6 empty] | BU20-0026A |  | 1 |  |  |  | 1
[6 empty] | BU20-0026B |  | 1 |  |  |  | 1
[6 empty] | BU24-0040 |  | 16 |  |  |  | 16
[6 empty] | BU24-0023 |  | 12 |  |  |  | 12
[6 empty] | BU24-0019 |  | 12 |  |  |  | 12
[6 empty] | BU24-0179 |  | 3 |  |  |  | 3
[6 empty] | BU24-0160 |  | 18 |  |  |  | 18
[6 empty] | AJ23-0551 | 1 |  |  |  |  | 1
[6 empty] | BU24-0012 |  | 1 |  |  |  | 1
[6 empty] | BU24-0174 |  | 34 |  |  |  | 34
[6 empty] | BU24-0129 |  | 1 |  |  |  | 1
[6 empty] | BU24-0006 |  | 1 |  |  |  | 1
[6 empty] | BU23-0379 |  | 1 |  |  |  | 1
[6 empty] | Grand Total | 1192 | 1454 | 31 |  | 1 | 2678

## PJT_BOM_Month (hidden)
year | 2023 | [14 empty] | year | 2024
Count of PROJECT# | Column Labels | [14 empty] | Count of PROJECT# | Column Labels
Row Labels | January | February | March | April | May | June | July | August | September | October | November | December |  |  |  | Row Labels | January | February | March
AJ20-0135 | [8 empty] | 1 | [6 empty] | AJ23-0079 |  | 1
AJ21-0011 | [11 empty] | 2 | Jan | 8 | January | AJ23-0470 | 1 |  |  | Jan | 44 | January
AJ21-0038 |  |  | 1 |  |  |  |  | 1 |  | 1 |  |  | Feb | 6 | February | AJ23-0512 | 1 |  |  | Feb | 53 | February
AJ22-0004 | [7 empty] | 1 | 1 |  |  |  | Mar | 13 | March | BU23-0193 | 67 |  |  | Mar | 17 | March
AJ22-0021 | 1 | [11 empty] | Apr | 20 | April | BU23-0366 | 1 |  |  | Apr | 0 | April
AJ22-0044 |  |  |  | 1 | [8 empty] | May | 31 | May | BU23-276 | 21 |  |  | May | 0 | May
AJ22-0055 | [8 empty] | 1 |  |  |  | Jun | 9 | June | BU24-0005 | 26 |  |  | Jun | 0 | June
AJ22-0073 | [7 empty] | 1 |  | 1 |  |  | Jul | 6 | July | BU24-0064 | 1 |  |  | Jul | 0 | July
AJ22-0110 | [11 empty] | 1 | Aug | 63 | August | BU24-0103 | 9 |  |  | Aug | 0 | August
AJ22-0120 | [11 empty] | 1 | Sep | 26 | September | BU24-0081 | 2 |  |  | Sep | 0 | September
AJ22-0123 | [7 empty] | 1 | 1 |  |  |  | Oct | 43 | October | AJ23-0723 | 1 |  |  | Oct | 0 | October
AJ22-0135 | 58 |  |  | 5 |  |  |  | 57 | 88 | 8 | 19 |  | Nov | 21 | November | BU24-0015 | 5 |  |  | Nov | 0 | November
AJ22-0136 |  |  | 21 | [9 empty] | Dec | 71 | December | BU24-0117 | 42 |  |  | Dec | 0 | December
AJ22-0143, |  |  | 1 | [12 empty] | AJ23-0667 | 1
AJ22-0149 | [5 empty] | 1 |  | 1 | [7 empty] | BU24-0028 | 6
AJ22-0152 |  | 1 |  |  | 2 | 3 | 3 | 49 | 4 | 6 | [5 empty] | BU24-0066 | 13
AJ22-0168 | [11 empty] | 1 |  |  |  | AJ23-0472 | 1
AJ22-0184 | [7 empty] | 1 | 1 | [6 empty] | AJ23-0750 | 1
AJ22-0189 | [7 empty] | 1 |  |  | 1 |  |  |  |  | AJ23-0475 | 1
AJ22-0190 | [10 empty] | 1 |  |  |  |  | AJ23-0420 | 1
AJ22-0198 |  |  |  |  | 1 |  |  |  | 1 | [6 empty] | AJ23-0473 | 1
AJ22-0199 | [8 empty] | 1 | [6 empty] | AJ23-0474 | 1
AJ22-0205 | 1 |  |  | 1 | [11 empty] | BU23-0352 | 1
AJ22-0222 |  |  |  |  | 1 |  |  | 1 | [7 empty] | AJ23-0471 | 1
AJ22-0231 |  |  |  | 1 | [11 empty] | BU24-0132 | 26
AJ22-0233 | 1 | [14 empty] | BU24-0048 | 3
AJ22-0240 | [7 empty] | 1 |  | 1 | [5 empty] | AJ23-0699 | 1
AJ22-0267 | [11 empty] | 1 |  |  |  | AJ23-0229 | 1
AJ22-0297 |  | 1 | [13 empty] | AJ24-0170 | 1
AJ22-0317 |  |  | 1 | [12 empty] | BU24-0139 | 22
AJ22-0321 |  |  |  | 1 | [11 empty] | BU24-0140 | 1
AJ22-0322 |  |  |  | 1 | 1 |  |  | 1 | [7 empty] | AJ22-0179 | 1
AJ22-0323 | [7 empty] | 1 |  | 1 | [5 empty] | BU24-0071 | 23
AJ22-0324 |  |  |  | 1 | 1 | [10 empty] | BU24-0059 | 105
AJ22-0326 |  |  |  | 1 | 1 |  |  | 1 | [7 empty] | AJ23-0566 | 1
AJ22-0327 |  |  |  | 1 | [11 empty] | AJ23-0423 | 1
AJ22-0351 |  |  | 1 | [12 empty] | AJ23-0584 | 1
AJ22-0371 | [7 empty] | 1 |  |  |  | 1 |  |  |  | BU24-0072 | 36
AJ22-0378 | [8 empty] | 1 | [6 empty] | AJ23-0701 | 1
AJ22-0380 | [7 empty] | 1 | 1 | [6 empty] | BU23-0368 | 1
AJ22-0390 | [7 empty] | 1 |  | 1 | [5 empty] | AJ21-0097 | 1
AJ22-0399 | [10 empty] | 1 |  |  |  |  | AJ22-0266 | 1
AJ22-0400 |  |  |  |  | 1 |  |  | 1 | [7 empty] | AJ22-0258 | 1
AJ22-0406 | [7 empty] | 1 | 1 | [6 empty] | BU24-0141 | 20
AJ22-0417 |  |  |  |  | 1 |  |  |  | 1 | [6 empty] | AJ24-0202 | 1
AJ22-0455 | [7 empty] | 1 | [7 empty] | AJ23-0093 |  | 1
AJ22-0465 | [7 empty] | 1 |  |  | 1 |  |  |  |  | AJ24-0022 |  | 1
AJ22-0474 | [10 empty] | 1 |  |  |  |  | AJ22-0300 |  | 1
AJ22-0475 | [7 empty] | 1 |  |  |  | 1 |  |  |  | BU24-0147 |  | 2
AJ22-0497 |  |  |  |  | 1 |  |  | 1 | [7 empty] | BU23-241 |  | 65
AJ22-0505 | [10 empty] | 1 |  |  |  |  | BU24-0051 |  | 54
AJ22-0507 |  |  |  |  | 1 | [10 empty] | BU24-0050 |  | 54
AJ22-0524 | [7 empty] | 1 |  |  | 1 |  |  |  |  | BU23-0275 |  | 1
AJ22-0530 | [11 empty] | 1 |  |  |  | BU23-0083 |  | 1
AJ22-0534 | 1 | [14 empty] | BU23-0031 |  | 1
AJ22-0536 |  |  |  |  | 1 |  |  |  |  | 1 | [5 empty] | BU23-0082 |  | 1
AJ22-0537 | [7 empty] | 1 | [7 empty] | AJ23-0250 |  | 1
AJ22-0546 | [9 empty] | 1 | [5 empty] | AJ23-0219 |  | 1
AJ22-0547 |  |  |  |  | 1 |  |  | 1 | [7 empty] | AJ23-0751 |  | 1
AJ22-0549 | [7 empty] | 1 |  | 1 | [5 empty] | AJ23-0143 |  | 1
AJ22-0551 | [10 empty] | 3 |  |  |  |  | AJ24‐0009 |  | 1
AJ23-0004 | [5 empty] | 1 |  | 1 | [7 empty] | BU24-0144 |  | 9
AJ23-0005 |  |  |  |  | 1 |  |  | 1 | [7 empty] | AJ23-0238 |  | 1
AJ23-0006 |  |  |  |  | 1 |  |  | 1 | [7 empty] | AJ23-0740 |  | 1
AJ23-0007 | [7 empty] | 1 | 1 | [6 empty] | BU24-0058 |  | 34
AJ23-0040 | [7 empty] | 1 |  |  |  | 1 |  |  |  | BU24-0148 |  | 13
AJ23-0045 |  |  |  | 1 | [11 empty] | BU24-0151 |  | 16
AJ23-0068 | [7 empty] | 1 |  |  | 1 |  |  |  |  | AJ24-0203 |  | 1
AJ23-0079 | [7 empty] | 1 |  | 1 | [5 empty] | BU23-270 |  | 64
AJ23-0089 |  |  | 1 | [12 empty] | BU24-0076 |  | 1
AJ23-0090 |  |  |  | 1 | [11 empty] | AJ23-0620 |  | 1
AJ23-0101 | [7 empty] | 1 |  | 1 | [5 empty] | AJ23-0247 |  | 1
AJ23-0122 |  |  |  | 26 | [11 empty] | BU24-0167 |  | 3
AJ23-0132 |  |  |  |  | 1 | [10 empty] | BU24-0165 |  | 1
AJ23-0133 |  |  |  |  | 1 | [10 empty] | BU24-0171 |  | 16
AJ23-0134 |  |  |  | 1 | [11 empty] | AJ23-0376 |  | 1
AJ23-0166 | [7 empty] | 1 |  | 1 | [5 empty] | BU24-0168 |  | 15
AJ23-0167 | [8 empty] | 1 | [6 empty] | BU24-0169 |  | 15
AJ23-0172 | [7 empty] | 1 |  | 1 | [5 empty] | BU24-0175 |  | 7
AJ23-0179 | [7 empty] | 1 | 1 | [6 empty] | BU24-0143 |  | 3 | 3
AJ23-0192 | [8 empty] | 1 | [6 empty] | BU24-0172 |  | 7
AJ23-0193 |  |  |  |  | 1 |  |  |  | 1 | [6 empty] | BU23-0226 |  | 46
AJ23-0225 | [7 empty] | 1 |  | 1 | [5 empty] | BU24-0170 |  | 15
AJ23-0237 | [11 empty] | 1 |  |  |  | BU24-0173 |  | 16
AJ23-0240 | [11 empty] | 1 |  |  |  | BU24-0177 |  | 1
AJ23-0241 | [11 empty] | 1 |  |  |  | BU23-0221 |  | 1
AJ23-0242 | [11 empty] | 1 |  |  |  | BU23-223 |  | 2
AJ23-0243 | [11 empty] | 1 |  |  |  | AJ23-0378 |  | 1
AJ23-0245 | [9 empty] | 1 | [5 empty] | AJ23-0494 |  | 1
AJ23-0252 | [11 empty] | 1 |  |  |  | AJ21-0051 |  | 1
AJ23-0258 | [7 empty] | 1 | 1 | [6 empty] | AJ23-0254 |  | 1
AJ23-0260 | [7 empty] | 2 |  | 1 | 1 |  |  |  |  | BU24-0118 |  |  | 39
AJ23-0268 | [7 empty] | 1 |  | 1 | [5 empty] | AJ23-0439 |  | 1
AJ23-0300 | [7 empty] | 1 |  | 1 | [5 empty] | AJ24-0050 |  |  | 1
AJ23-0306 | [8 empty] | 1 | [6 empty] | AJ23-0767 |  |  | 1
AJ23-0337 | [7 empty] | 1 | [7 empty] | AJ23-0380 |  |  | 1
AJ23-0365 | [7 empty] | 1 | [7 empty] | AJ23-0382 |  |  | 1
AJ23-0366 | [8 empty] | 1 | [6 empty] | BU24-0060 |  |  | 1
AJ23-0413 |  |  |  | 1 | [11 empty] | AJ23-0789 |  | 126
AJ23-0425 | [9 empty] | 1 | [5 empty] | BU20-0026A |  |  | 1
AJ23-0437 | [9 empty] | 1 | [5 empty] | BU20-0026B |  |  | 1
AJ23-0442 | [9 empty] | 1 | [5 empty] | BU24-0040 |  |  | 16
AJ23-0450 | [7 empty] | 1 |  |  |  | 1 |  |  |  | BU24-0023 |  | 12
AJ23-0467 |  |  |  |  | 15 | 1 | 2 | 48 | [7 empty] | BU24-0019 |  | 11
AJ23-0467 | [7 empty] | 1 | [7 empty] | BU24-0179 |  |  | 3
AJ23-0468 | [11 empty] | 1 |  |  |  | BU24-0160 |  |  | 18
AJ23-0469 | [11 empty] | 1 |  |  |  | AJ23-0551 |  | 1
AJ23-0481 | [9 empty] | 1 | [5 empty] | BU24-0012 |  |  | 1
AJ23-0482 | [7 empty] | 1 |  | 1 | [5 empty] | BU24-0174 |  | 1 | 33
AJ23-0492 | [11 empty] | 1 |  |  |  | BU24-0129 |  |  | 1
AJ23-0493 | [7 empty] | 1 |  | 1 | [5 empty] | BU24-0006 |  |  | 1
AJ23-0496 | [11 empty] | 1 |  |  |  | BU23-0379 |  |  | 1
AJ23-0499 | [7 empty] | 1
AJ23-0502 | [10 empty] | 1
AJ23-0508 | [7 empty] | 2 | 78 | 2 | 35
AJ23-0510 | [11 empty] | 1
AJ23-0512 | [11 empty] | 1
AJ23-0532 | [9 empty] | 1
AJ23-0536 | [11 empty] | 2
AJ23-0540 | [7 empty] | 1
AJ23-0563 | [7 empty] | 1
AJ23-0574 | [6 empty] | 1 | 1
AJ23-0579 | [7 empty] | 1 |  | 1
AJ23-0593 | [11 empty] | 1
AJ23-0598 | [7 empty] | 1 |  | 1
AJ23-0606 | [11 empty] | 1
AJ23-0610 | [11 empty] | 1
AJ23-0611 | [11 empty] | 1
AJ23-0619 | [11 empty] | 1
AJ23-0645 | [10 empty] | 1
AJ23-0666 | 1
AJ23-0668 | [7 empty] | 1 |  | 1
AJ23-0676 | [11 empty] | 1
AJ23-0708 | [11 empty] | 32
AJ23-0726 | [10 empty] | 1
AJ23-0747 | [8 empty] | 1 |  | 23 | 3
AJ23-0782 | [7 empty] | 1
AJ23-0788 | [11 empty] | 1
AJ24-0065 | [11 empty] | 1
BU22-0007 | [11 empty] | 2
BU22-0028 |  |  |  | 1
BU22-0031 | [9 empty] | 1
BU22-0045 | [9 empty] | 1
BU22-0055 |  |  |  |  | 1
BU22-0066 |  |  |  |  | 1
BU22-0105 |  |  |  | 1
BU22-0105 | [9 empty] | 1
BU22-0109 | [5 empty] | 1
BU22-0110 |  |  | 1
BU22-031 |  |  |  | 1
BU22-038 |  |  |  | 1
BU22-039 | 1
BU22-041 |  | 1
BU22-047 |  |  | 1
BU22-048 | 1 | [8 empty] | 1
BU22-057 |  |  | 1
BU22-062 |  |  |  |  | 1
BU22-064 |  |  | 1
BU22-065 |  |  | 1
BU22-066 |  |  | 1
BU22-066 |  |  |  | 1
BU22-069 |  |  |  | 1
BU22-070 |  | 1
BU22-089 |  |  | 1
BU23-0023 |  | 1
BU23-0029 | [8 empty] | 1
BU23-0077 | [5 empty] | 1
BU23-0094 | [6 empty] | 1
BU23-0094 |  |  |  |  | 1
BU23-0102 |  |  |  |  | 1
BU23-0111 |  |  |  |  | 1
BU23-0123 | [7 empty] | 1
BU23-0124 | [10 empty] | 1
BU23-0143 |  |  |  |  | 1 |  | 1
BU23-0160 | [11 empty] | 1
BU23-0166 |  |  |  |  | 1 | 1
BU23-0175 | [5 empty] | 1
BU23-0182 | [6 empty] | 1
BU23-0183 | [9 empty] | 1
BU23-0192 | [9 empty] | 1
BU23-0193 | [7 empty] | 1 |  |  |  | 1
BU23-0205 | [11 empty] | 1
BU23-0206 | [5 empty] | 1
BU23-0208 | [11 empty] | 1
BU23-0232 | [8 empty] | 1
BU23-0233 | [9 empty] | 1
BU23-0262 | [9 empty] | 1
BU23-0264 | [7 empty] | 1 |  |  |  | 1
BU23-0279 | [9 empty] | 1
BU23-0281 | [9 empty] | 1
BU23-029 |  |  |  |  | 1
BU23-030 |  |  |  |  | 1
BU23-0306 | [9 empty] | 1
BU23-0314 | [11 empty] | 1
BU23-032 |  |  |  |  | 1
BU23-0332 | [11 empty] | 13
BU23-0338 | [11 empty] | 1
BU23-0350 | [10 empty] | 1
BU23-0351 | [9 empty] | 1
BU23-0353 | [10 empty] | 1
BU23-0353 | [7 empty] | 1 |  |  | 1
BU23-0357 | [11 empty] | 1
BU23-0366 | [11 empty] | 23
BU23-0371 | [11 empty] | 11
BU23-0372 | [8 empty] | 1 | 1
BU23-0373 | [11 empty] | 1
BU23-0375 | [11 empty] | 1
BU23-249 | [11 empty] | 1
BU24-0014 | [11 empty] | 11
BU24-0018 | [11 empty] | 4
BU24-0020 | [11 empty] | 11
BU24-0021 | [11 empty] | 11
BU24-0022 | [11 empty] | 13
BU24-0027 | [11 empty] | 1
BU24-0073 | [11 empty] | 1
BU24-0085 | [11 empty] | 30
BU24-0086 | [11 empty] | 39
BU24-0087 | [11 empty] | 6
BU24-0089 | [11 empty] | 11
BU24-0092 | [11 empty] | 9
BU24-0093 | [11 empty] | 1
BU24-0095 | [11 empty] | 2
BU24-0096 | [11 empty] | 2
BU24-0097 | [11 empty] | 5
BU24-0098 | [11 empty] | 7
BU-24-0098 | [11 empty] | 84
BU24-0107 | [11 empty] | 6
BU240110 | [11 empty] | 20
BU24-0112 | [11 empty] | 3
BU24-0119 | [11 empty] | 7
UCO23-0003 |  |  |  |  | 14
UCO-P0045 |  | 16 |  |  | 1
(blank)
BU23-0310 | [10 empty] | 1
BU24-0019 | [11 empty] | 1

## pr_aj_and_bj_month (hidden)
Color Code list | AJ
year | 2023
Column Labels
| January | February | March | April | May | June | July | August | September | October | November | December | Grand Total | Jan | 63 | January
Count of PR # | 63 | 2 | 26 | 43 | 33 | 6 | 6 | 212 | 190 | 43 | 92 | 67 | 783 | Feb | 2 | February
[14 empty] | Mar | 26 | March
[14 empty] | Apr | 43 | April
[14 empty] | May | 33 | May
[14 empty] | Jun | 6 | June
[14 empty] | Jul | 6 | July
[14 empty] | Aug | 212 | August
[14 empty] | Sep | 190 | September
[14 empty] | Oct | 43 | October
[14 empty] | Nov | 92 | November
[14 empty] | Dec | 67 | December
Color Code list | BU
year | 2023
Column Labels
| January | February | March | April | May | June | July | August | September | October | November | December | Grand Total | Jan | 2 | January
Count of PR # | 2 | 3 | 7 | 6 | 11 | 5 | 3 | 4 | 3 | 13 | 5 | 338 | 400 | Feb | 3 | February
[14 empty] | Mar | 7 | March
[14 empty] | Apr | 6 | April
[14 empty] | May | 11 | May
[14 empty] | Jun | 5 | June
[14 empty] | Jul | 3 | July
[14 empty] | Aug | 4 | August
[14 empty] | Sep | 3 | September
[14 empty] | Oct | 13 | October
[14 empty] | Nov | 5 | November
[14 empty] | Dec | 338 | December
Color Code list | AJ
year | 2024
Column Labels
| January | February | March | Grand Total | [9 empty] | Jan | 21 | January
Count of PR # | 21 | 20 | 4 | 45 | [9 empty] | Feb | 20 | February
[14 empty] | Mar | 4 | March
[14 empty] | Apr | 0 | April
[14 empty] | May | 0 | May
[14 empty] | Jun | 0 | June
[14 empty] | Jul | 0 | July
[14 empty] | Aug | 0 | August
[14 empty] | Sep | 0 | September
[14 empty] | Oct | 0 | October
[14 empty] | Nov | 0 | November
[14 empty] | Dec | 0 | December
Color Code list | BU
year | 2024
Column Labels
| January | February | March | Grand Total | [9 empty] | Jan | 427 | January
Count of PR # | 427 | 474 | 117 | 1018 | [9 empty] | Feb | 474 | February
[14 empty] | Mar | 117 | March
[14 empty] | Apr | 0 | April
[14 empty] | May | 0 | May
[14 empty] | Jun | 0 | June
[14 empty] | Jul | 0 | July
[14 empty] | Aug | 0 | August
[14 empty] | Sep | 0 | September
[14 empty] | Oct | 0 | October
[14 empty] | Nov | 0 | November
[14 empty] | Dec | 0 | December

## pr_mx_month (hidden)
table | (Multiple Items)
year | 2023
Column Labels
| January | February | March | April | May | June | July | August | September | October | November | December | Grand Total
Count of PR # | 57 | 17 | 21 | 32 | 34 | 3 | 4 | 218 | 172 | 15 | 74 | 356 | 1003 | Jan | 57 | January
[14 empty] | Feb | 17 | February
[14 empty] | Mar | 21 | March
[14 empty] | Apr | 32 | April
[14 empty] | May | 34 | May
[14 empty] | Jun | 3 | June
[14 empty] | Jul | 4 | July
[14 empty] | Aug | 218 | August
[14 empty] | Sep | 172 | September
[14 empty] | Oct | 15 | October
[14 empty] | Nov | 74 | November
[14 empty] | Dec | 356 | December
table | (Multiple Items)
year | 2024
Column Labels
| January | February | March | Grand Total
Count of PR # | 416 | 456 | 110 | 982 | [9 empty] | Jan | 416 | January
[14 empty] | Feb | 456 | February
[14 empty] | Mar | 110 | March
[14 empty] | Apr | 0 | April
[14 empty] | May | 0 | May
[14 empty] | Jun | 0 | June
[14 empty] | Jul | 0 | July
[14 empty] | Aug | 0 | August
[14 empty] | Sep | 0 | September
[14 empty] | Oct | 0 | October
[14 empty] | Nov | 0 | November
[14 empty] | Dec | 0 | December

## pr_mx_aj_month (hidden)
Color Code list | AJ
table | (Multiple Items)
year | 2023
Column Labels
| January | February | March | April | May | June | July | August | September | October | November | December | Grand Total | Jan | 57 | January
Count of PR # | 57 | 1 | 21 | 32 | 19 | 3 | 4 | 211 | 171 | 15 | 73 | 34 | 641 | Feb | 1 | February
[14 empty] | Mar | 21 | March
[14 empty] | Apr | 32 | April
[14 empty] | May | 19 | May
[14 empty] | Jun | 3 | June
[14 empty] | Jul | 4 | July
[14 empty] | Aug | 211 | August
[14 empty] | Sep | 171 | September
[14 empty] | Oct | 15 | October
[14 empty] | Nov | 73 | November
[14 empty] | Dec | 34 | December
Color Code list | AJ
table | (Multiple Items)
year | 2024
Column Labels
| February | Grand Total | [11 empty] | Jan | 0 | January
Count of PR # | [13 empty] | Feb | 0 | February
[14 empty] | Mar | 0 | March
[14 empty] | Apr | 0 | April
[14 empty] | May | 0 | May
[14 empty] | Jun | 0 | June
[14 empty] | Jul | 0 | July
[14 empty] | Aug | 0 | August
[14 empty] | Sep | 0 | September
[14 empty] | Oct | 0 | October
[14 empty] | Nov | 0 | November
[14 empty] | Dec | 0 | December

## pr_mx_bu_month (hidden)
table | (Multiple Items)
Color Code list | BU
year | 2023
| Column Labels |  |  |  |  | Jan | 0 | January
| August | September | November | December | Grand Total | Feb | 0 | February
Count of PR # | 3 | 1 | 1 | 322 | 327 | Mar | 0 | March
[6 empty] | Apr | 0 | April
[6 empty] | May | 0 | May
[6 empty] | Jun | 0 | June
[6 empty] | Jul | 0 | July
[6 empty] | Aug | 3 | August
[6 empty] | Sep | 1 | September
[6 empty] | Oct | 0 | October
[6 empty] | Nov | 1 | November
[6 empty] | Dec | 322 | December
table | (Multiple Items)
Color Code list | BU
year | 2024
| Column Labels |  |  |  |  | Jan | 416 | January
| January | February | March | Grand Total |  | Feb | 456 | February
Count of PR # | 416 | 456 | 110 | 982 |  | Mar | 110 | March
[6 empty] | Apr | 0 | April
[6 empty] | May | 0 | May
[6 empty] | Jun | 0 | June
[6 empty] | Jul | 0 | July
[6 empty] | Aug | 0 | August
[6 empty] | Sep | 0 | September
[6 empty] | Oct | 0 | October
[6 empty] | Nov | 0 | November
[6 empty] | Dec | 0 | December

## pr_fab_aj_month (hidden)
Color Code list | AJ
table | Fab table
year | 2023
Column Labels
| January | March | April | May | June | July | September | October | November | December | Grand Total | Jan | 1 | January
Count of PR # | 1 | 2 | 2 | 1 | 1 | 1 | 2 | 1 | 9 | 7 | 27 | Feb | 0 | February
[12 empty] | Mar | 2 | March
[12 empty] | Apr | 2 | April
[12 empty] | May | 1 | May
[12 empty] | Jun | 1 | June
[12 empty] | Jul | 1 | July
[12 empty] | Aug | 0 | August
[12 empty] | Sep | 2 | September
[12 empty] | Oct | 1 | October
[12 empty] | Nov | 9 | November
[12 empty] | Dec | 7 | December
Color Code list | AJ
table | Fab table
year | 2024
Column Labels
| January | February | Grand Total | [8 empty] | Jan | 1 | January
Count of PR # | 1 | 1 | 2 | [8 empty] | Feb | 1 | February
[12 empty] | Mar | 0 | March
[12 empty] | Apr | 0 | April
[12 empty] | May | 0 | May
[12 empty] | Jun | 0 | June
[12 empty] | Jul | 0 | July
[12 empty] | Aug | 0 | August
[12 empty] | Sep | 0 | September
[12 empty] | Oct | 0 | October
[12 empty] | Nov | 0 | November
[12 empty] | Dec | 0 | December

## pr_fab_bu_month (hidden)
Color Code list | BU
table | Fab table
year | 2023
Column Labels
| December | Grand Total |  |  | Jan | 0 | January
Count of PR # | 5 | 5 |  |  | Feb | 0 | February
[5 empty] | Mar | 0 | March
[5 empty] | Apr | 0 | April
[5 empty] | May | 0 | May
[5 empty] | Jun | 0 | June
[5 empty] | Jul | 0 | July
[5 empty] | Aug | 0 | August
[5 empty] | Sep | 0 | September
[5 empty] | Oct | 0 | October
[5 empty] | Nov | 0 | November
[5 empty] | Dec | 5 | December
Color Code list | BU
table | Fab table
year | 2024
Column Labels
| January | February | March | Grand Total | Jan | 10 | January
Count of PR # | 10 | 16 | 1 | 27 | Feb | 16 | February
[5 empty] | Mar | 1 | March
[5 empty] | Apr | 0 | April
[5 empty] | May | 0 | May
[5 empty] | Jun | 0 | June
[5 empty] | Jul | 0 | July
[5 empty] | Aug | 0 | August
[5 empty] | Sep | 0 | September
[5 empty] | Oct | 0 | October
[5 empty] | Nov | 0 | November
[5 empty] | Dec | 0 | December

## pr_sub_aj_month (hidden)
Color Code list | AJ
table | Sub table
year | 2023
Column Labels
| January | February | March | April | May | June | July | August | September | October | November | December | Grand Total | Jan | 5 | January
Count of PR # | 5 | 1 | 3 | 9 | 13 | 2 | 1 | 1 | 17 | 27 | 10 | 26 | 115 | Feb | 1 | February
[14 empty] | Mar | 3 | March
[14 empty] | Apr | 9 | April
[14 empty] | May | 13 | May
[14 empty] | Jun | 2 | June
[14 empty] | Jul | 1 | July
[14 empty] | Aug | 1 | August
[14 empty] | Sep | 17 | September
[14 empty] | Oct | 27 | October
[14 empty] | Nov | 10 | November
[14 empty] | Dec | 26 | December
Color Code list | AJ
table | Sub table
year | 2024
Column Labels
| January | February | March | Grand Total | [9 empty] | Jan | 20 | January
Count of PR # | 20 | 19 | 4 | 43 | [9 empty] | Feb | 19 | February
[14 empty] | Mar | 4 | March
[14 empty] | Apr | 0 | April
[14 empty] | May | 0 | May
[14 empty] | Jun | 0 | June
[14 empty] | Jul | 0 | July
[14 empty] | Aug | 0 | August
[14 empty] | Sep | 0 | September
[14 empty] | Oct | 0 | October
[14 empty] | Nov | 0 | November
[14 empty] | Dec | 0 | December

## pr_sub_bu_month (hidden)
Color Code list | BU
table | Sub table
year | 2023
Column Labels
| January | February | March | April | May | June | July | August | September | October | November | December | Grand Total | Jan | 2 | January
Count of PR # | 2 | 3 | 7 | 6 | 11 | 5 | 3 | 1 | 2 | 13 | 4 | 11 | 68 | Feb | 3 | February
[14 empty] | Mar | 7 | March
[14 empty] | Apr | 6 | April
[14 empty] | May | 11 | May
[14 empty] | Jun | 5 | June
[14 empty] | Jul | 3 | July
[14 empty] | Aug | 1 | August
[14 empty] | Sep | 2 | September
[14 empty] | Oct | 13 | October
[14 empty] | Nov | 4 | November
[14 empty] | Dec | 11 | December
Color Code list | BU
table | Sub table
year | 2024
Column Labels
| January | February | March | Grand Total | [9 empty] | Jan | 1 | January
Count of PR # | 1 | 2 | 6 | 9 | [9 empty] | Feb | 2 | February
[14 empty] | Mar | 6 | March
[14 empty] | Apr | 0 | April
[14 empty] | May | 0 | May
[14 empty] | Jun | 0 | June
[14 empty] | Jul | 0 | July
[14 empty] | Aug | 0 | August
[14 empty] | Sep | 0 | September
[14 empty] | Oct | 0 | October
[14 empty] | Nov | 0 | November
[14 empty] | Dec | 0 | December

## vendor_cost_month (hidden)
Vendor | AL BAYADER INTER.GROUP COMPANY |  | AL BAYADER INTER.GROUP COMPANY
year | 2023 |  | Jan | 0
|  |  | Feb | 0
Row Labels | Count of PO # |  | Mar | 0
August | 2 |  | Apr | 0
September | 2 |  | May | 0
October | 1 |  | Jun | 0
Grand Total | 5 |  | Jul | 0
|  |  | Aug | 2
|  |  | Sep | 2
|  |  | Oct | 1
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | AL-IRTEKAZ NATIONAL GEN.TRDG.C |  | AL-IRTEKAZ NATIONAL GEN.TRDG.C
year | 2023 |  | Jan | 0
|  |  | Feb | 0
Row Labels | Count of PO # |  | Mar | 0
September | 4 |  | Apr | 0
Grand Total | 4 |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 4
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO
|  |  | Jan | 0
|  |  | Feb | 0
Vendor | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO |  | Mar | 0
year | 2023 |  | Apr | 0
|  |  | May | 0
Row Labels | Count of PO # |  | Jun | 0
August | 2 |  | Jul | 0
October | 4 |  | Aug | 2
November | 2 |  | Sep | 0
Grand Total | 8 |  | Oct | 4
|  |  | Nov | 2
|  |  | Dec | 0
CARRIER KUWAIT AIR CONDITIONING
|  |  | Jan | 0
|  |  | Feb | 0
Vendor | CARRIER KUWAIT AIR CONDITIONING |  | Mar | 0
year | 2023 |  | Apr | 0
|  |  | May | 0
Row Labels | Count of PO # |  | Jun | 0
September | 1 |  | Jul | 0
Grand Total | 1 |  | Aug | 0
|  |  | Sep | 1
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
COMMERCIAL UNITED GINCO EST.
|  |  | Jan | 0
Vendor | COMMERCIAL UNITED GINCO EST. |  | Feb | 0
year | 2023 |  | Mar | 0
|  |  | Apr | 0
Row Labels | Count of PO # |  | May | 1
May | 1 |  | Jun | 1
June | 1 |  | Jul | 0
August | 17 |  | Aug | 17
September | 4 |  | Sep | 4
December | 4 |  | Oct | 0
Grand Total | 27 |  | Nov | 0
|  |  | Dec | 4
CREDENCE TRADING EST.
|  |  | Jan | 0
Vendor | CREDENCE TRADING EST. |  | Feb | 0
year | 2023 |  | Mar | 0
|  |  | Apr | 0
Row Labels | Count of PO # |  | May | 0
August | 22 |  | Jun | 0
September | 6 |  | Jul | 0
October | 3 |  | Aug | 22
Grand Total | 31 |  | Sep | 6
|  |  | Oct | 3
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | EMCOR INTERNATIONAL GENERAL TRADING CO WLL
year | 2023
EMCOR INTERNATIONAL GENERAL TRADING CO WLL
Row Labels | Count of PO # |  | Jan | 0
September | 3 |  | Feb | 0
December | 2 |  | Mar | 0
Grand Total | 5 |  | Apr | 0
|  |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 3
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 2
Vendor | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST |  | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST
year | 2023 |  | Jan | 0
|  |  | Feb | 0
Row Labels | Count of PO # |  | Mar | 0
April | 6 |  | Apr | 6
May | 5 |  | May | 5
July | 1 |  | Jun | 0
August | 4 |  | Jul | 1
September | 14 |  | Aug | 4
October | 2 |  | Sep | 14
November | 2 |  | Oct | 2
December | 4 |  | Nov | 2
Grand Total | 38 |  | Dec | 4
Vendor | GULF PIONEER COMPANY LLC |  | GULF PIONEER COMPANY LLC
year | 2023 |  | Jan | 0
|  |  | Feb | 0
Row Labels | Count of PO # |  | Mar | 0
December | 5 |  | Apr | 0
Grand Total | 5 |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 5
Vendor | KASAR MARJAN CONTRACTING CO.
year | 2023 |  | KASAR MARJAN CONTRACTING CO.
|  |  | Jan | 0
Row Labels | Count of PO # |  | Feb | 0
August | 8 |  | Mar | 0
Grand Total | 8 |  | Apr | 0
|  |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 8
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | MARATHON INC TRADING LLC
year | 2023 |  | MARATHON INC TRADING LLC
|  |  | Jan | 0
Row Labels | Count of PO # |  | Feb | 0
November | 3 |  | Mar | 0
December | 5 |  | Apr | 0
Grand Total | 8 |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 3
|  |  | Dec | 5
Vendor | MERIT INTERNATIONAL GENERAL TRADING CO WLL |  | MERIT INTERNATIONAL GENERAL TRADING CO WLL
year | 2023 |  | Jan | 0
|  |  | Feb | 11
Row Labels | Count of PO # |  | Mar | 18
February | 11 |  | Apr | 0
March | 18 |  | May | 24
May | 24 |  | Jun | 0
August | 114 |  | Jul | 0
September | 41 |  | Aug | 114
October | 4 |  | Sep | 41
November | 16 |  | Oct | 4
December | 244 |  | Nov | 16
Grand Total | 472 |  | Dec | 244
Vendor | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL
year | 2023 |  | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL
|  |  | Jan | 0
Row Labels | Count of PO # |  | Feb | 0
September | 11 |  | Mar | 0
Grand Total | 11 |  | Apr | 0
|  |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 11
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO |  | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO
year | 2023 |  | Jan | 0
|  |  | Feb | 0
Row Labels | Count of PO # |  | Mar | 0
September | 6 |  | Apr | 0
November | 5 |  | May | 0
December | 6 |  | Jun | 0
Grand Total | 17 |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 6
|  |  | Oct | 0
|  |  | Nov | 5
|  |  | Dec | 6
RITAJ AL KUWAIT GENERAL TRADING CONTRACTING CO
Vendor | RITAJ AL KUWAIT GENERAL TRADING CONTRACTING CO |  | Jan | 0
year | 2023 |  | Feb | 0
|  |  | Mar | 0
Row Labels | Count of PO # |  | Apr | 0
September | 3 |  | May | 0
Grand Total | 3 |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 3
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | TRADEX INTERNATIONAL TRADING LLC
year | 2023 |  | TRADEX INTERNATIONAL TRADING LLC
|  |  | Jan | 0
Row Labels | Count of PO # |  | Feb | 0
November | 1 |  | Mar | 0
December | 2 |  | Apr | 0
Grand Total | 3 |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 1
|  |  | Dec | 2
Vendor | UNITEC INTERNATIONAL GENERAL TRADING CO |  | UNITEC INTERNATIONAL GENERAL TRADING CO
year | 2023 |  | Jan | 0
|  |  | Feb | 5
Row Labels | Count of PO # |  | Mar | 1
February | 5 |  | Apr | 25
March | 1 |  | May | 2
April | 25 |  | Jun | 0
May | 2 |  | Jul | 2
July | 2 |  | Aug | 24
August | 24 |  | Sep | 24
September | 24 |  | Oct | 1
October | 1 |  | Nov | 39
November | 39 |  | Dec | 83
December | 83
Grand Total | 206
Vendor | (All)
year | 2023
all
Row Labels | Count of PO # |  | Jan | 64
January | 64 |  | Feb | 21
February | 21 |  | Mar | 33
March | 33 |  | Apr | 49
April | 49 |  | May | 59
May | 59 |  | Jun | 11
June | 11 |  | Jul | 9
July | 9 |  | Aug | 220
August | 220 |  | Sep | 193
September | 193 |  | Oct | 56
October | 56 |  | Nov | 97
November | 97 |  | Dec | 384
December | 384
Grand Total | 1196
Vendor | MERIT INTERNATIONAL INC
year | 2023
MERIT INTERNATIONAL INC
Row Labels | Count of PO # |  | Jan | 0
March | 1 |  | Feb | 0
Grand Total | 1 |  | Mar | 1
|  |  | Apr | 0
|  |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | AL NISF ELECTRICAL CO WLL
year | 2023
AL NISF ELECTRICAL CO WLL
Row Labels | Count of PO # |  | Jan | 0
November | 4 |  | Feb | 0
December | 5 |  | Mar | 0
Grand Total | 9 |  | Apr | 0
|  |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 4
|  |  | Dec | 5
Vendor | EGYKUW
year | 2023
EGYKUW
Row Labels | Count of PO # |  | Jan | 0
December | 3 |  | Feb | 0
Grand Total | 3 |  | Mar | 0
|  |  | Apr | 0
|  |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 3
Vendor | Schneider
year | 2023
Schneider
Row Labels | Count of PO # |  | Jan | 0
December | 4 |  | Feb | 0
Grand Total | 4 |  | Mar | 0
|  |  | Apr | 0
|  |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 4
year | 2023
Row Labels | Count of Vendor | 21
158
AL BAYADER INTER.GROUP COMPANY | 5
AL-IRTEKAZ NATIONAL GEN.TRDG.C | 4
AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 8
CARRIER KUWAIT AIR CONDITIONING | 1
COMMERCIAL UNITED GINCO EST. | 27
CREDENCE TRADING EST. | 31
EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 5
FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 38
GULF PIONEER COMPANY LLC | 5
KASAR MARJAN CONTRACTING CO. | 8
MARATHON INC TRADING LLC | 8
MERIT INTERNATIONAL GENERAL TRADING CO WLL | 472
NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 11
RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 17
RITAJ AL KUWAIT GENERAL TRADING CONTRACTING CO | 3
TRADEX INTERNATIONAL TRADING LLC | 3
UNITEC INTERNATIONAL GENERAL TRADING CO | 206
(blank)
MERIT INTERNATIONAL INC | 1
AL NISF ELECTRICAL CO WLL | 9
EGYKUW | 3
Schneider | 4
Grand Total | 1027

## vendor_cost_month 24 (hidden)
Vendor | AL BAYADER INTER.GROUP COMPANY |  | AL BAYADER INTER.GROUP COMPANY
year | 2024 |  | Jan | 4
|  |  | Feb | 26
Row Labels | Count of PO # |  | Mar | 0
January | 4 |  | Apr | 0
February | 26 |  | May | 0
Grand Total | 30 |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | AL-IRTEKAZ NATIONAL GEN.TRDG.C |  | AL-IRTEKAZ NATIONAL GEN.TRDG.C
year | 2024 |  | Jan | 0
|  |  | Feb | 1
Row Labels | Count of PO # |  | Mar | 0
February | 1 |  | Apr | 0
Grand Total | 1 |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO |  | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO
year | 2024 |  | Jan | 0
|  |  | Feb | 4
Row Labels | Count of PO # |  | Mar | 0
February | 4 |  | Apr | 0
Grand Total | 4 |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
CARRIER KUWAIT AIR CONDITIONING
Vendor | CARRIER KUWAIT AIR CONDITIONING |  | Jan | 1
year | 2024 |  | Feb | 0
|  |  | Mar | 0
Row Labels | Count of PO # |  | Apr | 0
January | 1 |  | May | 0
Grand Total | 1 |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | COMMERCIAL UNITED GINCO EST. |  | COMMERCIAL UNITED GINCO EST.
year | 2024 |  | Jan | 1
|  |  | Feb | 8
Row Labels | Count of PO # |  | Mar | 0
January | 1 |  | Apr | 0
February | 8 |  | May | 0
Grand Total | 9 |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
CREDENCE TRADING EST.
Vendor | CREDENCE TRADING EST. |  | Jan | 4
year | 2024 |  | Feb | 33
|  |  | Mar | 0
Row Labels | Count of PO # |  | Apr | 0
January | 4 |  | May | 0
February | 33 |  | Jun | 0
Grand Total | 37 |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | EMCOR INTERNATIONAL GENERAL TRADING CO WLL |  | EMCOR INTERNATIONAL GENERAL TRADING CO WLL
year | 2024 |  | Jan | 27
|  |  | Feb | 2
Row Labels | Count of PO # |  | Mar | 0
January | 27 |  | Apr | 0
February | 2 |  | May | 0
Grand Total | 29 |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST |  | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST
year | 2024 |  | Jan | 37
|  |  | Feb | 0
Row Labels | Count of PO # |  | Mar | 0
January | 37 |  | Apr | 0
Grand Total | 37 |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
GULF PIONEER COMPANY LLC
Vendor | GULF PIONEER COMPANY LLC |  | Jan | 2
year | 2024 |  | Feb | 0
|  |  | Mar | 0
Row Labels | Count of PO # |  | Apr | 0
January | 2 |  | May | 0
Grand Total | 2 |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | KASAR MARJAN CONTRACTING CO. |  | KASAR MARJAN CONTRACTING CO.
year | 2024 |  | Jan | 0
|  |  | Feb | 0
Row Labels | Count of PO # |  | Mar | 0
Grand Total |  |  | Apr | 0
|  |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | MARATHON INC TRADING LLC |  | MARATHON INC TRADING LLC
year | 2024 |  | Jan | 14
|  |  | Feb | 13
Row Labels | Count of PO # |  | Mar | 4
January | 14 |  | Apr | 0
February | 13 |  | May | 0
March | 4 |  | Jun | 0
Grand Total | 31 |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
MERIT INTERNATIONAL GENERAL TRADING CO WLL
Vendor | MERIT INTERNATIONAL GENERAL TRADING CO WLL |  | Jan | 135
year | 2024 |  | Feb | 146
|  |  | Mar | 28
Row Labels | Count of PO # |  | Apr | 0
January | 135 |  | May | 0
February | 146 |  | Jun | 0
March | 28 |  | Jul | 0
Grand Total | 309 |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL
year | 2024 |  | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL
|  |  | Jan | 0
Row Labels | Count of PO # |  | Feb | 0
Grand Total |  |  | Mar | 0
|  |  | Apr | 0
|  |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO |  | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO
year | 2024 |  | Jan | 70
|  |  | Feb | 75
Row Labels | Count of PO # |  | Mar | 0
January | 70 |  | Apr | 0
February | 75 |  | May | 0
Grand Total | 145 |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | RITAJ AL KUWAIT GENERAL TRADING CONTRACTING CO
year | 2024 |  | RITAJ AL KUWAIT GENERAL TRADING CONTRACTING CO
|  |  | Jan | 0
Row Labels | Count of PO # |  | Feb | 0
Grand Total |  |  | Mar | 0
|  |  | Apr | 0
|  |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | TRADEX INTERNATIONAL TRADING LLC
year | 2024 |  | TRADEX INTERNATIONAL TRADING LLC
|  |  | Jan | 4
Row Labels | Count of PO # |  | Feb | 4
January | 4 |  | Mar | 2
February | 4 |  | Apr | 0
March | 2 |  | May | 0
Grand Total | 10 |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | UNITEC INTERNATIONAL GENERAL TRADING CO |  | UNITEC INTERNATIONAL GENERAL TRADING CO
year | 2024 |  | Jan | 113
|  |  | Feb | 126
Row Labels | Count of PO # |  | Mar | 22
January | 113 |  | Apr | 0
February | 126 |  | May | 0
March | 22 |  | Jun | 0
Grand Total | 261 |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | (All) |  | all
year | 2024 |  | Jan | 431
|  |  | Feb | 606
Row Labels | Count of PO # |  | Mar | 112
January | 431 |  | Apr | 0
February | 606 |  | May | 0
March | 112 |  | Jun | 0
Grand Total | 1149 |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | MERIT INTERNATIONAL INC
year | 2024
MERIT INTERNATIONAL INC
Row Labels | Count of PO # |  | Jan | 0
Grand Total |  |  | Feb | 0
|  |  | Mar | 0
|  |  | Apr | 0
|  |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | AL NISF ELECTRICAL CO WLL
year | 2024
AL NISF ELECTRICAL CO WLL
Row Labels | Count of PO # |  | Jan | 4
January | 4 |  | Feb | 0
Grand Total | 4 |  | Mar | 0
|  |  | Apr | 0
|  |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
Vendor | EGYKUW
year | 2024
EGYKUW
Row Labels | Count of PO # |  | Jan | 0
Grand Total |  |  | Feb | 0
|  |  | Mar | 0
|  |  | Apr | 0
|  |  | May | 0
|  |  | Jun | 0
|  |  | Jul | 0
|  |  | Aug | 0
|  |  | Sep | 0
|  |  | Oct | 0
|  |  | Nov | 0
|  |  | Dec | 0
year | 2024
Row Labels | Count of Vendor | 15
239
AL BAYADER INTER.GROUP COMPANY | 30
AL-IRTEKAZ NATIONAL GEN.TRDG.C | 1
AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 4
CARRIER KUWAIT AIR CONDITIONING | 1
COMMERCIAL UNITED GINCO EST. | 9
CREDENCE TRADING EST. | 37
EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 29
FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 37
GULF PIONEER COMPANY LLC | 2
MARATHON INC TRADING LLC | 31
MERIT INTERNATIONAL GENERAL TRADING CO WLL | 309
RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 145
TRADEX INTERNATIONAL TRADING LLC | 10
UNITEC INTERNATIONAL GENERAL TRADING CO | 262
(blank)
AL NISF ELECTRICAL CO WLL | 4
Grand Total | 1150

## com_pj_month (hidden)
Color Code list | AJ
year | 2023
Count of PROJECT# | Column Labels
Row Labels | January | February | March | April | May | June | July | August | September | October | November | December | Grand Total | January | 59
|  |  | 2 |  |  |  | 1 | 16 | 13 |  | 5 | 1 | 38 | February | 1
COMP | 59 | 1 | 19 | 32 | 19 | 3 | 3 | 195 | 158 | 15 | 75 | 64 | 643 | March | 19
(blank) | 4 | 1 | 5 | 11 | 14 | 3 | 2 | 1 | 19 | 28 | 12 | 3 | 103 | April | 32
Grand Total | 63 | 2 | 26 | 43 | 33 | 6 | 6 | 212 | 190 | 43 | 92 | 68 | 784 | May | 19
[14 empty] | June | 3
[14 empty] | July | 3
[14 empty] | August | 195
[14 empty] | September | 158
[14 empty] | October | 15
[14 empty] | November | 75
[14 empty] | December | 64
Color Code list | BU
year | 2023
Count of PROJECT# | Column Labels
Row Labels | January | February | March | April | May | June | July | August | September | October | November | December | Grand Total | January | 0
[9 empty] | 1 |  |  | 8 | 9 | February | 0
COMP | [7 empty] | 3 |  |  | 1 | 334 | 338 | March | 0
(blank) | 2 | 3 | 7 | 6 | 11 | 5 | 3 | 1 | 2 | 13 | 4 | 3 | 60 | April | 0
Grand Total | 2 | 3 | 7 | 6 | 11 | 5 | 3 | 4 | 3 | 13 | 5 | 345 | 407 | May | 0
[14 empty] | June | 0
[14 empty] | July | 0
[14 empty] | August | 3
[14 empty] | September | 0
[14 empty] | October | 0
[14 empty] | November | 1
[14 empty] | December | 334
Color Code list | (All)
year | 2023
Count of PROJECT# | Column Labels
Row Labels | January | February | March | April | May | June | July | August | September | October | November | December | Grand Total | January | 59
|  | 1 | 2 |  | 3 |  | 1 | 16 | 14 |  | 5 | 9 | 51 | February | 16
COMP | 59 | 16 | 19 | 32 | 31 | 3 | 3 | 198 | 158 | 15 | 76 | 398 | 1008 | March | 19
(blank) | 6 | 4 | 12 | 17 | 25 | 8 | 5 | 2 | 21 | 41 | 16 | 6 | 163 | April | 32
Grand Total | 65 | 21 | 33 | 49 | 59 | 11 | 9 | 216 | 193 | 56 | 97 | 413 | 1222 | May | 31
[14 empty] | June | 3
[14 empty] | July | 3
[14 empty] | August | 198
[14 empty] | September | 158
[14 empty] | October | 15
[14 empty] | November | 76
[14 empty] | December | 398
Color Code list | AJ
year | 2024
Count of PROJECT# | Column Labels
Row Labels | January | February | March | Grand Total | [9 empty] | January | 21
|  | 123 |  | 123 | [9 empty] | February | 19
COMP | 21 | 19 | 4 | 44 | [9 empty] | March | 4
(blank) | 1 | 5 |  | 6 | [9 empty] | April | 0
Grand Total | 22 | 147 | 4 | 173 | [9 empty] | May | 0
[14 empty] | June | 0
[14 empty] | July | 0
[14 empty] | August | 0
[14 empty] | September | 0
[14 empty] | October | 0
[14 empty] | November | 0
[14 empty] | December | 0
Color Code list | BU
year | 2024
Count of PROJECT# | Column Labels
Row Labels | January | February | March | Grand Total | [9 empty] | January | 402
| 26 | 90 | 94 | 210 | [9 empty] | February | 384
COMP | 402 | 384 | 22 | 808 | [9 empty] | March | 22
(blank) | 3 | 14 | 3 | 20 | [9 empty] | April | 0
Grand Total | 431 | 488 | 119 | 1038 | [9 empty] | May | 0
[14 empty] | June | 0
[14 empty] | July | 0
[14 empty] | August | 0
[14 empty] | September | 0
[14 empty] | October | 0
[14 empty] | November | 0
[14 empty] | December | 0
Color Code list | (All)
year | 2024
Count of PROJECT# | Column Labels
Row Labels | January | February | March | Grand Total | [9 empty] | January | 424
| 26 | 213 | 94 | 333 | [9 empty] | February | 403
COMP | 424 | 403 | 26 | 853 | [9 empty] | March | 26
(blank) | 4 | 19 | 3 | 26 | [9 empty] | April | 0
Grand Total | 454 | 635 | 123 | 1212 | [9 empty] | May | 0
[14 empty] | June | 0
[14 empty] | July | 0
[14 empty] | August | 0
[14 empty] | September | 0
[14 empty] | October | 0
[14 empty] | November | 0
[14 empty] | December | 0

## deshb2 (hidden)
NO. OF PROJECTS | BOM Received date | TASK | PROJECT# | PROJECT DESCRIPTION | WO# | CATALOG | Item # | PR # | PR REQUESTED DATE | PR APPROVED DATE | PR Cur. Status | PR Line # | Unit of Issue | Order Qty. | Unit Cost | Ext. Cost (Line Cost) | RFQ # | RFQ Status | RFQ Status Date | RFQ Due Date | PO # | PO Line # | PO Award Date | PO Status | PO Status Date | Buyer | Vendor | Vendor Date (EDD) | Delivery Status | Delivery Date | Recv. Qty | Remarks | Color Code list | table | month | year | Name
1 | 2022-09-10 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0097 | TUBE, METALLIC, REFRIGERATION, COPPER, 3/8 INCH X 50 FEET | 17049 | 2022-09-10 | 2022-09-21 |  | 14 | RO | 20 | [6 empty] | KW1-5620 | 13 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 20 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-10 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0110 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 17049 | 2022-09-10 | 2022-09-21 |  | 11 | EA | 16 | [6 empty] | KW1-5620 | 11 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 16 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-10 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 17049 | 2022-09-10 | 2022-09-21 |  | 10 | BX | 5 | [6 empty] | KW1-5620 | 10 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 5 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-10 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5305-60-V00-0148 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 17049 | 2022-09-10 | 2022-09-21 |  | 17 | BX | 80 | [6 empty] | KW1-5620 | 17 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 80 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-10 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5530-00-618-8073 | PLYWOOD, MAPLE, PUREBOND, 3/4 IN x 4 FT x 8 FT | 17049 | 2022-09-10 | 2022-09-21 |  | 13 | SH | 30 | [6 empty] | KW1-5620 | 13 | [5 empty] | 2022-11-17 | COMP | 2022-10-22 | 30 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-10 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0048 | DRYWALL SHEET, (GYPSUM BOARD), 4 X 8 FEET X 1/2 INCH | 17044 | 2022-09-10 | 2022-09-15 |  | 2 | EA | 50 | [6 empty] | KW1-5212 | 5 | [5 empty] | 2022-10-05 | comp | 2022-09-27 | 50 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-10 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 7210-60-V00-0059 | FLOOR COVERING, VINYL RESIN, 3 MM X 40 FEET | 17049 | 2022-09-10 | 2022-09-21 |  | 19 | RO | 5 | [6 empty] | KW1-5620 | 19 | [5 empty] | 2022-11-17 |  |  |  |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-11 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5940-60-V00-0083 | LUG, TERMINAL, FORK, INSULATED, YELLOW, 12-10 AWG | 17052 | 2022-09-11 | 2022-09-17 |  | 2 | PG | 25 | [6 empty] | KW1-5267 | 3 | [5 empty] | 2022-10-24 | COMP | 2022-10-03 | 25 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-12 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4130-60-V00-0137 | MOUNTING BASE, AIR-CONDITIONER, POLYPROPYLENE, IVORY, 17 X 3 X 5.12 INCHES | 17045 | 2022-09-12 | 2022-09-19 |  | 1 | PG | 16 | [6 empty] | KW1-5181 | 1 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 16 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-12 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8030-60-V00-0053 | FOAM, CONSTRUCTION, CREAM, 700ML | 17042 | 2022-09-12 | 2022-09-20 |  | 24 | EA | 4 | [6 empty] | KWA-5530 | 24 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0098 | TUBE, METALLIC, REFRIGERATION, COPPER, 5/8 INCH X 50 FEET | 17046 | 2022-09-19 | 2022-09-24 |  | 1 | RO | 20 | [6 empty] | KW1-5212 | 1 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 20 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0288 | COUPLING, DRAINAGE PIPE, POLYPROPYLENE, ORANGE, 4.33 INCHES | 17046 | 2022-09-19 | 2022-09-24 |  | 2 | EA | 8 | [6 empty] | KW1-5212 | 8 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 8 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0288 | COUPLING, DRAINAGE PIPE, POLYPROPYLENE, ORANGE, 4.33 INCHES | 17046 | 2022-09-19 | 2022-09-24 |  | 3 | EA | 8 | [6 empty] | KW1-5212 | 13 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 8 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0304 | COUPLING, DRAINAGE PIPE, (PAN CONNECTOR), POLYPROPYLENE, WHITE, 4 INCHES X 110 MM | 17046 | 2022-09-19 | 2022-09-24 |  | 5 | EA | 2 | [6 empty] | KW1-5212 | 5 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0304 | COUPLING, DRAINAGE PIPE, (PAN CONNECTOR), POLYPROPYLENE, WHITE, 4 INCHES X 110 MM | 17046 | 2022-09-19 | 2022-09-24 |  | 4 | EA | 4 | [6 empty] | KW1-5212 | 4 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0390 | TEE-Y, DRAINAGE PIPE, PVC-U, 45 DEGREE, TERRACOTTA, 110 MILLIMETER | 17046 | 2022-09-19 | 2022-09-24 |  | 6 | EA | 4 | [6 empty] | KW1-5212 | 3 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 5 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0390 | TEE-Y, DRAINAGE PIPE, PVC-U, 45 DEGREE, TERRACOTTA, 110 MILLIMETER | 17046 | 2022-09-19 | 2022-09-24 |  | 8 | EA | 5 | [6 empty] | KW1-5212 | 9 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 5 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0390 | TEE-Y, DRAINAGE PIPE, PVC-U, 45 DEGREE, TERRACOTTA, 110 MILLIMETER | 17046 | 2022-09-19 | 2022-09-24 |  | 7 | EA | 5 | [6 empty] | KW1-5212 | 14 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 5 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0830 | COUPLING, UPVC, SCH-40, GRAY, 2 INCHES | 17046 | 2022-09-19 | 2022-09-24 |  | 9 | EA | 4 | [6 empty] | KW1-5212 | 9 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0830 | COUPLING, UPVC, SCH-40, GRAY, 2 INCHES | 17046 | 2022-09-19 | 2022-09-24 |  | 10 | EA | 4 | [6 empty] | KW1-5212 | 10 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0834 | COUPLING, CPVC, SCH-40, TAN, 25 MM | 17046 | 2022-09-19 | 2022-09-24 |  | 11 | EA | 4 | [6 empty] | KW1-5212 | 11 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0834 | COUPLING, CPVC, SCH-40, TAN, 25 MM | 17046 | 2022-09-19 | 2022-09-24 |  | 13 | EA | 8 | [6 empty] | KW1-5212 | 12 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 8 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0834 | COUPLING, CPVC, SCH-40, TAN, 25 MM | 17046 | 2022-09-19 | 2022-09-24 |  | 12 | EA | 8 | [6 empty] | KW1-5212 | 13 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 8 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0927 | TEE, PIPE, SOCKET X SOCKET X FIPT, SCH-80, CPVC, OFF-WHITE, 25 MM X 1/2 INCH | 17046 | 2022-09-19 | 2022-09-24 |  | 14 | EA | 10 | [6 empty] | KW1-5212 | 14 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 10 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0927 | TEE, PIPE, SOCKET X SOCKET X FIPT, SCH-80, CPVC, OFF-WHITE, 25 MM X 1/2 INCH | 17046 | 2022-09-19 | 2022-09-24 |  | 15 | EA | 10 | [6 empty] | KW1-5212 | 15 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 10 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0973 | TEE, PIPE, SEWER AND DRAIN FITTINGS, PVC, SCH-80, ORANGE, 110 MM | 17046 | 2022-09-19 | 2022-09-24 |  | 16 | EA | 2 | [6 empty] | KW1-5212 | 16 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4820-60-V00-0234 | VALVE, BALL, BRASS, 1 INCH | 17046 | 2022-09-19 | 2022-09-24 |  | 17 | EA | 1 | [6 empty] | KW1-5212 | 17 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5340-60-V00-0449 | ANCHOR, KIT, CONICAL, PLASTIC, #10 X 1 X 1/4 INCH | 17046 | 2022-09-19 | 2022-09-24 |  | 18 | KT | 5 | [6 empty] | KW1-5212 | 18 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 5 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0042 | TILE, CEILING, PVC, WHITE, 2 X 2 FEET | 17046 | 2022-09-19 | 2022-09-24 |  | 19 | BX | 1 | [6 empty] | KW1-5212 | 19 | [5 empty] | 2022-09-24 | COMP | 2022-09-28 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-19 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 17046 | 2022-09-19 | 2022-09-24 |  | 20 | EA | 20 | [6 empty] | KW1-5212 | 20 | [5 empty] | 2022-09-24 | COMP | 2022-10-01 | 20 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5930-60-V00-0243 | LIGHT-SWITCH, METAL, 2 WAY, 1 GANG, 250V, 10A | 17041 | 2022-09-21 | 2022-09-30 |  | 10 | EA | 19 | [6 empty] | KW1-5358 | 10 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 19 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4130-60-V00-0288 | TAPE, WRAP, INSULATION, 3 INCHES X 150 FEET | 17041 | 2022-09-21 | 2022-09-30 |  | 1 | RO | 31 | [6 empty] | KW1-5358 | 1 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 31 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4320-60-V00-0078 | PUMP, CENTRIFUGAL, WATER, 2740 RPM, 50 HZ | 17041 | 2022-09-21 | 2022-09-24 |  | 2 | EA | 1 | [6 empty] | KW1-5358 | 2 | [5 empty] | 2022-11-25 | COMP | 2022-10-11 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4510-60-V00-0049 | TRAP, BOTTLE, ADJUSTABLE INLET, WHITE, 1-1/2 INCHES | 17051 | 2022-09-21 | 2022-09-24 |  | 1 | EA | 1 | [6 empty] | KW1-5212 | 6 | [5 empty] | 2022-10-22 | COMP | 2022-10-01 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4510-60-V00-0102 | COVER, DRAIN, w/HOLE, SQUARE, METAL, 6 X 6 INCHES | 17049 | 2022-09-21 | 2022-09-24 |  | 6 | EA | 2 | [6 empty] | KW1-5620 | 6 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4510-60-V00-0102 | COVER, DRAIN, w/HOLE, SQUARE, METAL, 6 X 6 INCHES | 17049 | 2022-09-21 | 2022-09-24 |  | 5 | EA | 2 | [6 empty] | KW1-5620 | 5 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 5 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4510-60-V00-0124 | FAUCET, LEVER, SINGLE, CHROME, BRASS, WASH BASIN MIXER | 17044 | 2022-09-21 | 2022-09-24 |  | 1 | EA | 1 | [6 empty] | KW1-5212 | 4 | [5 empty] | 2022-10-05 | COMP | 2022-09-29 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0054 | PIPE, UPVC, SCH40, NON-PRESSURE, GREY, 50 MM X 2.2MM X 6 METER | 17053 | 2022-09-21 | 2022-09-21 |  | 1 | EA | 1 | [6 empty] | KW1-5679 | 1 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0054 | PIPE, UPVC, SCH40, NON-PRESSURE, GREY, 50 MM X 2.2MM X 6 METER | 17053 | 2022-09-21 | 2022-09-21 |  | 3 | EA | 1 | [6 empty] | KW1-5679 | 3 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0054 | PIPE, UPVC, SCH40, NON-PRESSURE, GREY, 50 MM X 2.2MM X 6 METER | 17053 | 2022-09-21 | 2022-09-21 |  | 2 | EA | 2 | [6 empty] | KW1-5679 | 2 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0054 | PIPE, UPVC, SCH40, NON-PRESSURE, GREY, 50 MM X 2.2MM X 6 METER | 17053 | 2022-09-21 | 2022-09-21 |  | 4 | EA | 2 | [6 empty] | KW1-5679 | 4 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0101 | PIPE, PLASTIC, PVC, ORANGE, 4 INCHES X 13 FEET | 17048 | 2022-09-21 | 2022-09-24 |  | 4 | EA | 1 | [6 empty] | KW1-5212 | 24 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0101 | PIPE, PLASTIC, PVC, ORANGE, 4 INCHES X 13 FEET | 17048 | 2022-09-21 | 2022-09-19 |  | 1 | EA | 4 | [6 empty] | KW1-5212 | 21 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0101 | PIPE, PLASTIC, PVC, ORANGE, 4 INCHES X 13 FEET | 17048 | 2022-09-21 | 2022-09-24 |  | 3 | EA | 4 | [6 empty] | KW1-5212 | 23 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0101 | PIPE, PLASTIC, PVC, ORANGE, 4 INCHES X 13 FEET | 17048 | 2022-09-21 | 2022-09-24 |  | 2 | EA | 4 | [6 empty] | KW1-5212 | 22 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0103 | PIPE, PLASTIC, SCH-40, UPVC, GRAY, 2 INCHES | 17053 | 2022-09-21 | 2022-09-21 |  | 5 | EA | 4 | [6 empty] | KW1-5679 | 5 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0103 | PIPE, PLASTIC, SCH-40, UPVC, GRAY, 2 INCHES | 17053 | 2022-09-21 | 2022-09-21 |  | 6 | EA | 4 | [6 empty] | KW1-5679 | 6 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0107 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 2 INCHES | 17045 | 2022-09-21 | 2022-09-24 |  | 2 | EA | 2 | [6 empty] | KW1-5181 | 2 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0108 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 17048 | 2022-09-21 | 2022-09-24 |  | 8 | EA | 2 | [6 empty] | KW1-5212 | 28 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0108 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 17048 | 2022-09-21 | 2022-09-24 |  | 5 | EA | 8 | [6 empty] | KW1-5212 | 25 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 8 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0108 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 17048 | 2022-09-21 | 2022-09-24 |  | 7 | EA | 10 | [6 empty] | KW1-5212 | 27 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 10 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0108 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 17048 | 2022-09-21 | 2022-09-24 |  | 6 | EA | 10 | [6 empty] | KW1-5212 | 26 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 10 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4710-60-V00-0111 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 1 INCH | 17045 | 2022-09-21 | 2022-09-24 |  | 3 | EA | 3 | [6 empty] | KW1-5181 | 3 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 3 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4720-60-V00-0262 | HOSE, METALLIC, FLEXIBLE, SINGLE NUT, STAINLESS STEEL BRAIDED, 1/2-INCH X 1 FEET | 17042 | 2022-09-21 | 2022-09-24 |  | 1 | EA | 1 | [6 empty] | KWA-5530 | 1 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0251 | COUPLING, POLYPROPYLENE, GREEN, 20 MM | 17048 | 2022-09-21 | 2022-09-19 |  | 9 | EA | 4 | [6 empty] | KW1-5212 | 29 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0458 | ELBOW, PIPE, SOCKET X SPIGOT, 45°, PVC, ORANGE, 110MM | 17048 | 2022-09-21 | 2022-09-19 |  | 10 | EA | 5 | [6 empty] | KW1-5212 | 30 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 5 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0458 | ELBOW, PIPE, SOCKET X SPIGOT, 45°, PVC, ORANGE, 110MM | 17048 | 2022-09-21 | 2022-09-24 |  | 12 | EA | 8 | [6 empty] | KW1-5212 | 32 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 8 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0458 | ELBOW, PIPE, SOCKET X SPIGOT, 45°, PVC, ORANGE, 110MM | 17048 | 2022-09-21 | 2022-09-24 |  | 11 | EA | 8 | [6 empty] | KW1-5212 | 31 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 8 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0501 | FLANGE, PVC-U, GRAY, 160MM | 17053 | 2022-09-21 | 2022-09-21 |  | 7 | EA | 1 | [6 empty] | KW1-5679 | 7 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0594 | C-CLAMP W/ RUBBER, GALVANIZED STEEL, 2 INCHES | 17041 | 2022-09-21 | 2022-09-30 |  | 3 | EA | 69 | [6 empty] | KW1-5358 | 3 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 69 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0705 | TEE, PIPE, SOCKET X SOCKET X SPIGOT, 87 °, PVC, ORANGE, 110MM | 17053 | 2022-09-21 | 2022-09-21 |  | 8 | EA | 4 | [6 empty] | KW1-5679 | 8 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0705 | TEE, PIPE, SOCKET X SOCKET X SPIGOT, 87 °, PVC, ORANGE, 110MM | 17053 | 2022-09-21 | 2022-09-21 |  | 9 | EA | 4 | [6 empty] | KW1-5679 | 9 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0706 | TEE, PIPE, SOCKET X SOCKET X SPIGOT, 87.5 °, UPVC, GRAY, 50MM | 17050 | 2022-09-21 | 2022-09-21 |  | 1 | EA | 3 | [6 empty] | KW1-5212 | 4 | [5 empty] | 2022-10-22 | COMP | 2022-10-01 | 3 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0708 | TRAP, DRAINAGE PIPE, UNDERGROUND, 45°, PVC-U, TERRACOTTA, 110 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 10 | EA | 2 | [6 empty] | KW1-5679 | 10 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0708 | TRAP, DRAINAGE PIPE, UNDERGROUND, 45°, PVC-U, TERRACOTTA, 110 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 12 | EA | 3 | [6 empty] | KW1-5679 | 12 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 3 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0708 | TRAP, DRAINAGE PIPE, UNDERGROUND, 45°, PVC-U, TERRACOTTA, 110 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 11 | EA | 3 | [6 empty] | KW1-5679 | 11 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 3 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0754 | ADAPTER, PRESSURE FITTINGS, MALE, CPVC, STANDARD, SOCKET X MIPT, PN16, OFF-WHITE, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 2 | EA | 6 | [6 empty] | KWA-5530 | 2 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 6 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0754 | ADAPTER, PRESSURE FITTINGS, MALE, CPVC, STANDARD, SOCKET X MIPT, PN16, OFF-WHITE, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 3 | EA | 6 | [6 empty] | KWA-5530 | 3 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 6 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0755 | ADAPTER, PIPE, SCH 40, MIPT X SOCKET, CPVC, OFF-WHITE, 32 MM X 1 INCH | 17049 | 2022-09-21 | 2022-09-24 |  | 2 | EA | 2 | [6 empty] | KW1-5620 | 2 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0755 | ADAPTER, PIPE, SCH 40, MIPT X SOCKET, CPVC, OFF-WHITE, 32 MM X 1 INCH | 17049 | 2022-09-21 | 2022-09-21 |  | 3 | EA | 4 | [6 empty] | KW1-5620 | 3 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0757 | ADAPTER, MALE, CPVC, STRAIGHT, SOCKET X MIPT, SCH-40, OFF-WHITE, 63 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 4 | EA | 4 | [6 empty] | KWA-5530 | 4 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0761 | ADAPTER, PRESSURE FITTINGS, FEMALE, CPVC, STANDARD, SOCKET X SR FIPT, SCH- 40, OFF-WHITE, 50 MM | 17049 | 2022-09-21 | 2022-09-19 |  | 7 | EA | 4 | [6 empty] | KW1-5620 | 7 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0763 | ADAPTER, PRESSURE FITTINGS, FEMALE, CPVC, REDUCTION, SOCKET X FIPT, SCH- 40, OFF-WHITE, 3/4 X 1/2 INCH | 17041 | 2022-09-21 | 2022-09-24 |  | 5 | EA | 3 | [6 empty] | KW1-5358 | 5 | [5 empty] | 2022-10-30 | COMP | 2022-10-12 | 3 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0763 | ADAPTER, PRESSURE FITTINGS, FEMALE, CPVC, REDUCTION, SOCKET X FIPT, SCH- 40, OFF-WHITE, 3/4 X 1/2 INCH | 17041 | 2022-09-21 | 2022-09-24 |  | 4 | EA | 4 | [6 empty] | KW1-5358 | 4 | [5 empty] | 2022-10-30 | COMP | 2022-10-12 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0770 | ADAPTER, PRESSURE FITTINGS, FEMALE, CPVC, STANDARD, SOCKET X SR FIPT, SCH- 40, OFF-WHITE, 63 MM | 17041 | 2022-09-21 | 2022-09-24 |  | 6 | EA | 3 | [6 empty] | KW1-5358 | 6 | [5 empty] | 2022-10-30 | COMP | 2022-10-12 | 3 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0773 | ADAPTER, PRESSURE FITTINGS, MALE, CPVC, REDUCTION, SOCKET X MIPT, SCH- 40, OFF-WHITE, 3 X 2 INCHES | 17049 | 2022-09-21 | 2022-09-24 |  | 8 | EA | 4 | [6 empty] | KW1-5620 | 8 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0795 | CAP, PIPE, UPVC, SPIGOT, SCH-80, ORANGE, 4 INCHES | 17049 | 2022-09-21 | 2022-09-24 |  | 1 | EA | 2 | [6 empty] | KW1-5620 | 1 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0798 | CAP, PIPE, UPVC, SCH-40, GRAY, 2 INCHES | 17045 | 2022-09-21 | 2022-09-24 |  | 4 | EA | 2 | [6 empty] | KW1-5181 | 4 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0798 | CAP, PIPE, UPVC, SCH-40, GRAY, 2 INCHES | 17045 | 2022-09-21 | 2022-09-24 |  | 5 | EA | 2 | [6 empty] | KW1-5181 | 5 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0817 | COUPLING, WASTE, SHOWER, BRASS, 1-1/2 INCHES | 17042 | 2022-09-21 | 2022-09-19 |  | 5 | EA | 2 | [6 empty] | KWA-5530 | 5 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0829 | COUPLING, UPVC, SCH-40, GRAY, 50 MM | 17045 | 2022-09-21 | 2022-09-19 |  | 6 | EA | 4 | [6 empty] | KW1-5181 | 6 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0845 | WYE, TRUE, PIPE, SCH 40, UPVC, GRAY, 45 °, 50MM | 17048 | 2022-09-21 | 2022-09-19 |  | 13 | EA | 2 | [6 empty] | KW1-5212 | 33 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0847 | WYE, PIPE, SEWAGE, 45 °, UPVC, ORANGE, 110MM | 17053 | 2022-09-21 | 2022-09-21 |  | 13 | EA | 1 | [6 empty] | KW1-5679 | 13 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0850 | ELBOW, CPVC, SOCKET X SOCKET, SCH 40, OFF-WHITE, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 9 | EA | 4 | [6 empty] | KWA-5530 | [6 empty] | 2022-09-24 | COMP | 2022-10-17 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0850 | ELBOW, CPVC, SOCKET X SOCKET, SCH 40, OFF-WHITE, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 6 | EA | 10 | [6 empty] | KWA-5530 | 6 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 10 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0850 | ELBOW, CPVC, SOCKET X SOCKET, SCH 40, OFF-WHITE, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 8 | EA | 10 | [6 empty] | KWA-5530 | 8 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 10 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0850 | ELBOW, CPVC, SOCKET X SOCKET, SCH 40, OFF-WHITE, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 7 | EA | 10 | [6 empty] | KWA-5530 | 10 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 10 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0851 | ELBOW, CPVC, 90 DEGREE, SCH- 40, OFF-WHITE, 1 INCH | 17045 | 2022-09-21 | 2022-09-24 |  | 7 | EA | 5 | [6 empty] | KW1-5181 | 7 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 5 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0854 | ELBOW, CPVC, 90 DEGREE, SCH- 40, OFF-WHITE, 2 INCHES | 17049 | 2022-09-21 | 2022-09-24 |  | 4 | EA | 4 | [6 empty] | KW1-5620 | 4 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0856 | ELBOW, PRESSURE FITTINGS, CPVC, STANDARD, 45 °, SOCKET X SOCKET, SCH- 40, OFF-WHITE, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 10 | EA | 6 | [6 empty] | KWA-5530 | 10 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 6 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0861 | ELBOW, CPVC, 45 DEGREE, SCH- 40, OFF-WHITE, 2 INCHES | 17048 | 2022-09-21 | 2022-09-24 |  | 14 | EA | 2 | [6 empty] | KW1-5212 | 34 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0863 | ELBOW, PRESSURE FITTINGS, CPVC, BRASS, REDUCTION, 90 °, SOCKET X FIPT, SCH- 40, OFF-WHITE, 25 x 20 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 11 | EA | 2 | [6 empty] | KWA-5530 | 11 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0863 | ELBOW, PRESSURE FITTINGS, CPVC, BRASS, REDUCTION, 90 °, SOCKET X FIPT, SCH- 40, OFF-WHITE, 25 x 20 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 13 | EA | 6 | [6 empty] | KWA-5530 | 13 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 6 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0863 | ELBOW, PRESSURE FITTINGS, CPVC, BRASS, REDUCTION, 90 °, SOCKET X FIPT, SCH- 40, OFF-WHITE, 25 x 20 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 12 | EA | 6 | [6 empty] | KWA-5530 | 12 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 6 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0869 | ELBOW, PIPE, SCH-40, SOCKET X SOCKET, 90°, PVC, GRAY, 63 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 14 | EA | 2 | [6 empty] | KW1-5679 | 14 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0869 | ELBOW, PIPE, SCH-40, SOCKET X SOCKET, 90°, PVC, GRAY, 63 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 16 | EA | 8 | [6 empty] | KW1-5679 | 16 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 8 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0869 | ELBOW, PIPE, SCH-40, SOCKET X SOCKET, 90°, PVC, GRAY, 63 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 15 | EA | 8 | [6 empty] | KW1-5679 | 15 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 8 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0874 | ELBOW, PIPE, UPVC, STANDARD, 90 °, SOCKET X SOCKET, SCH- 40, GRAY, 50 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 17 | EA | 6 | [6 empty] | KW1-5679 | 17 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 6 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0876 | ELBOW, PIPE, SOCKET X SOCKET, 45 °, UPVC, GRAY, 50MM | 17053 | 2022-09-21 | 2022-09-21 |  | 18 | EA | 6 | [6 empty] | KW1-5679 | 18 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 6 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0877 | ELBOW, PIPE, UPVC, 45 °, SOCKET X SOCKET, PN16, GRAY, 63 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 19 | EA | 10 | [6 empty] | KW1-5679 | 19 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 10 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0877 | ELBOW, PIPE, UPVC, 45 °, SOCKET X SOCKET, PN16, GRAY, 63 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 20 | EA | 10 | [6 empty] | KW1-5679 | 20 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 10 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0880 | ELBOW, UPVC, SCH-80, ORANGE, 4 INCHES | 17045 | 2022-09-21 | 2022-09-19 |  | 8 | EA | 6 | [6 empty] | KW1-5181 | 8 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 6 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0897 | BUSHING, PIPE, REDUCER, SCH-40, CPVC, OFF-WHITE, 2 X 1 INCHES | 17048 | 2022-09-21 | 2022-09-24 |  | 15 | EA | 2 | [6 empty] | KW1-5212 | 35 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0899 | BUSHING, PIPE, REDUCTION, SCH- 40, CPVC, OFF-WHITE, 2 X 1-1/2 INCHES | 17041 | 2022-09-21 | 2022-09-24 |  | 7 | EA | 1 | [6 empty] | KW1-5358 | 7 | [5 empty] | 2022-09-24 | COMP | 2022-10-30 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0900 | BUSHING, PIPE, REDUCER, SCH-40, CPVC, OFF-WHITE, 4 X 2 INCHES | 17053 | 2022-09-21 | 2022-09-21 |  | 21 | EA | 1 | [6 empty] | KW1-5679 | 21 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0900 | BUSHING, PIPE, REDUCER, SCH-40, CPVC, OFF-WHITE, 4 X 2 INCHES | 17053 | 2022-09-21 | 2022-09-21 |  | 23 | EA | 3 | [6 empty] | KW1-5679 | 23 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 3 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0900 | BUSHING, PIPE, REDUCER, SCH-40, CPVC, OFF-WHITE, 4 X 2 INCHES | 17053 | 2022-09-21 | 2022-09-21 |  | 22 | EA | 3 | [6 empty] | KW1-5679 | 22 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 3 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0908 | BUSHING, PIPE, SEWAGE, REDUCTION, SCH-40, PVC, ORANGE, 4 X 1-1/2 INCHES | 17053 | 2022-09-21 | 2022-09-21 |  | 24 | EA | 1 | [6 empty] | KW1-5679 | 24 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0923 | TEE, PIPE, CPVC, SCH-40, OFF-WHITE, 63 MM | 17048 | 2022-09-21 | 2022-09-24 |  | 16 | EA | 1 | [6 empty] | KW1-5212 | 36 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0940 | TEE, PIPE, SOCKET X SOCKET X SOCKET, CPVC, OFF-WHITE, SCH 40, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 14 | EA | 4 | [6 empty] | KWA-5530 | 14 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0940 | TEE, PIPE, SOCKET X SOCKET X SOCKET, CPVC, OFF-WHITE, SCH 40, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 16 | EA | 6 | [6 empty] | KWA-5530 | 16 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 6 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0940 | TEE, PIPE, SOCKET X SOCKET X SOCKET, CPVC, OFF-WHITE, SCH 40, 25 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 15 | EA | 6 | [6 empty] | KWA-5530 | 15 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 6 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0949 | UNION, PIPE, SOCKET X SOCKET, SCH- 40, CPVC, OFF-WHITE, 32 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 17 | EA | 2 | [6 empty] | KWA-5530 | 17 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0970 | ELBOW, PRESSURE FITTINGS, PVC, STANDARD, 90 °, SPIGOT X SOCKET, ORANGE, 110 MM | 17042 | 2022-09-21 | 2022-09-19 |  | 18 | EA | 5 | [6 empty] | KWA-5530 | 18 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 5 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0970 | ELBOW, PRESSURE FITTINGS, PVC, STANDARD, 90 °, SPIGOT X SOCKET, ORANGE, 110 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 20 | EA | 6 | [6 empty] | KWA-5530 | 20 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 6 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0970 | ELBOW, PRESSURE FITTINGS, PVC, STANDARD, 90 °, SPIGOT X SOCKET, ORANGE, 110 MM | 17042 | 2022-09-21 | 2022-09-24 |  | 19 | EA | 6 | [6 empty] | KWA-5530 | 19 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 6 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4820-60-V00-0227 | VALVE, ANGLE, 1/2 X 1/2 INCHES | 17047 | 2022-09-21 | 2022-09-24 |  | 1 | EA | 2 | [6 empty] | KW1-5212 | 2 | [5 empty] | 2022-10-22 | COMP | 2022-10-01 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4820-60-V00-0227 | VALVE, ANGLE, 1/2 X 1/2 INCHES | 17047 | 2022-09-21 | 2022-09-24 |  | 2 | EA | 16 | [6 empty] | KW1-5212 | 3 | [5 empty] | 2022-10-22 | COMP | 2022-10-01 | 16 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4820-60-V00-0229 | VALVE, BALL, BRASS, PN25, RED, 3/4 INCH | 17042 | 2022-09-21 | 2022-09-24 |  | 21 | EA | 2 | [6 empty] | KWA-5530 | 21 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4820-60-V00-0229 | VALVE, BALL, BRASS, PN25, RED, 3/4 INCH | 17042 | 2022-09-21 | 2022-09-24 |  | 22 | EA | 2 | [6 empty] | KWA-5530 | 22 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4820-60-V00-0235 | VALVE, BALL, BRASS, 2 INCHES | 17048 | 2022-09-21 | 2022-09-24 |  | 17 | EA | 1 | [6 empty] | KW1-5212 | 37 | [5 empty] | 2022-10-22 | COMP | 2022-09-28 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 17049 | 2022-09-21 | 2022-09-21 |  | 15 | BX | 52 | [6 empty] | KW1-5620 | 15 | [5 empty] | 2022-11-17 | COMP | 2022-10-20 | 52 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5305-60-V00-0175 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 3-1/2 INCHES | 17053 | 2022-09-21 | 2022-09-21 |  | 25 | BX | 10 | [6 empty] | KW1-5679 | 25 | [5 empty] | 2022-11-14 | COMP | 2022-10-20 | 10 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 17042 | 2022-09-21 | 2022-09-24 |  | 23 | BX | 1 | [6 empty] | KWA-5530 | 23 | [5 empty] | 2022-11-10 | COMP | 2022-10-17 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5340-60-V00-0497 | LATCH, DOOR, STAINLESS STEEL, 3 INCHES | 17045 | 2022-09-21 | 2022-09-24 |  | 9 | EA | 6 | [6 empty] | KW1-5181 | 9 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 6 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5530-00-129-7721 | PLYWOOD, CONSTRUCTION, 1/4 X 48 X 96 INCHES | 17040 | 2022-09-21 | 2022-09-24 |  | 1 | SH | 3 | [6 empty] | KW1-5212 | 7 | [5 empty] | 2022-09-24 | COMP | 2022-09-29 | 3 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0030 | INSULATION SLEEVING, THERMAL, 3/8 X 72 INCHES | 17041 | 2022-09-21 | 2022-09-30 |  | 8 | EA | 166 | [6 empty] | KW1-5358 | 8 | [5 empty] | 2022-10-30 | COMP | 2022-10-06 | 166 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0031 | INSULATION SLEEVING, THERMAL, 5/8 X 72 INCHES | 17041 | 2022-09-21 | 2022-09-30 |  | 9 | EA | 166 | [6 empty] | KW1-5358 | 9 | [5 empty] | 2022-10-30 | COMP | 2022-10-06 | 166 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0044 | TAPE, SELF ADHESIVE, DRYWALL JOINT, FIBERGLASS, 2 INCHES X 300 FEET | 17045 | 2022-09-21 | 2022-09-24 |  | 10 | EA | 20 | [6 empty] | KW1-5181 | 10 | [5 empty] | 2022-10-20 | COMP | 2022-09-28 | 20 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5650-60-V00-0004 | CHANNEL, STRUCTURAL, C-SHAPE, STEEL, 1-5/8 X 3-5/8 INCHES X 10 FEET | 17049 | 2022-09-21 | 2022-09-24 |  | 12 | EA | 76 | [6 empty] | KW1-5620 | 12 | [5 empty] | 2022-11-17 | COMP | 2022-10-22 | 76 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5670-60-V00-0026 | WALL ANGLE / GRID, CEILING, TEE, GALVANIZED STEEL, WHITE, 12 FEET | 17049 | 2022-09-21 | 2022-09-24 |  | 16 | EA | 90 | [6 empty] | KW1-5620 | 16 | [5 empty] | 2022-11-17 | COMP | 2022-10-22 | 90 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5680-60-V00-0006 | GRID, CEILING, TEE, WHITE, 24 INCHES | 17049 | 2022-09-21 | 2022-09-24 |  | 21 | EA | 1400 | [6 empty] | KW1-5620 | 21 | [5 empty] | 2022-11-17 | COMP | 2022-10-22 | 300 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5680-60-V00-0007 | GRID, CEILING, T-RUNNER, WHITE, 12 FEET | 17049 | 2022-09-21 | 2022-09-24 |  | 20 | EA | 300 | [6 empty] | KW1-5620 | 20 | [5 empty] | 2022-11-17 | COMP | 2022-10-22 | 300 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 17041 | 2022-09-21 | 2022-09-30 |  | 11 | EA | 62 | [6 empty] | KW1-5358 | 11 | [5 empty] | 2022-11-25 | COMP | 2022-10-11 | 62 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 17041 | 2022-09-21 | 2022-09-30 |  | 12 | EA | 47 | [6 empty] | KW1-5358 | 12 | [5 empty] | 2022-11-25 | COMP | 2022-10-11 | 47 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5935-60-V00-0160 | SOCKET, OUTLET, WEATHERPROOF, 2 GANG, 2 POLES, 13 AMPS | 17052 | 2022-09-21 | 2022-09-17 |  | 1 | EA | 4 | [6 empty] | KW1-5267 | 2 | [5 empty] | 2022-09-24 | COMP | 2022-10-03 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5935-60-V00-0167 | CONNECTOR, WIRE, RED, 18 -10 AWG | 17041 | 2022-09-21 | 2022-09-30 |  | 13 | PG | 20 | [6 empty] | KW1-5358 | 13 | [5 empty] | 2022-10-30 | COMP | 2022-10-15 | 20 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 17041 | 2022-09-21 | 2022-09-30 |  | 14 | PG | 20 | [6 empty] | KW1-5358 | 14 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 20 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-00-156-3253 | STRAP, TIE DOWN, ELECTRICAL COMPONE, 13-7/20 INCHES | 17041 | 2022-09-21 | 2022-09-30 |  | 15 | HD | 6 | [6 empty] | KW1-5358 | 15 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 6 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0235 | RACEWAY, NONMETALLIC (CABLE TRUNKING), PVC, WHITE, 100 X 100 MM, 3 METERS | 17041 | 2022-09-21 | 2022-09-30 |  | 16 | EA | 25 | [6 empty] | KW1-5358 | 16 | [5 empty] | 2022-11-25 | COMP | 2022-10-11 | 25 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0235 | RACEWAY, NONMETALLIC (CABLE TRUNKING), PVC, WHITE, 100 X 100 MM, 3 METERS | 17041 | 2022-09-21 | 2022-09-30 |  | 17 | EA | 35 | [6 empty] | KW1-5358 | 17 | [5 empty] | 2022-11-25 | COMP | 2022-10-11 | 35 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0373 | COUPLING, ELECTRICAL CONDUIT, PVC, BLACK, 20 MM | 17041 | 2022-09-21 | 2022-09-30 |  | 18 | EA | 300 | [6 empty] | KW1-5358 | 18 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 300 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0436 | ADAPTER, CONDUIT, w/ BUSH, MALE, PVC, WHITE, 20MM | 17041 | 2022-09-21 | 2022-09-30 |  | 19 | EA | 400 | [6 empty] | KW1-5358 | 19 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 400 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0480 | JUNCTION BOX, w/ BLANK SIDE, 100 X 100 X 50 MM | 17041 | 2022-09-21 | 2022-09-30 |  | 20 | EA | 10 | [6 empty] | KW1-5358 | 20 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 10 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0500 | CLAMP, ELECTRICAL, CONDUIT, PVC, BLACK, 20 MM | 17041 | 2022-09-21 | 2022-09-30 |  | 21 | EA | 62 | [6 empty] | KW1-5358 | 21 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 62 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0500 | CLAMP, ELECTRICAL, CONDUIT, PVC, BLACK, 20 MM | 17041 | 2022-09-21 | 2022-09-30 |  | 22 | EA | 1200 | [6 empty] | KW1-5358 | 22 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 1200 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0505 | STUFFING TUBE (CABLE GLAND), PG16, POLYAMIDE, GRAY, 9 -14 MM | 17041 | 2022-09-21 | 2022-09-30 |  | 23 | EA | 140 | [6 empty] | KW1-5358 | 23 | [5 empty] | 2002-11-13 | COMP | 2022-10-11 | 140 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0526 | CONDUIT, NONMETALLIC, RIGID, PVC, BLACK, 3/4 INCH X 10 FEET | 17041 | 2022-09-21 | 2022-09-30 |  | 24 | EA | 365 | [6 empty] | KW1-5358 | 24 | [5 empty] | 2022-10-30 | COMP | 2022-10-15 | 365 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 17041 | 2022-09-21 | 2022-09-30 |  | 25 | RO | 2 | [6 empty] | KW1-5358 | 25 | [5 empty] | 2022-10-30 | COMP | 2022-10-15 | 2 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 17041 | 2022-09-21 | 2022-09-30 |  | 26 | RO | 5 | [6 empty] | KW1-5358 | 26 | [5 empty] | 2022-10-30 | COMP | 2022-10-15 | 5 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V01-0029 | JUNCTION BOX, PVC, BLACK, 2 WAY, 20MM | 17704 | 2022-09-21 | 2022-09-21 |  | 1 | EA | 100 | [6 empty] | KW1-5212 | 13 | [5 empty] | 2022-12-28 | COMP | 2022-10-08 | 100 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 17041 | 2022-09-21 | 2022-09-30 |  | 27 | RL | 1 | [6 empty] | KW1-5358 | 27 | [5 empty] | 2022-10-30 | COMP | 2022-10-10 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 17041 | 2022-09-21 | 2022-09-30 |  | 28 | RL | 58 | [6 empty] | KW1-5358 | 28 | [5 empty] | 2022-10-30 | COMP | 2022-10-10 | 58 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6145-60-V00-0143 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4 MM² | 17041 | 2022-09-21 | 2022-09-30 |  | 29 | RL | 7 | [6 empty] | KW1-5358 | 29 | [5 empty] | 2022-10-30 | COMP | 2022-10-10 | 7 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6145-60-V00-0151 | WIRE, ELECTRICAL, BLACK, 1 CORE, 2.5 mm² | 17041 | 2022-09-21 | 2022-09-30 |  | 30 | RO | 56 | [6 empty] | KW1-5358 | 30 | [5 empty] | 2022-10-30 | COMP | 2022-10-10 | 56 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6145-60-V00-0152 | WIRE, ELECTRICAL, RED, 1 CORE, 2.5 MM ² | 17041 | 2022-09-21 | 2022-09-30 |  | 31 | RL | 22 | [6 empty] | KW1-5358 | 31 | [5 empty] | 2022-10-30 | COMP | 2022-10-10 | 22 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6145-60-V00-0154 | WIRE, ELECTRICAL, BLACK, 1 CORE, 4 MM ² | 17041 | 2022-09-21 | 2022-09-30 |  | 32 | RO | 4 | [6 empty] | KW1-5358 | 32 | [5 empty] | 2022-10-30 | COMP | 2022-10-10 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6145-60-V00-0156 | WIRE, ELECTRICAL, BLUE, 1 CORE, 2.5 MM ² | 17041 | 2022-09-21 | 2022-09-30 |  | 33 | RO | 20 | [6 empty] | KW1-5358 | 33 | [5 empty] | 2022-10-30 | COMP | 2022-10-10 | 20 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 17041 | 2022-09-21 | 2022-09-30 |  | 34 | EA | 1 | [6 empty] | KW1-5358 | 34 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6210-60-V00-0136 | LIGHT UNIT, EMERGENCY, (EXIT LIGHT), LED, 120-277 V, 50/60 HZ, 2 W | 17041 | 2022-09-21 | 2022-09-30 |  | 35 | EA | 4 | [6 empty] | KW1-5358 | 35 | [5 empty] | 2022-10-30 | COMP | 2022-10-11 | 4 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8010-60-V00-0006 | PAINT, LATEX, MATT, OFF-WHITE, 3.2 LITER | 17049 | 2022-09-21 | 2022-09-24 |  | 18 | CN | 60 | [6 empty] | KW1-5620 | 18 | [5 empty] | 2022-11-17 | COMP | 2022-10-30 | 60 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8020-00-260-1302 | BRUSH, PAINT, BRISTLES, CHISELED, 2 INCHES | 17050 | 2022-09-21 | 2022-09-24 |  | 2 | EA | 20 | [6 empty] | KW1-5212 | 5 | [5 empty] | 2022-10-22 | COMP | 2022-10-01 | 5 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8040-60-V00-0045 | ADHESIVE, CEMENT, PVC, CLEAR, 16 FL. OUNCES | 17041 | 2022-09-21 | 2022-09-30 |  | 36 | CN | 1 | [6 empty] | KW1-5358 | 36 | [5 empty] | 2022-10-30 | COMP | 2022-10-12 | 1 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5660-60-V00-0046 | FENCING, WIRE, PVC COATED, GREEN, 2.5 MM | 17049 | 2022-09-21 | 2022-09-21 |  | 9 | RO | 3 | [6 empty] | KW1-5620 | 9 | [5 empty] | 2022-11-17 | WINSP | 2022-10-31 | 3 |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 17043 | 2022-09-21 | 2022-09-21 |  | 1 | EA | 400 | [6 empty] | KW1-5212 | 3 | [5 empty] | 2022-09-24 |  |  |  |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-05-V00-0005 | PANEL, DRYWALL, WALL BOARD, REGULAR, MOLD-GUARD, 1/2 INCH X 4 X 8 FEET | 17053 | 2022-09-21 | 2022-09-21 |  | 26 | EA | 20 | [6 empty] | KW1-5679 | 26 | [5 empty] | 2022-11-14 |  |  |  |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5650-60-V00-0002 | ROOFING METAL, WHITE, 0.35 MM X 3 METER | 17045 | 2022-09-21 | 2022-09-24 |  | 11 | SH | 40 | [6 empty] | KW1-5212 | 11 | [5 empty] | 2022-10-30 |  |  |  |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5680-60-V00-0001 | CORNER BEAD, PAPER-FACED METAL, OFF-WHITE, 1 INCH X 10 FEET | 17053 | 2022-09-21 | 2022-09-21 |  | 27 | EA | 65 | [6 empty] | KW1-5679 | 27 | [5 empty] | 2022-11-14 |  |  |  |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5930-60-V00-0215 | SWITCH, BOX, POP-UP, FLOOR, 2-GANG, STAINLESS STEEL, SILVER, 110-220V, 10-20A | 17053 | 2022-09-21 | 2022-09-21 |  | 28 | EA | 60 | [6 empty] | KW1-5679 | 28 | [5 empty] | 2022-11-14 |  |  |  |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0103 | JUNCTION BOX, PVC, BLACK, 3 WAY, 20 MM | 17053 | 2022-09-21 | 2022-09-21 |  | 29 | EA | 50 | [6 empty] | KW1-5679 | 29 | [5 empty] | 2022-11-14 |  |  |  |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0413 | ANCHOR, PLASTIC, BUTTERFLY, WHITE, 6MM | 17053 | 2022-09-21 | 2022-09-21 |  | 30 | BX | 5 | [6 empty] | KW1-5679 | 30 | [5 empty] | 2022-11-14 |  |  |  |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V01-0223 | BEND, ELECTRICAL CONDUIT, PVC, BLACK, 3/4 INCHES | 17704 | 2022-09-21 | 2022-09-21 |  | 1 | EA | 100 | [6 empty] | KW1-5212 | 3 | [5 empty] | 2022-09-24 |  |  |  |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6145-60-V00-0153 | WIRE, ELECTRICAL, YELLOW, 1 CORE, 2.5 MM² | 17053 | 2022-09-21 | 2022-09-21 |  | 31 | RL | 18 | [6 empty] | KW1-5679 | 31 | [5 empty] | 2022-11-14 |  |  |  |  | AJ | AJ table | September | 2022 | MM_AJ
1 | 2022-09-21 | 20 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6210-60-V00-0011 | FIXTURE, LIGHTING, LED, 5000K, 100-277V, 20W, 2 FEET | 17053 | 2022-09-21 | 2022-09-21 |  | 32 | EA | 8 | [6 empty] | KW1-5679 | 32 | [5 empty] | 2022-11-14 |  |  |  |  | AJ | AJ table | September | 2022 | MM_AJ
2 | 2023-01-14 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6210-60-V00-0082 | LIGHT, PANEL, LED, COOL WHITE, 50/60 HZ, 40W, w/ EMERGENCY BATTERY | 25435 | 2023-01-14 | 2023-01-15 |  | 1 | EA | 5 | [6 empty] | KW1-7626 | 3 | [5 empty] | 2023-02-11 | COMP | 2023-01-29 | 5 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-14 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6210-60-V00-0094 | FIXTURE, LIGHTING, LED, RETROFIT, POLYCARBONATE, PURE WHITE, 40W | 25435 | 2023-01-14 | 2023-01-15 |  | 2 | EA | 6 | [6 empty] | KW1-7626 | 4 | [5 empty] | 2023-02-11 | COMP | 2023-01-29 | 6 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-14 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 25435 | 2023-01-14 | 2023-01-15 |  | 3 | EA | 3 | [6 empty] | KW1-7626 | 5 | [5 empty] | 2023-02-11 | COMP | 2023-01-29 | 3 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-14 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6210-60-V00-0099 | FIXTURE, LIGHTING, LED, FLOOD, 5000K, 50/60HZ, 90W | 25436 | 2023-01-14 | 2023-01-15 |  | 1 | EA | 2 | [6 empty] | KW1-7626 | 7 | [5 empty] | 2023-02-11 | COMP | 2023-01-29 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 25492 | 2023-01-15 | 2023-01-16 |  | 9 | RO | 1 | [6 empty] | KW1-7510 | 9 | [5 empty] | 2023-01-25 | COMP | 2023-01-25 | 1 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 25492 | 2023-01-15 | 2023-01-16 |  | 2 | RO | 3 | [6 empty] | KW1-7510 | 2 | [5 empty] | 2023-01-25 | COMP | 2023-01-25 | 3 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0428 | LUG, TERMINAL, ROUND TYPE, ONE-HOLE, M12, 120MM² | 25492 | 2023-01-15 | 2023-01-16 |  | 6 | PG | 1 | [6 empty] | KW1-7510 | 6 | [5 empty] | 2023-01-25 | COMP | 2023-01-25 | 1 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0417 | LUG, TERMINAL, SINGLE-HOLE, 240MM² X M12 | 25492 | 2023-01-15 | 2023-01-16 |  | 5 | PG | 2 | [6 empty] | KW1-7510 | 4 | [5 empty] | 2023-01-25 | COMP | 2023-01-25 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0353 | STUFFING TUBE (CABLE GLAND), SINGLE WIRE ARMOR, BRASS, M63, 54.6-65.8 MM | 25492 | 2023-01-15 | 2023-01-16 |  | 4 | EA | 20 | [6 empty] | KW1-7510 | 4 | [5 empty] | 2023-03-31 | COMP | 2023-01-25 | 20 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5935-60-V00-0167 | CONNECTOR, WIRE, RED, 18 -10 AWG | 25496 | 2023-01-15 | 2023-01-16 |  | 1 | BX | 2 | [6 empty] | KW1-7508 | 7 | [5 empty] | 2023-01-25 | COMP | 2023-01-25 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0487 | COUPLING, ELECTRICAL CONDUIT, w/ SCREW, Â½ INCH | 25495 | 2023-01-15 | 2023-01-16 |  | 3 | EA | 50 | [6 empty] | KW1-7508 | 2 | [5 empty] | 2023-02-11 | COMP | 2023-03-20 | 50 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0483 | BOX CONNECTOR, ELECTRICAL, ZINC DIE CAST, 1/2 INCH | 25495 | 2023-01-15 | 2023-01-16 |  | 2 | EA | 50 | [6 empty] | KW1-7508 | 3 | [5 empty] | 2023-02-11 | COMP | 2023-03-20 | 50 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0381 | CLAMP, ELECTRICAL, CONDUIT, 2 HOLE, STEEL, 1/2 INCH | 25495 | 2023-01-15 | 2023-01-16 |  | 1 | EA | 25 | [6 empty] | KW1-7508 | 4 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 25 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0528 | CONDUIT, RIGID, EMT, GALVANIZED STEEL, 1/2 INCH X 10 FEET | 25495 | 2023-01-15 | 2023-01-16 |  | 4 | EA | 15 | [6 empty] | KW1-7508 | 5 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 15 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0335 | STRAP, TIE DOWN, ELECTRICAL, COMPON (CABLE TIE), BLACK, 50 LBS, 4.6 MM X 11.02 INCHES | 25492 | 2023-01-15 | 2023-01-16 |  | 3 | BX | 2 | [6 empty] | KW1-7508 | 3 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 25494 | 2023-01-15 | 2023-01-16 |  | 1 | BX | 2 | [6 empty] | KW1-7508 | [6 empty] | 2023-02-11 | COMP | 2023-01-25 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5970-01-013-9368 | TAPE, INSULATION, ELECTRICAL, GREEN, 3/4 X 792 INCHES | 25492 | 2023-01-15 | 2023-01-16 |  | 1 | RO | 1 | [6 empty] | KW1-7508 | 1 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 1 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6350-60-V00-0102 | ALARM, SMOKE, AUTOMATIC, PLASTIC | 25492 | 2023-01-15 | 2023-01-16 |  | 13 | EA | 8 | [6 empty] | KW1-7508 | 13 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 8 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5305-60-V00-0001 | SCREW, SELF DRILLING, HEX WASHER HEAD, STEEL, 5/16 X 1 INCH | 25493 | 2023-01-15 | 2023-01-16 |  | 1 | PG | 2 | [6 empty] | KW1-7508 | [6 empty] | 2023-02-11 | COMP | 2023-01-25 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0484 | BOX CONNECTOR, ELECTRICAL, METALLIC CONDUIT, ZINC, 3/4 INCH | 25492 | 2023-01-15 | 2023-01-16 |  | 7 | EA | 15 | [6 empty] | KW1-7508 | 7 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 15 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 25492 | 2023-01-15 | 2023-01-16 |  | 8 | RO | 2 | [6 empty] | KW1-7508 | 10 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0153 | WIRE, ELECTRICAL, YELLOW, 1 CORE, 2.5 MM² | 25492 | 2023-01-15 | 2023-01-16 |  | 10 | RO | 2 | [6 empty] | KW1-7508 | 11 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0157 | WIRE, ELECTRICAL, YELLOW, 1 CORE, 4MM ² | 25492 | 2023-01-15 | 2023-01-16 |  | 11 | RO | 4 | [6 empty] | KW1-7508 | 12 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 4 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0159 | WIRE, ELECTRICAL, BLUE, 1 CORE, 4 MM ² | 25492 | 2023-01-15 | 2023-01-16 |  | 12 | RO | 2 | [6 empty] | KW1-7508 | 12 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-15 | 40 | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0136 | WIRE, ELECTRICAL, RED, 1 CORE, 4 MM ² | 25495 | 2023-01-15 |  |  | 5 | RO | 2 | [6 empty] | KW1-7508 | 6 | [5 empty] | 2023-02-11 | COMP | 2023-01-25 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0458 | ELBOW, PIPE, SOCKET X SPIGOT, 45°, PVC, ORANGE, 110MM | 25577 | 2023-01-17 | 2023-01-19 |  | 7 | EA | 4 | [6 empty] | KW1-7799 | 1 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 4 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0390 | TEE-Y, DRAINAGE PIPE, PVC-U, 45 DEGREE, TERRACOTTA, 110 MILLIMETER | 25577 | 2023-01-17 | 2023-01-19 |  | 6 | EA | 1 | [6 empty] | KW1-7799 | 7 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 1 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0589 | PLUG, ACCESS, w/ THREADED CAP, UPVC, GRAY, 110MM | 25578 | 2023-01-17 | 2023-01-19 |  | 1 | EA | 2 | [6 empty] | KW1-8003 | 15 | [5 empty] | 2023-03-15 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0973 | TEE, PIPE, SEWER AND DRAIN FITTINGS, PVC, SCH-80, ORANGE, 110 MM | 25577 | 2023-01-17 | 2023-01-19 |  | 16 | EA | 2 | [6 empty] | KW1-7799 | 8 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0964 | COUPLING, SEWAGE, w/RUBBER GASKET, PVC, ORANGE, 4 INCHES | 25575 | 2023-01-17 | 2023-01-19 |  | 5 | EA | 8 | [6 empty] | KW1-8003 | 16 | [5 empty] | 2023-03-15 | COMP | 2023-03-15 | 8 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4710-60-V00-0101 | PIPE, PLASTIC, PVC, ORANGE, 4 INCHES X 13 FEET | 25577 | 2023-01-17 | 2023-01-19 |  | 3 | EA | 5 | [6 empty] | KW1-7799 | 9 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 5 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0132 | STRAP, METAL | 25577 | 2023-01-17 | 2023-01-19 |  | 1 | EA | 3 | [6 empty] | KW1-7799 | 2 | [5 empty] | 2023-03-05 | COMP | 2023-03-15 | 3 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 8040-60-V00-0051 | ADHESIVE, CEMENT, PVC, WET 'R DRY, MEDIUM BODY, AQUA BLUE, 32 OZ. | 25575 | 2023-01-17 | 2023-01-19 |  | 8 | EA | 2 | [6 empty] | KW1-8003 | 10 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0908 | BUSHING, PIPE, SEWAGE, REDUCTION, SCH-40, PVC, ORANGE, 4 X 1-1/2 INCHES | 25577 | 2023-01-17 | 2023-01-19 |  | 13 | EA | 4 | [6 empty] | KW1-7799 | 3 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 4 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 8030-60-V00-0051 | TAPE, ANTISEIZING, (TEFLON TAPE), 0.5 X 520 INCHES | 25577 | 2023-01-17 | 2023-01-19 |  | 17 | EA | 10 | [6 empty] | KW1-7799 | 10 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 10 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0708 | TRAP, DRAINAGE PIPE, UNDERGROUND, 45°, PVC-U, TERRACOTTA, 110 MM | 25577 | 2023-01-17 | 2023-01-19 |  | 8 | EA | 1 | [6 empty] | KW1-7799 | 4 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 1 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0795 | CAP, PIPE, UPVC, SPIGOT, SCH-80, ORANGE, 4 INCHES | 25574 | 2023-01-17 | 2023-01-19 |  | 1 | EA | 2 | [6 empty] | KW1-8003 | 1 | [5 empty] | 2023-03-15 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4820-60-V00-0235 | VALVE, BALL, BRASS, 2 INCHES | 25574 | 2023-01-17 | 2023-01-19 |  | 3 | EA | 2 | [6 empty] | KW1-8003 | 1 | [5 empty] | 2023-03-15 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0845 | WYE, TRUE, PIPE, SCH 40, UPVC, GRAY, 45 °, 50MM | 25576 | 2023-01-17 | 2023-01-19 |  | 1 | EA | 2 | [6 empty] | KW1-8003 | 1 | [5 empty] | 2023-03-15 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0632 | BUSHING, PIPE, REDUCER, SOCKET X SOCKET, CPVC, OFFWHITE, 32 X 25 MM | 25578 | 2023-01-17 | 2023-01-19 |  | 2 | EA | 2 | [6 empty] | KW1-8003 | 16 | [5 empty] | 2023-03-15 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0829 | COUPLING, UPVC, SCH-40, GRAY, 50 MM | 25574 | 2023-01-17 | 2023-01-19 |  | 2 | EA | 4 | [6 empty] | KW1-8003 | 1 | [5 empty] | 2023-03-15 | COMP | 2023-03-15 | 4 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0757 | ADAPTER, MALE, CPVC, STRAIGHT, SOCKET X MIPT, SCH-40, OFF-WHITE, 63 MM | 25575 | 2023-01-17 | 2023-01-19 |  | 2 | EA | 6 | [6 empty] | KW1-8003 | 5 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 6 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4710-60-V00-0054 | PIPE, UPVC, SCH40, NON-PRESSURE, GREY, 50 MM X 2.2MM X 6 METER | 25577 | 2023-01-17 | 2023-01-19 |  | 2 | EA | 6 | [6 empty] | KW1-7799 | 5 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 6 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0835 | COUPLING, CPVC, SCH-40, TAN, 32 MM | 25575 | 2023-01-17 | 2023-01-19 |  | 2 | EA | 4 | [6 empty] | KW1-8003 | 6 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 4 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0970 | ELBOW, PRESSURE FITTINGS, PVC, STANDARD, 90 °, SPIGOT X SOCKET, ORANGE, 110 MM | 25577 | 2023-01-17 | 2023-01-19 |  | 15 | EA | 8 | [6 empty] | KW1-7799 | 6 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 8 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0897 | BUSHING, PIPE, REDUCER, SCH-40, CPVC, OFF-WHITE, 2 X 1 INCHES | 25575 | 2023-01-17 | 2023-01-19 |  | 3 | EA | 2 | [6 empty] | KW1-8003 | 7 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0854 | ELBOW, CPVC, 90 DEGREE, SCH- 40, OFF-WHITE, 2 INCHES | 25577 | 2023-01-17 | 2023-01-19 |  | 12 | EA | 5 | [6 empty] | KW1-8003 | 11 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 5 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0940 | TEE, PIPE, SOCKET X SOCKET X SOCKET, CPVC, OFF-WHITE, SCH 40, 25 MM | 25577 | 2023-01-17 | 2023-01-19 |  | 14 | EA | 2 | [6 empty] | KW1-8003 | 12 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0850 | ELBOW, CPVC, SOCKET X SOCKET, SCH 40, OFF-WHITE, 25 MM | 25577 | 2023-01-17 | 2023-01-19 |  | 11 | EA | 6 | [6 empty] | KW1-8003 | 13 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 6 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4710-60-V00-0108 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 25577 | 2023-01-17 | 2023-01-19 |  | 5 | EA | 2 | [6 empty] | KW1-8003 | 14 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0949 | UNION, PIPE, SOCKET X SOCKET, SCH- 40, CPVC, OFF-WHITE, 32 MM | 25575 | 2023-01-17 | 2023-01-19 |  | 4 | EA | 2 | [6 empty] | KW1-8003 | 8 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4710-60-V00-0111 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 1 INCH | 25575 | 2023-01-17 | 2023-01-19 |  | 1 | EA | 10 | [6 empty] | KW1-8003 | 9 | [5 empty] | 2023-04-21 | COMP | 2023-03-15 | 10 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4710-60-V00-0107 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 2 INCHES | 25577 | 2023-01-17 | 2023-01-19 |  | 4 | EA | 4 | [6 empty] | KW1-7799 | 15 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 4 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0770 | ADAPTER, PRESSURE FITTINGS, FEMALE, CPVC, STANDARD, SOCKET X SR FIPT, SCH- 40, OFF-WHITE, 63 MM | 25577 | 2023-01-17 | 2023-01-19 |  | 10 | EA | 2 | [6 empty] | KW1-7799 | 16 | [5 empty] | 2023-03-05 | COMP | 2023-02-13 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-17 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0923 | TEE, PIPE, CPVC, SCH-40, OFF-WHITE, 63 MM | 25576 | 2023-01-17 | 2023-01-19 |  | 2 | EA | 1 | [6 empty] | KW1-8003 | 13 | [5 empty] | 2023-03-15 | COMP | 2023-03-12 | 1 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-19 |  | AJ22-0135 | Replace 65 Street Light Heads | 238765 | PANEL | FABRICATION,LIGHT CONTROL PANEL (LC3) WITH LIGHT CONTROL PANEL MOUNTING STAND , APPROVED SUBMITTAL VIA TRANSMITTAL # AJ220044-LCV-ELE-DSN-0001 | 41575 | 2023-01-19 | 2023-01-21 |  | 1 | AY | 1 | [6 empty] | KW1-11546 | 10 | [5 empty] | 2023-03-08 | COMP | 2023-04-04 | 1 |  | AJ | AJ table | January | 2023 | MM_AJ
2 | 2023-01-23 | 70 | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0584 | OUTLET, DRAIN, MALE, BRASS, 2 INCHES | 25945 | 2023-01-23 | 2023-01-26 |  | 2 | EA | 2 | [6 empty] | KW1-7727 | 3 | [5 empty] | 2023-02-18 | COMP | 2023-02-15 | 2 |  | AJ | AJ table | January | 2023 | MM_AJ
3 | 2023-02-11 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5975-60-V00-0036 | PROTECTOR, CABLE, SPIRAL WRAPPING BAND, w/ CLIP, POLYETHYLENE, BLACK, 15 MM X 1.5 METER | 27260 | 2023-02-11 | 2023-02-12 | CLOSE | 1 | RO | 100 | 8.25 | 825 | 11082 | CLOSE | 2023-03-05 | 2023-02-15 | KW1-8005 | 23 | 2023-03-05 | CLOSE | 2023-08-14 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-04-30 | COMP | 2023-04-27 | 100.00 |  | UCO | AJ table | February | 2023 | MM_AJ
3 | 2023-02-11 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5975-60-V00-0090 | COUPLING, ELECTRICAL CONDUIT, COMPRESSION, ZINC DIE CAST, 3/4 INCH | 27260 | 2023-02-11 | 2023-02-12 | CLOSE | 2 | EA | 30 | 9.49 | 284.7 | 11082 | CLOSE | 2023-03-05 | 2023-02-15 | KW1-8005 | 24 | 2023-03-05 | CLOSE | 2023-08-14 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-05-30 | COMP | 2023-04-30 | 30.00 |  | UCO | AJ table | February | 2023 | MM_AJ
3 | 2023-02-11 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5975-60-V00-0530 | CONDUIT, RIGID, GALVANIZED STEEL, THREADED, 3/4 INCH X 10 FEET | 27260 | 2023-02-11 | 2023-02-12 | CLOSE | 3 | EA | 60 | 55.13 | 3307.8 | 11082 | CLOSE | 2023-03-05 | 2023-02-15 | KW1-8005 | 25 | 2023-03-05 | CLOSE | 2023-08-14 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-04-30 | COMP | 2023-03-13 | 60.00 |  | UCO | AJ table | February | 2023 | MM_AJ
3 | 2023-02-11 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5995-60-V00-0132 | STRAP, TIE DOWN (CABLE TIE), NYLON 6/6, BLACK, 7 INCHES | 27260 | 2023-02-11 | 2023-02-12 | CLOSE | 4 | PG | 10 | 16.5 | 165 | 11082 | CLOSE | 2023-03-05 | 2023-02-15 | KW1-8005 | 26 | 2023-03-05 | CLOSE | 2023-08-14 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-04-30 | COMP | 2023-03-14 | 10.00 |  | UCO | AJ table | February | 2023 | MM_AJ
3 | 2023-02-11 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 27292 | 2023-02-11 | 2023-02-12 | CLOSE | 2 | RL | 6 | 57.75 | 346.5 | 11086 | CLOSE | 2023-02-21 | 2023-02-15 | KW1-7987 | 1 | 2023-02-21 | CLOSE | 2023-05-09 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-03-30 | COMP | 2023-02-27 | 6.00 |  | UCO | AJ table | February | 2023 | MM_AJ
3 | 2023-02-11 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 6145-60-V00-0151 | WIRE, ELECTRICAL, BLACK, 1 CORE, 2.5 mm² | 27292 | 2023-02-11 | 2023-02-12 | CLOSE | 3 | RO | 15 | 57.34 | 860.1 | 11086 | CLOSE | 2023-02-21 | 2023-02-15 | KW1-7987 | 2 | 2023-02-21 | CLOSE | 2023-05-09 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-03-30 | COMP | 2023-02-27 | 15.00 |  | UCO | AJ table | February | 2023 | MM_AJ
3 | 2023-02-11 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 6145-60-V00-0152 | WIRE, ELECTRICAL, RED, 1 CORE, 2.5 MM ² | 27292 | 2023-02-11 | 2023-02-12 | CLOSE | 4 | RO | 15 | 57.34 | 860.1 | 11086 | CLOSE | 2023-02-21 | 2023-02-15 | KW1-7987 | 3 | 2023-02-21 | CLOSE | 2023-05-09 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-03-30 | COMP | 2023-02-27 | 15.00 |  | UCO | AJ table | February | 2023 | MM_AJ
3 | 2023-02-11 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 6145-60-V00-0153 | WIRE, ELECTRICAL, YELLOW, 1 CORE, 2.5 MM² | 27292 | 2023-02-11 | 2023-02-12 | CLOSE | 5 | RL | 15 | 57.34 | 860.1 | 11086 | CLOSE | 2023-02-21 | 2023-02-15 | KW1-7987 | 4 | 2023-02-21 | CLOSE | 2023-05-09 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-03-30 | COMP | 2023-02-27 | 15.00 |  | UCO | AJ table | February | 2023 | MM_AJ
3 | 2023-02-11 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 6145-60-V00-0156 | WIRE, ELECTRICAL, BLUE, 1 CORE, 2.5 MM ² | 27292 | 2023-02-11 | 2023-02-12 | CLOSE | 6 | RO | 15 | 55.62 | 834.3 | 11086 | CLOSE | 2023-02-21 | 2023-02-15 | KW1-7987 | 5 | 2023-02-21 | CLOSE | 2023-05-09 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-03-30 | COMP | 2023-02-27 | 15.00 |  | UCO | AJ table | February | 2023 | MM_AJ
3 | 2023-02-15 | 30 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5306-60-V00-0118 | NUT AND BOLT, 1-1/2 X 3/8 INCHES | 27610 | 2023-02-15 | 2023-02-20 | CLOSE | 1 | EA | 300 | 0.85 | 255 | 11608 | CLOSE | 2023-03-23 | 2023-03-07 | KW1-8626 | 1 | 2023-03-27 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-14 | COMP | 2023-03-30 | 300.00 |  | UCO | AJ table | February | 2023 | MM_AJ
3 | 2023-02-15 | 30 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5940-01-619-8810 | TERMINAL, LUG, 4-16 AWG, BLUE, 0.19 X 0.33 INCHES | 27609 | 2023-02-15 | 2023-02-16 | CLOSE | 1 | EA | 300 | 1.18 | 354 | 11213 | CLOSE | 2023-02-23 | 2023-02-19 | KW1-8050 | 20 | 2023-03-07 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-05-07 | COMP | 2023-03-28 | 300.00 |  | UCO | AJ table | February | 2023 | MM_AJ
3 | 2023-02-15 | 30 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5975-60-V00-0741 | BOX CONNECTOR, ELECTRICAL (CONDUIT HUB), RIGID, ZINC, 3/4 INCH | 27611 | 2023-02-15 | 2023-05-28 | CLOSE | 1 | EA | 90 | 17.3 | 1557 | 13866 | CLOSE | 2023-05-31 | 2023-06-01 | KW1-9751 | 1 | 2023-05-31 | CLOSE | 2023-11-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-07-15 | COMP | 2023-06-20 | 90.00 |  | UCO | AJ table | February | 2023 | MM_AJ
3 | 2023-02-15 | 30 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5975-60-V00-0743 | BOX CONNECTOR, ELECTRICAL, CONDUIT, SET SCREW, STEEL, 3/4 INCH | 27611 | 2023-02-15 | 2023-05-28 | CLOSE | 3 | EA | 150 | 3.2 | 480 | 13866 | CLOSE | 2023-05-31 | 2023-06-01 | KW1-9751 | 2 | 2023-05-31 | CLOSE | 2023-11-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-08-15 | COMP | 2023-07-06 | 36.00 |  | UCO | AJ table | February | 2023 | MM_AJ
3 | 2023-02-15 | 30 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5975-60-V00-0744 | RACEWAY, NONMETALLIC, OPEN SLOT WIRING CABLE, DUCT w/COVER, PVC, 2 X 1 INCHES X 6 FEET | 27611 | 2023-02-15 | 2023-05-28 | CLOSE | 4 | EA | 60 | 11.25 | 675 | 13866 | CLOSE | 2023-05-31 | 2023-06-01 | KW1-9751 | 3 | 2023-05-31 | CLOSE | 2023-11-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-08-15 | COMP | 2023-07-13 | 10.00 |  | UCO | AJ table | February | 2023 | MM_AJ
3 | 2023-02-15 | 30 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 6145-60-V00-0009 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 10 MM ² | 27609 | 2023-02-15 | 2023-02-16 | CLOSE | 2 | RL | 10 | 206.64 | 2066.4 | 11213 | CLOSE | 2023-02-23 | 2023-02-19 | KW1-8050 | 21 | 2023-03-07 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-04-05 | COMP | 2023-03-11 | 9.00 |  | UCO | AJ table | February | 2023 | MM_AJ
3 | 2023-02-15 | 30 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 5975-60-V00-0812 | CONDUIT, METAL, RIGID IMC, THREADED, STEEL, 3/4 INCH X 3 MTR | 55710 | 2024-02-29 | 2024-03-07 | APPR | 1 | EA | 40 | 25.68 | 1027.2 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | UCO | AJ table | February | 2023 | MM_AJ
4 | 2023-02-27 | 60 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5650-60-V00-0004 | CHANNEL, STRUCTURAL, C-SHAPE, STEEL, 1-5/8 X 3-5/8 INCHES X 10 FEET | 28446 | 2023-02-27 | 2023-02-27 | CLOSE | 1 | EA | 86 | 4.13 | 355.18 | 11608 | CLOSE | 2023-03-23 | 2023-03-07 | KW1-8626 | 5 | 2023-03-27 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-06 | COMP | 2023-05-02 | 86.00 |  | AJ | AJ table | February | 2023 | MM_AJ
5 | 2023-03-25 |  | AJ22-0136 | T353 Relocation | 2141524 | 4240-60-V00-0104 | MESH, SAFETY, FLUORESCENT ORANGE, 1 X 50 METER | 30405 | 2023-03-25 | 2023-03-26 | CLOSE | 1 | RO | 10 | 237.6 | 2376 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 1 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-07-03 | 10.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5940-60-V00-0090 | LUG, TERMINAL, ROUND TYPE, COPPER, ONE-HOLE, 25MM² X 10MM | 30462 | 2023-03-26 | 2023-03-26 | CLOSE | 2 | PK | 2 | 9.09 | 18.18 | 13217 | SENT | 2023-05-11 | 2023-05-06 | KW1-9447 | 1 | 2023-05-16 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-16 | COMP | 2023-05-16 | 2.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5975-60-V00-0521 | CLAMP, GROUNDING, BRONZE, 5/8 - 1/2 INCH | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 10 | EA | 4 | 24.98 | 99.92 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 12 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 4.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 9 | RO | 1 | 262.24 | 262.24 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 11 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 1.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 4130-60-V00-0137 | MOUNTING BASE, AIR-CONDITIONER, POLYPROPYLENE, IVORY, 17 X 3 X 5.12 INCHES | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 8 | EA | 2 | 62.94 | 125.88 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 10 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 2.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 4730-60-V00-0594 | C-CLAMP W/ RUBBER, GALVANIZED STEEL, 2 INCHES | 30460 | 2023-03-26 | 2023-03-26 | CLOSE | 5 | EA | 20 | 10.32 | 206.4 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 20 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 20.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 4130-60-V00-0288 | TAPE, WRAP, INSULATION, 3 INCHES X 150 FEET | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 7 | RO | 6 | 32.3 | 193.8 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 9 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 6.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 8030-60-V00-0053 | FOAM, CONSTRUCTION, CREAM, 700ML | 30459 | 2023-03-26 | 2023-03-26 | CLOSE | 1 | EA | 2 | 19.65 | 39.3 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 14 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 2.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5940-60-V00-0083 | LUG, TERMINAL, FORK, INSULATED, YELLOW, 12-10 AWG | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 6 | PG | 1 | 63.77 | 63.77 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 8 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 1.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 30461 | 2023-03-26 | 2023-03-26 | CLOSE | 1 | EA | 4 | 57.7 | 230.8 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 22 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 4.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 5 | RO | 1 | 65.6 | 65.6 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 7 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 1.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5975-00-156-3253 | STRAP, TIE DOWN, ELECTRICAL COMPONE, 13-7/20 INCHES | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 4 | HD | 2 | 18.98 | 37.96 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 6 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 2.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 3 | EA | 10 | 3.5 | 35 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 5 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 10.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5975-60-V00-0504 | UNION, ELECTRICAL CONDUIT, NYLON POLYAMIDE, LONG THREAD, 5-10 MM | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 2 | EA | 10 | 3.33 | 33.3 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 4 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 10.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 4710-60-V00-0110 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 30458 | 2023-03-26 | 2023-03-30 | CLOSE | 1 | EA | 4 | 19.98 | 79.92 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 3 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-24 | 4.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 4730-60-V00-0833 | COUPLING, PIPE, SCH-40, SOCKET X SOCKET, CPVC, TAN, 20 MM | 30460 | 2023-03-26 | 2023-03-26 | CLOSE | 4 | EA | 10 | 4 | 40 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 19 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-24 | 10.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 30460 | 2023-03-26 | 2023-03-26 | CLOSE | 3 | BX | 2 | 29.94 | 59.88 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 18 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 2.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5305-60-V00-0173 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 30460 | 2023-03-26 | 2023-03-26 | CLOSE | 2 | BX | 2 | 33.8 | 67.6 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 17 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 2.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 5305-60-V00-0196 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 3/8 INCHES | 30460 | 2023-03-26 | 2023-03-26 | CLOSE | 1 | BX | 2 | 32.63 | 65.26 | 12533 | SENT | 2023-07-12 | 2023-04-06 | KW1-8897 | 16 | 2023-06-18 | CLOSE | 2023-10-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-29 | COMP | 2023-06-22 | 2.00 |  | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 6145-60-V00-0119 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 25MM Â² | 30458 | 2023-03-26 |  |  | 1 | M | 100 | [17 empty] | CANCELLED AS PER JUNE | AJ | AJ table | March | 2023 | MM_AJ
5 | 2023-03-26 |  | AJ22-0136 | T353 Relocation | 2141524 | 6145-60-V00-0088 | CABLE, POWER, ELECTRICAL, WHITE, 7 CORE, 1.5 MM² | 30462 | 2023-03-26 | 2023-03-26 | CLOSE | 1 | RO | 2 | 165.26 | 330.52 | 13383 | CLOSE | 2023-05-09 | 2023-05-10 | KW1-9448 | 1 | 2023-05-09 | APPR | 2023-05-09 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL INC | 2023-05-10 |  |  |  |  | AJ | AJ table | March | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4710-60-V00-0073 | PIPE, PN16, UPVC, GREY, 110 X 8.1 MM X 6 METERS | 31564 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | EA | 1.00 | 184.1 | 184.1 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 1 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 1.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4730-60-V00-0935 | TEE, PIPE, PRESSURE FITTINGS, REDUCTION, SOCKET X SOCKET X SOCKET, PVC, GRAY, 8 X 6 INCHES | 31566 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | EA | 2.00 | 141.65 | 283.3 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 2 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 2.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4730-60-V00-0383 | ELBOW, PIPE, 45 DEGREE, UPVC PLASTIC, GREY, 110 X 131 MILLIMETER | 31568 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | EA | 4.00 | 48.72 | 194.88 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 3 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 4.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4730-60-V00-0978 | FLANGE, PIPE, RING TYPE, PN10, SCH-80, PVC, 200MM | 31568 | 2023-04-13 | 2023-04-15 | CLOSE | 2 | EA | 2.00 | 113.8 | 227.6 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 4 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 2.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4730-60-V00-0904 | BUSHING, PIPE, REDUCER, PVC, GRAY, 8 X 6 INCHES | 31568 | 2023-04-13 | 2023-04-15 | CLOSE | 3 | EA | 4.00 | 45.78 | 183.12 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 5 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 4.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4730-60-V00-0410 | ELBOW, PIPE, PVC, 45°, SOCKET X SOCKET, SCH-80, GRAY, 8 INCHES | 31568 | 2023-04-13 | 2023-04-15 | CLOSE | 4 | EA | 6.00 | 156.96 | 941.76 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 6 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 6.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4710-60-V00-0074 | PIPE, PN16, UPVC, GREY, 200 X 14.7 MM X 6 METERS | 31568 | 2023-04-13 | 2023-04-15 | CLOSE | 5 | EA | 3.00 | 391.09 | 1173.27 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 7 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 3.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4240-60-V00-0151 | TAPE, WARNING, ELECTRIC LINE BELOW, RED, POLYETHYLENE PLASTIC, 6 INCHES X 1000 FEET | 31570 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | CA | 1.00 | 474.8 | 474.8 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 8 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-31 07:00 | COMP | 2023-04-17 | 1.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4240-60-V00-0150 | TAPE, WARNING, UNDERGROUND, CAUTION BURIED WATER LINE BELOW, BLUE & BLACK, 6 INCHES X 1000 FEET | 31570 | 2023-04-13 | 2023-04-15 | CLOSE | 2 | RL | 1.00 | 196.55 | 196.55 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 9 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-31 07:00 | COMP | 2023-04-17 | 1.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4730-60-V00-0285 | COUPLING, PIPE, DOUBLE SOCKET, PLASTIC, UPVC, GREY, 110 X 131 MILLIMETER | 31570 | 2023-04-13 | 2023-04-15 | CLOSE | 3 | EA | 4.00 | 10 | 40 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 10 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 4.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4730-60-V00-0903 | BUSHING, PIPE, REDUCER, PVC, GRAY, 6 X 4 INCHES | 31570 | 2023-04-13 | 2023-04-15 | CLOSE | 4 | EA | 4.00 | 20.3 | 81.2 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 11 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 4.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4730-60-V00-0827 | COUPLING, PVC, PN10, 5-7/8 X 8 INCHES | 31570 | 2023-04-13 | 2023-04-15 | CLOSE | 5 | EA | 4.00 | 37.13 | 148.52 | 12753 | CLOSE | 2023-04-15 | 2023-04-15 | KW1-9067 | 12 | 2023-04-15 | CLOSE | 2023-05-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-04-23 07:00 | COMP | 2023-04-17 | 4.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4730-60-V00-1652 | CAP, PIPE, END, UPVC, GRAY, 200 MM | 31585 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | EA | 2.00 | 117.62 | 235.24 | 12768 | CLOSE | 2023-04-20 | 2023-04-17 | KW1-9125 | 1 | 2023-04-20 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-04 | COMP | 2023-04-25 | 2.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 8135-60-V00-0003 | PLASTIC SHEET, POLYETHYLENE, CLEAR, 6 MIL, 32 X 100 FEET | 31586 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | RO | 1.00 | 348.91 | 348.91 | 12768 | CLOSE | 2023-04-20 | 2023-04-17 | KW1-9125 | 3 | 2023-04-20 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-04 | COMP | 2023-04-25 | 1.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 5640-60-V00-0057 | BACKER ROD, GAPS, CLOSED-CELL POLYETHYLENE, GRAY, 5/8 INCH X 20 FEET | 31587 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | EA | 5.00 | 20.19 | 100.95 | 12768 | CLOSE | 2023-04-20 | 2023-04-17 | KW1-9125 | 5 | 2023-04-20 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-04 | COMP | 2023-04-25 | 5.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 5530-60-V00-0010 | PLYWOOD, CONSTRUCTION, MARINE GRADE, 3/4 INCH X 8 X 4 FEET | 31588 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | SH | 6.00 | 60.31 | 361.86 | 12927 | CLOSE | 2023-05-16 | 2023-04-26 | KW1-9235 | 14 | 2023-04-27 | CLOSE | 2023-08-26 | Kannoth, Shajee -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-07 | COMP | 2023-05-02 | 6.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 5660-60-V00-0015 | TIE WIRE, ANNEALED, STEEL, 9 GAGE, 100 LB | 31589 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | CL | 1.00 | 855.11 | 855.11 | 12768 | CLOSE | 2023-04-20 | 2023-04-17 | KW1-9125 | 7 | 2023-04-20 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-04 | COMP | 2023-04-29 | 1.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 5610-60-V00-0018 | CONCRETE MIX, GRAY, 4000 PSI, 80 LBS | 31590 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | EA | 80.00 | 15.66 | 1252.8 | 12768 | CLOSE | 2023-04-20 | 2023-04-17 | KW1-9125 | 9 | 2023-04-20 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-04 | COMP | 2023-04-25 | 20.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 4240-60-V00-0104 | MESH, SAFETY, FLUORESCENT ORANGE, 1 X 50 METER | 31591 | 2023-04-13 | 2023-04-15 | CLOSE | 1 | RO | 3.00 | 237.6 | 712.8 | 12768 | CLOSE | 2023-04-20 | 2023-04-17 | KW1-9125 | 11 | 2023-04-20 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-04 | COMP | 2023-04-25 | 3.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 8135-60-V00-0024 | FIBREBOARD, SOLID, BITUMEN, BLACK, 2400 X 100 X 9.5 MM | 31591 | 2023-04-13 | 2023-04-15 | CLOSE | 2 | EA | 21.00 | 8.97 | 188.37 | 12768 | CLOSE | 2023-04-20 | 2023-04-17 | KW1-9125 | 12 | 2023-04-20 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-04 | COMP | 2023-05-03 | 21.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 5620-60-V00-0012 | CONCRETE SPACER (COVER BLOCK), w/TIE-WIRE ATTACHMENT HOLE, 65/75 MM | 31591 | 2023-04-13 | 2023-04-15 | CLOSE | 3 | PG | 1.00 | 634.83 | 634.83 | 12768 | CLOSE | 2023-04-20 | 2023-04-17 | KW1-9125 | 13 | 2023-04-20 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-04 | COMP | 2023-04-25 | 1.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 8030-60-V00-0005 | SEALING COMPOUND, TWO PART POLYSULPHIDE, GREY, 2 LITRES | 31591 | 2023-04-13 | 2023-04-15 | CLOSE | 4 | PG | 4.00 | 121.08 | 484.32 | 12768 | CLOSE | 2023-04-20 | 2023-04-17 | KW1-9125 | 14 | 2023-04-20 | CLOSE | 2023-08-14 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-06-20 | COMP | 2023-05-03 | 4.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-17 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 8030-60-V00-0062 | CLEANER, PIPE, PURLE, 16 OUNCES | 31822 | 2023-04-17 | 2023-04-19 | CLOSE | 1 | CN | 10 | 22.98 | 229.8 | 12883 | INPRG | 2023-04-26 | 2023-04-25 | KW1-9220 | 10 | 2023-04-26 | CLOSE | 2023-08-19 | Kannoth, Shajee -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-07 | COMP | 2023-05-01 | 10.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-17 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 7930-60-V00-0047 | CLEANER, CLEAR, 16 FL OZ | 31822 | 2023-04-17 | 2023-04-19 | CLOSE | 2 | CN | 15 | 26.31 | 394.65 | 12883 | INPRG | 2023-04-26 | 2023-04-25 | KW1-9220 | 11 | 2023-04-26 | CLOSE | 2023-08-19 | Kannoth, Shajee -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-07 | COMP | 2023-05-01 | 15.00 |  | AJ | AJ table | April | 2023 | MM_AJ
6 | 2023-04-17 |  | AJ23-0122 | Z1 Pool Water Leak Assessment | 5434294 | 8040-60-V00-0051 | ADHESIVE, CEMENT, PVC, WET 'R DRY, MEDIUM BODY, AQUA BLUE, 32 OZ. | 31822 | 2023-04-17 | 2023-04-19 | CLOSE | 3 | EA | 8 | 87.41 | 699.28 | 12883 | INPRG | 2023-04-26 | 2023-04-25 | KW1-9220 | 12 | 2023-04-26 | CLOSE | 2023-08-19 | Kannoth, Shajee -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-05-07 | COMP | 2023-05-01 | 8.00 |  | AJ | AJ table | April | 2023 | MM_AJ
7 | 2023-04-29 | 80 | AJ22-0044 | T357 Relocation | 2141526 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 32769 | 2023-04-29 | 2023-05-03 | CLOSE | 2 | BX | 2 | 51.5 | 103 | 13233 | CLOSE | 2023-05-07 | 2023-05-06 | KW1-9404 | 4 | 2023-05-07 | CLOSE | 2023-09-24 | Reghuraman, Karthik -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-14 07:00 | COMP | 2023-05-11 | 2.00 |  | AJ | AJ table | April | 2023 | MM_AJ
8 | 2023-04-29 | 80 | AJ22-0135 | T357 Relocation | 2141526 | 5640-60-V00-0041 | PANEL, CEILING (ACOUSTICAL TILE), MINERAL FIBER, WHITE, 24 X 24 X 3/4 INCHES | 32772 | 2023-04-29 | 2023-05-03 | CLOSE | 1 | EA | 70 | 9.4 | 658 | 13233 | CLOSE | 2023-05-07 | 2023-05-06 | KW1-9404 | 7 | 2023-05-07 | CLOSE | 2023-09-24 | Reghuraman, Karthik -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-14 07:00 | COMP | 2023-05-11 | 70.00 |  | AJ | AJ table | April | 2023 | MM_AJ
8 | 2023-04-29 | 80 | AJ22-0135 | T357 Relocation | 2141526 | 5305-60-V00-0009 | SCREW, SELF TAPPING, STEEL, 5/16 X 6 INCHES | 32771 | 2023-04-29 | 2023-05-03 | CLOSE | 1 | PG | 2 | 53.98 | 107.96 | 13233 | CLOSE | 2023-05-07 | 2023-05-06 | KW1-9404 | 6 | 2023-05-07 | CLOSE | 2023-09-24 | Reghuraman, Karthik -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-14 07:00 | COMP | 2023-05-11 | 2.00 |  | AJ | AJ table | April | 2023 | MM_AJ
8 | 2023-04-29 | 80 | AJ22-0135 | T357 Relocation | 2141526 | 5305-60-V00-0015 | SCREW, SELF DRILLING, HEX WASHER, STEEL, 1/4 -14 X 3/4 INCHES | 32773 | 2023-04-29 | 2023-05-03 | CLOSE | 1 | EA | 50 | 0.31 | 15.5 | 13233 | CLOSE | 2023-05-07 | 2023-05-06 | KW1-9404 | 10 | 2023-05-07 | CLOSE | 2023-09-24 | Reghuraman, Karthik -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-14 07:00 | COMP | 2023-05-11 | 50.00 |  | AJ | AJ table | April | 2023 | MM_AJ
8 | 2023-04-29 | 80 | AJ22-0135 | T357 Relocation | 2141526 | 5680-60-V00-0006 | GRID, CEILING, TEE, WHITE, 24 INCHES | 32772 | 2023-04-29 | 2023-05-03 |  | 1 | EA | 70 | [6 empty] | KW1-9404 | 7 | [6 empty] | COMP | 2023-05-11 | 70 |  | AJ | AJ table | April | 2023 | MM_AJ
8 | 2023-04-29 | 80 | AJ22-0135 | T357 Relocation | 2141526 | 5305-60-V00-0199 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 -1/2 INCHES | 32769 | 2023-04-29 | 2023-05-03 | CLOSE | 1 | BX | 10 | 27.03 | 270.3 | 13233 | CLOSE | 2023-05-07 | 2023-05-06 | KW1-9404 | 3 | 2023-05-07 | CLOSE | 2023-09-24 | Reghuraman, Karthik -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-14 07:00 | COMP | 2023-05-11 | 10.00 |  | AJ | AJ table | April | 2023 | MM_AJ
9 | 2023-04-29 | 80 | AJ22-0205 | T357 Relocation | 2141526 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 32772 | 2023-04-29 | 2023-05-03 | CLOSE | 3 | EA | 2 | 13.73 | 27.46 | 13233 | CLOSE | 2023-05-07 | 2023-05-06 | KW1-9404 | 9 | 2023-05-07 | CLOSE | 2023-09-24 | Reghuraman, Karthik -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-14 07:00 | COMP | 2023-05-11 | 2.00 |  | AJ | AJ table | April | 2023 | MM_AJ
10 | 2023-05-09 | 20 | UCO-P0045 | 50 Electrical Meter Installation | 4103915 | 6625-60-V00-0094 | METER, w/NEMA, CUSTOM ENCLOSURE, 4X PM5560 | 33443 | 2023-05-09 |  | CAN | 1 | EA | 54 | 6817 | 368118 | [16 empty] | UCO | AJ table | May | 2023 | MM_AJ
11 | 2023-05-10 |  | AJ22-0417 | Z1 Pool Water Leak Assessment | 5171089 | 5975-60-V00-0530 | CONDUIT, RIGID, GALVANIZED STEEL, THREADED, 3/4 INCH X 10 FEET | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 3 | EA | 60 | 63.27 | 3796.2 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 3 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-10 | COMP | 2023-06-13 | 60.00 |  | AJ | AJ table | May | 2023 | MM_AJ
12 | 2023-05-10 |  | AJ22-0536 | T357 Relocation | 5171089 | 5995-60-V00-0132 | STRAP, TIE DOWN (CABLE TIE), NYLON 6/6, BLACK, 7 INCHES | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 5 | PG | 10 | 15.48 | 154.8 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 5 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-10 | COMP | 2023-06-08 | 10.00 |  | AJ | AJ table | May | 2023 | MM_AJ
13 | 2023-05-10 |  | AJ23-0193 | 43 Electrical Meter Installation | 5171089 | 5975-60-V00-0090 | COUPLING, ELECTRICAL CONDUIT, COMPRESSION, ZINC DIE CAST, 3/4 INCH | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 2 | EA | 30 | 19.98 | 599.4 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 2 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-07-25 | COMP | 2023-07-25 | 30.00 |  | AJ | AJ table | May | 2023 | MM_AJ
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 7 | RL | 6 | 65.6 | 393.6 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 7 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-10 | COMP | 2023-06-06 | 6.00 |  | UCO | AJ table | May | 2023 | MM_AJ
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 6145-60-V00-0153 | WIRE, ELECTRICAL, YELLOW, 1 CORE, 2.5 MM² | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 8 | RL | 15 | 59.44 | 891.6 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 8 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-10 | COMP | 2023-06-06 | 15.00 |  | UCO | AJ table | May | 2023 | MM_AJ
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 6145-60-V00-0156 | WIRE, ELECTRICAL, BLUE, 1 CORE, 2.5 MM ² | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 9 | RO | 15 | 64.42 | 966.3 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 9 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-10 | COMP | 2023-06-06 | 15.00 |  | UCO | AJ table | May | 2023 | MM_AJ
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 6145-60-V00-0151 | WIRE, ELECTRICAL, BLACK, 1 CORE, 2.5 mm² | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 10 | RO | 15 | 65.6 | 984 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 10 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-10 | COMP | 2023-06-06 | 15.00 |  | UCO | AJ table | May | 2023 | MM_AJ
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 6145-60-V00-0152 | WIRE, ELECTRICAL, RED, 1 CORE, 2.5 MM ² | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 11 | RL | 15 | 65.6 | 984 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 11 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-10 | COMP | 2023-06-06 | 15.00 |  | UCO | AJ table | May | 2023 | MM_AJ
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 5975-60-V00-0036 | PROTECTOR, CABLE, SPIRAL WRAPPING BAND, w/ CLIP, POLYETHYLENE, BLACK, 15 MM X 1.5 METER | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 12 | RO | 100 | 16.48 | 1648 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 12 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-07-25 | COMP | 2023-07-25 | 100.00 |  | UCO | AJ table | May | 2023 | MM_AJ
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 5975-60-V00-0741 | BOX CONNECTOR, ELECTRICAL (CONDUIT HUB), RIGID, ZINC, 3/4 INCH | 33484 | 2023-05-10 | 2023-05-28 | CLOSE | 1 | EA | 90 | 56.4 | 5076 | 13619 | CLOSE | 2023-05-29 | 2023-05-23 | KW1-9710 | 1 | 2023-05-29 | APPR | 2023-05-29 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-07-24 | COMP | 2023-06-14 | 90.00 |  | UCO | AJ table | May | 2023 | MM_AJ
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 5975-60-V00-0743 | BOX CONNECTOR, ELECTRICAL, CONDUIT, SET SCREW, STEEL, 3/4 INCH | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 1 | EA | 150 | 13.29 | 1993.5 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 1 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-26 | COMP | 2023-07-25 | 5.00 |  | UCO | AJ table | May | 2023 | MM_AJ
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 5940-01-619-8810 | TERMINAL, LUG, 4-16 AWG, BLUE, 0.19 X 0.33 INCHES | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 4 | EA | 25 | 1.5 | 37.5 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 4 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-07-25 | COMP | 2023-08-06 | 25.00 |  | UCO | AJ table | May | 2023 | MM_AJ
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 6145-60-V00-0009 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 10 MM ² | 33483 | 2023-05-10 | 2023-05-28 | CLOSE | 6 | RL | 10 | 231.6 | 2316 | 13802 | CLOSE | 2023-05-30 | 2023-05-30 | KW1-9736 | 6 | 2023-05-30 | CLOSE | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-10 | COMP | 2023-06-07 | 10.00 |  | UCO | AJ table | May | 2023 | MM_AJ
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 6625-60-V00-0094 | METER, w/NEMA, CUSTOM ENCLOSURE, 4X PM5560 | 33442 | 2023-05-10 |  | CAN | 1 | EA | 60 | 6817 | 409020 | [16 empty] | UCO | AJ table | May | 2023 | MM_AJ
14 | 2023-05-10 | 40 | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 5975-60-V00-0812 | CONDUIT, METAL, RIGID IMC, THREADED, STEEL, 3/4 INCH X 3 MTR | 55709 | 2024-02-29 | 2024-03-09 | CLOSE | 1 | EA | 40 | 25.68 | 1027.2 | 22248 | CLOSE | 2024-03-10 |  | KW1-15518 | 1 | 2024-03-10 | APPR | 2024-03-10 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-04-30 |  |  |  |  | UCO | AJ table | May | 2023 | MM_AJ
14 | 2023-05-10 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 5975-60-V00-0744 | RACEWAY, NONMETALLIC, OPEN SLOT WIRING CABLE, DUCT w/COVER, PVC, 2 X 1 INCHES X 6 FEET | 33484 | 2023-05-10 | 2023-05-28 | CLOSE | 2 | EA | 60 | 40.1 | 2406 | 13619 | CLOSE | 2023-05-29 | 2023-05-23 | KW1-9710 | 2 | 2023-05-29 | APPR | 2023-05-29 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-31 | COMP | 2023-12-22 | 40.00 |  | UCO | AJ table | May | 2023 | MM_AJ
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0521 | CLAMP, GROUNDING, BRONZE, 5/8 - 1/2 INCH | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 1 | EA | 10 | 24.98 | 249.8 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 1 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 10.00 |  | AJ | AJ table | May | 2023 | MM_AJ
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0349 | STRAP, TIE DOWN, ELECTRICAL COMPONENT, (CABLE TIE) NYLON, BLACK, 360.68 X 4.83 MM | 33620 | 2023-05-13 | 2023-05-13 | CLOSE | 1 | PG | 1 | 104.2 | 104.2 | 13490 | INPRG | 2023-05-19 | 2023-05-16 | KW1-9546 | 5 | 2023-05-17 | CLOSE | 2023-09-09 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-07-12 | COMP | 2023-05-30 | 1.00 |  | AJ | AJ table | May | 2023 | MM_AJ
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 2 | RO | 1 | 13.65 | 13.65 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 2 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 1.00 |  | AJ | AJ table | May | 2023 | MM_AJ
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-01-613-4740 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 3 | PG | 1 | 62.44 | 62.44 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 3 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 1.00 |  | AJ | AJ table | May | 2023 | MM_AJ
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-01-015-5060 | TAPE, INSULATION, ELECTRICAL, BLUE, 3/4 X 792 INCHES | 33620 | 2023-05-13 | 2023-05-13 | CLOSE | 2 | RO | 1 | 9.5 | 9.5 | 13490 | INPRG | 2023-05-19 | 2023-05-16 | KW1-9546 | 6 | 2023-05-17 | CLOSE | 2023-09-09 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-31 | COMP | 2023-05-21 | 1.00 |  | AJ | AJ table | May | 2023 | MM_AJ
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-01-174-5651 | TAPE, INSULATION, ELECTRICAL, YELLOW, 3/4 X 792 INCHES | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 4 | RO | 1 | 9.99 | 9.99 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 4 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-06-01 | 1.00 |  | AJ | AJ table | May | 2023 | MM_AJ
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-01-013-9369 | TAPE, INSULATION, ELECTRICAL, RED, 3/4 X 792 INCHES | 33621 | 2023-05-13 | 2023-05-13 | CLOSE | 1 | RO | 1 | 11 | 11 | 13582 | CLOSE | 2023-05-25 | 2023-05-21 | KW1-9671 | 23 | 2023-05-27 | CLOSE | 2023-09-24 | Bharadwajan, Sajan - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-31 | COMP | 2023-05-30 | 1.00 |  | AJ | AJ table | May | 2023 | MM_AJ
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 5 | EA | 3 | 351.32 | 1053.96 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 5 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 3.00 |  | AJ | AJ table | May | 2023 | MM_AJ
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0504 | UNION, ELECTRICAL CONDUIT, NYLON POLYAMIDE, LONG THREAD, 5-10 MM | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 6 | EA | 10 | 3.33 | 33.3 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 6 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 10.00 |  | AJ | AJ table | May | 2023 | MM_AJ
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0429 | LUG, TERMINAL, ROUND TYPE, ONE-HOLE, 16MM²-M6 | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 7 | PG | 1 | 64.1 | 64.1 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 7 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-15 | COMP | 2023-08-01 | 1.00 |  | AJ | AJ table | May | 2023 | MM_AJ
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5940-60-V00-0026 | TERMINAL, LUG, TUBULAR, TIN PLATED, 8.4 MM X 50 MM² | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 8 | EA | 20 | 3.16 | 63.2 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 8 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 20.00 |  | AJ | AJ table | May | 2023 | MM_AJ
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 9 | RL | 1 | 262.24 | 262.24 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 9 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-06-01 | 1.00 |  | AJ | AJ table | May | 2023 | MM_AJ
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0122 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 50 MM² | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 10 | MR | 120 | 45.29 | 5434.8 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 10 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-06-01 | 120.00 |  | AJ | AJ table | May | 2023 | MM_AJ
15 | 2023-05-13 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0516 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, BRASS, CW, 50S | 33619 | 2023-05-13 | 2023-05-13 | CLOSE | 1 | EA | 5 | 43.29 | 216.45 | 13582 | CLOSE | 2023-05-25 | 2023-05-21 | KW1-9671 | 22 | 2023-05-27 | CLOSE | 2023-09-24 | Bharadwajan, Sajan - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-31 | COMP | 2023-05-30 | 5.00 |  | AJ | AJ table | May | 2023 | MM_AJ
15 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 5 | EA | 3 | 351.32 | 1053.96 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 5 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 3.00 |  | AJ | AJ table | August | 2023 | MM_AJ
15 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0504 | UNION, ELECTRICAL CONDUIT, NYLON POLYAMIDE, LONG THREAD, 5-10 MM | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 6 | EA | 10 | 3.33 | 33.3 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 6 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 10.00 |  | AJ | AJ table | August | 2023 | MM_AJ
15 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0429 | LUG, TERMINAL, ROUND TYPE, ONE-HOLE, 16MM²-M6 | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 7 | PG | 1 | 64.1 | 64.1 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 7 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-15 | COMP | 2023-08-01 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
15 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5940-60-V00-0026 | TERMINAL, LUG, TUBULAR, TIN PLATED, 8.4 MM X 50 MM² | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 8 | EA | 20 | 3.16 | 63.2 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 8 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 20.00 |  | AJ | AJ table | August | 2023 | MM_AJ
15 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 9 | RL | 1 | 262.24 | 262.24 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 9 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-06-01 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
15 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0122 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 50 MM² | 33618 | 2023-05-13 | 2023-05-20 | CLOSE | 10 | MR | 120 | 45.29 | 5434.8 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 10 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-06-01 | 120.00 |  | AJ | AJ table | August | 2023 | MM_AJ
16 | 2023-05-16 |  | UCO23-0003 | 43 Electrical Meter Installation | 5171089 | 5306-60-V00-0118 | NUT AND BOLT, 1-1/2 X 3/8 INCHES | 33647 | 2023-05-16 | 2023-05-16 | CLOSE | 1 | EA | 300 | 0.85 | 255 | 13569 | CLOSE | 2023-05-23 | 2023-05-21 | KW1-9646 | 14 | 2023-05-23 | CLOSE | 2023-12-02 | Kannoth, Shajee -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-31 | COMP | 2023-05-28 | 300.00 |  | UCO | AJ table | May | 2023 | MM_AJ
17 | 2023-05-27 | 50 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5510-60-V00-0028 | PLYWOOD, CONSTRUCTION, MARINE GRADE, 1/2 INCH X 8 X 4 FEET | 34457 | 2023-05-27 | 2023-06-01 | CLOSE | 1 | SH | 15 | 30.7 | 460.5 | 13892 | SENT | 2023-06-08 | 2023-06-05 | KW1-9904 | 4 | 2023-06-08 | CLOSE | 2023-11-19 | Kannoth, Shajee -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-06-16 | COMP | 2023-06-11 | 15.00 |  | AJ | AJ table | May | 2023 | MM_AJ
17 | 2023-05-27 | 50 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8030-60-V00-0008 | SEALING COMPOUND, GUTTER & SEAM, WHITE, 10 OZ. | 34501 | 2023-05-27 | 2023-05-30 | CLOSE | 1 | CA | 2 | 23.1 | 46.2 | 13872 | CLOSE | 2023-06-08 | 2023-06-01 | KW1-9836 | 8 | 2023-06-06 | CLOSE | 2023-11-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-06-13 07:00 | COMP | 2023-06-10 | 2.00 |  | AJ | AJ table | May | 2023 | MM_AJ
17 | 2023-06-06 | 100 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8030-60-V00-0008 | SEALING COMPOUND, GUTTER & SEAM, WHITE, 10 OZ | 34501, 35130 | 2023-06-06 | 2023-06-07 |  | 1 | CQ | 26 | [6 empty] | KW1-10029 | 1 | [5 empty] | 2023-06-28 | COMP | 2023-06-27 | 26 |  | AJ | AJ table | June | 2023 | MM_AJ
17 | 2023-06-07 | 60 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0065 | INSULATION BOARD, THERMAL, XPS FOAM (STYROFOAM), BLUE, 1250 X 600 X 50 MM | 35132 | 2023-06-07 | 2023-06-20 | CLOSE | 1 | PK | 50 | 98.3 | 4915 | 14349 | CLOSE | 2023-06-22 | 2023-06-21 | KW1-10030 | 1 | 2023-06-22 | CLOSE | 2023-07-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | COMMERCIAL UNITED GINCO EST. | 2023-06-29 07:00 | COMP | 2023-07-03 | 50.00 |  | AJ | AJ table | June | 2023 | MM_AJ
17 | 2023-06-07 | 20,60,100 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5530-60-V00-0003 | PLYWOOD, CONSTRUCTION, MARINE GRADE, 3/4 INCH X 8 X 4 FEET | 35133, 35131, 35146 | 2023-06-07 | 2023-06-21 |  | 1 | EA | 210 | [6 empty] | KW1-10030 | 5 | [5 empty] | 2023-07-15 | COMP | 2023-07-06 | 210 |  | AJ | AJ table | June | 2023 | MM_AJ
17 | 2023-07-09 | 110 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 36925 | 2023-07-09 | 2023-07-13 | CLOSE | 1 | BX | 50 | 27.96 | 1398 | 15257 | CLOSE | 2023-08-02 | 2023-07-26 | KW1-10683 | 1 | 2023-08-03 | CLOSE | 2024-01-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-08-12 | COMP | 2023-08-07 | 50.00 |  | AJ | AJ table | July | 2023 | MM_AJ
18 | 2023-07-13 |  | AJ23-0467 | Z2 B506 Additional Power for AVIS System | 6185682 | PANEL | FABRICATION, PANEL MAIN BREAKER-100A 3 POLE MCCB (SUB BREAKERS 30MA 20A RCBO (8EA) 8 WAYS INDOOR DB PANEL | 48307 | 2023-07-13 | 2023-07-13 | [22 empty] | AJ | AJ table | July | 2023 | MM_AJ
19 | 2023-07-23 | 50 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-05-V00-0005 | PANEL, DRYWALL, WALL BOARD, REGULAR, MOLD-GUARD, 1/2 INCH X 4 X 8 FEET | 37969 | 2023-07-23 | 2023-07-24 | CLOSE | 1 | EA | 10 | 28.14 | 281.4 | 15285 | CLOSE | 2023-07-30 | 2023-07-27 | KW1-10628 | 8 | 2023-07-30 | CLOSE | 2023-11-05 | Kandankara, Thomas -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-08-12 | COMP | 2023-08-03 | 10.00 |  | AJ | AJ table | July | 2023 | MM_AJ
19 | 2023-07-23 | 50 | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0048 | DRYWALL SHEET, (GYPSUM BOARD), 4 X 8 FEET X 1/2 INCH | 37970 | 2023-07-23 | 2023-07-23 | CLOSE | 1 | EA | 180 | 19.31 | 3475.8 | 15265 | CLOSE | 2023-07-27 | 2023-07-26 | KW1-10539 | 3 | 2023-07-27 | CLOSE | 2023-11-05 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-08-03 | COMP | 2023-07-29 | 180.00 |  | AJ | AJ table | July | 2023 | MM_AJ
20 | 2023-08-01 |  | AJ23-0467 | Z5 TI Repairs 5620T | 5857174 | PANEL | FABRICATION PANEL, DB PANEL INCOMER 63A 240V/415V-63A (SEE ATTACHED SUBMITTAL) | 49007 | 2023-08-01 | 2023-08-01 | [22 empty] | AJ | AJ table | August | 2023 | MM_AJ
20 | 2023-08-01 |  | AJ23-0467 | Replace The Senior Pods T6028 Electrical Panel | 6236594 | PANEL | FABRICATION PANEL, MSB (MAIN SWITCH BOARD ) 415/240V,3PH,4W,50HZ, 1600A (SEE ATTACHED SUBMITTAL | 49280 | 2023-08-01 | 2023-08-10 | [22 empty] | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-02 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0041 | PANEL, CEILING (ACOUSTICAL TILE), MINERAL FIBER, WHITE, 24 X 24 X 3/4 INCHES | 38834 | 2023-08-02 | 2023-08-07 | CLOSE | 1 | EA | 500 | 8.99 | 4495 | 15672 | CLOSE | 2023-08-12 | 2023-08-10 | KW1-10892 | 1 | 2023-08-12 | CLOSE | 2023-11-19 | Santhumayor, Santhosh - Vectrus - No Export | KASAR MARJAN CONTRACTING CO. | 2023-08-19 | COMP | 2023-08-16 | 500.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-02 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5670-60-V00-0026 | WALL ANGLE / GRID, CEILING, TEE, GALVANIZED STEEL, WHITE, 12 FEET | 38833 | 2023-08-02 | 2023-08-07 | CLOSE | 2 | EA | 30 | 18.48 | 554.4 | 15670 | CLOSE | 2023-08-12 | 2023-08-10 | KW1-10890 | 27 | 2023-08-12 | APPR | 2023-08-12 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-08-19 | COMP | 2023-08-16 | 30.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-02 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5680-60-V00-0006 | GRID, CEILING, TEE, WHITE, 24 INCHES | 38833 | 2023-08-02 | 2023-08-07 | CLOSE | 3 | EA | 500 | 4.33 | 2165 | 15670 | CLOSE | 2023-08-12 | 2023-08-10 | KW1-10890 | 28 | 2023-08-12 | APPR | 2023-08-12 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-08-19 | COMP | 2023-08-16 | 500.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-02 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5680-60-V00-0007 | GRID, CEILING, T-RUNNER, WHITE, 12 FEET | 38833 | 2023-08-02 | 2023-08-07 | CLOSE | 1 | EA | 50 | 19.15 | 957.5 | 15670 | CLOSE | 2023-08-12 | 2023-08-10 | KW1-10890 | 26 | 2023-08-12 | APPR | 2023-08-12 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-08-19 | COMP | 2023-08-16 | 50.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5305-60-V00-0196 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 3/8 INCHES | 38837 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | BX | 5 | 32.63 | 163.15 | 15618 | CLOSE | 2023-08-09 | 2023-08-08 | KW1-10826 | 2 | 2023-08-10 | CLOSE | 2023-11-25 | Santhumayor, Santhosh - Vectrus - No Export | KASAR MARJAN CONTRACTING CO. | 2023-08-16 | COMP | 2023-08-14 | 5.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5305-60-V00-0223 | SCREW, TAPPING, FLAT HEAD, PHILIPS, STEEL, #8 X 1-1/4 INCHES | 38844 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | BX | 4 | 53.61 | 214.44 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 6 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-17 | COMP | 2023-08-15 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5340-60-V00-0141 | DOORSTOP, FLOOR MOUNT, BRASS, 1-3/4 X 1-1/4 INCHES | 38847 | 2023-08-05 | 2023-08-06 | CLOSE | 4 | EA | 16 | 13.65 | 218.4 | 15621 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10866 | 7 | 2023-08-10 | APPR | 2023-08-10 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-09-07 | COMP | 2023-08-15 | 16.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5340-60-V00-0169 | LOCK SET, MORTISE, RIM EXIT DEVICE, KEY OUTSIDE UNLOCKS/LOCKS TRIM | 39068, 39071 | 2023-08-05 | 2023-08-06 |  | 1 | EA | 4 | [6 empty] | KW1-10818 | 1 | [5 empty] | 2023-08-22 | COMP | 2023-08-14 | 4 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5340-60-V00-0267 | COVER STRIP, DRIP, RAIN GUARD, ALUMINUM, 2-1/2 X 1-1/2 INCHES | 38842 | 2023-08-05 | 2023-08-06 | CLOSE | 2 | FT | 50 | 21.98 | 1099 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 3 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-09-21 | COMP | 2023-09-04 | 50.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5340-60-V00-0457 | LOCK SET, DOOR, CYLINDRICAL, w/ KNOB, 5-PIN, 1-3/8 X 3/4 INCHES | 38841 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | ST | 17 | 64.3 | 1093.1 | 15618 | CLOSE | 2023-08-09 | 2023-08-08 | KW1-10826 | 7 | 2023-08-10 | CLOSE | 2023-11-25 | Santhumayor, Santhosh - Vectrus - No Export | KASAR MARJAN CONTRACTING CO. | 2023-08-16 | COMP | 2023-08-14 | 17.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5340-60-V00-0476 | HINGE, DOOR, STAINLESS STEEL, 2.5 MM X 3-1/2 X 3 INCHES | 38844 | 2023-08-05 | 2023-08-06 | CLOSE | 2 | EA | 51 | 30.97 | 1579.47 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 7 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-17 | COMP | 2023-08-15 | 51.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5340-60-V00-0491 | STOPPER, DOOR, RUBBER, 2 INCHES | 38840 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | EA | 21 | 10.32 | 216.72 | 15618 | CLOSE | 2023-08-09 | 2023-08-08 | KW1-10826 | 6 | 2023-08-10 | CLOSE | 2023-11-25 | Santhumayor, Santhosh - Vectrus - No Export | KASAR MARJAN CONTRACTING CO. | 2023-08-16 | COMP | 2023-08-14 | 21.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0005 | WEATHER STRIP, THRESHOLD, ALUMINUM, 3.2 X 6.4 X 12.7 X 127.0 MM | 38846 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | EA | 4 | 42.6 | 170.4 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 10 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-09-28 | COMP | 2023-09-04 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0035 | WEATHER STRIP, DOOR, W/BRUSH, 2 X 36 INCHES | 38844 | 2023-08-05 | 2023-08-06 | CLOSE | 4 | EA | 4 | 30.47 | 121.88 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 9 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-17 | COMP | 2023-08-15 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0036 | WEATHER STRIP, FLUTE TOP, ALUMINIUM, 16 FEET X 1-1/2 INCHES | 38847 | 2023-08-05 | 2023-08-06 | CLOSE | 3 | EA | 5 | 23.39 | 116.95 | 15621 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10866 | 6 | 2023-08-10 | APPR | 2023-08-10 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-24 | COMP | 2023-08-15 | 5.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0066 | TAPE, ROOF SEAL, BLACK, 65MIL X 6 INCH X 25 FEET | 38847 | 2023-08-05 | 2023-08-06 | CLOSE | 2 | RL | 20 | 99.7 | 1994 | 15621 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10866 | 5 | 2023-08-10 | APPR | 2023-08-10 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-10-11 | COMP | 2023-10-11 | 20.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5660-60-V00-0045 | WIRE, STEEL, GALVANIZED, 28 GAGE, 100 FEET | 38844 | 2023-08-05 | 2023-08-06 | CLOSE | 3 | EA | 20 | 58.28 | 1165.6 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 8 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-17 | COMP | 2023-08-15 | 20.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 7230-60-V00-0009 | VENETIAN BLIND (WINDOW BLIND), VERTICAL, VINYL, CREAM/BEIGE, 50 X 50 INCHES | 39069 | 2023-08-05 | 2023-08-16 | CLOSE | 1 | EA | 10 | 49.5 | 495 | 15927 | CLOSE | 2023-08-22 | 2023-08-20 | KW1-11107 | 18 | 2023-08-23 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2023-09-10 | COMP | 2023-09-09 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GL | 38845 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | GL | 5 | 228.5 | 1142.5 | 15621 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10866 | 1 | 2023-08-10 | APPR | 2023-08-10 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-24 | COMP | 2023-08-17 | 3.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8010-60-V00-0006 | PAINT, LATEX, MATT, OFF-WHITE, 3.2 LITER | 38838 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | CN | 30 | 44.16 | 1324.8 | 15618 | CLOSE | 2023-08-09 | 2023-08-08 | KW1-10826 | 4 | 2023-08-10 | CLOSE | 2023-11-25 | Santhumayor, Santhosh - Vectrus - No Export | KASAR MARJAN CONTRACTING CO. | 2023-08-16 | COMP | 2023-08-19 | 30.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8010-60-V00-0028 | PAINT, ENAMEL, GLOSS, DESERT SAND, 3.6 LITER | 38842 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | CN | 26 | 39.96 | 1038.96 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 2 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-21 | COMP | 2023-08-19 | 26.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8010-60-V00-0053 | PAINT, LATEX, MATT, BROWN, 3.2 AND 3.6 LITERS | 38932 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | CN | 7 | 41.25 | 288.75 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 11 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-31 | COMP | 2023-08-27 | 7.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8010-60-V00-0089 | PRIMER, PAINT, LATEX, INTERIOR, WATERBASED, WHITE, 5 GALLON | 39066 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | CN | 6 | 41.63 | 249.78 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 12 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-21 | COMP | 2023-08-17 | 6.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8010-60-V00-0124 | PRIMER, RED OXIDE, OIL BASED, RED, 1 GL | 38843 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | CN | 5 | 27.64 | 138.2 | 15620 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10870 | 4 | 2023-08-10 | CLOSE | 2023-12-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-21 | COMP | 2023-08-17 | 5.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8030-01-075-1156 | CAULKING COMPOUND, CARTRIDGE, WHITE, 10 OZ | 39067 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | EA | 72 | 3.27 | 235.44 | 15618 | CLOSE | 2023-08-09 | 2023-08-08 | KW1-10826 | 8 | 2023-08-10 | CLOSE | 2023-11-25 | Santhumayor, Santhosh - Vectrus - No Export | KASAR MARJAN CONTRACTING CO. | 2023-10-04 | COMP | 2023-08-22 | 72.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8030-60-V00-0052 | PUTTY, ALL PURPOSE, LIGHT GRAY, 3.43 KG | 38845 | 2023-08-05 | 2023-08-06 | CLOSE | 3 | CN | 3 | 125.2 | 375.6 | 15621 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10866 | 3 | 2023-08-10 | APPR | 2023-08-10 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-24 | COMP | 2023-08-17 | 3.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8030-60-V00-0053 | FOAM, CONSTRUCTION, CREAM, 700ML | 38837 | 2023-08-05 | 2023-08-06 | CLOSE | 2 | CN | 7 | 19.65 | 137.55 | 15618 | CLOSE | 2023-08-09 | 2023-08-08 | KW1-10826 | 3 | 2023-08-10 | CLOSE | 2023-11-25 | Santhumayor, Santhosh - Vectrus - No Export | KASAR MARJAN CONTRACTING CO. | 2023-08-16 | COMP | 2023-08-14 | 7.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8040-60-V00-0033 | ADHESIVE, RESIN, SYNTHETIC, WHITE, 5 KG | 38847 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | CN | 1 | 20.57 | 20.57 | 15621 | CLOSE | 2023-08-10 | 2023-08-08 | KW1-10866 | 4 | 2023-08-10 | APPR | 2023-08-10 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2023-08-24 | COMP | 2023-08-15 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
21 | 2023-08-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 9540-60-V00-0009 | ANGLE, STRUCTURAL, ALUMINUM, CREAM, 2 X 2 INCH X 20 FEET | 38839 | 2023-08-05 | 2023-08-06 | CLOSE | 1 | EA | 20 | 14.99 | 299.8 | 15618 | CLOSE | 2023-08-09 | 2023-08-08 | KW1-10826 | 5 | 2023-08-10 | CLOSE | 2023-11-25 | Santhumayor, Santhosh - Vectrus - No Export | KASAR MARJAN CONTRACTING CO. | 2023-08-16 | COMP | 2023-08-14 | 20.00 |  | AJ | AJ table | August | 2023 | MM_AJ
22 | 2023-08-05 |  | AJ23-0467 | Deficiency repairs | 6590045 | PANEL | FABRICATION PANEL, ( MAIN BREAKER-100/125 3 POLE MCCB (SUB BREAKERS 32A 3 POLE MCCB ( 1 EA), 20A 1 POLE MCCB (3 EA) , 63A 3 POLE MCCB (2EA) , | 49124 | 2023-08-05 | [23 empty] | AJ | AJ table | August | 2023 | MM_AJ
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5930-60-V00-0066 | LIGHT-SWITCH, 2 WAY, 2 GANG, WHITE, 230V, 10A | 39146 | 2023-08-06 | 2023-08-24 |  | 3 | EA | 4 | [6 empty] | KW1-11148 | 2 | [5 empty] | 2023-10-19 | COMP | 2023-09-30 | 4 |  | AJ | AJ table | August | 2023 | MM_AJ
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5930-60-V00-0243 | LIGHT-SWITCH, METAL, 2 WAY, 1 GANG, 250V, 10A | 39144 | 2023-08-06 | 2023-08-15 |  | 3 | EA | 4 | [6 empty] | KW1-11019 | 5 | [6 empty] | COMP | 2023-08-22 | 4 |  | AJ | AJ table | August | 2023 | MM_AJ
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5930-60-V00-0387 | SWITCH, TOGGLE, METALCLAD, W/MOUNTING BOX, 1-WAY, 1-GANG, 250V, 10 A | 39146 | 2023-08-06 | 2023-08-24 |  | 2 | EA | 14 | [6 empty] | KW1-11148 | 1 | [5 empty] | 2023-10-19 | COMP | 2023-10-18 | 14 |  | AJ | AJ table | August | 2023 | MM_AJ
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 39144 | 2023-08-06 | 2023-08-15 | CLOSE | 1 | EA | 65 | 10.32 | 670.8 | 15880 | CLOSE | 2023-08-18 | 2023-08-17 | KW1-11019 | 2 | 2023-08-18 | CLOSE | 2023-12-02 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 03:00 | COMP | 2023-09-02 | 65.00 |  | AJ | AJ table | August | 2023 | MM_AJ
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 39144 | 2023-08-06 | 2023-08-15 | CLOSE | 2 | RO | 5 | 13.65 | 68.25 | 15880 | CLOSE | 2023-08-18 | 2023-08-17 | KW1-11019 | 3 | 2023-08-18 | CLOSE | 2023-12-02 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-25 03:00 | COMP | 2023-08-22 | 5.00 |  | AJ | AJ table | August | 2023 | MM_AJ
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 39144 | 2023-08-06 | 2023-08-15 | CLOSE | 5 | EA | 4 | 351.32 | 1405.28 | 15880 | CLOSE | 2023-08-18 | 2023-08-17 | KW1-11019 | 6 | 2023-08-18 | CLOSE | 2023-12-02 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-25 03:00 | COMP | 2023-08-22 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0042 | BOX CONNECTOR, ELECTRICAL, STRAIGHT, LIQUID TIGHT CONDUIT, NICKEL PLATED BRASS, 1/2 INCH | 39144 | 2023-08-06 | 2023-08-15 |  | 8 | EA | 150 | [6 empty] | KW1-11019 | 7 | [6 empty] | COMP | 2023-08-22 | 150 |  | AJ | AJ table | August | 2023 | MM_AJ
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 39144 | 2023-08-06 | 2023-08-15 | CLOSE | 3 | RO | 5 | 92.57 | 462.85 | 15880 | CLOSE | 2023-08-18 | 2023-08-17 | KW1-11019 | 4 | 2023-08-18 | CLOSE | 2023-12-02 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-25 03:00 | COMP | 2023-08-22 | 5.00 |  | AJ | AJ table | August | 2023 | MM_AJ
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6110-60-V00-0166 | SENSOR, PHOTOCELL CONTROL, 15A, 50/60 HZ | 39144 | 2023-08-06 | 2023-08-15 | CLOSE | 7 | EA | 1 | 63.94 | 63.94 | 15880 | CLOSE | 2023-08-18 | 2023-08-17 | KW1-11019 | 8 | 2023-08-18 | CLOSE | 2023-12-02 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-25 03:00 | COMP | 2023-08-22 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6130-60-V00-0097 | BATTERY, EMERGENCY LED DRIVER, 50/60HZ, 15W, 100-277V | 39144 | 2023-08-06 | 2023-08-15 | CLOSE | 8 | EA | 4 | 113.22 | 452.88 | 15880 | CLOSE | 2023-08-18 | 2023-08-17 | KW1-11019 | 9 | 2023-08-18 | CLOSE | 2023-12-02 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-25 03:00 | COMP | 2023-08-22 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6210-60-V00-0040 | FIXTURE, LIGHTING, LED, WALL PACK, 5000K, 100-277 VAC, 30W | 39146 | 2023-08-06 | 2023-08-24 | CLOSE | 3 | EA | 4 | 141 | 564 | 15929 | CLOSE | 2023-08-24 | 2023-08-20 | KW1-11148 | 3 | 2023-08-25 | APPR | 2023-08-25 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-02 | COMP | 2023-08-29 | 4.00 | Need Battery Back up | AJ | AJ table | August | 2023 | MM_AJ
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6210-60-V00-0082 | LIGHT, PANEL, LED, COOL WHITE, 50/60 HZ, 40W, w/ EMERGENCY BATTERY | 39147 | 2023-08-06 | 2023-08-15 | CLOSE | 1 | EA | 21 | 277.56 | 5828.76 | 15907 | CLOSE | 2023-09-01 | 2023-08-19 | KW1-11321 | 1 | 2023-09-04 | CLOSE | 2023-12-09 | Jayaraj, Sudha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-16 | COMP | 2023-09-09 | 21.00 |  | AJ | AJ table | August | 2023 | MM_AJ
23 | 2023-08-06 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 9905-60-V00-0066 | SIGN, DANGER, 415 VOLTS , 5 X 3-3/4 INCHES | 39145 | 2023-08-06 | 2023-08-14 | CLOSE | 1 | RO | 2 | 17.48 | 34.96 | 15906 | CLOSE | 2023-09-03 | 2023-08-19 | KW1-11378 | 3 | 2023-09-04 | CLOSE | 2023-12-09 | Jayaraj, Sudha - No Export | COMMERCIAL UNITED GINCO EST. | 2023-11-05 | COMP | 2023-09-11 | 2.00 |  | AJ | AJ table | August | 2023 | MM_AJ
24 | 2023-08-16 | 60 | AJ21-0038 | Z7 Relocation of Building 370 | 5876937 | 5975-00-156-3253 | STRAP, TIE DOWN, ELECTRICAL COMPONE, 13-7/20 INCHES | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 10 | HD | 1 | 18.64 | 18.64 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 36 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-09-03 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
25 | 2023-08-16 | 60 | AJ22-0004 | Z7 Relocation of Building 370 | 5876937 | 5640-60-V00-0030 | INSULATION SLEEVING, THERMAL, 3/8 X 72 INCHES | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 14 | EA | 10 | 2.62 | 26.2 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 40 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-08-31 | 10.00 |  | AJ | AJ table | August | 2023 | MM_AJ
26 | 2023-08-16 | 60 | AJ22-0073 | Z7 Relocation of Building 370 | 5876937 | 5640-60-V00-0031 | INSULATION SLEEVING, THERMAL, 5/8 X 72 INCHES | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 15 | EA | 10 | 3.92 | 39.2 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 41 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-08-31 | 10.00 |  | AJ | AJ table | August | 2023 | MM_AJ
27 | 2023-08-16 | 60 | AJ22-0123 | Z7 Relocation of Building 370 | 5876937 | 4710-60-V00-0110 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 7 | EA | 4 | 19.62 | 78.48 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 33 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-08-30 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
28 | 2023-08-16 | 60 | AJ22-0149 | Z7 Relocation of Building 370 | 5876937 | 5970-01-013-9369 | TAPE, INSULATION, ELECTRICAL, RED, 3/4 X 792 INCHES | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 1 | RO | 1 | 9.81 | 9.81 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 27 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-08-31 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
29 | 2023-08-16 | 60 | AJ22-0184 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0504 | UNION, ELECTRICAL CONDUIT, NYLON POLYAMIDE, LONG THREAD, 5-10 MM | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 8 | EA | 10 | 3.27 | 32.7 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 34 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-08-31 | 10.00 |  | AJ | AJ table | August | 2023 | MM_AJ
30 | 2023-08-16 | 40 | AJ22-0222 | Z7 Relocation of Building 370 | 5876937 | 5315-60-V00-0052 | PIN, HINGE, BLACK, 2 INCHES | 40058 | 2023-08-16 | 2023-08-20 | CLOSE | 1 | EA | 12 | 13.32 | 159.84 | 16111 | CLOSE | 2023-08-27 | 2023-08-26 | KW1-11206 | 7 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 | COMP | 2023-09-07 | 12.00 |  | AJ | AJ table | August | 2023 | MM_AJ
31 | 2023-08-16 | 40 | AJ22-0322 | Z7 Relocation of Building 370 | 5876937 | 8030-60-V00-0053 | FOAM, CONSTRUCTION, CREAM, 700ML | 40058 | 2023-08-16 | 2023-08-20 | CLOSE | 3 | EA | 3 | 19.65 | 98.25 | 16111 | CLOSE | 2023-08-27 | 2023-08-26 | KW1-11206 | 9 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 | COMP | 2023-09-03 | 5.00 |  | AJ | AJ table | August | 2023 | MM_AJ
32 | 2023-08-16 | 60 | AJ22-0323 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 11 | RO | 1 | 64.42 | 64.42 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 37 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-09-05 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
33 | 2023-08-16 | 40 | AJ22-0326 | Z7 Relocation of Building 370 | 5876937 | 8030-01-075-1156 | CAULKING COMPOUND, CARTRIDGE, WHITE, 10 OZ | 40055 | 2023-08-16 | 2023-08-20 | CLOSE | 1 | CA | 4 | 14.99 | 59.96 | 16109 | CLOSE | 2023-08-27 | 2023-08-26 | KW1-11204 | 3 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 | COMP | 2023-09-02 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
34 | 2023-08-16 | 60 | AJ22-0390 | Z7 Relocation of Building 370 | 5876937 | 4130-60-V00-0288 | TAPE, WRAP, INSULATION, 3 INCHES X 150 FEET | 40098 | 2023-08-16 | 2023-08-20 | CLOSE | 2 | RO | 6 | 31.72 | 190.32 | 16109 | CLOSE | 2023-08-27 | 2023-08-26 | KW1-11204 | 6 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 | COMP | 2023-09-02 | 6.00 |  | AJ | AJ table | August | 2023 | MM_AJ
35 | 2023-08-16 | 40 | AJ22-0547 | Z7 Relocation of Building 370 | 5876937 | 8040-00-273-8713 | ADHESIVE, FLOORING, WHITE, 1 GL | 40057 | 2023-08-16 | 2023-08-20 | CLOSE | 1 | GL | 5 | 186.81 | 934.05 | 16111 | CLOSE | 2023-08-27 | 2023-08-26 | KW1-11206 | 6 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-22 | COMP | 2023-10-24 | 5.00 |  | AJ | AJ table | August | 2023 | MM_AJ
36 | 2023-08-16 | 40 | AJ23-0006 | Z7 Relocation of Building 370 | 5876937 | 5340-60-V00-0461 | HANDLE, DOOR, ALUMINUM, BLACK | 40059 | 2023-08-16 | 2023-08-20 | CLOSE | 1 | EA | 2 | 27.74 | 55.48 | 16111 | CLOSE | 2023-08-27 | 2023-08-26 | KW1-11206 | 10 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 | COMP | 2023-09-07 | 2.00 |  | AJ | AJ table | August | 2023 | MM_AJ
37 | 2023-08-16 | 60 | AJ23-0079 | Z7 Relocation of Building 370 | 5876937 | 8030-60-V00-0053 | FOAM, CONSTRUCTION, CREAM, 700ML | 40058, 40100 | 2023-08-16 | 2023-08-20 |  | 1,3 | EA | 7 | [6 empty] | KW1-11206 | 9 | [5 empty] | 2023-09-03 | COMP | 2023-09-03 | 7 |  | AJ | AJ table | August | 2023 | MM_AJ
38 | 2023-08-16 | 60 | AJ23-0172 | Z7 Relocation of Building 370 | 5876937 | 4710-60-V00-0098 | TUBE, METALLIC, REFRIGERATION, COPPER, 5/8 INCH X 50 FEET | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 17 | RO | 1 | 100.39 | 100.39 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 43 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-08-31 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
39 | 2023-08-16 | 60 | AJ23-0300 | Z7 Relocation of Building 370 | 5876937 | 4130-60-V00-0137 | MOUNTING BASE, AIR-CONDITIONER, POLYPROPYLENE, IVORY, 17 X 3 X 5.12 INCHES | 40100 | 2023-08-16 | 2023-08-20 | CLOSE | 2 | PG | 16 | 61.8 | 988.8 | 16109 | CLOSE | 2023-08-27 | 2023-08-26 | KW1-11204 | 9 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 | COMP | 2023-09-02 | 16.00 |  | AJ | AJ table | August | 2023 | MM_AJ
40 | 2023-08-16 | 60 | AJ23-0365 | Z7 Relocation of Building 370 | 5876937 | 5970-01-174-5651 | TAPE, INSULATION, ELECTRICAL, YELLOW, 3/4 X 792 INCHES | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 3 | RO | 1 | 9.81 | 9.81 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 29 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-08-31 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0521 | CLAMP, GROUNDING, BRONZE, 5/8 - 1/2 INCH | 33618 | 2023-08-16 | 2023-05-20 | CLOSE | 1 | EA | 10 | 24.98 | 249.8 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 1 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 10.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0349 | STRAP, TIE DOWN, ELECTRICAL COMPONENT, (CABLE TIE) NYLON, BLACK, 360.68 X 4.83 MM | 33620 | 2023-08-16 | 2023-05-13 | CLOSE | 1 | PG | 1 | 104.2 | 104.2 | 13490 | INPRG | 2023-05-19 | 2023-05-16 | KW1-9546 | 5 | 2023-05-17 | CLOSE | 2023-09-09 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-07-12 | COMP | 2023-05-30 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 33618 | 2023-08-16 | 2023-05-20 | CLOSE | 2 | RO | 1 | 13.65 | 13.65 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 2 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-01-613-4740 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 33618 | 2023-08-16 | 2023-05-20 | CLOSE | 3 | PG | 1 | 62.44 | 62.44 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 3 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-05-31 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-01-015-5060 | TAPE, INSULATION, ELECTRICAL, BLUE, 3/4 X 792 INCHES | 33620 | 2023-08-16 | 2023-05-13 | CLOSE | 2 | RO | 1 | 9.5 | 9.5 | 13490 | INPRG | 2023-05-19 | 2023-05-16 | KW1-9546 | 6 | 2023-05-17 | CLOSE | 2023-09-09 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-31 | COMP | 2023-05-21 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-01-174-5651 | TAPE, INSULATION, ELECTRICAL, YELLOW, 3/4 X 792 INCHES | 33618 | 2023-08-16 | 2023-05-20 | CLOSE | 4 | RO | 1 | 9.99 | 9.99 | 13621 | CLOSE | 2023-05-28 | 2023-05-22 | KW1-9700 | 4 | 2023-05-28 | CLOSE | 2023-11-05 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-06-03 | COMP | 2023-06-01 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-01-013-9369 | TAPE, INSULATION, ELECTRICAL, RED, 3/4 X 792 INCHES | 33621 | 2023-08-16 | 2023-05-13 | CLOSE | 1 | RL | 1 | 11 | 11 | 13582 | CLOSE | 2023-05-25 | 2023-05-21 | KW1-9671 | 23 | 2023-05-27 | CLOSE | 2023-09-24 | Bharadwajan, Sajan - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-31 | COMP | 2023-05-30 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0516 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, BRASS, CW, 50S | 33619 | 2023-08-16 | 2023-05-13 | CLOSE | 1 | EA | 5 | 43.29 | 216.45 | 13582 | CLOSE | 2023-05-25 | 2023-05-21 | KW1-9671 | 22 | 2023-05-27 | CLOSE | 2023-09-24 | Bharadwajan, Sajan - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-05-31 | COMP | 2023-05-30 | 5.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0521 | CLAMP, GROUNDING, BRONZE, 5/8 - 1/2 INCH | 39911 | 2023-08-20 | 2023-08-20 | CLOSE | 1 | EA | 10 | 24.53 | 245.3 | 16112 | SENT | 2023-09-06 | 2023-08-26 | KW1-11208 | 1 | 2023-08-27 | CLOSE | 2023-12-16 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 10.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6350-01-094-4171 | ALARM, SMOKE, AUTOMATIC, 9 V DC | 39861 | 2023-08-17 | 2023-08-17 | CLOSE | 1 | EA | 13 | 59.4 | 772.2 | 15929 | CLOSE | 2023-08-24 | 2023-08-20 | KW1-11148 | 6 | 2023-08-25 | APPR | 2023-08-25 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-02 | COMP | 2023-08-29 | 13.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6210-60-V00-0082 | LIGHT, PANEL, LED, COOL WHITE, 50/60 HZ, 40W, w/ EMERGENCY BATTERY | 39911 | 2023-08-20 | 2023-08-20 | CLOSE | 2 | EA | 12 | 277.8 | 3333.6 | 16112 | SENT | 2023-09-06 | 2023-08-26 | KW1-11208 | 2 | 2023-08-27 | CLOSE | 2023-12-16 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 12.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6110-60-V00-0166 | SENSOR, PHOTOCELL CONTROL, 15A, 50/60 HZ | 39860 | 2023-08-19 | 2023-08-19 | CLOSE | 1 | EA | 1 | 71.2 | 71.2 | 15985 | CLOSE | 2023-08-23 | 2023-08-22 | KW1-11135 | 3 | 2023-08-23 | CLOSE | 2023-11-21 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-31 | COMP | 2023-08-28 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 39911 | 2023-08-20 | 2023-08-20 | CLOSE | 3 | RO | 2 | 13.41 | 26.82 | 16112 | SENT | 2023-09-06 | 2023-08-26 | KW1-11208 | 3 | 2023-08-27 | CLOSE | 2023-12-16 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 2.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5930-60-V00-0387 | SWITCH, TOGGLE, METALCLAD, W/MOUNTING BOX, 1-WAY, 1-GANG, 250V, 10 A | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 7 | EA | 8 | 34.13 | 273.04 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 7 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-22 | COMP | 2023-10-08 | 8.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 11 | EA | 5 | 52.28 | 261.4 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 11 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 5.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5930-60-V00-0243 | LIGHT-SWITCH, METAL, 2 WAY, 1 GANG, 250V, 10A | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 6 | EA | 4 | 33.33 | 133.32 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 6 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0158 | WIRE, ELECTRICAL, RED, 1 CORE, 2.5 MM ² | 39859 | 2023-08-17 | 2023-08-17 | CLOSE | 1 | RL | 1 | 57.78 | 57.78 | 15929 | CLOSE | 2023-08-24 | 2023-08-20 | KW1-11148 | 5 | 2023-08-25 | APPR | 2023-08-25 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-02 | COMP | 2023-08-30 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5940-60-V00-0060 | TERMINAL, LUG, ROUND TYPE, COPPER, ONE-HOLE, 4 - 6 MM² X M3 | 39911 | 2023-08-20 | 2023-08-20 | CLOSE | 4 | PG | 1 | 68.67 | 68.67 | 16112 | SENT | 2023-09-06 | 2023-08-26 | KW1-11208 | 4 | 2023-08-27 | CLOSE | 2023-12-16 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5305-60-V00-0001 | SCREW, SELF DRILLING, HEX WASHER HEAD, STEEL, 5/16 X 1 INCH | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 1 | BX | 2 | 19.31 | 38.62 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 1 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 2.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5935-60-V00-0160 | SOCKET, OUTLET, WEATHERPROOF, 2 GANG, 2 POLES, 13 AMPS | 39857 | 2023-08-19 | 2023-08-19 | CLOSE | 1 | EA | 2 | 39.96 | 79.92 | 15985 | CLOSE | 2023-08-23 | 2023-08-22 | KW1-11135 | 2 | 2023-08-23 | CLOSE | 2023-11-21 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-08-30 | COMP | 2023-08-28 | 2.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 39911 | 2023-08-20 | 2023-08-20 | CLOSE | 5 | EA | 34 | 10.33 | 351.22 | 16112 | SENT | 2023-09-06 | 2023-08-26 | KW1-11208 | 5 | 2023-08-27 | CLOSE | 2023-12-16 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-22 | COMP | 2023-09-02 | 34.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5935-60-V00-0167 | CONNECTOR, WIRE, RED, 18 -10 AWG | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 19 | PG | 30 | 25.64 | 769.2 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 19 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 30.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5970-01-613-4740 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 10 | PG | 4 | 62.94 | 251.76 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 10 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0462 | TIE, CABLE, BLACK, 8 INCHES X 4.8 MILLIMETER | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 4 | PG | 3 | 24.48 | 73.44 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 4 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 3.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 39911 | 2023-08-20 | 2023-08-20 | CLOSE | 6 | RO | 3 | 92.65 | 277.95 | 16282 | CLOSE | 2023-08-30 |  | KW1-11271 | 1 | 2023-08-30 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-25 | COMP | 2023-09-12 | 3.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0376 | COUPLING, CONDUIT, w/ SET SCREW, STEEL, 3/4 INCH | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 5 | EA | 50 | 1.96 | 98 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 5 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 50.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 8 | EA | 3 | 61.27 | 183.81 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 8 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 3.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0379 | CLAMP, ELECTRICAL, CONDUIT, 2 HOLE, GALVANIZED STEEL, 3/4 INCH | 39911 | 2023-08-20 | 2023-08-20 | CLOSE | 7 | EA | 100 | 2.66 | 266 | 16112 | SENT | 2023-09-06 | 2023-08-26 | KW1-11208 | 6 | 2023-08-27 | CLOSE | 2023-12-16 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 100.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-00-178-1217 | CONDUIT, METAL, RIGID, STEEL, 3/4 INCH X 10 FEET | 39911 | 2023-08-20 | 2023-08-20 | CLOSE | 8 | LG | 30 | 13.66 | 409.8 | 16112 | SENT | 2023-09-06 | 2023-08-26 | KW1-11208 | 7 | 2023-08-27 | CLOSE | 2023-12-16 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 30.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0159 | WIRE, ELECTRICAL, BLUE, 1 CORE, 4 MM ² | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 13 | RL | 3 | 91.41 | 274.23 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 13 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 3.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0157 | WIRE, ELECTRICAL, YELLOW, 1 CORE, 4MM ² | 39856 | 2023-08-20 | 2023-08-20 | CLOSE | 17 | MR | 270 | 1.33 | 359.1 | 16114 | SENT | 2023-09-06 | 2023-08-26 | KW1-11214 | 17 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-04 | COMP | 2023-09-02 | 270.00 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0136 | WIRE, ELECTRICAL, RED, 1 CORE, 4 MM ² | 39856 | 2023-08-16 | 2023-08-20 |  | 16 | RL | 3 | [6 empty] | KW1-11214 | 16 | [5 empty] | 2023-09-04 | COMP | 2023-09-02 | 3 |  | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0001 | WIRE, ELECTRICAL, BLACK, 1 CORE, 4MM ² | 39856 | 2023-08-16 | 2023-05-13 |  | 13 | MR | 810 | [18 empty] | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6210-60-V00-0081 | LIGHT, PANEL, LED, COOL WHITE, 50/60 HZ, 40W | 39856 | 2023-08-16 | 2023-08-20 |  | 1 | EA | 20 | [6 empty] | KW1-11214 | [11 empty] | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0210 | RACEWAY, METALLIC, GALVANIZED STEEL, 3 X 2 INCHES, 10 FEET | 39856 | 2023-08-16 | 2023-08-20 |  | 6 | EA | 6 | [6 empty] | KW1-11214 | [11 empty] | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 39856 | 2023-08-16 | 2023-08-20 |  | 17 | EA | 30 | [6 empty] | KW1-11214 | [11 empty] | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0042 | BOX CONNECTOR, ELECTRICAL, STRAIGHT, LIQUID TIGHT CONDUIT, NICKEL PLATED BRASS, 1/2 INCH | 39856 | 2023-08-16 | 2023-08-20 |  | 18 | EA | 200 | [6 empty] | KW1-11214 | [11 empty] | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0484 | BOX CONNECTOR, ELECTRICAL, METALLIC CONDUIT, ZINC, 3/4 INCH | 39856 | 2023-08-16 | 2023-08-20 |  | 11 | EA | 300 | [6 empty] | KW1-11214 | [11 empty] | AJ | AJ table | August | 2023 | MM_AJ
41 | 2023-08-16 | 30 | AJ23-0467 | Z7 Relocation of Building 370 | 5876937 | 6145-60-V00-0143 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4 MM² | 39856 | 2023-08-16 | 2023-08-20 |  | 12 | RL | 9 | [6 empty] | KW1-11214 | [11 empty] | AJ | AJ table | August | 2023 | MM_AJ
42 | 2023-08-16 | 60 | AJ23-0493 | Z7 Relocation of Building 370 | 5876937 | 4710-60-V00-0097 | TUBE, METALLIC, REFRIGERATION, COPPER, 3/8 INCH X 50 FEET | 40097 | 2023-08-16 | 2023-08-21 |  | 17 | RO | 1 | [6 empty] | KW1-11171 | 43 | [6 empty] | COMP | 2023-08-31 | 1 |  | AJ | AJ table | August | 2023 | MM_AJ
43 | 2023-08-16 | 60 | AJ23-0499 | Z7 Relocation of Building 370 | 5876937 | 5970-01-013-9366 | TAPE, INSULATION, ELECTRICAL, GREEN, 1/2 X 240 INCHES | 40102 | 2023-08-16 | 2023-08-21 | CLOSE | 1 | RO | 1 | 1.69 | 1.69 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 44 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-08-31 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
44 | 2023-08-16 | 60 | AJ23-0540 | Z7 Relocation of Building 370 | 5876937 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 40097 | 2023-08-16 | 2023-08-21 | CLOSE | 6 | EA | 8 | 60.17 | 481.36 | 16061 | CLOSE | 2023-08-28 | 2023-08-24 | KW1-11171 | 32 | 2023-08-26 | CLOSE | 2023-12-31 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 03:00 | COMP | 2023-08-31 | 8.00 |  | AJ | AJ table | August | 2023 | MM_AJ
45 | 2023-08-16 | 60 | AJ23-0563 | Z7 Relocation of Building 370 | 5876937 | 4730-60-V00-0427 | ELBOW, PIPE, SOCKET X SOCKET, 90°, CPVC, OFFWHITE, 25 X 25 MM | 40101 | 2023-08-16 | 2023-08-20 | CLOSE | 1 | EA | 10 | 13.57 | 135.7 | 16109 | CLOSE | 2023-08-27 | 2023-08-26 | KW1-11204 | 10 | 2023-08-27 | APPR | 2023-08-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-03 | COMP | 2023-09-02 | 10.00 |  | AJ | AJ table | August | 2023 | MM_AJ
46 | 2023-08-17 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0041 | PANEL, CEILING (ACOUSTICAL TILE), MINERAL FIBER, WHITE, 24 X 24 X 3/4 INCHES | 39794 | 2023-08-17 | 2023-08-19 | CLOSE | 1 | EA | 250 | 8.83 | 2207.5 | 15983 | CLOSE | 2023-08-29 | 2023-08-23 | KW1-11249 | 29 | 2023-09-07 | APPR | 2023-09-07 | Kandankara, Thomas -Vectrus -GSD -No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2023-09-21 | COMP | 2023-09-11 | 250.00 |  | AJ | AJ table | August | 2023 | MM_AJ
46 | 2023-08-17 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 39795 | 2023-08-17 | 2023-08-19 | CLOSE | 1 | CN | 10 | 36.79 | 367.9 | 15983 | CLOSE | 2023-08-29 | 2023-08-23 | KW1-11249 | 30 | 2023-09-07 | APPR | 2023-09-07 | Kandankara, Thomas -Vectrus -GSD -No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2023-09-21 | COMP | 2023-09-11 | 10.00 |  | AJ | AJ table | August | 2023 | MM_AJ
47 | 2023-08-17 |  | AJ22-0400 | REPLACE WOODEN DOOR WITH METAL DOOR | 7177768 |  | COST OF LABOR, MATERIALS AND EQUIPMENT TO REPLACE WOODEN DOOR WITH METAL DOOR, CAMP BUEHRING, KUWAIT | 49519 | 2023-08-17 | 2023-08-19 | [22 empty] | AJ | AJ table | August | 2023 | MM_AJ
48 | 2023-08-26 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 3040-60-V00-0075 | : EXTENSION SHAFT, LOAD BREAK SWITCH, EXTERNAL HANDLE, 150 MM | 40730 | 2023-08-26 | 2023-09-02 | CLOSE | 2 | EA | 4 | 3.69 | 14.76 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 3 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-18 | COMP | 2023-10-05 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
48 | 2023-08-26 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5930-60-V00-0405 | SWITCH DISCONNECT, AC, 3POLE, 400-690V, 100A | 40730 | 2023-08-26 | 2023-09-02 | CLOSE | 3 | EA | 4 | 52.03 | 208.12 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 4 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-18 | COMP | 2023-10-08 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
48 | 2023-08-26 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5935-60-V00-0253 | CONNECTOR, WIRE, w/ QUICK-GRIP SPRING, WING NUTS, THERMOPLASTIC, BLUE, 600V, 14-6 AWG | 40730 | 2023-08-26 | 2023-09-02 | CLOSE | 1 | PG | 4 | 11.59 | 46.36 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 2 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-18 | COMP | 2023-09-23 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
48 | 2023-08-26 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 6110-60-V00-0275 | SWITCH, DISCONNECT, NEUTRAL POLE, UNSWITCHED, SINGLE POLE, M3, 100-125 A | 40730 | 2023-08-26 | 2023-09-02 | CLOSE | 4 | EA | 4 | 23 | 92 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 5 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-18 | COMP | 2023-10-08 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
48 | 2023-08-26 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 9515-60-V00-0016 | SHEET, METAL, ALUMINIUM, FLAT, 4 X 8 FEET X 1/16 INCH | 40729 | 2023-08-26 | 2023-09-02 | CLOSE | 1 | EA | 5 | 88.25 | 441.25 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 1 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-14 | 5.00 |  | AJ | AJ table | August | 2023 | MM_AJ
49 | 2023-08-27 |  | AJ23-0508 | T357 Relocation | 2141526 | 6210-60-V00-0165 | FIXTURE, LIGHTING, LED, FLOOD, 50W, 100-240V, 50/60HZ | 40852 | 2023-08-27 | 2023-08-29 | CLOSE | 1 | EA | 4 | 601.35 | 2405.4 | 16291 | CLOSE | 2023-09-01 | 2023-08-31 | KW1-11331 | 1 | 2023-09-01 | CLOSE | 2023-12-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-16 | COMP | 2023-12-08 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5640-60-V00-0048 | DRYWALL SHEET, (GYPSUM BOARD), 4 X 8 FEET X 1/2 INCH | 40879 | 2023-08-28 | 2023-09-02 | CLOSE | 7 | EA | 120 | 19.31 | 2317.2 | 16429 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11425 | 8 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 120.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5305-60-V00-0157 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, COARSE THREAD, #7 X 1-3/8 INCHES | 40887 | 2023-08-28 | 2023-09-02 | CLOSE | 8 | BX | 9 | 29.37 | 264.33 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 9 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 9.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0136 | WIRE, ELECTRICAL, RED, 1 CORE, 4MM² | 40909 | 2023-08-28 | 2023-09-02 | CLOSE | 6 | RL | 5 | 90.58 | 452.9 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 11 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-18 | COMP | 2023-09-14 | 5.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0157 | WIRE, ELECTRICAL, YELLOW, 1 CORE, 4MM² | 40909 | 2023-08-28 | 2023-09-02 | CLOSE | 5 | MR | 460 | 1.32 | 607.2 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 10 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-18 | COMP | 2023-09-14 | 460.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0159 | WIRE, ELECTRICAL, BLUE, 1 CORE, 4 MM² | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | RL | 15 | 90.58 | 452.9 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 1 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-12 | 5.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0154 | WIRE, ELECTRICAL, BLACK, 1 CORE, 4MM² | 40909 | 2023-08-28 | 2023-09-02 | CLOSE | 4 | RO | 15 | 89.76 | 1346.4 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 9 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-14 | 15.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6000-CA-255-0142 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4MM² | 40873 | 2023-08-28 |  |  | 1 | MR | 1380 | [18 empty] | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0013 | WIRE, ELECTRICAL, RED, 1 CORE,6MM² | 40909 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | RL | 5 | 135.38 | 676.9 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 8 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-14 | 5.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0011 | WIRE, ELECTRICAL, YELLOW , 1 CORE,6MM² | 40909 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | RO | 5 | 135.38 | 676.9 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 7 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-14 | 5.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0012 | WIRE, ELECTRICAL, BLUE, 1 CORE,6MM² | 40909 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | RO | 5 | 135.38 | 676.9 | 16436 | CLOSE | 2023-09-06 | 2023-09-04 | KW1-11477 | 6 | 2023-09-06 | CLOSE | 2023-10-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-14 | 5.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0048 | WIRE, ELECTRICAL, BLACK, 1 CORE,6MM² | 40908 | 2023-08-28 |  |  | 8 | RO | 8 | [18 empty] | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0046 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE,6MM² | 40911 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | RO | 15 | 121.44 | 1821.6 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 7 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-14 | 15.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-00-178-1217 | CONDUIT, RIGID, EMT, GALVANIZED STEEL, 3/4" INCH X 10 FEET | 40908 | 2023-08-28 | 2023-09-02 | CLOSE | 7 | LG | 30 | 13.41 | 402.3 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 10 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 30.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0379 | CLAMP, ELECTRICAL, CONDUIT, 2 HOLE, GALVANIZED STEEL, ¾ INCH | 40908 | 2023-08-28 | 2023-09-02 | CLOSE | 6 | EA | 100 | 2.62 | 262 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 9 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 100.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0376 | COUPLING, CONDUIT, WITH SET SCREW, GALVANIZED, 5XC28, 3/4" | 40908 | 2023-08-28 | 2023-09-02 | CLOSE | 5 | EA | 20 | 1.93 | 38.6 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 8 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 20.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0484 | CONNECTOR, EMT, SET SCREW, 3/4" | 40908 | 2023-08-28 | 2023-09-02 | CLOSE | 4 | EA | 100 | 3.27 | 327 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 7 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 100.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0203 | ELBOW, ELECTRICAL CONDUIT, ZINC PLATED, 3/4 INCH | 40908 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | EA | 10 | 30.08 | 300.8 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 6 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 10.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5305-60-V00-0001 | SCREW, SELF DRILLING, HEX HEAD, METAL WASHER, #14 X 1 INCH | 40908 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | BX | 2 | 18.97 | 37.94 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 5 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-10 | 2.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6350-60-V00-0102 | ALARM, SMOKE, AUTOMATIC, PLASTIC | 40871 | 2023-08-28 | 2023-08-30 | CLOSE | 1 | EA | 12 | 28.97 | 347.64 | 16416 | CLOSE | 2023-09-12 | 2023-09-05 | KW1-11634 | 7 | 2023-09-12 | CLOSE | 2023-12-23 | Bharadwajan, Sajan - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-15 | COMP | 2023-09-17 | 12.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5970-01-013-9369 | TAPE, INSULATION ELECTRICAL, RED | 40907 | 2023-08-28 | 2023-09-02 | CLOSE | 4 | RO | 1 | 9.9 | 9.9 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 5 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-12 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5970-01-015-5060 | TAPE, INSULATION ELECTRICAL BLUE | 40907 | 2023-08-28 |  |  | 4 | RO | 1 | [18 empty] | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5970-01-174-5651 | TAPE, INSULATION ELECTRICAL, YELLOW | 40907 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | RO | 1 | 9.9 | 9.9 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 4 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-12 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK 3/4" | 40907 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | RL | 2 | 20.7 | 41.4 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 3 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-12 | 2.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW & GREEN, 3/4", | 40908 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | RO | 4 | 13.41 | 53.64 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 4 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0529 | CONDUIT, PIPE FLEXIBLE, CORRUGATED, GALVANIZED, PVC COATED, 3/4" | 40907 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | RO | 5 | 96.6 | 483 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 2 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-20 | 5.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0042 | BOX CONNECTOR, ELECTRICAL, STRAIGHT, LIQUID TIGHT CONDUIT, NICKEL PLATED BRASS, 1/2 INCH | 40870 | 2023-08-28 |  |  | 13 | EA | 13 | [18 empty] | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-CA-005-0006 | RACEWAY, METALLIC, GALVANIZED STEEL, 4 X 4 INCHES X 10 FEET | 40874 | 2023-08-28 |  |  | 1 | EA | 6 | [18 empty] | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0335 | STRAP, TIE DOWN, ELECTRICAL, COMPON (CABLE TIE), BLACK, 50 LBS, 4.6 MM X 11.02 INCHES | 40906 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | PG | 2 | 14.72 | 29.44 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 3 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 2.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6210-60-V00-0099 | FIXTURE, LIGHTING, LED, FLOOD, 5000K, 50/60HZ, 90W | 40906 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | EA | 2 | 656.37 | 1312.74 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 2 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 2.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6210-60-V00-0082 | LIGHT, PANEL, LED, COOL WHITE, 50/60 HZ, 40W, w/ EMERGENCY BATTERY | 40906 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | EA | 11 | 276.85 | 3045.35 | 16435 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11437 | 1 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 11.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6210-60-V00-0011 | FIXTURE, LIGHTING, LED, 5000K, 100-277V, 20W, 2 FEET | 40911 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | EA | 18 | 167.47 | 3014.46 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 6 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-12 | 18.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 10 | EA | 27 | 10.33 | 278.91 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 10 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 27.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5935-60-V00-0167 | CONNECTOR, WIRE, RED, 18 -10 AWG | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 9 | PG | 30 | 25.41 | 762.3 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 9 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 30.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5930-60-V00-0243 | LIGHT-SWITCH, METAL, 2 WAY, 1 GANG, 250V, 10A | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 8 | EA | 2 | 33.3 | 66.6 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 8 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 2.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5930-60-V00-0387 | LIGHT-SWITCH, METAL, 1 WAY, 1 GANG, 250V, 10A | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 7 | EA | 8 | 33.82 | 270.56 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 7 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-17 | COMP | 2023-10-18 | 8.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5930-60-V00-0387 | LIGHT-SWITCH, METAL, 1 WAY, 1 GANG, 250V, 10A weather proof | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 6 | EA | 2 | 33.82 | 67.64 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 6 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-17 | COMP | 2023-10-18 | 2.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 5 | EA | 10 | 52.28 | 522.8 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 5 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 10.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 4 | EA | 30 | 27.13 | 813.9 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 4 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-11 | 30.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 5940-60-V00-0060 | TERMINAL LUGS 4mm x 6M | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | PG | 1 | 69.3 | 69.3 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 3 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 6110-60-V00-0166 | SENSOR, PHOTOCELL CONTROL, 15A, 50/60 HZ | 40905 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | EA | 1 | 63.36 | 63.36 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 2 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-17 | COMP | 2023-10-18 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
50 | 2023-08-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 4720-60-V00-0370 | ALUMINUM SEMI RIGID FLEXIBLE DUCT Diameter 170mm, Length 9 meters. | 41149 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | EA | 3 | 15.43 | 46.29 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 21 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-19 | 3.00 |  | AJ | AJ table | August | 2023 | MM_AJ
51 | 2023-08-28 |  | AJ22-0189 | T357 Relocation | 2141526 | 5305-60-V00-0158 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, COARSE THREAD, #7 X 1-1/2 INCHES | 40887 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | BX | 2 | 26.67 | 53.34 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 3 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 2.00 |  | AJ | AJ table | August | 2023 | MM_AJ
52 | 2023-08-28 |  | AJ22-0240 | T357 Relocation | 2141526 | 8030-60-V00-0052 | PUTTY, ALL PURPOSE, LIGHT GRAY, 3.43 KG | 40882 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | CN | 2 | 141.53 | 283.06 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 4 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-20 | 2.00 |  | AJ | AJ table | August | 2023 | MM_AJ
53 | 2023-08-28 |  | AJ22-0380 | T357 Relocation | 2141526 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 40876 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | EA | 20 | 13.99 | 279.8 | 16430 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11427 | 3 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-19 | COMP | 2023-09-20 | 20.00 |  | AJ | AJ table | August | 2023 | MM_AJ
54 | 2023-08-28 |  | AJ22-0406 | T357 Relocation | 2141526 | 8010-60-V00-0095 | PRIMER, COATING, RED OXIDE, LIQUID, 3.78 TO 4 LITERS | 40879 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | CN | 3 | 41.63 | 124.89 | 16429 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11425 | 4 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-12 | 3.00 |  | AJ | AJ table | August | 2023 | MM_AJ
55 | 2023-08-28 |  | AJ22-0455 | T357 Relocation | 2141526 | 5640-60-V00-0012 | INSULATION BLANKET, THERMAL, GLASS WOOL, YELLOW, 4 FEET X 10 METER | 40876 | 2023-08-28 | 2023-09-02 | CLOSE | 4 | RO | 22 | 214.45 | 4717.9 | 16430 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11427 | 4 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-19 | COMP | 2023-09-16 | 21.00 |  | AJ | AJ table | August | 2023 | MM_AJ
56 | 2023-08-28 |  | AJ22-0465 | T357 Relocation | 2141526 | 8030-60-V00-0008 | SEALING COMPOUND, GUTTER & SEAM, WHITE, 10 OZ. | 40885 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | CQ | 12 | 23.31 | 279.72 | 16430 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11427 | 7 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-19 | COMP | 2023-09-20 | 12.00 |  | AJ | AJ table | August | 2023 | MM_AJ
57 | 2023-08-28 |  | AJ22-0497 | T357 Relocation | 2141526 | 5680-60-V00-0007 | GRID, CEILING, T-RUNNER, WHITE, 12 FEET | 40880 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | EA | 60 | 19.15 | 1149 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 2 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 60.00 |  | AJ | AJ table | August | 2023 | MM_AJ
58 | 2023-08-28 |  | AJ22-0524 | T357 Relocation | 2141526 | 5510-01-433-1244 | LUMBER, SOFTWOOD, 2 X 4 INCHES X 16 FEET | 40879 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | EA | 20 | 30.64 | 612.8 | 16429 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11425 | 2 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 20.00 |  | AJ | AJ table | August | 2023 | MM_AJ
59 | 2023-08-28 |  | AJ22-0549 | T357 Relocation | 2141526 | 5305-60-V00-0169 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 3 INCHES | 40879 | 2023-08-28 | 2023-09-02 | CLOSE | 4 | BX | 3 | 30.97 | 92.91 | 16429 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11425 | 5 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 3.00 |  | AJ | AJ table | August | 2023 | MM_AJ
60 | 2023-08-28 |  | AJ23-0004 | T357 Relocation | 2141526 | 5680-60-V00-0006 | GRID, CEILING, TEE, WHITE, 24 INCHES | 40882 | 2023-08-28 | 2023-09-02 | CLOSE | 8 | EA | 260 | 4.33 | 1125.8 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 10 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 260.00 |  | AJ | AJ table | August | 2023 | MM_AJ
61 | 2023-08-28 |  | AJ23-0005 | T357 Relocation | 2141526 | 5640-60-V00-0041 | TILES, ACOUSTIC CEILING, 2' X 2' X 3/4" | 40878 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | EA | 260 | 8.99 | 2337.4 | 16429 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11425 | 1 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 260.00 |  | AJ | AJ table | August | 2023 | MM_AJ
62 | 2023-08-28 |  | AJ23-0007 | T357 Relocation | 2141526 | 5650-60-V00-0004 | CHANNEL, STRUCTURAL, C-SHAPE, STEEL, 1-5/8 X 3-5/8 INCHES X 10 FEET | 40880 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | EA | 100 | 9.66 | 966 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 1 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-19 | 100.00 |  | AJ | AJ table | August | 2023 | MM_AJ
63 | 2023-08-28 |  | AJ23-0068 | T357 Relocation | 2141526 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GL | 40886 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | GL | 3 | 228.5 | 685.5 | 16430 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11427 | 9 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-19 | COMP | 2023-09-21 | 3.00 |  | AJ | AJ table | August | 2023 | MM_AJ
64 | 2023-08-28 |  | AJ23-0101 | T357 Relocation | 2141526 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 40876 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | EA | 10 | 29.14 | 291.4 | 16430 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11427 | 2 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-19 | COMP | 2023-09-10 | 10.00 |  | AJ | AJ table | August | 2023 | MM_AJ
65 | 2023-08-28 |  | AJ23-0166 | T357 Relocation | 2141526 | 5640-60-V00-0038 | STRIP, ALUMINIUM, 3MM X 1-1/2 INCHES X 12FEET | 40877 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | EA | 2 | 44.96 | 224.8 | 16430 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11427 | 5 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-19 | COMP | 2023-09-10 | 5.00 |  | AJ | AJ table | August | 2023 | MM_AJ
66 | 2023-08-28 |  | AJ23-0179 | T357 Relocation | 2141526 | 5640-05-V00-0005 | PANEL, DRYWALL, WALL BOARD, REGULAR, MOLD-GUARD, 1/2 INCH X 4 X 8 FEET | 40882 | 2023-08-28 | 2023-09-02 | CLOSE | 6 | EA | 30 | 28.14 | 844.2 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 8 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 30.00 |  | AJ | AJ table | August | 2023 | MM_AJ
67 | 2023-08-28 |  | AJ23-0225 | T357 Relocation | 2141526 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 40881 | 2023-08-28 | 2023-09-10 | CLOSE | 2 | EA | 40 | 45.62 | 1824.8 | 16744 | CLOSE | 2023-09-15 | 2023-09-13 | KW1-11708 | 2 | 2023-09-15 | APPR | 2023-09-15 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2023-09-29 | COMP | 2023-09-20 | 40.00 |  | AJ | AJ table | August | 2023 | MM_AJ
68 | 2023-08-28 |  | AJ23-0258 | T357 Relocation | 2141526 | 5305-60-V00-0197 | SCREW, PHILLIPS DRIVE, SELF-DRILLING, ZINC PLATED, TRUSS HEAD, # 8, 8 X 1/2 INCH | 40884 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | BX | 4 | 29.3 | 117.2 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 12 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
69 | 2023-08-28 |  | AJ23-0260 | T357 Relocation | 2141526 | 5510-60-V00-0031 | WOOD, SOLID, MOULDING/ DECORATIVE, NATURAL, 1/2 X 2 INCHES X 10 FEET | 40887 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | EA | 55 | 24.75 | 1361.25 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 4 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 55.00 |  | AJ | AJ table | August | 2023 | MM_AJ
69 | 2023-08-28 |  | AJ23-0260 | T357 Relocation | 2141526 | 8010-00-598-5460 | PAINT, ENAMEL, FLAT, SAND, 1 GL | 40887 | 2023-08-28 | 2023-09-02 | CLOSE | 4 | GL | 4 | 55.35 | 221.4 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 5 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-17 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
70 | 2023-08-28 |  | AJ23-0268 | T357 Relocation | 2141526 | 9540-60-V00-0009 | ANGLE, STRUCTURAL, ALUMINUM, CREAM, 2 X 2 INCH X 20 FEET | 40884 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | EA | 15 | 43.62 | 654.3 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 11 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 15.00 |  | AJ | AJ table | August | 2023 | MM_AJ
71 | 2023-08-28 |  | AJ23-0337 | T357 Relocation | 2141526 | 8030-60-V00-0029 | SEALING COMPOUND, GAPS AND CRACKS, POLYURETHANE FOAM, 24 OZ | 40884 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | CS | 1 | 265.57 | 265.57 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 13 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-20 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
72 | 2023-08-28 |  | AJ23-0467 | T357 Relocation | 2141526 | 5305-60-V00-0174 | SCREW, HEX, STEEL, w/ RUBBER WASHER, # 14 X 2 ½ INCHES | 40882 | 2023-08-28 | 2023-09-02 |  | 15 | BX | 1 | [6 empty] | KW1-11429 | 3 | [5 empty] | 2023-09-19 | COMP | 2023-09-10 | 1 |  | AJ | AJ table | August | 2023 | MM_AJ
73 | 2023-08-28 |  | AJ23-0482 | T357 Relocation | 2141526 | 5530-00-129-7721 | PLYWOOD, CONSTRUCTION, 1/4 X 48 X 96 INCHES | 40883 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | SH | 42 | 48.12 | 2021.04 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 1 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 42.00 |  | AJ | AJ table | August | 2023 | MM_AJ
74 | 2023-08-28 |  | AJ23-0508 | B506 Electrical Box faceplates | 2141526 | 5640-60-V00-0044 | TAPE, SELF ADHESIVE, DRYWALL JOINT, FIBERGLASS, 2 INCHES X 300 FEET | 40882 | 2023-08-28 | 2023-09-02 | CLOSE | 5 | EA | 3 | 18.65 | 55.95 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 7 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 3.00 |  | AJ | AJ table | August | 2023 | MM_AJ
75 | 2023-08-28 |  | AJ23-0574 | T357 Relocation | 2141526 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 40879 | 2023-08-28 | 2023-09-02 | CLOSE | 6 | CN | 5 | 37.46 | 187.3 | 16429 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11425 | 7 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 5.00 |  | AJ | AJ table | August | 2023 | MM_AJ
76 | 2023-08-28 |  | AJ23-0579 | T357 Relocation | 2141526 | 4710-60-V00-0160 | PIPE, METALLIC, SEAMLESS, MILD STEEL, 41.3 X 3.25 X 5700 MM | 40887 | 2023-08-28 | 2023-09-02 | CLOSE | 1 | EA | 4 | 193.68 | 774.72 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 2 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
77 | 2023-08-28 |  | AJ23-0598 | T357 Relocation | 2141526 | 5340-60-V00-0492 | STOPPER, DOOR, DROP DOWN, METAL, 5 INCHES | 40882 | 2023-08-28 | 2023-09-02 | CLOSE | 3 | EA | 12 | 19.65 | 235.8 | 16431 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11429 | 5 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 12.00 |  | AJ | AJ table | August | 2023 | MM_AJ
78 | 2023-08-28 |  | AJ23-0668 | T357 Relocation | 2141526 | 5640-60-V00-0035 | WEATHER STRIP, DOOR, W/BRUSH, 2 X 36 INCHES | 40879 | 2023-08-28 | 2023-09-02 | CLOSE | 5 | EA | 12 | 30.47 | 365.64 | 16429 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11425 | 6 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-10 | 12.00 |  | AJ | AJ table | August | 2023 | MM_AJ
79 | 2023-08-28 |  | AJ23-0782 | T357 Relocation | 2141526 | 4710-60-V00-0004 | TUBE, METALLIC, SQUARE, UNPOLISHED 2 X 2 X 1/8 INCHES | 40879 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | FT | 400 | 2.83 | 1132 | 16429 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11425 | 3 | 2023-09-05 | CLOSE | 2023-09-19 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-19 | COMP | 2023-09-16 | 400.00 |  | AJ | AJ table | August | 2023 | MM_AJ
80 | 2023-08-28 |  | BU23-0193 | T357 Relocation | 2141526 | 5510-01-433-1371 | LUMBER, SOFTWOOD, 2 X 6 INCHES X 16 FEET | 40881 | 2023-08-28 | 2023-09-10 | CLOSE | 1 | EA | 40 | 30.64 | 1225.6 | 16744 | CLOSE | 2023-09-15 | 2023-09-13 | KW1-11708 | 1 | 2023-09-15 | APPR | 2023-09-15 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2023-09-29 | COMP | 2023-09-20 | 40.00 |  | BU | AJ table | August | 2023 | MM_AJ
81 | 2023-08-28 |  | BU23-0353 | T357 Relocation | 2141526 | 8010-60-V00-0050 | PAINT, ENAMEL, GLOSS, DARK BROWN, 3.2 AND 3.6 LITER | 40885 | 2023-08-28 | 2023-09-02 | CLOSE | 2 | CN | 5 | 34 | 170 | 16430 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11427 | 8 | 2023-09-05 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-19 | COMP | 2023-09-21 | 5.00 |  | BU | AJ table | August | 2023 | MM_AJ
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0027 | DRAIN, FLOOR, TRAP, MINI, 2 WAY, UPVC, GRAY, 4 X 2 INCHES | 41139 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 1 | 23.81 | 23.81 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 13 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0029 | DRAIN, FLOOR, COVER, UPVC, BEIGE, 160/110MM | 41145 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 3 | 11.19 | 33.57 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 12 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 3.00 |  | AJ | AJ table | August | 2023 | MM_AJ
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0030 | DRAIN, FLOOR, TRAP, EXTENSION, UPVC, GRAY, 4 INCHES | 41146 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 1 | 6.6 | 6.6 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 15 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0094 | TRAP, BOTTLE, ADJUSTABLE INLET, 1-1/4 INCHES | 41142 | 2023-08-31 | 2023-09-02 | CLOSE | 3 | EA | 3 | 19.15 | 57.45 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 17 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 3.00 |  | AJ | AJ table | August | 2023 | MM_AJ
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0095 | TRAP, BOTTLE, ADJUSTABLE INLET, 1-1/2 INCHES | 41145 | 2023-08-31 | 2023-09-02 | CLOSE | 2 | EA | 1 | 56.01 | 56.01 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 13 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0131 | SPRAYER, TOILET, 48 INCHES | 41145 | 2023-08-31 | 2023-09-02 | CLOSE | 3 | ST | 2 | 33.47 | 66.94 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 14 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 2.00 |  | AJ | AJ table | August | 2023 | MM_AJ
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4720-60-V00-0266 | HOSE, METALLIC, FLEXIBLE, DOUBLE NUT, STAINLESS STEEL BRAIDED, 1/2 INCH X 1-1/2 FEET | 41140 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 10 | 11.66 | 116.6 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 8 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 10.00 |  | AJ | AJ table | August | 2023 | MM_AJ
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4720-60-V00-0370 | HOSE, AIR DUCT, FLEXIBLE, SEMI-RIGID, ALUMINUM, 125 MM X 3 METER | 41149 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 3 | 15.43 | 46.29 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 21 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-19 | 3.00 |  | AJ | AJ table | August | 2023 | MM_AJ
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0444 | ELBOW, PIPE, SOCKET X FPT, 90 °, CPVC, OFFWHITE, 25MM X 1/2 INCH | 41146 | 2023-08-31 | 2023-09-02 | CLOSE | 2 | EA | 6 | 3.15 | 18.9 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 16 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 6.00 |  | AJ | AJ table | August | 2023 | MM_AJ
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0845 | WYE, TRUE, PIPE, SCH 40, UPVC, GRAY, 45 °, 50MM | 41141 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 2 | 11.99 | 23.98 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 10 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-12 | 2.00 |  | AJ | AJ table | August | 2023 | MM_AJ
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0917 | BUSHING, PIPE, REDUCER, SPIGOT X SOCKET, UPVC, GRAY, 2 X 1-1/2 INCHES | 41142 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 1 | 4.5 | 4.5 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 15 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0929 | TEE, PIPE, SOCKET X SOCKET X SOCKET, SCH-80, CPVC, OFF-WHITE, 25 MM | 41141 | 2023-08-31 | 2023-09-02 | CLOSE | 2 | EA | 10 | 7.66 | 76.6 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 11 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 10.00 |  | AJ | AJ table | August | 2023 | MM_AJ
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 6130-60-V00-0097 | BATTERY, EMERGENCY LED DRIVER, 50/60HZ, 15W, 100-277V | 41148 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 4 | 118.88 | 475.52 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 20 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-12 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 8030-60-V00-0051 | TAPE, ANTISEIZING, (TEFLON TAPE), 0.5 X 520 INCHES | 41142 | 2023-08-31 | 2023-09-02 | CLOSE | 2 | EA | 10 | 1.67 | 16.7 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 16 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 10.00 |  | AJ | AJ table | August | 2023 | MM_AJ
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 41138 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | BX | 1 | 143.19 | 143.19 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 10 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 1.00 |  | AJ | AJ table | August | 2023 | MM_AJ
82 | 2023-08-31 |  | AJ22-0135 | T357 Relocation | 2141526 | 9330-60-V00-0015 | SHEET, ACRYLIC, WHITE, 48 X 96 INCHES | 41146 | 2023-08-31 | 2023-09-02 | CLOSE | 3 | SH | 2 | 122.87 | 245.74 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 17 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-14 | 2.00 |  | AJ | AJ table | August | 2023 | MM_AJ
83 | 2023-08-31 |  | AJ22-0371 | T357 Relocation | 2141526 | 4730-60-V00-0430 | ELBOW, PIPE, SOCKET X SOCKET, 45 °, CPVC, OFF WHITE, 25 MM | 41138 | 2023-08-31 | 2023-09-02 | CLOSE | 3 | EA | 10 | 3.16 | 31.6 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 12 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 10.00 |  | AJ | AJ table | August | 2023 | MM_AJ
84 | 2023-08-31 |  | AJ22-0475 | T357 Relocation | 2141526 | 4820-60-V00-0227 | VALVE, ANGLE, 1/2 X 1/2 INCHES | 41143 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 12 | 17.65 | 211.8 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 18 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 12.00 |  | AJ | AJ table | August | 2023 | MM_AJ
85 | 2023-08-31 |  | AJ23-0040 | T357 Relocation | 2141526 | 4730-60-V00-0632 | BUSHING, PIPE, REDUCER, SOCKET X SOCKET, CPVC, OFFWHITE, 32 X 25 MM | 41140 | 2023-08-31 | 2023-09-02 | CLOSE | 2 | EA | 2 | 10.49 | 41.96 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 9 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 4.00 |  | AJ | AJ table | August | 2023 | MM_AJ
86 | 2023-08-31 |  | AJ23-0450 | T357 Relocation | 2141526 | 4730-60-V00-0427 | ELBOW, PIPE, SOCKET X SOCKET, 90°, CPVC, OFFWHITE, 25 X 25 MM | 41138 | 2023-08-31 | 2023-09-02 | CLOSE | 2 | EA | 10 | 13.82 | 138.2 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 11 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 10.00 |  | AJ | AJ table | August | 2023 | MM_AJ
87 | 2023-08-31 |  | BU23-0264 | T357 Relocation | 2141526 | 4730-60-V00-0326 | COUPLING, PIPE, SOCKET X SOCKET, CPVC, OFFWHITE, 25MM | 41144 | 2023-08-31 | 2023-09-02 | CLOSE | 2 | EA | 5 | 25.97 | 129.85 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 20 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 5.00 |  | BU | AJ table | August | 2023 | MM_AJ
88 | 2023-08-31 |  |  | T357 Relocation | 2141526 | 4730-60-V00-0718 | UNION, PIPE, SOCKET, CPVC, GRAY, SCH 80, 3/4 INCH | 41146 | 2023-08-31 | 2023-09-02 | CLOSE | 5 | EA | 5 | 50 | 150 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 19 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 3.00 |  |  | AJ table | August | 2023 | MM_AJ
88 | 2023-08-31 |  |  | T357 Relocation | 2141526 | 4730-60-V00-0810 | CLAMP, PIPE, CPVC, BEIGE, 25 MM | 41146 | 2023-08-31 | 2023-09-02 | CLOSE | 4 | EA | 20 | 0.93 | 18.6 | 16433 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11451 | 18 | 2023-09-05 | APPR | 2023-09-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-20 | COMP | 2023-09-11 | 20.00 |  |  | AJ table | August | 2023 | MM_AJ
88 | 2023-08-31 |  |  | T357 Relocation | 2141526 | 4730-60-V00-0812 | MONO D' CLIPS, CPVC PIPE, 32MM | 41144 | 2023-08-31 | 2023-09-02 | CLOSE | 1 | EA | 20 | 2.5 | 50 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 19 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 20.00 |  |  | AJ table | August | 2023 | MM_AJ
88 | 2023-08-31 |  |  | T357 Relocation | 2141526 | 4730-60-V00-0927 | TEE, PIPE, SOCKET X SOCKET X FIPT, SCH-80, CPVC, OFF-WHITE, 25 MM X 1/2 INCH | 41139 | 2023-08-31 | 2023-09-02 | CLOSE | 2 | EA | 5 | 17.32 | 86.6 | 16432 | CLOSE | 2023-09-03 | 2023-09-04 | KW1-11386 | 14 | 2023-09-03 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-17 | COMP | 2023-09-09 | 5.00 |  |  | AJ table | August | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-09-V00-0065 | DOWNSPOUT, GUTTER, B ELBOW, ALUMINUM, MUSKET BROWN, 3 X 4 INCHES | 41343 | 2023-09-02 | 2023-09-06 | CLOSE | 3 | EA | 6 | 4.49 | 26.94 | 16646 | CLOSE | 2023-09-12 | 2023-09-09 | KW1-11642 | 8 | 2023-09-12 | APPR | 2023-09-12 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-10-30 03:00 | COMP | 2023-10-04 | 6.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 5345-60-V00-0026 | DISK, ABRASIVE,8 HOLE, ALUMINUM OXIDE, COATED, 9 INCHES | 41342 | 2023-09-02 | 2023-09-06 |  | 4 | PG | 4 | [6 empty] | KW1-11642 | 5 | [6 empty] | COMP | 2023-10-02 | 4 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 5680-09-V00-0001 | CORNER BEAD, QUICKSILVER, METAL, 8 FEET X 1-1/4 INCHES | 41343 | 2023-09-02 | 2023-09-06 | CLOSE | 2 | EA | 28 | 4.5 | 126 | 16646 | CLOSE | 2023-09-12 | 2023-09-09 | KW1-11642 | 7 | 2023-09-12 | APPR | 2023-09-12 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-10-31 | COMP | 2023-10-25 | 28.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 8030-09-V01-0003 | SEALING COMPOUND, CAULK, ACRYLIC, WHITE, 5.5 OZ | 41343 | 2023-09-02 | 2023-09-06 | CLOSE | 1 | EA | 50 | 9 | 450 | 16646 | CLOSE | 2023-09-12 | 2023-09-09 | KW1-11642 | 6 | 2023-09-12 | APPR | 2023-09-12 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-10-30 03:00 | COMP | 2023-10-02 | 50.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 5130-60-V00-0125 | DISK, ABRASIVE, SANDING, HOOK AND LOOP, 220 GRIT, 8 HOLE, 5 INCHES | 41340 | 2023-09-02 | 2023-09-05 | CLOSE | 1 | PK | 3 | 95.04 | 285.12 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 15 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 3.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 41341 | 2023-09-02 | 2023-09-06 | CLOSE | 1 | BX | 3 | 11.8 | 35.4 | 16727 | CLOSE | 2023-09-17 | 2023-09-12 | KW1-11770 | 3 | 2023-09-17 | APPR | 2023-09-17 | Bharadwajan, Sajan - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-20 | COMP | 2023-09-23 | 3.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | Zone 7 Fire Station 4 Refer Power Connec | 2141526 | 8010-60-V00-0238 | PAINT, LATEX, GLOSSY, BRIGHT WHITE, 1 GL | 41343 | 2023-09-02 | 2023-09-06 | CLOSE | 4 | CN | 6 | 48.52 | 291.12 | 16646 | CLOSE | 2023-09-12 | 2023-09-09 | KW1-11642 | 9 | 2023-09-12 | APPR | 2023-09-12 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-09-26 03:00 | COMP | 2023-09-24 | 6.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 8010-60-V00-0237 | PAINT, LATEX, INTERIOR, WATER BASED, WHITE, 16 LITERS | 41343 | 2023-09-02 | 2023-09-06 | CLOSE | 5 | CN | 3 | 45.4 | 136.2 | 16646 | CLOSE | 2023-09-12 | 2023-09-09 | KW1-11642 | 10 | 2023-09-12 | APPR | 2023-09-12 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-10-03 03:00 | COMP | 2023-09-21 | 3.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0094 | TRAP, BOTTLE, ADJUSTABLE INLET, 1-1/4 INCHES | 41336 | 2023-09-02 | 2023-09-05 | CLOSE | 3 | EA | 1 | 14.09 | 14.09 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 7 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T7282 and T7283 TI Repairs Z7 | 2141526 | 4510-60-V00-0124 | FAUCET, LEVER, SINGLE, CHROME, BRASS, WASH BASIN MIXER | 41335 | 2023-09-02 | 2023-09-05 | CLOSE | 1 | EA | 2 | 59.51 | 119.02 | 16605 | CLOSE | 2023-09-13 | 2023-09-07 | KW1-11652 | 1 | 2023-09-13 | CLOSE | 2023-12-16 | Kandankara, Thomas -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-27 | COMP | 2023-09-18 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0131 | SPRAYER, TOILET, 48 INCHES | 41335 | 2023-09-02 | 2023-09-05 | CLOSE | 2 | EA | 1 | 44.96 | 44.96 | 16605 | CLOSE | 2023-09-13 | 2023-09-07 | KW1-11652 | 2 | 2023-09-13 | CLOSE | 2023-12-16 | Kandankara, Thomas -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-27 | COMP | 2023-09-18 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4720-60-V00-0266 | HOSE, METALLIC, FLEXIBLE, DOUBLE NUT, STAINLESS STEEL BRAIDED, 1/2 INCH X 1-1/2 FEET | 41335 | 2023-09-02 | 2023-09-05 | CLOSE | 3 | EA | 4 | 9.83 | 39.32 | 16605 | CLOSE | 2023-09-13 | 2023-09-07 | KW1-11652 | 3 | 2023-09-13 | CLOSE | 2023-12-16 | Kandankara, Thomas -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-27 | COMP | 2023-09-18 | 4.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0435 | ELBOW, PIPE, 87.5 °, SPIGOT X SOCKET, UPVC, GRAY, 50MM | 41339 | 2023-09-02 | 2023-09-05 | CLOSE | 2 | EA | 6 | 10 | 60 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 13 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 6.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0448 | ELBOW, PIPE, SOCKET X SPIGOT, 45°, UPVC, GRAY, 50MM | 41338 | 2023-09-02 | 2023-09-05 | CLOSE | 1 | EA | 4 | 13.73 | 54.92 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 10 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 4.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0734 | WYE, TRUE, PIPE, BRANCH, UPVC, 45 DEG, 50 MM | 41339 | 2023-09-02 | 2023-09-05 | CLOSE | 1 | EA | 2 | 3 | 6 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 12 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0965 | COUPLING, SEWAGE, w/RUBBER GASKET, PVC, ORANGE, 160 MM | 41336 | 2023-09-02 | 2023-09-05 | CLOSE | 2 | EA | 2 | 20.11 | 40.22 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 6 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0968 | ELBOW, DRAINAGE PIPE, SEWAGE, 45 °, PVC, SCH-80, ORANGE, 160 MM | 41336 | 2023-09-02 | 2023-09-05 | CLOSE | 1 | EA | 2 | 30.25 | 60.5 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 5 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4820-60-V00-0227 | VALVE, ANGLE, 1/2 X 1/2 INCHES | 41337 | 2023-09-02 |  |  | 2 | EA | 2 | [18 empty] | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0203 | HINGE, BUTT, DOOR, FULL MORTISE, STEEL, 3 HOLES PER LEAF, 3-1/2 X 1-1/2 INCHES | 41334 | 2023-09-02 | 2023-09-05 | CLOSE | 1 | EA | 32 | 15.26 | 488.32 | 16623 | CLOSE | 2023-09-16 | 2023-09-09 | KW1-11743 | 4 | 2023-09-16 | APPR | 2023-09-16 | Bharadwajan, Sajan - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-10-20 | COMP | 2023-09-21 | 32.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0870 | STRIKE, CATCH (PLATE), SASHLOCK, W/FOREND, POLISHED BRASS, 30 X 45 X 180 MM | 41334 | 2023-09-02 | 2023-09-05 | CLOSE | 2 | EA | 12 | 6.89 | 82.68 | 16623 | CLOSE | 2023-09-16 | 2023-09-09 | KW1-11743 | 5 | 2023-09-16 | APPR | 2023-09-16 | Bharadwajan, Sajan - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-10-20 | COMP | 2023-10-07 | 12.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 7920-00-148-9666 | RAG, WIPING, COTTON (MIXED COLOR), 50LB | 41333 | 2023-09-02 | 2023-09-05 | CLOSE | 1 | BE | 2 | 30.87 | 61.74 | 16623 | CLOSE | 2023-09-16 | 2023-09-09 | KW1-11743 | 3 | 2023-09-16 | APPR | 2023-09-16 | Bharadwajan, Sajan - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-22 | COMP | 2023-09-21 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 8010-60-V00-0146 | PRIMER COATING, WOOD, WHITE, 5 GL | 41481 | 2023-09-02 | 2023-09-06 | CLOSE | 1 | CN | 1 | 98.8 | 98.8 | 16646 | CLOSE | 2023-09-12 | 2023-09-09 | KW1-11642 | 29 | 2023-09-12 | APPR | 2023-09-12 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-09-26 03:00 | COMP | 2023-09-21 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 8040-60-V00-0065 | TAPE, PRESSURE SENSITIVE ADHESIVE, SEALANT, BLACK, 4 INCHES X 50 FEET | 41334 | 2023-09-02 | 2023-09-05 | CLOSE | 3 | RO | 10 | 70.3 | 703 | 16623 | CLOSE | 2023-09-16 | 2023-09-09 | KW1-11743 | 6 | 2023-09-16 | APPR | 2023-09-16 | Bharadwajan, Sajan - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-10-20 | COMP | 2023-10-04 | 10.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0335 | COUPLING, PIPE, w/ RUBBER SEAL, SOCKET X SOCKET, UPVC, GRAY, 50 MM | 41338 | 2023-09-02 | 2023-09-05 | CLOSE | 2 | EA | 3 | 10.79 | 32.37 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 11 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 3.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0112 | VALVE, FLUSH, URINAL, TOP PUSH, MECHANICAL RELEASE, CHROME PLATED BRASS, 1/2 INCH | 41335 | 2023-09-02 | 2023-09-05 | CLOSE | 4 | EA | 1 | 58.86 | 58.86 | 16605 | CLOSE | 2023-09-13 | 2023-09-07 | KW1-11652 | 4 | 2023-09-13 | CLOSE | 2023-12-16 | Kandankara, Thomas -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-27 | COMP | 2023-09-18 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-01-660-7689 | URINAL, STATIONARY, WALL MOUNTED, PORCELAIN, WHITE, 14 X 17-1/2 INCHES | 41339 | 2023-09-02 | 2023-09-05 | CLOSE | 3 | EA | 1 | 219.74 | 219.74 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 14 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-02 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0004 | COMMODE, WATER CLOSET, ONE-PIECE TOILET, FLOOR MOUNTED, WHITE | 41336 | 2023-09-02 | 2023-09-05 | CLOSE | 4 | EA | 1 | 429.19 | 429.19 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 8 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-03 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-05-V01-0827 | FLANGE, PIPE, (TOILET SEAL), WAX FREE, PVC, 3 INCHES | 41429 | 2023-09-03 |  |  | 3 | EA | 3 | [18 empty] | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-03 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-05-V00-0022 | COVER, TOILET SEAT, W/ SEAT, ROUND, PLASTIC, WHITE, 455 X 375 MM | 41429 | 2023-09-03 |  |  | 2 | EA | 2 | [18 empty] | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-05 |  | AJ22-0135 | T357 Relocation | 2141526 | 5650-60-V00-0002 | ROOFING METAL, WHITE, 0.35 MM X 3 METER | 41532 | 2023-09-05 | 2023-09-06 | CLOSE | 1 | SH | 30 | 25.02 | 750.6 | 16645 | CLOSE | 2023-09-13 | 2023-09-10 | KW1-11670 | 20 | 2023-09-14 | APPR | 2023-09-14 | Kandankara, Thomas -Vectrus -GSD -No Export | AL-IRTEKAZ NATIONAL GEN.TRDG.C | 2023-09-28 | COMP | 2023-09-19 | 30.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-05 |  | AJ22-0135 | T357 Relocation | 2141526 | 5640-05-V00-0005 | PANEL, DRYWALL, WALL BOARD, REGULAR, MOLD-GUARD, 1/2 INCH X 4 X 8 FEET | 41534 | 2023-09-05 | 2023-09-06 | CLOSE | 1 | EA | 10 | 27.63 | 276.3 | 16645 | CLOSE | 2023-09-13 | 2023-09-10 | KW1-11670 | 22 | 2023-09-14 | APPR | 2023-09-14 | Kandankara, Thomas -Vectrus -GSD -No Export | AL-IRTEKAZ NATIONAL GEN.TRDG.C | 2023-09-28 | COMP | 2023-09-20 | 10.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-05 |  | AJ22-0135 | T357 Relocation | 2141526 | 5640-60-V00-0042 | TILE, CEILING, PVC, WHITE, 2 X 2 FEET | 41534 | 2023-09-05 | 2023-09-06 | CLOSE | 2 | BX | 2 | 343.93 | 687.86 | 16645 | CLOSE | 2023-09-13 | 2023-09-10 | KW1-11670 | 23 | 2023-09-14 | APPR | 2023-09-14 | Kandankara, Thomas -Vectrus -GSD -No Export | AL-IRTEKAZ NATIONAL GEN.TRDG.C | 2023-09-28 | COMP | 2023-09-20 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
89 | 2023-09-07 |  | AJ22-0135 | T357 Relocation | 2141526 | 7105-60-V00-0019 | FABRICATION PANEL, DISTRIBUTION BOARD, APPROVED SUBMITTAL VIA TRANSMITTAL # AJ220135-LCV-ELE-DSN-0001. | 50213 | 2023-09-07 | 2023-09-07 |  | 1 | AY | 1 | [18 empty] | AJ | AJ table | September | 2023 | MM_AJ
90 | 2023-09-07 |  | AJ22-0198 | Replacing The Main Distribution Panel | 6669460 | PANEL | FABRICATION PANEL, MDP APPROVED SUBMITTAL VIA TRANSMITTAL#AJ230540-LCV-ELEDSN- 0001 | 50205 | 2023-09-07 | 2023-09-07 |  | 1 | AY | 1 | [18 empty] | AJ | AJ table | September | 2023 | MM_AJ
91 | 2023-09-07 |  | BU23-0372 | 43 Electrical Meter Installation | 2141526 | PANEL | FABRICATION PANEL, DISTRIBUTION BOARD, APPROVED SUBMITTAL VIA TRANSMITTAL #AJ220135-LCV-ELE-DSN-0001. | 50213 | 2023-09-07 | 2023-09-07 |  | 1 | AY | 1 | [18 empty] | BU | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 8020-00-260-1302 | BRUSH, PAINT, BRISTLES, CHISELED, 2 INCHES | 41919 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | EA | 10 | 13.15 | 131.5 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 20 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-10-13 | COMP | 2023-09-20 | 10.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5130-60-V00-0125 | DISK, ABRASIVE, SANDING, HOOK AND LOOP, 220 GRIT, 8 HOLE, 5 INCHES | 41912 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | PK | 1 | 49.28 | 49.28 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 13 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 8030-01-075-1156 | CAULKING COMPOUND, CARTRIDGE, WHITE, 10 OZ | 41911 | 2023-09-09 | 2023-09-11 |  | 1 | CA | 12 | [6 empty] | KW1-11721 | 11 | [5 empty] | 2023-09-20 | COMP | 2023-09-20 | 12 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5305-60-V00-0151 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, COARSE THREAD, #10 X 3-1/2 INCHES | 41918 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | BX | 1 | 316.25 | 316.25 | 16829 | CLOSE | 2023-09-19 | 2023-09-16 | KW1-11801 | 22 | 2023-09-19 | APPR | 2023-09-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-26 | COMP | 2023-09-24 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5530-60-V00-0008 | PLYWOOD, CONSTRUCTION, HEAT TREATED, 1/2 INCH X 4 X 8 FEET | 41914 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | SH | 12 | 32.97 | 395.64 | 16829 | CLOSE | 2023-09-19 | 2023-09-16 | KW1-11801 | 14 | 2023-09-19 | APPR | 2023-09-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-26 | COMP | 2023-09-24 | 12.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5340-60-V00-0473 | CLOSER, DOOR, HEAVY DUTY, HOLD OPEN, 12 X 2-1/4 INCHES | 41921 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | EA | 1 | 745.9 | 745.9 | 16787 | CLOSE | 2023-09-17 | 2023-09-13 | KW1-11771 | 1 | 2023-09-17 | CLOSE | 2023-10-17 | Vishwanath, Shet -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-21 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 8030-60-V00-0008 | SEALING COMPOUND, GUTTER & SEAM, WHITE, 10 OZ. | 41920 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | CQ | 12 | 23.31 | 279.72 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 26 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-10-15 | COMP | 2023-10-17 | 12.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5640-60-V00-0015 | INSULATION BLANKET, THERMAL, FIBERGLASS, R4.1, 50 MM X 1.2 X 10 METER | 41911 | 2023-09-09 | 2023-09-29 |  | 2 | RL | 6 | [6 empty] | KW1-11721 | 12 | [5 empty] | 2023-09-29 | COMP | 2023-09-21 | 6 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 7510-00-266-6710 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 41911 | 2023-09-09 | 2023-09-11 | CLOSE | 3 | RO | 10 | 8.33 | 83.3 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 8 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 10.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 41913 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | BX | 10 | 17.82 | 178.2 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 16 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 10.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 8010-60-V00-0028 | PAINT, ENAMEL, GLOSS, DESERT SAND, 3.6 LITER | 41919 | 2023-09-09 | 2023-09-11 | CLOSE | 2 | CN | 8 | 39.96 | 319.68 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 21 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-30 | COMP | 2023-09-30 | 8.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 8010-60-V00-0089 | PRIMER, COATING, WHITE, 4 - 5 LITERS | 41919 | 2023-09-09 | 2023-09-11 | CLOSE | 3 | CN | 4 | 41.63 | 166.52 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 22 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-30 | COMP | 2023-09-30 | 4.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 8010-60-V00-0113 | THINNER, PAINT PRODUCTS, 5 LITER | 41919 | 2023-09-09 | 2023-09-11 | CLOSE | 4 | CN | 3 | 54.95 | 164.85 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 23 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-30 | COMP | 2023-09-21 | 3.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 6850-60-V00-0005 | ADDITIVE, MILDEWCIDE, LIQUID, 50-GRAM | 41913 | 2023-09-09 | 2023-09-11 | CLOSE | 2 | EA | 5 | 35.8 | 179 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 17 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 5.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 8010-60-V00-0018 | PAINT, LATEX, SEMIGLOSS, SAHARA SAND, 3.6 LT | 41915 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | CN | 12 | 65.1 | 781.2 | 16829 | CLOSE | 2023-09-19 | 2023-09-16 | KW1-11801 | 16 | 2023-09-19 | APPR | 2023-09-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-29 | COMP | 2023-09-30 | 12.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 41911 | 2023-09-09 |  |  | 4 | BX | 1 | [18 empty] | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 41912 | 2023-09-09 | 2023-09-11 | CLOSE | 2 | EA | 12 | 45.62 | 547.44 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 14 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 12.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 8040-60-V00-0032 | ADHESIVE, FLOOR/WOOD, 5 GL | 41920 | 2023-09-09 | 2023-09-11 | CLOSE | 2 | CN | 2 | 161.51 | 323.02 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 27 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-10-02 | COMP | 2023-10-01 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 7210-60-V00-0059 | FLOOR COVERING, VINYL RESIN, 3 MM X 40 FEET | 41919 | 2023-09-09 | 2023-09-11 | CLOSE | 5 | RO | 1 | 722.61 | 722.61 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 24 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-26 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 3455-60-V00-0004 | BLADE, CIRCULAR SAW, METAL CUTTING, ALUMINUM OXIDE, 4 X 5/8 INCHES | 41911 | 2023-09-09 |  |  | 5 | PK | 3 | [18 empty] | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 9515-60-V00-0016 | SHEET, METAL, ALUMINIUM, FLAT, 4 X 8 FEET X 1/16 INCH | 41911 | 2023-09-09 |  |  | 6 | SH | 1 | [18 empty] | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5305-60-V00-0191 | SCREW, PHILLIPS, FLAT HEAD, STEEL, # 10 X 1-1/2 INCHES | 41912 | 2023-09-09 | 2023-09-11 | CLOSE | 3 | BX | 1 | 30.24 | 30.24 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 15 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5305-60-V00-0179 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 1-1/2 INCHES | 41919 | 2023-09-09 | 2023-09-11 | CLOSE | 6 | BX | 1 | 10.66 | 10.66 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 25 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 41916 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | BX | 1 | 19.98 | 19.98 | 16829 | CLOSE | 2023-09-19 | 2023-09-16 | KW1-11801 | 19 | 2023-09-19 | APPR | 2023-09-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-26 | COMP | 2023-09-24 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5510-01-433-1244 | LUMBER, SOFTWOOD, 2 X 4 INCHES X 16 FEET | 41915 | 2023-09-09 | 2023-09-11 | CLOSE | 2 | EA | 1 | 30.64 | 30.64 | 16829 | CLOSE | 2023-09-19 | 2023-09-16 | KW1-11801 | 17 | 2023-09-19 | APPR | 2023-09-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-26 | COMP | 2023-09-24 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5350-60-V00-0002 | PAPER, ABRASIVE (SANDPAPER), 320 GRIT, 9 X 11 INCHES | 41913 | 2023-09-09 | 2023-09-11 | CLOSE | 3 | PK | 1 | 44.96 | 44.96 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 18 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5345-60-V00-0005 | DISK, ABRASIVE w/GRIP, SANDING, 80 GRIT, 8 HOLES, 5 INCHES | 41920 | 2023-09-09 | 2023-09-11 | CLOSE | 3 | BX | 1 | 59.77 | 59.77 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 28 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 41916 | 2023-09-09 | 2023-09-11 | CLOSE | 2 | CN | 1 | 37.46 | 37.46 | 16829 | CLOSE | 2023-09-19 | 2023-09-16 | KW1-11801 | 20 | 2023-09-19 | APPR | 2023-09-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-26 | COMP | 2023-09-24 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5640-60-V00-0045 | TAPE, JOINT, WALLBOARD, SELF-ADHESIVE, 50 MM X 90 METERS | 41923 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | EA | 1 | 11.99 | 11.99 | 16841 | CLOSE | 2023-09-20 | 2023-09-14 | KW1-11839 | 1 | 2023-09-21 | CLOSE | 2023-12-31 | Jayaraj, Sudha - No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-28 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5640-05-V00-0005 | PANEL, DRYWALL, WALL BOARD, REGULAR, MOLD-GUARD, 1/2 INCH X 4 X 8 FEET | 41913 | 2023-09-09 | 2023-09-11 | CLOSE | 4 | EA | 1 | 28.14 | 28.14 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 19 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-29 | COMP | 2023-09-20 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5340-60-V00-0466 | HANDLE, DOOR, w/ LOCK, ALUMINUM | 41922 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | SE | 1 | 56.93 | 56.93 | 16787 | CLOSE | 2023-09-17 | 2023-09-13 | KW1-11771 | 3 | 2023-09-17 | CLOSE | 2023-10-17 | Vishwanath, Shet -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-07 | COMP | 2023-09-21 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 41911 | 2023-09-09 |  |  | 7 | BX | 2 | [18 empty] | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5650-60-V00-0002 | ROOFING METAL, WHITE, 0.35 MM X 3 METER | 41918 | 2023-09-09 | 2023-09-11 | CLOSE | 2 | SH | 34 | 25.47 | 865.98 | 16829 | CLOSE | 2023-09-19 | 2023-09-16 | KW1-11801 | 23 | 2023-09-19 | APPR | 2023-09-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-26 | COMP | 2023-09-24 | 34.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 20 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5620-60-V00-0002 | CONCRETE MASONRY UNIT, SOLID, 12 X 12 X 2 INCHES | 41917 | 2023-09-09 | 2023-09-11 | CLOSE | 1 | EA | 30 | 43.62 | 1308.6 | 16804 | CLOSE | 2023-09-18 | 2023-09-14 | KW1-11778 | 4 | 2023-09-18 | APPR | 2023-09-18 | Kandankara, Thomas -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2023-09-30 | COMP | 2023-09-23 | 30.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 30 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 41952 | 2023-09-09 | 2023-09-19 |  | 33 | RL | 1 | [6 empty] | KW1-11894 | [6 empty] | 2023-10-01 |  |  |  |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 30 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5110-60-V00-0079 | STRIPPER, FIBER OPTIC, DUAL-DUROMETER, 5 IN 1 PRESETS | 41954 | 2023-09-09 | 2023-09-25 | CLOSE | 1 | EA | 4 | 98 | 392 | 16848 | CLOSE | 2023-10-04 | 2023-09-14 | KW1-12135 | 1 | 2023-10-10 | APPR | 2023-10-10 | Jayaraj, Sudha - No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-25 | COMP | 2023-10-19 | 4.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 30 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5120-60-V00-0111 | SCREW DRIVER / NUT DRIVER, HEAVY DUTY, MULTI-BIT | 41952 | 2023-09-09 | 2023-09-19 | CLOSE | 1 | SE | 2 | 35.92 | 71.84 | 17123 | CLOSE | 2023-09-23 | 2023-09-21 | KW1-11894 | 2 | 2023-09-23 | APPR | 2023-09-23 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-01 | COMP | 2023-09-28 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 30 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5110-01-563-4373 | STRIPPER, WIRE, HAND, 7.125 INCHES | 41956 | 2023-09-09 | 2023-09-25 | CLOSE | 1 | EA | 4 | 66.74 | 266.96 | 16853 | CLOSE | 2023-10-05 | 2023-09-14 | KW1-12137 | 1 | 2023-10-10 | APPR | 2023-10-10 | Jayaraj, Sudha - No Export | AL BAYADER INTER.GROUP COMPANY | 2023-11-18 | COMP | 2023-10-18 | 4.00 |  | AJ | AJ table | September | 2023 | MM_AJ
92 | 2023-09-09 | 30 | AJ22-0135 | Technical Inspection Repairs, T5802 | 7162722 | 5120-60-V00-0001 | PLIER, CUTTING, DIAGONAL 8 INCHES | 41953 | 2023-09-09 | 2023-09-12 | CLOSE | 1 | EA | 4 | 39.48 | 157.92 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 29 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-10-28 | COMP | 2023-10-02 | 4.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5110-01-367-7278 | CUTTER, CABLE, HAND OPERATED, FORGED STEEL, PLASTIC DIPPED, 9-1/2 INCHES | 41957 | 2023-09-09 | 2023-09-12 | CLOSE | 1 | EA | 4 | 81.1 | 324.4 | 16859 | CLOSE | 2023-09-21 | 2023-09-14 | KW1-11850 | 1 | 2023-09-25 | APPR | 2023-09-25 | Jayaraj, Sudha - No Export | AL-IRTEKAZ NATIONAL GEN.TRDG.C | 2023-11-11 | COMP | 2023-10-04 | 4.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6210-60-V00-0165 | FIXTURE, LIGHTING, LED, FLOOD, 50W, 100-240V, 50/60HZ | 41984 | 2023-09-09 | 2023-09-12 |  | 1 | EA | 3 | [6 empty] | KW1-11698 | 2 | [5 empty] | 2023-12-16 | COMP | 2023-12-08 | 3 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6130-60-V00-0097 | BATTERY, EMERGENCY LED DRIVER, 50/60HZ, 15W, 100-277V | 41952 | 2023-09-09 | 2023-09-19 |  | 3 | EA | 1 | [6 empty] | KW1-11894 | 3 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 1 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0042 | BOX CONNECTOR, ELECTRICAL, STRAIGHT, LIQUID TIGHT CONDUIT, NICKEL PLATED BRASS, 1/2 INCH | 41952 | 2023-09-09 | 2023-09-19 |  | 4 | EA | 20 | [6 empty] | KW1-11894 | 4 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 20 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5940-60-V00-0129 | TERMINAL BLOCK, CONNECTOR, 2 WAY, GREY, 10AWG, 1000V, 125A | 41952 | 2023-09-09 | 2023-09-19 |  | 5 | EA | 5 | [6 empty] | KW1-11894 | 5 | [5 empty] | 2023-11-05 | COMP | 2023-10-08 | 5 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0769 | RACEWAY, METALLIC, (CABLE TRUNKING), HOT DIP GALVANIZED, 75 X 75 X 1.2 X 3000 MM | 41959 | 2023-09-09 | 2023-09-12 | CLOSE | 1 | EA | 14 | 39.08 | 547.12 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 31 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-11-10 | COMP | 2023-10-22 | 14.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 41952 | 2023-09-09 | 2023-09-19 |  | 6 | PG | 4 | [6 empty] | KW1-11894 | 6 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 4 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5935-60-V00-0156 | CONNECTOR, WIRE, RED, 18-6 AWG | 41952 | 2023-09-09 | 2023-09-19 |  | 7 | BX | 4 | [6 empty] | KW1-11894 | 7 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 4 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 41952 | 2023-09-09 | 2023-09-19 |  | 8 | BX | 1 | [6 empty] | KW1-11894 | 8 | [5 empty] | 2023-10-01 | COMP | 2023-10-01 | 1 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 41952 | 2023-09-09 | 2023-09-19 | CLOSE | 8 | RO | 1 | 13.41 | 13.41 | 17123 | CLOSE | 2023-09-23 | 2023-09-21 | KW1-11894 | 9 | 2023-09-23 | APPR | 2023-09-23 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-01 | COMP | 2023-09-28 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5970-60-V00-0044 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 INCH X 66 FEET | 41952 | 2023-09-09 | 2023-09-19 | CLOSE | 9 | RO | 1 | 14.72 | 14.72 | 17123 | CLOSE | 2023-09-23 | 2023-09-21 | KW1-11894 | 10 | 2023-09-23 | APPR | 2023-09-23 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-01 | COMP | 2023-09-28 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5970-60-V00-0040 | TAPE, INSULATION, RED, 3/4 INCH X 25 METER | 41952 | 2023-09-09 | 2023-09-19 |  | 11 | RO | 1 | [6 empty] | KW1-11894 | 9 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 1 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0505 | STUFFING TUBE (CABLE GLAND), PG16, POLYAMIDE, GRAY, 9 -14 MM | 41952 | 2023-09-09 | 2023-09-19 |  | 12 | EA | 10 | [6 empty] | KW1-11894 | 12 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 10 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0143 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4 MM² | 41952 | 2023-09-09 | 2023-09-19 |  | 13 | RL | 1 | [6 empty] | KW1-11894 | 13 | [5 empty] | 2023-10-01 | COMP | 2023-10-01 | 1 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0001 | WIRE, ELECTRICAL, BLACK, 1 CORE, 4MM ² | 41952 | 2023-09-09 | 2023-09-19 |  | 14 | MR | 50 | [6 empty] | KW1-11894 | 14 | [5 empty] | 2023-10-01 | COMP | 2023-10-01 | 50 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0136 | WIRE, ELECTRICAL, RED, 1 CORE, 4 MM ² | 41952 | 2023-09-09 | 2023-09-19 |  | 15 | RL | 1 | [6 empty] | KW1-11894 | 15 | [5 empty] | 2023-10-01 | COMP | 2023-10-01 | 1 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6110-60-V00-0166 | SENSOR, PHOTOCELL CONTROL, 15A, 50/60 HZ | 41952 | 2023-09-09 | 2023-09-19 |  | 16 | EA | 1 | [6 empty] | KW1-11894 | 16 | [5 empty] | 2023-11-05 | COMP | 2023-10-18 | 1 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5930-60-V00-0249 | BOX, SWITCH ENCLOSURE, 1 POLE, 3 GANG, 16A | 41952 | 2023-09-09 | 2023-09-19 |  | 17 | EA | 1 | [6 empty] | KW1-11894 | 17 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 1 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6210-60-V01-0091 | FIXTURE, LIGHT, LED, BULK HEAD, 120-277V, 50K | 41954 | 2023-09-09 | 2023-09-25 | CLOSE | 2 | EA | 1 | 190.46 | 190.46 | 16848 | CLOSE | 2023-10-04 | 2023-09-14 | KW1-12135 | 2 | 2023-10-10 | APPR | 2023-10-10 | Jayaraj, Sudha - No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-25 | COMP | 2023-11-20 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6210-60-V00-0099 | FIXTURE, LIGHTING, LED, FLOOD, 5000K, 50/60HZ, 90W | 41984 | 2023-09-09 | 2023-09-12 |  | 2 | EA | 3 | [6 empty] | KW1-11698 | 4 | [5 empty] | 2023-09-21 | COMP | 2023-09-19 | 3 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0480 | JUNCTION BOX, w/ BLANK SIDE, 100 X 100 X 50 MM | 41952 | 2023-09-09 | 2023-09-19 |  | 19 | EA | 2 | [6 empty] | KW1-11894 | 18 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 2 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0099 | WIRE, ELECTRICAL, BLACK, 1 CORE, 1.5 MM ² | 41952 | 2023-09-09 | 2023-09-19 |  | 20 | MR | 1 | [6 empty] | KW1-11894 | 19 | [5 empty] | 2023-10-01 | COMP | 2023-10-01 | 1 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0149 | WIRE, ELECTRICAL, RED, 1 CORE, 1.5 MM ² | 41952 | 2023-09-09 | 2023-09-19 |  | 21 | RO | 1 | [6 empty] | KW1-11894 | 20 | [5 empty] | 2023-10-01 | COMP | 2023-10-01 | 1 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0050 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 1.5 MM ² | 41952 | 2023-09-09 | 2023-09-19 |  | 22 | RL | 1 | [6 empty] | KW1-11894 | 21 | [5 empty] | 2023-10-01 | COMP | 2023-10-01 | 1 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 41952 | 2023-09-09 | 2023-09-19 |  | 23 | EA | 2 | [6 empty] | KW1-11894 | 22 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 2 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 41955 | 2023-09-09 | 2023-10-24 | CLOSE | 1 | EA | 8 | 4.23 | 33.84 | 16850 | CLOSE | 2023-11-03 | 2023-09-17 | KW1-12727 | 1 | 2023-11-06 | APPR | 2023-11-06 | Jayaraj, Sudha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-18 | COMP | 2023-11-16 | 8.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0462 | TIE, CABLE, BLACK, 8 INCHES X 4.8 MILLIMETER | 41952 | 2023-09-09 | 2023-09-19 |  | 24 | PG | 2 | [6 empty] | KW1-11894 | 22 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 2 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 41952 | 2023-09-09 | 2023-09-19 |  | 25 | EA | 10 | [6 empty] | KW1-11894 | 24 | [5 empty] | 2023-11-05 | COMP | 2023-10-01 | 10 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 41952 | 2023-09-09 | 2023-09-19 |  | 26 | RL | 1 | [6 empty] | KW1-11894 | 25 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 1 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 4210-60-V00-0189 | EXTINGUISHER, FIRE, DRY CHEMICAL, w/ BRASS VALVE, 10 LBS | 41953 | 2023-09-09 | 2023-09-12 | CLOSE | 2 | EA | 2 | 47.86 | 95.72 | 16795 | CLOSE | 2023-09-16 | 2023-09-14 | KW1-11721 | 30 | 2023-09-16 | APPR | 2023-09-16 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-09-30 | COMP | 2023-09-21 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6350-60-V00-0102 | ALARM, SMOKE, AUTOMATIC, PLASTIC | 41952 | 2023-09-09 | 2023-09-19 |  | 27 | EA | 2 | [6 empty] | KW1-11894 | 26 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 2 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0358 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, CW, BRASS, 25 MM | 41952 | 2023-09-09 | 2023-09-19 |  | 28 | KT | 4 | [6 empty] | KW1-11894 | 27 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 4 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5940-60-V00-0016 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 16 MM ² | 41952 | 2023-09-09 | 2023-09-19 |  | 29 | EA | 14 | [6 empty] | KW1-11894 | 28 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 14 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 4240-60-V00-0054 | TAPE, BARRICADE, "CAUTION BURIED ELECTRIC LINE BELOW", 3 INCHES X 1000 FEET | 41952 | 2023-09-09 | 2023-09-19 |  | 30 | RO | 1 | [6 empty] | KW1-11894 | 29 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 1 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 41952 | 2023-09-09 | 2023-09-19 |  | 31 | PG | 3 | [6 empty] | KW1-11894 | 29 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 3 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5305-60-V00-0179 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 1-1/2 INCHES | 41955 | 2023-09-09 | 2023-10-24 | CLOSE | 2 | BX | 1 | 10.42 | 10.42 | 16850 | CLOSE | 2023-11-03 | 2023-09-17 | KW1-12727 | 2 | 2023-11-06 | APPR | 2023-11-06 | Jayaraj, Sudha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-18 | COMP | 2023-11-13 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5930-60-V00-0169 | SWITCH, DISCONNECT, 3 POLE, 600 V, 100 A | 41984 | 2023-09-09 | 2023-09-12 |  | 3 | EA | 1 | [6 empty] | KW1-11698 | 1 | [5 empty] | 2023-09-21 | COMP | 2023-09-19 | 1 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 41952 | 2023-09-09 | 2023-09-19 |  | 34 | EA | 1 | [6 empty] | KW1-11894 | 32 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 1 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 41952 | 2023-09-09 | 2023-09-19 |  | 35 | EA | 1 | [6 empty] | KW1-11894 | 33 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 1 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0118 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 16 MM² | 41952 | 2023-09-09 | 2023-09-19 |  | 36 | MR | 35 | [6 empty] | KW1-11894 | 34 | [5 empty] | 2023-10-01 | COMP | 2023-10-01 | 35 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6210-60-V00-0082 | LIGHT, PANEL, LED, COOL WHITE, 50/60 HZ, 40W, w/ EMERGENCY BATTERY | 41952 | 2023-09-09 | 2023-09-19 |  | 37 | EA | 3 | [6 empty] | KW1-11894 | 35 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 3 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6210-60-V00-0081 | LIGHT, PANEL, LED, COOL WHITE, 50/60 HZ, 40W | 41984 | 2023-09-09 | 2023-09-12 | CLOSE | 3 | EA | 7 | 283.3 | 1983.1 | 16801 | CLOSE | 2023-09-15 | 2023-09-13 | KW1-11698 | 3 | 2023-09-15 | CLOSE | 2024-01-02 | Thomas, Vinu - Vectrus -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-21 | COMP | 2023-09-19 | 7.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0042 | BOX CONNECTOR, ELECTRICAL, STRAIGHT, LIQUID TIGHT CONDUIT, NICKEL PLATED BRASS, 1/2 INCH | 41952 | 2023-09-09 | 2023-09-19 |  | 39 | EA | 20 | [6 empty] | KW1-11894 | 36 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 20 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 41952 | 2023-09-09 | 2023-09-19 |  | 40 | EA | 14 | [6 empty] | KW1-11894 | 37 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 14 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6210-60-V00-0043 | LIGHT UNIT, EMERGENCY, w/COMBO LAMP, RED LETTERS, 120/277V AC | 41955 | 2023-09-09 | 2023-10-24 | CLOSE | 3 | EA | 1 | 133.49 | 133.49 | 16850 | CLOSE | 2023-11-03 | 2023-09-17 | KW1-12727 | 3 | 2023-11-06 | APPR | 2023-11-06 | Jayaraj, Sudha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-18 | COMP | 2023-11-12 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0483 | BOX CONNECTOR, ELECTRICAL, ZINC DIE CAST, 1/2 INCH | 41952 | 2023-09-09 | 2023-09-19 |  | 41 | EA | 44 | [6 empty] | KW1-11894 | 38 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 44 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0381 | CLAMP, ELECTRICAL, CONDUIT, 2 HOLE, STEEL, 1/2 INCH | 41952 | 2023-09-09 | 2023-09-19 |  | 42 | EA | 50 | [6 empty] | KW1-11894 | 39 | [5 empty] | 2023-10-01 | COMP | 2023-09-28 | 50 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 2 | RL | 2 | 21.26 | 42.52 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 2 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 3 | RO | 3 | 13.41 | 40.23 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 3 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 3.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 8030-60-V00-0029 | SEALING COMPOUND, GAPS AND CRACKS, POLYURETHANE FOAM, 24 OZ | 41974 | 2023-09-09 | 2023-09-10 | CLOSE | 1 | CS | 2 | 260.78 | 521.56 | 16746 | SENT | 2023-09-26 | 2023-09-13 | KW1-11705 | 16 | 2023-09-15 | APPR | 2023-09-15 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-11-05 | COMP | 2023-11-05 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5930-60-V00-0254 | SWITCH, DOUBLE POLE, METAL CLAD, 1 GANG, 32A | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 4 | EA | 2 | 69.81 | 139.62 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 4 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0502 | ROD, GROUNDING, KIT, WITH CLAMP, 5/8 INCH X 4 FEET | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 5 | KT | 2 | 145.35 | 290.7 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 5 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 6 | EA | 2 | 60.17 | 120.34 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 6 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-21 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5306-60-V00-0118 | NUT AND BOLT, 1-1/2 X 3/8 INCHES | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 7 | EA | 4 | 0.85 | 3.4 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 7 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 4.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5940-60-V00-0060 | TERMINAL, LUG, ROUND TYPE, COPPER, ONE-HOLE, 4 - 6 MM² X M3 | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 8 | PG | 1 | 68.67 | 68.67 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 8 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0046 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 6 MM² | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 9 | RL | 1 | 120.34 | 120.34 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 9 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-20 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 11 | RO | 1 | 161.7 | 161.7 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 10 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-20 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0505 | STUFFING TUBE (CABLE GLAND), PG16, POLYAMIDE, GRAY, 9 -14 MM | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 12 | EA | 6 | 4.09 | 24.54 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 11 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 6.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5340-60-V00-0449 | ANCHOR, KIT, CONICAL, PLASTIC, #10 X 1 INCHES | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 1 | KT | 1 | 34.34 | 34.34 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 1 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 4730-60-V00-0594 | C-CLAMP W/ RUBBER, GALVANIZED STEEL, 2 INCHES | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 13 | EA | 10 | 10.14 | 101.4 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 12 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 10.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 14 | EA | 3 | 51.5 | 154.5 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 13 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 3.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 4130-60-V00-0288 | TAPE, WRAP, INSULATION, 3 INCHES X 150 FEET | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 15 | RO | 3 | 31.72 | 95.16 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 14 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 3.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6850-01-192-2492 | SEALER, CHEMICAL, PLASTIC POLYURETHANE, WHITE, 12 OZ | 41975 | 2023-09-09 | 2023-09-10 | CLOSE | 1 | CN | 2 | 115.1 | 230.2 | 16746 | SENT | 2023-09-26 | 2023-09-13 | KW1-11705 | 17 | 2023-09-15 | APPR | 2023-09-15 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-11-10 | COMP | 2023-10-07 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 4710-60-V00-0110 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 16 | EA | 2 | 19.62 | 39.24 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 15 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-23 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5640-60-V00-0030 | INSULATION SLEEVING, THERMAL, 3/8 X 72 INCHES | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 17 | EA | 10 | 2.62 | 26.2 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 16 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 10.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5640-60-V00-0031 | INSULATION SLEEVING, THERMAL, 5/8 X 72 INCHES | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 18 | EA | 10 | 3.92 | 39.2 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 17 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 10.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 4710-60-V00-0097 | TUBE, METALLIC, REFRIGERATION, COPPER, 3/8 INCH X 50 FEET | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 19 | RO | 1 | 69.98 | 69.98 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 18 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 4710-60-V00-0098 | TUBE, METALLIC, REFRIGERATION, COPPER, 5/8 INCH X 50 FEET | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 20 | RO | 1 | 100.39 | 100.39 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 19 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-19 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5620-60-V00-0002 | CONCRETE MASONRY UNIT, SOLID, 12 X 12 X 2 INCHES | 41975 | 2023-09-09 | 2023-09-10 | CLOSE | 2 | EA | 8 | 42.84 | 342.72 | 16746 | SENT | 2023-09-26 | 2023-09-13 | KW1-11705 | 18 | 2023-09-15 | APPR | 2023-09-15 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-24 | COMP | 2023-09-20 | 8.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5975-60-V00-0435 | PAD, ANTI VIBRATION, RUBBER/CORK, 4 X 4 X 1 INCHES | 41973 | 2023-09-09 | 2023-09-10 | CLOSE | 21 | EA | 8 | 12.59 | 100.72 | 16976 | CLOSE | 2023-09-16 |  | KW1-11725 | 20 | 2023-09-16 | CLOSE | 2023-09-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-23 | 8.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 4120-60-V00-0018 | AIR CONDITIONER, SPLIT, INDOOR & OUTDOOR, 220-240V, 1 PH, 50/60 HZ, BTU 22000 | 41972 | 2023-09-09 | 2023-09-14 | CLOSE | 1 | EA | 2 | 1062.75 | 2125.5 | 17211 | CLOSE | 2023-09-28 | 2023-09-25 | KW1-12040 | 1 | 2023-09-28 | APPR | 2023-09-28 | Kannoth, Shajee -Vectrus -GSD -No Export | CARRIER KUWAIT AIR CONDITIONING | 2023-10-14 | COMP | 2023-10-16 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5935-60-V00-0160 | SOCKET, OUTLET, WEATHERPROOF, 2 GANG, 2 POLES, 13 AMPS | 41958 | 2023-09-09 | 2023-09-12 | CLOSE | 1 | EA | 2 | 34.6 | 69.2 | 16805 | CLOSE | 2023-09-17 | 2023-09-14 | KW1-11755 | 3 | 2023-09-17 | CLOSE | 2023-10-17 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 |  |  |  |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 30 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5935-60-V00-0160 | SOCKET, OUTLET, WEATHERPROOF, 2 GANG, 2 POLES, 13 AMPS | 41958 | 2023-09-09 | 2023-09-12 | CLOSE | 2 | EA | 3 | 34.6 | 103.8 | 16805 | CLOSE | 2023-09-17 | 2023-09-14 | KW1-11755 | 4 | 2023-09-17 | CLOSE | 2023-10-17 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 |  |  |  |  | AJ | AJ table | September | 2023 | MM_AJ
93 | 2023-09-09 | 40 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0093 | CABLE, POWER, ELECTRICAL, H07RN-F, BLACK, 5 CORE, 1.5 MM² | CANCELLED | 2023-09-09 |  |  |  | MR | 1 | [18 empty] | AJ | AJ table | September | 2023 | MM_AJ
94 | 2023-09-11 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5640-60-V00-0041 | PANEL, CEILING (ACOUSTICAL TILE), MINERAL FIBER, WHITE, 24 X 24 X 3/4 INCHES | 42021 | 2023-09-11 | 2023-09-14 |  | 500 | EA | 1 | [6 empty] | KW1-11811 | 9 | [5 empty] | 2023-09-27 | COMP | 2023-09-24 | 500 |  | AJ | AJ table | September | 2023 | MM_AJ
94 | 2023-09-11 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8010-60-V00-0089 | PRIMER, COATING, WHITE, 4 - 5 LITERS | 42022 | 2023-09-11 | 2023-09-12 | CLOSE | 1 | CN | 20 | 40.88 | 817.6 |  |  |  |  | KW1-11669 | 1 | 2023-09-13 | CLOSE | 2023-12-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RITAJ AL KUWAIT GENERAL TRADING CONTRACTING CO | 2023-09-14 03:00 | COMP | 2023-09-14 | 20.00 |  | AJ | AJ table | September | 2023 | MM_AJ
95 | 2023-09-12 | 150 | AJ22-0135 | T357 Relocation | 2141526 | 5305-60-V00-0001 | SCREW, SELF DRILLING, HEX WASHER HEAD, STEEL, 5/16 X 1 INCH | 44483 | 2023-09-12 | 2023-10-15 | CLOSE | 1 | BX | 1 | 19.31 | 19.31 | 18060 | CLOSE | 2023-10-19 | 2023-10-18 | KW1-12397 | 29 | 2023-10-19 | APPR | 2023-10-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-26 | COMP | 2023-10-23 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
95 | 2023-09-12 | 150 | AJ22-0135 | T357 Relocation | 2141526 | 5975-60-V00-0484 | BOX CONNECTOR, ELECTRICAL, METALLIC CONDUIT, ZINC, 3/4 INCH | 44483 | 2023-09-12 | 2023-10-15 | CLOSE | 2 | EA | 100 | 3.33 | 333 | 18060 | CLOSE | 2023-10-19 | 2023-10-18 | KW1-12397 | 30 | 2023-10-19 | APPR | 2023-10-19 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-24 | COMP | 2023-10-25 | 100.00 |  | AJ | AJ table | September | 2023 | MM_AJ
96 | 2023-09-12 | 60 | AJ23-0747 | Technical Inspection Repairs, T5802 | 7162722 | 5305-60-V00-0032 | SCREW, DRYWALL, FLAT COUNTERSUNK, PHILLIPS, COARSE THREAD, #6 X 1-1/4 INCHES | 42166 | 2023-09-12 | 2023-09-17 | CLOSE | 1 | BX | 20 | 15.04 | 300.8 | 17013 | SENT | 2023-09-27 | 2023-09-20 | KW1-11867 | 4 | 2023-09-22 | CLOSE | 2023-10-03 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2023-09-30 | COMP | 2023-09-26 | 20.00 |  | AJ | AJ table | September | 2023 | MM_AJ
97 | 2023-09-12 | 50 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5440-05-V01-0009 | LADDER, SAFETY STEP, ROLLING, 3 STEPS, STEEL, 30 INCHES, 450 LBS | 42126 | 2023-09-12 | 2023-09-14 | CLOSE | 1 | EA | 2 | 616.44 | 1232.88 | 16967 | CLOSE | 2023-09-23 | 2023-09-18 | KW1-11811 | 11 | 2023-11-17 | APPR | 2023-11-17 | Kannoth, Shajee -Vectrus -GSD -No Export | RITAJ AL KUWAIT GENERAL TRADING CONTRACTING CO | 2023-11-15 | COMP | 2023-10-05 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
97 | 2023-09-12 | 50 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 7510-05-V00-0023 | TAPE, PRESSURE SENSITIVE ADHESIVE, ANTI-SLIP, BLACK, 4 INCHES X 33 FEET | 42126 | 2023-09-12 | 2023-09-14 | CLOSE | 2 | EA | 8 | 45 | 360 | 16967 | CLOSE | 2023-09-23 | 2023-09-18 | KW1-11811 | 12 | 2023-11-17 | APPR | 2023-11-17 | Kannoth, Shajee -Vectrus -GSD -No Export | RITAJ AL KUWAIT GENERAL TRADING CONTRACTING CO | 2023-11-15 | COMP | 2023-10-04 | 8.00 |  | AJ | AJ table | September | 2023 | MM_AJ
98 | 2023-09-13 | 150 | AJ22-0135 | T357 Relocation | 2141526 | 5315-60-V00-0058 | NAIL, FLAT, STAINLESS-STEEL, 2D X 1 INCH | 42202 | 2023-09-13 | 2023-09-14 | CLOSE | 1 | BX | 3 | 12.49 | 37.47 | 16964 | CLOSE | 2023-09-20 | 2023-09-18 | KW1-11832 | 42 | 2023-09-20 | APPR | 2023-09-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-27 03:00 | COMP | 2023-09-26 | 3.00 |  | AJ | AJ table | September | 2023 | MM_AJ
98 | 2023-09-13 | 150 | AJ22-0135 | T357 Relocation | 2141526 | 5315-60-V00-0057 | NAIL, FLAT, STAINLESS STEEL, 3D X 1-1/4 INCHES | 42203 | 2023-09-13 | 2023-09-14 | CLOSE | 1 | BX | 3 | 47.29 | 141.87 | 16964 | CLOSE | 2023-09-20 | 2023-09-18 | KW1-11832 | 43 | 2023-09-20 | APPR | 2023-09-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-27 03:00 | COMP | 2023-09-26 | 3.00 |  | AJ | AJ table | September | 2023 | MM_AJ
99 | 2023-09-13 | 70 | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 6145-60-V00-0093 | CABLE, POWER, ELECTRICAL, H07RN-F, BLACK, 5 CORE, 1.5 MM² | 42192 | 2023-09-13 | 2023-09-17 | CLOSE | 1 | MR | 20 | 10.23 | 204.6 | 17006 | CLOSE | 2023-09-22 | 2023-09-20 | KW1-11873 | 1 | 2023-09-22 | CLOSE | 2023-11-14 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-30 | COMP | 2023-09-26 | 20.00 |  | AJ | AJ table | September | 2023 | MM_AJ
100 | 2023-09-14 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 6530-60-V00-0021 | BASIN, WASH, w/ PEDESTAL, CERAMIC, WHITE, 54 X 20 X 46 CENTIMETERS | 42332 | 2023-09-14 | 2023-09-17 | CLOSE | 1 | EA | 1 | 107.97 | 107.97 | 17069 | CLOSE | 2023-09-28 | 2023-09-20 | KW1-12052 | 28 | 2023-11-17 | APPR | 2023-11-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | COMMERCIAL UNITED GINCO EST. | 2023-10-07 03:00 | COMP | 2023-10-04 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
100 | 2023-09-14 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0124 | FAUCET, LEVER, SINGLE, CHROME, BRASS, WASH BASIN MIXER | 41335 | 2023-09-14 | 2023-09-05 | CLOSE | 1 | EA | 1 | 59.51 | 119.02 | 16605 | CLOSE | 2023-09-13 | 2023-09-07 | KW1-11652 | 1 | 2023-09-13 | CLOSE | 2023-12-16 | Kandankara, Thomas -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-09-27 | COMP | 2023-09-18 | 2.00 |  | AJ | AJ table | September | 2023 | MM_AJ
100 | 2023-09-14 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0094 | TRAP, BOTTLE, ADJUSTABLE INLET, 1-1/4 INCHES | 41336 | 2023-09-14 | 2023-09-05 | CLOSE | 3 | EA | 1 | 14.09 | 14.09 | 16582 | CLOSE | 2023-09-09 | 2023-09-07 | KW1-11535 | 7 | 2023-09-09 | APPR | 2023-09-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | NS INTERNATIONAL CONTRACTING FOR ELECTRICAL CO WLL | 2023-09-16 03:00 | COMP | 2023-09-12 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
100 | 2023-09-14 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0017 | DISPENSER, SOAP, HORIZONTAL, STEEL, 1200 ML | 42329 | 2023-09-14 | 2023-09-17 | CLOSE | 2 | EA | 1 | 126.54 | 126.54 | 17069 | CLOSE | 2023-09-28 | 2023-09-20 | KW1-12052 | 25 | 2023-11-17 | APPR | 2023-11-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | COMMERCIAL UNITED GINCO EST. | 2023-10-07 03:00 | COMP | 2023-10-03 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
100 | 2023-09-14 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0110 | FAUCET, SINK, HOT AND COLD, GOOSE NECK | 42328 | 2023-09-14 | 2023-09-17 | CLOSE | 1 | EA | 1 | 174.83 | 174.83 | 17069 | CLOSE | 2023-09-28 | 2023-09-20 | KW1-12052 | 23 | 2023-11-17 | APPR | 2023-11-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | COMMERCIAL UNITED GINCO EST. | 2023-10-07 03:00 | COMP | 2023-10-04 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
100 | 2023-09-14 | 60 | AJ22-0135 | T357 Relocation | 2141526 | 7105-60-V00-0019 | MIRROR, GLASS, ROUND, WALL MOUNTED, WHITE, 50 CM | 42329 | 2023-09-14 | 2023-09-17 | CLOSE | 1 | EA | 3 | 19.65 | 58.95 | 17069 | CLOSE | 2023-09-28 | 2023-09-20 | KW1-12052 | 24 | 2023-11-17 | APPR | 2023-11-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | COMMERCIAL UNITED GINCO EST. | 2023-10-07 03:00 | COMP | 2023-10-04 | 3.00 |  | AJ | AJ table | September | 2023 | MM_AJ
100 | 2023-09-18 | 160 | AJ22-0135 | T357 Relocation | 2141526 | 5650-60-V00-0002 | ROOFING METAL, WHITE, 0.35 MM X 3 METER | 42572 | 2023-09-18 | 2023-09-25 | CLOSE | 1 | SH | 30 | 25.47 | 764.1 | 17327 | CLOSE | 2023-09-30 | 2023-09-27 | KW1-12081 | 1 | 2023-09-30 | CLOSE | 2023-11-14 | Vishwanath, Shet -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-21 | COMP | 2023-10-08 | 30.00 |  | AJ | AJ table | September | 2023 | MM_AJ
100 | 2023-09-20 | 160 | AJ22-0135 | T357 Relocation | 2141526 | 5940-60-V00-0003 | LUG, TERMINAL, FORK, INSULATED, BLUE, 16-14 AWG | 42817 | 2023-09-20 | 2023-09-28 | CLOSE | 1 | BG | 1 | 53.63 | 53.63 | 17397 | CLOSE | 2023-10-04 | 2023-10-01 | KW1-12130 | 7 | 2023-10-04 | CLOSE | 2023-11-14 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-12 | COMP | 2023-10-09 | 1.00 |  | AJ | AJ table | September | 2023 | MM_AJ
100 | 2023-09-20 | 160 | AJ22-0135 | T357 Relocation | 2141526 | 6145-60-V00-0093 | CABLE, POWER, ELECTRICAL, H07RN-F, BLACK, 5 CORE, 1.5 MM² | 42816 | 2023-09-20 | 2023-09-28 | CLOSE | 1 | MR | 90 | 27.31 | 2457.9 | 17508 | CLOSE | 2023-10-12 | 2023-10-02 | KW1-12261 | 3 | 2023-11-17 | APPR | 2023-11-17 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-19 | COMP | 2023-10-17 | 90.00 |  | AJ | AJ table | September | 2023 | MM_AJ
100 | 2023-09-20 | 160 | AJ22-0135 | T357 Relocation | 2141526 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 40905 | 2023-09-20 | 2023-09-02 | CLOSE | 5 | EA | 5 | 52.28 | 522.8 | 16434 | CLOSE | 2023-09-05 | 2023-09-04 | KW1-11435 | 5 | 2023-09-05 | CLOSE | 2023-10-24 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-09-19 | COMP | 2023-09-09 | 10.00 |  | AJ | AJ table | September | 2023 | MM_AJ
100 | 2023-09-20 | 160 | AJ22-0135 | T357 Relocation | 2141526 | 5930-60-V00-0254 | SWITCH, DOUBLE POLE, METAL CLAD, 1 GANG, 32A | 42816 | 2023-09-20 | 2023-09-28 | CLOSE | 3 | EA | 11 | 71.1 | 782.1 | 17508 | CLOSE | 2023-10-12 | 2023-10-02 | KW1-12261 | 5 | 2023-11-17 | APPR | 2023-11-17 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-19 | COMP | 2023-10-17 | 11.00 |  | AJ | AJ table | September | 2023 | MM_AJ
101 | 2023-09-20 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 3030-60-V00-0252 | BELT, V, RIBBED, RUBBER, 21.5 X 18 X 0.7 CENTIMETERS | 42764 | 2023-09-20 | 2023-09-28 | CLOSE | 1 | EA | 3 | 21.05 | 63.15 | 17467 | CLOSE | 2023-10-06 | 2023-10-01 | KW1-12158 | 5 | 2023-10-06 | APPR | 2023-10-06 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL BAYADER INTER.GROUP COMPANY | 2023-11-22 | COMP | 2023-10-11 | 3.00 |  | AJ | AJ table | September | 2023 | MM_AJ
101 | 2023-09-20 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8030-60-V00-0050 | PUTTY, WOOD FILLER, MEDIUM OAK, 250 ML | 42831 | 2023-09-20 | 2023-09-28 | CLOSE | 1 | CN | 3 | 68.27 | 204.81 | 17486 | CLOSE | 2023-10-05 | 2023-10-02 | KW1-12145 | 9 | 2023-10-05 | APPR | 2023-10-05 | Kannoth, Shajee -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2023-10-21 | COMP | 2023-10-19 | 3.00 |  | AJ | AJ table | September | 2023 | MM_AJ
102 | 2023-09-21 |  | AJ22-0135 | T357 Relocation | 2141526 | 8030-60-V00-0008 | SEALING COMPOUND, GUTTER & SEAM, WHITE, 10 OZ. | 42899 | 2023-09-21 | 2023-09-28 | CLOSE | 1 | CQ | 12 | 23.31 | 279.72 | 17511 | CLOSE | 2023-10-06 | 2023-10-02 | KW1-12161 | 1 | 2023-10-25 | APPR | 2023-10-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-10-30 | COMP | 2023-11-01 | 12.00 |  | AJ | AJ table | September | 2023 | MM_AJ
102 | 2023-10-01 |  | AJ22-0135 | T357 Relocation | 2141526 | 8010-60-V00-0050 | PAINT, ENAMEL, GLOSS, DARK BROWN, 3.2 AND 3.6 LITER | 43584 | 2023-10-01 | 2023-10-09 | CLOSE | 1 | CN | 6 | 39.96 | 239.76 | 17823 | CLOSE | 2023-10-19 | 2023-10-12 | KW1-12361 | 7 | 2023-10-17 | APPR | 2023-10-17 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-05 | COMP | 2023-11-07 | 6.00 |  | AJ | AJ table | October | 2023 | MM_AJ
103 | 2023-10-05 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 4140-60-V00-0120 | FAN, VENTILATING, SQUARE, 220V, 8 INCHES | 43886 | 2023-10-05 | 2023-10-10 | CLOSE | 1 | EA | 3 | 85.32 | 255.96 | 17855 | CLOSE | 2023-10-17 | 2023-10-12 | KW1-12375 | 1 | 2023-10-17 | CLOSE | 2023-11-14 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-10-31 | COMP | 2023-10-22 | 3.00 |  | AJ | AJ table | October | 2023 | MM_AJ
103 | 2023-10-08 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5315-60-V00-0057 | NAIL, FLAT, STAINLESS STEEL, 3D X 1-1/4 INCHES | 44114 | 2023-10-08 | 2023-10-15 | CLOSE | 1 | BX | 5 | 47.29 | 236.45 | 18112 | CLOSE | 2023-10-24 | 2023-10-19 | KW1-12486 | 1 | 2023-10-24 | APPR | 2023-10-24 | Bharadwajan, Sajan - Vectrus - No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2023-10-30 | COMP | 2023-10-28 | 5.00 |  | AJ | AJ table | October | 2023 | MM_AJ
103 | 2023-10-08 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5315-60-V00-0058 | NAIL, FLAT, STAINLESS-STEEL, 2D X 1 INCH | 44114 | 2023-10-08 | 2023-10-15 | CLOSE | 2 | BX | 5 | 13.65 | 68.25 | 18112 | CLOSE | 2023-10-24 | 2023-10-19 | KW1-12486 | 2 | 2023-10-24 | APPR | 2023-10-24 | Bharadwajan, Sajan - Vectrus - No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2023-10-30 | COMP | 2023-10-28 | 5.00 |  | AJ | AJ table | October | 2023 | MM_AJ
103 | 2023-10-08 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5510-60-V00-0028 | PLYWOOD, CONSTRUCTION, MARINE GRADE, 1/2 INCH X 8 X 4 FEET | 44115 | 2023-10-08 | 2023-10-15 | CLOSE | 1 | SH | 10 | 58.28 | 582.8 | 18112 | CLOSE | 2023-10-24 | 2023-10-19 | KW1-12486 | 3 | 2023-10-24 | APPR | 2023-10-24 | Bharadwajan, Sajan - Vectrus - No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2023-10-30 | COMP | 2023-10-28 | 10.00 |  | AJ | AJ table | October | 2023 | MM_AJ
103 | 2023-10-08 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 8040-60-V00-0033 | ADHESIVE, RESIN, SYNTHETIC, WHITE, 5 KG | 44144 | 2023-10-08 | 2023-10-15 | CLOSE | 1 | CN | 3 | 26.64 | 79.92 | 18112 | CLOSE | 2023-10-24 | 2023-10-19 | KW1-12486 | 4 | 2023-10-24 | APPR | 2023-10-24 | Bharadwajan, Sajan - Vectrus - No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2023-10-30 | COMP | 2023-10-28 | 3.00 |  | AJ | AJ table | October | 2023 | MM_AJ
104 | 2023-10-15 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0102 | COVER, DRAIN, w/HOLE, SQUARE, METAL, 6 X 6 INCHES | 44761 | 2023-10-15 | 2023-10-16 | CLOSE | 1 | EA | 2 | 20.46 | 40.92 | 18082 | CLOSE | 2023-11-01 | 2023-10-19 | KW1-12689 | 10 | 2023-11-01 | APPR | 2023-11-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-11-07 | COMP | 2023-11-05 | 2.00 |  | AJ | AJ table | October | 2023 | MM_AJ
104 | 2023-10-15 |  | AJ22-0135 | T357 Relocation | 2141526 | 4730-60-V00-0304 | COUPLING, DRAINAGE PIPE, (PAN CONNECTOR), POLYPROPYLENE, WHITE, 4 INCHES X 110 MM | 44760 | 2023-10-15 | 2023-10-16 | CLOSE | 1 | EA | 4 | 15.04 | 60.16 | 18082 | CLOSE | 2023-11-01 | 2023-10-19 | KW1-12689 | 8 | 2023-11-01 | APPR | 2023-11-01 | Reghunath, Rajesh -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-11-07 | COMP | 2023-11-05 | 4.00 |  | AJ | AJ table | October | 2023 | MM_AJ
105 | 2023-10-15 |  | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | 5340-60-V00-0169 | LOCK SET, MORTISE, RIM EXIT DEVICE, KEY OUTSIDE UNLOCKS/LOCKS TRIM | 44762 | 2023-10-15 | 2023-10-16 | CLOSE | 1 | EA | 1 | 2317.61 | 2317.61 | 18098 | CLOSE | 2023-10-29 | 2023-10-19 | KW1-12624 | 1 | 2023-10-29 | APPR | 2023-10-29 | Reghunath, Rajesh -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2023-11-05 | COMP | 2023-11-02 | 1.00 |  | AJ | AJ table | October | 2023 | MM_AJ
106 | 2023-10-18 |  | AJ22-0152 | Vectrus T572 Relocation | 2671736 | 5510-60-V00-0031 | WOOD, SOLID, MOULDING/ DECORATIVE, NATURAL, 1/2 X 2 INCHES X 10 FEET | 45096 | 2023-10-18 | 2023-10-22 | CLOSE | 1 | EA | 25 | 25.83 | 645.75 | 18243 | CLOSE | 2023-10-29 | 2023-10-23 | KW1-12638 | 7 | 2023-10-29 | APPR | 2023-10-29 | Bharadwajan, Sajan - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2023-11-03 | COMP | 2023-11-04 | 25.00 |  | AJ | AJ table | October | 2023 | MM_AJ
107 | 2023-10-22 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0883 | CAP, PROTECTIVE (COVER CAP), PUSH FITTING, PLASTIC, LIGHT GREY, 15 MM | 45319 | 2023-10-22 | 2023-11-01 | CLOSE | 1 | EA | 200 | 0.14 | 28 | 18566 | CLOSE | 2023-11-03 | 2023-11-02 | KW1-12736 | 5 | 2023-11-03 | APPR | 2023-11-03 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-11-17 | COMP | 2023-11-08 | 200.00 |  | AJ | AJ table | October | 2023 | MM_AJ
107 | 2023-10-28 |  | AJ22-0135 | T357 Relocation | 2141526 | 8010-60-V00-0238 | PAINT, LATEX, GLOSSY, BRIGHT WHITE, 1 GL | 45847 | 2023-10-28 | 2023-11-01 | CLOSE | 1 | GL | 12 | 39.96 | 479.52 | 18543 | CLOSE | 2023-11-03 | 2023-11-02 | KW1-12735 | 5 | 2023-11-17 | APPR | 2023-11-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2023-11-11 | COMP | 2023-11-13 | 12.00 |  | AJ | AJ table | October | 2023 | MM_AJ
107 | 2023-10-29 |  | AJ22-0135 | T357 Relocation | 2141526 | 5930-60-V00-0246 | SWITCH, WEATHERPROOF, GRAY, 1 GANG, 16 A | 45910 | 2023-10-29 | 2023-11-04 | CLOSE | 1 | EA | 5 | 21.15 | 105.75 | 18674 | CLOSE | 2023-11-15 |  | KW1-12993 | 1 | 2023-11-15 | APPR | 2023-11-15 | Reghunath, Rajesh -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-20 | COMP | 2023-11-19 | 5.00 |  | AJ | AJ table | October | 2023 | MM_AJ
107 | 2023-10-30 |  | AJ22-0135 | T357 Relocation | 2141526 | 5210-60-V00-0040 | CHALK LINE AND REEL, w/ BLUE CHALK, 100 FEET | 45917 | 2023-10-30 | 2023-11-05 | CLOSE | 1 | EA | 5 | 43.96 | 219.8 |  |  |  |  | KW1-12801 | 5 | 2023-11-17 | APPR | 2023-11-17 | Thomas, Vinu - Vectrus -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-20 | COMP | 2023-11-21 | 5.00 |  | AJ | AJ table | October | 2023 | MM_AJ
107 | 2023-10-30 |  | AJ22-0135 | T357 Relocation | 2141526 | 5670-60-V00-0026 | WALL ANGLE / GRID, CEILING, TEE, GALVANIZED STEEL, WHITE, 12 FEET | 45939 | 2023-10-30 | 2023-11-05 | CLOSE |  | EA | 50 | 18.48 | 924 | 18706 | CLOSE | 2023-11-10 | 2023-11-08 | KW1-12881 | 6 | 2023-11-10 | APPR | 2023-11-10 | Thomas, Vinu - Vectrus -No Export | CREDENCE TRADING EST. | 2023-11-16 | COMP | 2023-11-15 | 50.00 |  | AJ | AJ table | October | 2023 | MM_AJ
107 | 2023-11-01 |  | AJ22-0135 | T357 Relocation | 2141526 | 4020-60-V00-0004 | TWINE, NYLON, FLOURESCENT YELLOW, 500 FEET | 46216 | 2023-11-01 | 2023-11-05 | CLOSE |  | RO | 5 | 21.45 | 107.25 | 18708 | SENT | 2023-11-07 | 2023-11-08 | KW1-12883 | 9 | 2023-11-10 | APPR | 2023-11-10 | Thomas, Vinu - Vectrus -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-12-10 | COMP | 2023-12-07 | 5.00 |  | AJ | AJ table | November | 2023 | MM_AJ
107 | 2023-11-06 |  | AJ22-0135 | T357 Relocation | 2141526 | 6210-60-V00-0136 | LIGHT UNIT, EMERGENCY, (EXIT LIGHT), LED, 120-277 V, 50/60 HZ, 2 W | 46744 | 2023-11-06 | 2023-11-08 | CLOSE | 1 | EA | 6 | 134.07 | 804.42 | 18809 | CLOSE | 2023-11-15 | 2023-11-12 | KW1-13012 | 12 | 2023-11-16 | APPR | 2023-11-16 | Thomas, Vinu - Vectrus -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-22 | COMP | 2023-11-20 | 6.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 5120-60-V00-0267 | KNIFE, PUTTY, STAINLESS STEEL, BLACK/BLUE, 5 INCHES | 46722 | 2023-11-08 | 2023-11-19 | CLOSE | 1 | EA | 3 | 16.48 | 49.44 | 19144 | CLOSE | 2023-11-30 | 2023-11-22 | KW1-13216 | 4 | 2023-11-23 | APPR | 2023-11-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-11-28 | COMP | 2023-11-27 | 3.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 4240-60-V00-0121 | TAPE, WARNING, BARRICADE, "CAUTION", YELLOW/BLACK | 46722 | 2023-11-08 | 2023-11-19 | CLOSE | 2 | RL | 1 | 185.31 | 185.31 | 19144 | CLOSE | 2023-11-30 | 2023-11-22 | KW1-13216 | 5 | 2023-11-23 | APPR | 2023-11-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-11-28 | COMP | 2023-11-26 | 1.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8105-01-175-5533 | BAG, PLASTIC, NATURAL, 24 X 24 INCHES, 7-10 GL | 46728 | 2023-11-08 | 2023-11-08 | CLOSE | 1 | BX | 2 | 92.57 | 185.14 | 18852 | CLOSE | 2023-11-10 |  | KW1-12884 | 39 | 2023-11-13 | APPR | 2023-11-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-24 | COMP | 2023-11-15 | 2.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 5345-60-V00-0007 | DISK, ABRASIVE, SANDING, GOLD, 100 GRIT, 6 INCHES | 46731 | 2023-11-08 | 2023-11-09 | CLOSE | 2 | RO | 5 | 77.55 | 387.75 | 18889 | CLOSE | 2023-11-15 | 2023-11-13 | KW1-13011 | 2 | 2023-11-15 | APPR | 2023-11-15 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-12-24 | COMP | 2023-12-05 | 5.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8415-01-013-7382 | GLOVES, CHEMICAL AND OIL PROTECTION, GREEN, SIZE 10 | 46727 | 2023-11-08 | 2023-11-08 | CLOSE | 1 | PR | 20 | 31.5 | 630 | 18787 | CLOSE | 2023-11-12 | 2023-11-11 | KW1-12926 | 12 | 2023-11-12 | APPR | 2023-11-12 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-25 | COMP | 2023-12-05 | 20.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8415-01-610-7322 | GLOVES, IMPACT, LEATHER, BLACK, X-SMALL | 46731 | 2023-11-08 | 2023-11-09 | CLOSE | 3 | PR | 6 | 99.42 | 596.52 | 18889 | CLOSE | 2023-11-15 | 2023-11-13 | KW1-13011 | 3 | 2023-11-15 | APPR | 2023-11-15 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-11-30 | COMP | 2023-11-29 | 6.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 4240-01-463-5449 | RESPIRATOR, PARTICULATE, DISPOSABLE | 46725 | 2023-11-08 | 2023-11-08 | CLOSE | 1 | BX | 3 | 44.12 | 132.36 | 18907 | CLOSE | 2023-11-16 | 2023-11-15 | KW1-13025 | 3 | 2023-11-19 | APPR | 2023-11-19 | Kandankara, Thomas -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-12-07 | COMP | 2023-11-23 | 3.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 7920-60-V00-0039 | MOP, DUST, W/HANDLE, SWIVEL HEAD, LEIGHT WEIGHT, 24 X 60 INCHES | 46726 | 2023-11-08 | 2023-11-08 | CLOSE | 1 | EA | 4 | 81.59 | 326.36 | 18787 | CLOSE | 2023-11-12 | 2023-11-11 | KW1-12926 | 11 | 2023-11-12 | APPR | 2023-11-12 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-21 | COMP | 2023-11-16 | 4.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 7920-00-148-9666 | RAG, WIPING, COTTON (MIXED COLOR), 50LB | 46728 | 2023-11-08 | 2023-11-08 | CLOSE | 2 | BE | 1 | 72.26 | 72.26 | 18787 | CLOSE | 2023-11-12 | 2023-11-11 | KW1-12926 | 13 | 2023-11-12 | APPR | 2023-11-12 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-25 | COMP | 2023-11-15 | 1.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 7510-00-266-6707 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 3 INCHES X 60 YARDS | 46729 | 2023-11-08 | 2023-11-08 | CLOSE | 1 | RO | 30 | 21.5 | 645 | 18873 | CLOSE | 2023-11-10 |  | KW1-12899 | 1 | 2023-11-10 | APPR | 2023-11-11 | Santhumayor, Santhosh - Vectrus - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-01-19 | COMP | 2023-11-13 | 30.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8020-00-260-1302 | BRUSH, PAINT, BRISTLES, CHISELED, 2 INCHES | 46730 | 2023-11-08 | 2023-11-08 | CLOSE | 1 | EA | 25 | 13.1 | 327.5 | 18789 | CLOSE | 2023-11-10 | 2023-11-08 | KW1-12892 | 7 | 2023-11-10 | APPR | 2023-11-10 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2023-11-18 | COMP | 2023-11-14 | 25.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 46730 | 2023-11-08 | 2023-11-08 | CLOSE | 2 | EA | 50 | 13.9 | 695 | 18789 | CLOSE | 2023-11-10 | 2023-11-08 | KW1-12892 | 8 | 2023-11-10 | APPR | 2023-11-10 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2023-11-22 | COMP | 2023-11-22 | 50.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 46724 | 2023-11-08 | 2023-11-08 | CLOSE | 1 | EA | 20 | 29.3 | 586 |  |  |  |  | KW1-12860 | 5 | 2023-11-08 | APPR | 2023-11-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-12 | COMP | 2023-11-12 | 20.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 5120-60-V00-0276 | DISPENSER, SEALANT, RED, 500 ML | 46723 | 2023-11-08 | 2023-11-08 | CLOSE | 1 | EA | 2 | 276.89 | 553.78 | 18787 | CLOSE | 2023-11-12 | 2023-11-11 | KW1-12926 | 10 | 2023-11-12 | APPR | 2023-11-12 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-11-30 | COMP | 2023-11-27 | 2.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8030-60-V00-0081 | PUTTY, MULTI PURPOSE, PLASTIC, GRAY, 1-QUART | 46725 | 2023-11-08 | 2023-11-08 | CLOSE | 2 | CN | 5 | 141.53 | 707.65 | 18907 | CLOSE | 2023-11-16 | 2023-11-15 | KW1-13025 | 4 | 2023-11-19 | APPR | 2023-11-19 | Kandankara, Thomas -Vectrus -GSD -No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2023-11-30 | COMP | 2023-11-29 | 5.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8040-60-V00-0020 | ADHESIVE, INJECTABLE MORTAR, HYBRID, ANCHORING SYSTEM, GREY/WHITE, 500ML | 46722 | 2023-11-08 | 2023-11-19 | CLOSE | 3 | PG | 20 | 104.73 | 2094.6 | 19144 | CLOSE | 2023-11-30 | 2023-11-22 | KW1-13216 | 6 | 2023-11-23 | APPR | 2023-11-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-11-28 | COMP | 2023-11-29 | 20.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8010-60-V00-0091 | EPOXY PRIMER COATING, CLEAR, GALLON | 46722 | 2023-11-08 | 2023-11-19 | CLOSE | 4 | GL | 4 | 193.14 | 772.56 | 19144 | CLOSE | 2023-11-30 | 2023-11-22 | KW1-13216 | 7 | 2023-11-23 | APPR | 2023-11-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-06 | COMP | 2023-11-27 | 4.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8010-60-V00-0100 | EPOXY COATING KIT, GRAY, PART A&B, 20 LITER | 46722 | 2023-11-08 | 2023-11-19 | CLOSE | 5 | KT | 9 | 243.92 | 2195.28 | 19144 | CLOSE | 2023-11-30 | 2023-11-22 | KW1-13216 | 8 | 2023-11-23 | APPR | 2023-11-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-11-28 | COMP | 2023-11-26 | 9.00 |  | AJ | AJ table | November | 2023 | MM_AJ
108 | 2023-11-08 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8415-60-V00-0336 | SUIT, CHEMICAL PROTECTIVE, WHITE, XL | 46782 | 2023-11-08 | 2023-11-15 | CAN | 1 | CA | 4 | 1084.99 | 4339.96 | [14 empty] | CAN |  | AJ | AJ table | November | 2023 | MM_AJ
109 | 2023-11-08 | 30 | AJ23-0508 | Bay 3 Floor Painting | 7971778 | 3895-60-V00-0006 | MIXER, PAINT, STEEL, 4 X 23-1/2 INCHES | 46731 | 2023-11-08 | 2023-11-09 | CLOSE | 1 | EA | 3 | 10.39 | 31.17 | 18889 | CLOSE | 2023-11-15 | 2023-11-13 | KW1-13011 | 1 | 2023-11-15 | APPR | 2023-11-15 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-11-22 | COMP | 2023-11-19 | 3.00 |  | AJ | AJ table | November | 2023 | MM_AJ
110 | 2023-11-09 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 7930-05-V00-0002 | CLEANER, ALL PURPOSE, LIQUID, ALCOHOL, PK2, GREEN, 1GAL | 47114 | 2023-11-09 | 2023-11-09 | CLOSE | 1 | PK | 3 | 11.4 | 34.2 | 18889 | CLOSE | 2023-11-15 | 2023-11-13 | KW1-13011 | 13 | 2023-11-15 | APPR | 2023-11-15 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2023-12-13 | COMP | 2023-11-21 | 3.00 |  | AJ | AJ table | November | 2023 | MM_AJ
110 | 2023-11-09 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 5110-05-V01-0010 | KNIFE, PUTTY, STEEL, 4 INCHES | 47115 | 2023-11-09 | 2023-11-15 |  | 13 | EA | 5 | [6 empty] | KW1-12994 | 13 | [5 empty] | 2023-11-15 |  |  |  |  | AJ | AJ table | November | 2023 | MM_AJ
112 | 2023-11-12 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 8415-60-V00-0352 | COVERALLS, DISPOSABLE PROTECTIVE, TYVEK400, WHITE, XL | 47327 | 2023-11-12 | 2023-11-15 |  | 5 | BX | 2 | [6 empty] | KW1-13276 | 5 | [5 empty] | 2023-11-25 |  |  |  |  | AJ | AJ table | November | 2023 | MM_AJ
112 | 2023-11-12 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 4240-60-V00-0143 | RESPIRATOR, AIR FILTERING, REUSABLE, MEDIUM | 47327 | 2023-11-12 | 2023-11-15 |  | 6 | BX | 1 | [6 empty] | KW1-13276 | 6 | [5 empty] | 2023-11-25 |  |  |  |  | AJ | AJ table | November | 2023 | MM_AJ
112 | 2023-12-24 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 4240-60-V00-0093 | RETAINER, PREFILTER, RESPIRATOR, POLYPROPYLENE, TRANSLUCENT WHITE, 8.5 X 4.5 X 4 INCHES | 50489 | 2023-12-24 | 2023-12-25 | CLOSE | 1 | BX | 1 | 251.82 | 251.82 | 20354 | CLOSE | 2024-01-15 | 2024-01-10 | KW1-14235 | 3 | 2024-01-15 | APPR | 2024-01-15 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-11 | COMP | 2024-01-21 | 1.00 |  | AJ | AJ table | December | 2023 | MM_AJ
112 | 2023-12-24 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 4240-01-342-2857 | CARTRIDGE, RESPIRATOR, AIR FILTERING, 3.4 X 4.2 INCHES | 50488 | 2023-12-24 | 2023-12-25 | CLOSE | 1 | PG | 1 | 759.2 | 759.2 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 28 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-11 | COMP | 2024-01-20 | 1.00 |  | AJ | AJ table | December | 2023 | MM_AJ
112 | 2023-12-24 | 30 | AJ23-0747 | Bay 3 Floor Painting | 7971778 | 4240-60-V00-0004 | FILTER, RESPIRATOR, AIR FILTERING, PARTICULATE, 3.4 X 4.2 INCHES | 50487 | 2023-12-24 | 2023-12-25 | CLOSE | 1 | BX | 1 | 27.64 | 55.28 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 27 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 2.00 |  | AJ | AJ table | December | 2023 | MM_AJ
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0891 | STRIKE AND KEEPER, INSWING, STAINLESS STEEL, SATIN, 3/4 X 1-1/2 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 24 | EA | 2 | 43.5 | 87 | 19396 | CLOSE | 2023-11-30 |  | KW1-13396 | 6 | 2023-11-30 | CLOSE | 2024-01-09 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-24 | COMP | 2023-12-24 | 2.00 |  | AJ | AJ table | November | 2023 | MM_AJ
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0892 | LATCH, SLIDE, SURFACE MOUNTED, ZAMAC, POLISHED CHROME, 3-1/2 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 23 | EA | 2 | 16.5 | 33 | 19396 | CLOSE | 2023-11-30 |  | KW1-13396 | 5 | 2023-11-30 | CLOSE | 2024-01-09 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-24 | COMP | 2023-12-24 | 2.00 |  | AJ | AJ table | November | 2023 | MM_AJ
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0893 | DOORSTOP, ZAMAC, POLISHED CHROME, 2-1/8 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 22 | EA | 1 | 5 | 5 | 19396 | CLOSE | 2023-11-30 |  | KW1-13396 | 4 | 2023-11-30 | CLOSE | 2024-01-09 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-24 | COMP | 2023-12-24 | 1.00 |  | AJ | AJ table | November | 2023 | MM_AJ
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0894 | COVER STRIP (PRIVACY STRIP), ALUMINIUM, OFFSET, 1/8 X 60 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 21 | EA | 8 | 16.5 | 132 | 19396 | CLOSE | 2023-11-30 |  | KW1-13396 | 3 | 2023-11-30 | CLOSE | 2024-01-09 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-24 | COMP | 2023-12-30 | 8.00 |  | AJ | AJ table | November | 2023 | MM_AJ
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0887 | BRACKET, MOUNTING(U-BRACKET), STAINLESS STEEL, SATIN, 3/4 X 54 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 20 | EA | 10 | 99.5 | 995 | 19396 | CLOSE | 2023-11-30 |  | KW1-13396 | 2 | 2023-11-30 | CLOSE | 2024-01-09 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-24 | COMP | 2023-12-25 | 10.00 |  | AJ | AJ table | November | 2023 | MM_AJ
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0888 | BRACKET, MOUNTING(H-BRACKET), STAINLESS STEEL, 3/4 X 57 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 19 | EA | 8 | 235 | 1880 | 19396 | CLOSE | 2023-11-30 |  | KW1-13396 | 1 | 2023-11-30 | CLOSE | 2024-01-09 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-24 | COMP | 2023-12-25 | 8.00 |  | AJ | AJ table | November | 2023 | MM_AJ
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0889 | BRACKET, MOUNTING, WALL, HINGED, STAINLESS STEEL, SATIN, 3/4 X 3 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 18 | EA | 4 | 40 | 160 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 22 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-24 | COMP | 2023-12-24 | 4.00 |  | AJ | AJ table | November | 2023 | MM_AJ
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5340-60-V00-0890 | BRACKET, MOUNTING (WALL BRACKET), TWO EAR, STAINLESS STEEL, SATIN, 3/4 X 57 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 17 | EA | 4 | 253.5 | 1014 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 21 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-24 | COMP | 2024-01-07 | 4.00 |  | AJ | AJ table | November | 2023 | MM_AJ
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5530-60-V00-0006 | PLYWOOD, DECOR, MELAMINE, 18MM X 4 X 8 FEET | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 16 | EA | 5 | 26 | 130 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 20 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-05 | 5.00 |  | AJ | AJ table | November | 2023 | MM_AJ
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5305-60-V00-0054 | SCREW, TAPPING, TRUSS HEAD, PHILLIPS, STAINLESS STEEL, #8 X 1/2 INCHES | 48350 | 2023-11-26 | 2023-11-27 | CLOSE | 1 | BG | 2 | 28 | 56 | 19316 | CLOSE | 2023-11-28 |  | KW1-13345 | 2 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-01 | 2.00 |  | AJ | AJ table | November | 2023 | MM_AJ
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 5640-60-V00-0072 | SHEET, WALL, ACRYLIC, WHITE, PLEXIGLASS, 1/4 X 24 X 96 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 15 | EA | 3 | 336.86 | 1010.58 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 19 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 3.00 |  | AJ | AJ table | November | 2023 | MM_AJ
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 7230-00-849-9839 | CURTAIN, SHOWER, VINYL FILM, PLASTIC, WHITE, 36 X 72 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 14 | EA | 1 | 11.79 | 11.79 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 18 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-24 | COMP | 2023-12-05 | 1.00 |  | AJ | AJ table | November | 2023 | MM_AJ
113 | 2023-11-26 |  | AJ22-0135 | T357 Relocation | 2141526 | 4510-60-V00-0143 | ROD, SHOWER CURTAIN, EXTENDABLE, ALUMINIUM ALLOY, WHITE, 25 X 25 MM X 2.2 METERS | 48355 | 2023-11-26 | 2023-11-27 | CLOSE | 5 | EA | 1 | 22.8 | 22.8 | 19316 | CLOSE | 2023-11-28 |  | KW1-13339 | 9 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-10 | COMP | 2023-12-01 | 1.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 8040-60-V00-0040 | CEMENT, HEAVY BODIED, CPVC, ORANGE, 16 OZ | 48353 | 2023-11-26 | 2023-11-27 | CLOSE | 2 | CN | 1 | 17.99 | 17.99 | 19316 | CLOSE | 2023-11-28 |  | KW1-13339 | 4 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-10 | COMP | 2023-12-01 | 1.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4510-60-V00-0001 | SHOWER FLOOR, MOLDED STONE, WHITE, 6 X 36 X 36 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 13 | EA | 1 | 208.49 | 208.49 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 17 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-05 | 1.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-1715 | END CAP, SOCKET, CPVC, OFF WHITE, 32 MM | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 7 | EA | 6 | 5.85 | 35.1 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 11 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 6.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-0862 | ELBOW, PIPE, CPVC, BRASS, STANDARD, 90 °, SOCKET X SOCKET, PN25, OFF-WHITE, 20 MM | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 12 | EA | 6 | 7.37 | 44.22 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 16 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 6.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-1714 | SOCKET, PIPE, PVC, GRAY, 1-1/2 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 6 | EA | 6 | 5.51 | 33.06 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 10 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 6.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-1091 | ELBOW, PIPE, CPVC, 45 DEGREE, SOCKET X SOCKET, 25 MM | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 11 | EA | 10 | 2.9 | 29 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 15 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 10.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4710-60-V00-0164 | PIPE, PLASTIC, PVC, GRAY, 1-1/2 INCHES X 6 METERS | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 5 | EA | 1 | 25.77 | 25.77 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 9 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 1.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-0850 | ELBOW, CPVC, SOCKET X SOCKET, SCH 40, OFF-WHITE, 25 MM | 48354 | 2023-11-26 | 2023-11-27 | CLOSE | 5 | EA | 7 | 3.63 | 25.41 | 19316 | CLOSE | 2023-11-28 |  | KW1-13345 | 7 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-01 | 7.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-1716 | REDUCER, PIPE (NIPPLE), MALE X FEMALE, BRASS, 3/4 X 1/2 INCHES X 15MM | 48357, 48400 | 2023-11-26 | 2023-11-27 |  | 4 | EA | 6 | [6 empty] | KW1-13395 | 8 | [5 empty] | 2023-12-10 | COMP | 2023-12-04 | 6 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-0759 | ADAPTER, PRESSURE FITTINGS, FEMALE, CPVC, STANDARD, SOCKET X SR FIPT, SCH- 40, OFF-WHITE, 25 MM | 48352 | 2023-11-26 | 2023-11-27 | CLOSE | 2 | EA | 4 | 3.63 | 14.52 | 19316 | CLOSE | 2023-11-28 |  | KW1-13345 | 3 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-01 | 4.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 48354 | 2023-11-26 | 2023-11-27 | CLOSE | 2 | BX | 10 | 29 | 290 | 19316 | CLOSE | 2023-11-28 |  | KW1-13345 | 5 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-01 | 10.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-0940 | TEE, PIPE, SOCKET X SOCKET X SOCKET, CPVC, OFF-WHITE, SCH 40, 25 MM | 48354 | 2023-11-26 | 2023-11-27 | CLOSE | 4 | EA | 4 | 7.2 | 28.8 | 19316 | CLOSE | 2023-11-28 |  | KW1-13345 | 6 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-01 | 4.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 48355 | 2023-11-26 | 2023-11-27 | CLOSE | 4 | EA | 10 | 13.9 | 139 | 19316 | CLOSE | 2023-11-28 |  | KW1-13339 | 8 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-10 | COMP | 2023-12-01 | 10.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4510-60-V00-0049 | TRAP, BOTTLE, ADJUSTABLE INLET, WHITE, 1-1/2 INCHES | 48349 | 2023-11-26 | 2023-11-27 | CLOSE | 2 | EA | 1 | 22.73 | 22.73 | 19316 | CLOSE | 2023-11-28 |  | KW1-13339 | 2 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-10 | COMP | 2023-12-01 | 1.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 9515-60-V00-0016 | SHEET, METAL, ALUMINIUM, FLAT, 4 X 8 FEET X 1/16 INCH | 48352 | 2023-11-26 | 2023-11-27 | CLOSE | 1 | SH | 3 | 86.66 | 259.98 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 4 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 3.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4510-60-V00-0094 | TRAP, BOTTLE, ADJUSTABLE INLET, 1-1/4 INCHES | 48354 | 2023-11-26 | 2023-11-27 | CLOSE | 3 | EA | 1 | 18.98 | 18.98 | 19316 | CLOSE | 2023-11-28 |  | KW1-13352 | 1 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2023-12-24 | COMP | 2023-12-01 | 1.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 48355 | 2023-11-26 | 2023-11-27 | CLOSE | 3 | BX | 1 | 141.9 | 141.9 | 19316 | CLOSE | 2023-11-28 |  | KW1-13339 | 7 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-10 | COMP | 2023-12-01 | 1.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-1708 | REDUCER, BOSS (REDUCER BUSH), PVC, GRAY, 1-1/4 X 1-1/2 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 10 | EA | 2 | 4.38 | 8.76 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 14 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 2.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GL | 48353 | 2023-11-26 | 2023-11-27 | CLOSE | 1 | GL | 5 | 227.7 | 1138.5 | 19316 | CLOSE | 2023-11-28 |  | KW1-13339 | 3 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-10 | COMP | 2023-12-01 | 5.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-1709 | REDUCER, PIPE, BUSHING, PVC, GRAY, 1-1/2 X 1-1/4 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 9 | EA | 2 | 4.38 | 8.76 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 13 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 2.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 5640-60-V00-0005 | WEATHER STRIP, THRESHOLD, ALUMINUM, 3.2 X 6.4 X 12.7 X 127.0 MM | 48351 | 2023-11-26 | 2023-11-27 | CLOSE | 2 | EA | 1 | 16.02 | 16.02 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 3 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-14 | COMP | 2023-12-04 | 1.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-1711 | ADAPTER, STRAIGHT, THREAD, PVC, GRAY, 1-1/4 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 8 | EA | 2 | 5.84 | 11.68 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 12 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 2.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 5340-60-V00-0492 | STOPPER, DOOR, DROP DOWN, METAL, 5" | 48354 | 2023-11-26 | 2023-11-27 | CLOSE | 1 | EA | 1 | 19.47 | 19.47 | 19316 | CLOSE | 2023-11-28 |  | KW1-13345 | 4 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-01 | 1.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-60-V00-1710 | ADAPTER, STRAIGHT, THREAD, PVC, GRAY, 1-1/2 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 1 | EA | 2 | 6 | 12 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 5 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 2.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 8030-60-V00-0053 | FOAM, CONSTRUCTION, CREAM, 700ML | 48355 | 2023-11-26 | 2023-11-27 | CLOSE | 2 | EA | 15 | 19.5 | 292.5 | 19316 | CLOSE | 2023-11-28 |  | KW1-13339 | 6 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-10 | COMP | 2023-12-01 | 15.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-00-162-2560 | ELBOW, PIPE, PVC, 90°, SOCKET X SOCKET, SCH 80, GRAY, 1-1/2 INCHES | 48356 | 2023-11-26 | 2023-11-27 | CLOSE | 1 | TE | 1 | 43.9 | 43.9 | 19316 | CLOSE | 2023-11-28 |  | KW1-13345 | 8 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-01 | 1.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 5305-60-V00-0174 | SCREW, HEX, STEEL, w/ RUBBER WASHER, # 14 X 2 ½ INCHES | 48349 | 2023-11-26 | 2023-11-27 | CLOSE | 1 | BX | 4 | 37.77 | 151.08 | 19316 | CLOSE | 2023-11-28 |  | KW1-13345 | 1 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-01 | 4.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 8030-60-V00-0017 | COATING COMPOUND, PROTECTIVE, 900 CERAMIC FINISH, WHITE, 5 GL | 48348 | 2023-11-26 | 2023-11-27 | CLOSE | 1 | CN | 3 | 236.58 | 709.74 | 19316 | CLOSE | 2023-11-28 |  | KW1-13339 | 1 | 2023-11-28 | APPR | 2023-11-28 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-10 | COMP | 2023-12-02 | 3.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 5975-60-V00-0413 | ANCHOR, PLASTIC, BUTTERFLY, WHITE, 6MM | 48355 | 2023-11-26 | 2023-11-27 |  | 1 | BX | 5 | [6 empty] | KW1-13339 | 5 | [5 empty] | 2023-12-10 | COMP | 2023-12-01 | 5 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 5305-60-V00-0155 | SCREW, DRYWALL, PHILLIPS, BUGLE HEAD, STEEL, #6 X 1-5/8 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 3 | BX | 1 | 14.85 | 14.85 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 7 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 1.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 5305-60-V00-0220 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, STEEL, #6 X 2 INCHES | 48357 | 2023-11-26 | 2023-11-27 | CLOSE | 2 | BX | 1 | 52 | 52 | 19315 | CLOSE | 2023-11-30 | 2023-11-30 | KW1-13395 | 6 | 2023-11-30 | APPR | 2023-11-30 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-10 | COMP | 2023-12-04 | 1.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-26 |  | AJ23-0508 | T357 Relocation | 2141526 | 9320-60-V00-0007 | TAPE, ADHESIVE, RUBBER, BUTYL, 4 INCHES X 50 FEET | 48351 | 2023-11-26 | 2023-11-27 |  | 1 | EA | 20 | [6 empty] | KW1-13395 | 3 | [5 empty] | 2023-12-24 |  |  |  |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-27 |  | AJ23-0508 | T357 Relocation | 2141526 | 4730-00-201-8409 | ELBOW, PIPE, PVC, 45°, SOCKET X SOCKET, SCH 80, GRAY, 1-1/2 INCHES | 48388 | 2023-11-27 | 2023-11-30 | CLOSE | 2 | EA | 6 | 5.12 | 30.72 | 19411 | CLOSE | 2023-12-06 | 2023-12-03 | KW1-13514 | 4 | 2023-12-06 | APPR | 2023-12-06 | Thomas, Vinu - Vectrus -No Export | MARATHON INC TRADING LLC | 2023-12-13 | COMP | 2023-12-09 | 6.00 |  | AJ | AJ table | November | 2023 | MM_AJ
114 | 2023-11-27 |  | AJ23-0508 | T357 Relocation | 2141526 | 4510-05-V00-0042 | DISH SOAP, STAINESS STEEL, SILVER, 2.25 X 5 X 3 INCHES | 48388 | 2023-11-27 | 2023-11-30 | CLOSE | 1 | EA | 1 | 58.18 | 58.18 | 19411 | CLOSE | 2023-12-06 | 2023-12-03 | KW1-13514 | 3 | 2023-12-06 | APPR | 2023-12-06 | Thomas, Vinu - Vectrus -No Export | MARATHON INC TRADING LLC | 2024-01-17 | COMP | 2023-12-21 | 1.00 |  | AJ | AJ table | November | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5530-60-V00-0004 | PLYWOOD, CONSTRUCTION, MARINE, 13 PLY BOARD, 3/4 INCH, 8 X 4 FEET | 49621 | 2023-12-14 | 2023-12-16 | CLOSE | 2 | SH | 85 | 137.36 | 11675.6 | 19909 | CLOSE | 2023-12-26 | 2023-12-21 | KW1-13925 | 4 | 2023-12-26 | APPR | 2023-12-26 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-10 | COMP | 2024-01-08 | 85.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 49625 | 2023-12-14 | 2023-12-16 | CLOSE | 6 | BX | 24 | 19.6 | 470.4 |  |  |  |  | KW1-13754 | 29 | 2023-12-18 | APPR | 2023-12-18 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-04 | COMP | 2023-12-21 | 24.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5305-60-V00-0170 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATE, # 8 X 3 INCHES | 49625 | 2023-12-14 | 2023-12-16 | CLOSE | 5 | BX | 12 | 35 | 420 |  |  |  |  | KW1-13754 | 28 | 2023-12-18 | APPR | 2023-12-18 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-04 | COMP | 2023-12-21 | 12.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 7210-60-V00-0059 | FLOOR COVERING, VINYL RESIN, 3 MM X 40 FEET | 49625 | 2023-12-14 | 2023-12-16 | CLOSE | 4 | RL | 3 | 716.1 | 2148.3 |  |  |  |  | KW1-13754 | 27 | 2023-12-18 | APPR | 2023-12-18 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-04 | COMP | 2023-12-27 | 3.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5640-60-V00-0034 | WEATHER STRIP, FLUTE TOPPED ALUMINUM THRESHOLD, 3' (L) X 4-1/4" (W) | 49623 | 2023-12-14 | 2023-12-16 | CLOSE | 7 | EA | 2 | 49 | 98 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 38 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 2.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 8040-00-273-8713 | ADHESIVE, FLOORING, WHITE, 1 GL | 49620 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | GL | 15 | 187.48 | 2812.2 |  |  |  |  | KW1-13755 | 9 | 2023-12-18 | APPR | 2023-12-18 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-18 | COMP | 2024-01-08 | 15.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 49623 | 2023-12-14 | 2023-12-16 | CLOSE | 6 | EA | 15 | 45.4 | 681 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 37 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2024-01-06 | 15.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 49621 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | BX | 2 | 29.64 | 59.28 | 19909 | CLOSE | 2023-12-26 | 2023-12-21 | KW1-13925 | 3 | 2023-12-26 | APPR | 2023-12-26 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-02 | COMP | 2023-12-30 | 2.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 49626 | 2023-12-14 | 2023-12-16 | CLOSE | 4 | BX | 1 | 142 | 142 | 19854 | CLOSE | 2023-12-19 |  | KW1-13782 | 3 | 2023-12-19 | APPR | 2023-12-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-31 | COMP | 2023-12-22 | 1.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5640-60-V00-0032 | WEATHER STRIP, DOOR, W/RUBBER BOTTOM SWEEP, 39 INCHES | 49617 | 2023-12-14 | 2023-12-16 | CLOSE | 5 | EA | 4 | 16.62 | 66.48 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 31 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 4.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 8105-01-336-6163 | BAG, SAND, TAN, 26 INCHES (EXCESS ) |  | 2023-12-14 |  |  |  | HD | [18 empty] | EXCESS | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 49622 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | BX | 1 | 16.5 | 16.5 |  |  |  |  | KW1-13868 | 3 | 2023-12-22 | APPR | 2023-12-22 | Bharadwajan, Sajan - Vectrus - No Export | TRADEX INTERNATIONAL TRADING LLC | 2023-12-28 | COMP | 2023-12-26 | 1.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 3230-60-V00-0024 | BLADE, CIRCULAR SAW, WOOD CUTTING, 36 TOOTH, 7-1/4 INCHES | 49623 | 2023-12-14 | 2023-12-16 | CLOSE | 5 | EA | 4 | 52.45 | 209.8 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 36 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-28 | COMP | 2024-02-29 | 4.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 3230-60-V00-0028 | BLADE SET, JIG SAW, BI-METAL, T-SHANK, 14-PIECES | 49617 | 2023-12-14 | 2023-12-16 | CLOSE | 4 | PG | 2 | 44.29 | 88.58 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 30 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 2.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 8415-01-610-7323 | GLOVES, BLACK, MEDIUM | 49619 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | PG | 3 | 133.1 | 399.3 |  |  |  |  | KW1-13868 | 2 | 2023-12-22 | APPR | 2023-12-22 | Bharadwajan, Sajan - Vectrus - No Export | TRADEX INTERNATIONAL TRADING LLC | 2023-12-28 | COMP | 2023-12-26 | 3.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5120-60-V00-0305 | BIT, SCREW DRIVER, SILVER, PH2, 69 MM | 49623 | 2023-12-14 | 2023-12-16 | CLOSE | 4 | EA | 5 | 8.33 | 41.65 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 35 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 5.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5110-00-277-4592 | BLADE, HAND HACKSAW, STEEL, 12 X 0.025 INCH | 49625 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | PK | 5 | 31.6 | 158 |  |  |  |  | KW1-13754 | 24 | 2023-12-18 | APPR | 2023-12-18 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-04 | COMP | 2023-12-21 | 5.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5110-00-277-4590 | BLADE, HAND HACKSAW, STEEL, 18 TPI, 12 X 0.025 INCH | 49627 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | PG | 5 | 19.8 | 99 | 19855 | CLOSE | 2024-02-17 | 2023-12-20 | KW1-13927 | 6 | 2023-12-26 | APPR | 2023-12-26 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2023-12-30 | 5.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 6210-60-V00-0136 | LIGHT UNIT, EMERGENCY, (EXIT LIGHT), LED, 120-277 V, 50/60 HZ, 2 W | 49624 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | EA | 2 | 135.7 | 271.4 |  |  |  |  | KW1-13755 | 11 | 2023-12-18 | APPR | 2023-12-18 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-11 | COMP | 2023-12-21 | 2.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5970-60-V00-0040 | TAPE, INSULATION, RED, 3/4 INCH X 25 METER | 49626 | 2023-12-14 | 2023-12-16 | CLOSE | 3 | RO | 1 | 19 | 19 | 19854 | CLOSE | 2023-12-19 |  | KW1-13783 | 1 | 2023-12-19 | APPR | 2023-12-19 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-10 | COMP | 2023-12-22 | 1.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5970-60-V00-0044 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 INCH X 66 FEET | 49617 | 2023-12-14 | 2023-12-16 | CLOSE | 3 | RO | 1 | 14.99 | 14.99 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 29 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 49617 | 2023-12-14 | 2023-12-16 | CLOSE | 2 | RO | 1 | 16.83 | 16.83 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 28 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5935-60-V00-0156 | CONNECTOR, WIRE, RED, 18-6 AWG | 49617 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | BX | 1 | 36.13 | 36.13 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 27 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 6210-60-V00-0031 | LIGHT UNIT, EMERGENCY, TWIN SPOT, LED, WHITE, 220V, 50HZ | 49626 | 2023-12-14 | 2023-12-16 | CLOSE | 2 | EA | 2 | 100.13 | 200.26 | 19854 | CLOSE | 2023-12-19 |  | KW1-13782 | 2 | 2023-12-19 | APPR | 2023-12-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-31 | COMP | 2023-12-22 | 2.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 49625 | 2023-12-14 | 2023-12-16 | CLOSE | 3 | BX | 1 | 51.5 | 51.5 |  |  |  |  | KW1-13754 | 26 | 2023-12-18 | APPR | 2023-12-18 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-04 | COMP | 2023-12-21 | 1.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5940-60-V00-0137 | FERRULE KIT, ELECTRICAL CONDUCTOR, INSULATED, 4 TYPE, 600V, 4MM TO 16 MM | 49618 | 2023-12-14 | 2023-12-16 | CLOSE | 2 | KT | 1 | 42.12 | 42.12 | 19971 | CLOSE | 2023-12-27 | 2023-12-24 | KW1-13949 | 10 | 2023-12-28 | APPR | 2023-12-28 | Thomas, Vinu - Vectrus -No Export | MARATHON INC TRADING LLC | 2024-01-04 | COMP | 2024-01-02 | 1.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 49626 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | EA | 1 | 260.02 | 260.02 | 19854 | CLOSE | 2023-12-19 |  | KW1-13782 | 1 | 2023-12-19 | APPR | 2023-12-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-31 | COMP | 2023-12-22 | 1.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 6350-60-V00-0102 | ALARM, SMOKE, AUTOMATIC, PLASTIC | 49623 | 2023-12-14 | 2023-12-16 | CLOSE | 3 | EA | 4 | 28.97 | 115.88 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 34 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 4.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5910-60-V00-0057 | CAPACITOR, RUN, 3P, 55+5 MFD, 370/440V, 50/60HZ | 49623 | 2023-12-14 | 2023-12-16 | CLOSE | 2 | EA | 1 | 17.98 | 17.98 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 33 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5975-60-V00-0435 | PAD, ANTI VIBRATION, RUBBER/CORK, 4 X 4 X 1 INCHES | 49625 | 2023-12-14 | 2023-12-16 | CLOSE | 2 | EA | 20 | 13.2 | 264 |  |  |  |  | KW1-13754 | 25 | 2023-12-18 | APPR | 2023-12-18 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-04 | COMP | 2023-12-21 | 20.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 5306-60-V00-0120 | BOLT AND NUT, HEX w/ WASHER, 2 INCHES X 10 MM | 49623 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | BX | 1 | 83.25 | 83.25 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 32 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | AJ | AJ table | December | 2023 | MM_AJ
115 | 2023-12-14 |  | AJ23-0708 | TI Repairs | 8012468 | 6830-01-527-1691 | REFRIGERANT GAS MIXTURE, 407C, 25 LBS | 49618 | 2023-12-14 | 2023-12-16 | CLOSE | 1 | CY | 1 | 162.9 | 162.9 | 19971 | CLOSE | 2023-12-27 | 2023-12-24 | KW1-13949 | 9 | 2023-12-28 | APPR | 2023-12-28 | Thomas, Vinu - Vectrus -No Export | MARATHON INC TRADING LLC | 2024-01-04 | COMP | 2024-01-02 | 1.00 |  | AJ | AJ table | December | 2023 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 40 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 50 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
116 | 2024-02-29 | 60 | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | [27 empty] | AJ | AJ table | February | 2024 | MM_AJ
[34 empty] | FALSE | January | 1900 | MM_AJ
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 6115-60-V00-0037 | GENERATOR SET, DIESEL ENGINE, 4-CYCLE, 400V, 24 KW, 50HZ | 48879 | 2023-12-04 | 2023-12-11 | CLOSE | 1 | EA | 1 | 14186.7 | 14186.7 | 19796 | CLOSE | 2023-12-20 | 2023-12-17 | KW1-13841 | 1 | 2023-12-20 | APPR | 2023-12-20 | Reghunath, Rajesh -Vectrus -GSD -No Export | GULF PIONEER COMPANY LLC | 2024-01-24 | COMP | 2024-01-23 | 1.00 | Pending Stenciling | BU | BU table | December | 2023 | MM_BU
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 48878 | 2023-12-04 | 2023-12-11 | CLOSE | 8 | EA | 2 | 300.19 | 600.38 |  |  |  |  | KW1-13652 | 7 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 48878 | 2023-12-04 | 2023-12-11 | CLOSE | 7 | EA | 2 | 60.17 | 120.34 |  |  |  |  | KW1-13652 | 6 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 6145-60-V00-0119 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 25 MM² | 48878 | 2023-12-04 | 2023-12-11 | CLOSE | 6 | MR | 15 | 204.38 | 3065.7 |  |  |  |  | KW1-13652 | 5 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 15.00 |  | BU | BU table | December | 2023 | MM_BU
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM ² | 48878 | 2023-12-04 | 2023-12-11 | CLOSE | 5 | RO | 25 | 240.35 | 240.35 |  |  |  |  | KW1-13652 | 4 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 5940-60-V00-0016 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 16 MM² | 48878 | 2023-12-04 | 2023-12-11 | CLOSE | 4 | EA | 8 | 1.8 | 14.4 |  |  |  |  | KW1-13653 | 1 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-23 | COMP | 2023-12-15 | 8.00 |  | BU | BU table | December | 2023 | MM_BU
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 5975-60-V00-0512 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, CW, BRASS, 32 MM | 48878 | 2023-12-04 | 2023-12-11 | CLOSE | 3 | KT | 2 | 21.26 | 42.52 |  |  |  |  | KW1-13652 | 3 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 5940-60-V00-0017 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 25 MM² | 48878 | 2023-12-04 | 2023-12-11 | CLOSE | 2 | EA | 8 | 1.8 | 14.4 |  |  |  |  | KW1-13652 | 2 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 8.00 |  | BU | BU table | December | 2023 | MM_BU
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 48880 | 2023-12-04 | 2023-12-06 | CLOSE | 1 | RO | 1 | 163.35 | 163.35 |  |  |  |  | KW1-13557 | 8 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-13 | COMP | 2023-12-11 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
1 | 2023-12-04 | 30 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 5975-60-V00-0209 | RACEWAY, METALLIC, GALVANIZED STEEL, 2 X 2 INCHES X 10 FEET | 48878 | 2023-12-04 | 2023-12-11 | CLOSE | 1 | EA | 1 | 55.59 | 55.59 |  |  |  |  | KW1-13652 | 1 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-07 | COMP | 2024-01-07 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 6115-60-V00-0037 | GENERATOR SET, DIESEL ENGINE, 4-CYCLE, 400V, 24 KW, 50HZ | 48882 | 2023-12-04 | 2023-12-11 | CLOSE | 1 | EA | 1 | 14186.7 | 14186.7 | 19796 | CLOSE | 2023-12-20 | 2023-12-17 | KW1-13841 | 3 | 2023-12-20 | APPR | 2023-12-20 | Reghunath, Rajesh -Vectrus -GSD -No Export | GULF PIONEER COMPANY LLC | 2024-01-24 | COMP | 2024-01-23 | 1.00 | Pending Stenciling | BU | BU table | December | 2023 | MM_BU
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 48881 | 2023-12-04 | 2023-12-11 | CLOSE | 8 | EA | 2 | 300.19 | 600.38 |  |  |  |  | KW1-13654 | 7 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 48881 | 2023-12-04 | 2023-12-11 | CLOSE | 7 | EA | 2 | 60.17 | 120.34 |  |  |  |  | KW1-13654 | 6 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 6145-60-V00-0119 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 25 MM² | 48881 | 2023-12-04 | 2023-12-11 | CLOSE | 6 | MR | 15 | 204.38 | 3065.7 |  |  |  |  | KW1-13654 | 5 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 15.00 |  | BU | BU table | December | 2023 | MM_BU
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 6145-60-V00-0148 | Thank | 48881 | 2023-12-04 | 2023-12-11 | CLOSE | 5 | RO | 25 | 240.35 | 240.35 |  |  |  |  | KW1-13654 | 4 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 5940-60-V00-0016 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 16 MM² | 48881 | 2023-12-04 | 2023-12-11 | CLOSE | 4 | EA | 8 | 1.8 | 14.4 |  |  |  |  | KW1-13655 | 1 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-23 | COMP | 2023-12-15 | 8.00 |  | BU | BU table | December | 2023 | MM_BU
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 5975-60-V00-0512 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, CW, BRASS, 32 MM | 48881 | 2023-12-04 | 2023-12-11 | CLOSE | 3 | KT | 2 | 21.26 | 42.52 |  |  |  |  | KW1-13654 | 3 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 5940-60-V00-0017 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 25 MM² | 48881 | 2023-12-04 | 2023-12-11 | CLOSE | 2 | EA | 8 | 1.8 | 14.4 |  |  |  |  | KW1-13654 | 2 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 8.00 |  | BU | BU table | December | 2023 | MM_BU
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 48883 | 2023-12-04 | 2023-12-06 | CLOSE | 1 | RO | 25 | 163.65 | 163.65 |  |  |  |  | KW1-13557 | 10 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-13 | COMP | 2023-12-11 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
2 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 5975-60-V00-0209 | RACEWAY, METALLIC, GALVANIZED STEEL, 2 X 2 INCHES X 10 FEET | 48881 | 2023-12-04 | 2023-12-11 | CLOSE | 1 | EA | 1 | 55.59 | 55.59 |  |  |  |  | KW1-13654 | 1 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-07 | COMP | 2024-01-07 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 6115-60-V00-0037 | GENERATOR SET, DIESEL ENGINE, 4-CYCLE, 400V, 24 KW, 50HZ | 48938 | 2023-12-05 | 2023-12-11 | CLOSE | 1 | EA | 1 | 14186.7 | 14186.7 | 19797 | CLOSE | 2023-12-20 | 2023-12-17 | KW1-13840 | 1 | 2023-12-20 | APPR | 2023-12-20 | Reghunath, Rajesh -Vectrus -GSD -No Export | GULF PIONEER COMPANY LLC | 2024-01-24 | COMP | 2024-01-23 | 1.00 | Pending Stenciling | BU | BU table | December | 2023 | MM_BU
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 48937 | 2023-12-05 | 2023-12-11 | CLOSE | 8 | EA | 2 | 300.19 | 600.38 |  |  |  |  | KW1-13656 | 7 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 48937 | 2023-12-05 | 2023-12-11 | CLOSE | 7 | EA | 2 | 60.17 | 120.34 |  |  |  |  | KW1-13656 | 6 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 6145-60-V00-0119 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 25 MM² | 48937 | 2023-12-05 | 2023-12-11 | CLOSE | 1 | MR | 15 | 204.38 | 3065.7 |  |  |  |  | KW1-13656 | 1 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-19 | 15.00 |  | BU | BU table | December | 2023 | MM_BU
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM ² | 48937 | 2023-12-05 | 2023-12-11 | CLOSE | 6 | RO | 25 | 240.35 | 240.35 |  |  |  |  | KW1-13656 | 5 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 5940-60-V00-0016 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 16 MM² | 48937 | 2023-12-05 | 2023-12-11 | CLOSE | 5 | EA | 8 | 1.8 | 14.4 |  |  |  |  | KW1-13657 | 1 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-23 | COMP | 2023-12-15 | 8.00 |  | BU | BU table | December | 2023 | MM_BU
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 5975-60-V00-0512 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, CW, BRASS, 32 MM | 48937 | 2023-12-05 | 2023-12-11 | CLOSE | 4 | KT | 2 | 21.26 | 42.52 |  |  |  |  | KW1-13656 | 4 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 5940-60-V00-0017 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 25 MM² | 48937 | 2023-12-05 | 2023-12-11 | CLOSE | 3 | EA | 8 | 1.8 | 14.4 |  |  |  |  | KW1-13656 | 3 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-23 | COMP | 2023-12-16 | 8.00 |  | BU | BU table | December | 2023 | MM_BU
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 48939 | 2023-12-05 | 2023-12-06 | CLOSE | 1 | RO | 1 | 161.7 | 161.7 |  |  |  |  | KW1-13557 | 12 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-13 | COMP | 2023-12-11 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
3 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 5975-60-V00-0209 | RACEWAY, METALLIC, GALVANIZED STEEL, 2 X 2 INCHES X 10 FEET | 48937 | 2023-12-05 | 2023-12-11 | CLOSE | 2 | EA | 1 | 55.59 | 55.59 |  |  |  |  | KW1-13656 | 2 | 2023-12-13 | APPR | 2023-12-13 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-07 | COMP | 2024-01-07 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
4 | 2023-12-04 | 40 | BU24-0020 | ADN 5 Generator Replacement | 8417458 | 5975-60-V00-0793 | RACEWAY, METALLIC, (CABLE TRAY), MEDIUM DUTY, HOT-DIP GALVANIZED, 1.20 X 50 X 3000 X 450 MM | 49131 | 2023-12-07 | 2023-12-11 | CLOSE | 1 | EA | 1 | 55.1 | 55.1 | 19734 | CLOSE | 2023-12-20 | 2023-12-17 | KW1-13824 | 1 | 2023-12-20 | APPR | 2023-12-20 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
5 | 2023-12-04 | 30 | BU24-0021 | ADN 1 Generator Replacement | 8417467 | 5975-60-V00-0793 | RACEWAY, METALLIC, (CABLE TRAY), MEDIUM DUTY, HOT-DIP GALVANIZED, 1.20 X 50 X 3000 X 450 MM | 49132 | 2023-12-07 | 2023-12-11 | CLOSE | 1 | EA | 1 | 55.1 | 55.1 | 19682 | CLOSE | 2023-12-20 | 2023-12-16 | KW1-13811 | 13 | 2023-12-20 | APPR | 2023-12-20 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
6 | 2023-12-04 | 30 | BU24-0014 | ADN 3 Generator Replacement | 8417447 | 5975-60-V00-0793 | RACEWAY, METALLIC, (CABLE TRAY), MEDIUM DUTY, HOT-DIP GALVANIZED, 1.20 X 50 X 3000 X 450 MM | 49133 | 2023-12-07 | 2023-12-11 | CLOSE | 1 | PR-PAIR | 1 | 55.1 | 55.1 | 19682 | CLOSE | 2023-12-20 | 2023-12-16 | KW1-13811 | 15 | 2023-12-20 | APPR | 2023-12-20 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 6145-60-V00-0119 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 25 MM² | 49482 | 2023-12-13 | 2023-12-15 | CLOSE | 9 | MR | 35 | 26.5 | 927.5 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 9 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-28 | COMP | 2024-01-08 | 35.00 |  | BU | BU table | December | 2023 | MM_BU
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 5975-60-V00-0512 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, CW, BRASS, 32 MM | 49482 | 2023-12-13 | 2023-12-15 | CLOSE | 8 | EA | 2 | 16 | 32 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 8 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 49482 | 2023-12-13 | 2023-12-15 | CLOSE | 7 | RO | 1 | 242.58 | 242.58 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 7 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 5940-60-V00-0017 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 25 MM² | 49482 | 2023-12-13 | 2023-12-15 | CLOSE | 6 | EA | 10 | 1.9 | 19 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 6 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 10.00 |  | BU | BU table | December | 2023 | MM_BU
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 6110-60-V00-0112 | SWITCH, DISCONNECT, 3P+N, Y4, 800V, 100A | 49484 | 2023-12-13 | 2023-12-15 | CLOSE | 3 | EA | 1 | 306.14 | 306.14 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 12 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-28 | COMP | 2024-01-07 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 6130-60-V00-0050 | CONVERTER, FREQUENCY, STATIC, 3 PHASE, 30KVA | 49484 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | EA | 1 | 11833.46 | 11833.46 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 11 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-28 | COMP | 2024-01-30 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 5925-60-V00-0087 | CIRCUIT BREAKER, 6 POLE, 277-480 VAC, 50A | 49484 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | EA | 1 | 326 | 326 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 10 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-28 | COMP | 2024-01-08 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 5975-60-V00-0512 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, CW, BRASS, 32 MM | 49482 | 2023-12-13 | 2023-12-15 | CLOSE | 5 | KT | 4 | 16 | 64 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 5 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 49482 | 2023-12-13 | 2023-12-15 | CLOSE | 4 | EA | 1 | 302.94 | 302.94 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 4 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 49482 | 2023-12-13 | 2023-12-15 | CLOSE | 3 | EA | 1 | 58.91 | 58.91 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 3 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 5975-60-V00-0418 | LUG, TERMINAL, ROUND TYPE, COPPER, ONE-HOLE, 16 mm²-M8 | 49482 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | EA | 20 | 1.07 | 21.4 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 2 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 20.00 |  | BU | BU table | December | 2023 | MM_BU
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 9520-60-V00-0017 | ANGLE, STRUCTURAL, STEEL, 2 X 2 INCHES X 20 FEET | 49482 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | EA | 1 | 49.12 | 49.12 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 1 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-30 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
7 | 2023-12-13 | 30 | BU23-0332 | Connect Battery Container Z5 TT526 | 8570280 | 5620-60-V00-0027 | CONCRETE BLOCK, CUBE, 40 X 40 X 40 CM | 49483 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | EA | 1 | 221.28 | 221.28 | 19831 | CLOSE | 2023-12-20 | 2023-12-18 | KW1-13821 | 1 | 2023-12-26 | APPR | 2023-12-26 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-15 | COMP | 2024-01-13 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 4730-60-V00-0046 | ADAPTER, ELECTRICAL CONDUIT, w/BUSH, FEMALE, PVC, WHITE, 25 MM | 49470 | 2023-12-13 | 2023-12-15 | CLOSE | 5 | EA | 10 | 8.49 | 84.9 | 19827 | CLOSE | 2023-12-18 |  | KW1-13777 | 1 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-01-31 | COMP | 2023-12-21 | 10.00 |  | BU | BU table | December | 2023 | MM_BU
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 5975-01-382-7318 | UNION, ELECTRICAL CONDUIT, PLASTIC, BLACK, 1/2 INCH | 49470 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | EA | 15 | 8.49 | 127.35 | 19826 | CLOSE | 2023-12-22 | 2023-12-18 | KW1-13875 | 3 | 2023-12-22 | APPR | 2023-12-23 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-02 | COMP | 2023-12-26 | 15.00 |  | BU | BU table | December | 2023 | MM_BU
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 5975-60-V00-0526 | CONDUIT, NONMETALLIC, RIGID, PVC, BLACK, 3/4 INCH X 10 FEET | 49473 | 2023-12-13 | 2023-12-15 | CLOSE | 4 | EA | 20 | 2.75 | 55 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 8 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-23 | 20.00 |  | BU | BU table | December | 2023 | MM_BU
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 5975-60-V00-0501 | CLAMP, ELECTRICAL, CONDUIT, PVC, BLACK, 25 MM | 49470 | 2023-12-13 | 2023-12-15 | CLOSE | 4 | EA | 30 | 3.16 | 94.8 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 4 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-22 | 30.00 |  | BU | BU table | December | 2023 | MM_BU
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 5975-60-V00-0373 | COUPLING, ELECTRICAL CONDUIT, PVC, BLACK, 20 MM | 49473 | 2023-12-13 | 2023-12-15 | CLOSE | 3 | EA | 10 | 0.88 | 8.8 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 7 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 10.00 |  | BU | BU table | December | 2023 | MM_BU
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 49470 | 2023-12-13 | 2023-12-15 | CLOSE | 3 | EA | 10 | 3.5 | 35 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 3 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 10.00 |  | BU | BU table | December | 2023 | MM_BU
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 5925-60-V00-0269 | CIRCUIT BREAKER, MINIATURE, 1 POLE, 20A | 49470 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | EA | 1 | 11.66 | 11.66 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 2 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 49473 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | EA | 4 | 10.32 | 41.28 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 6 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-15 | COMP | 2023-12-21 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 6145-60-V00-0163 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORE, 4 MM² | 49473 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | RL | 1 | 248.88 | 248.88 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 5 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 49471 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | RL | 1 | 21.65 | 21.65 | 19857 | CLOSE | 2023-12-17 | 2023-12-17 | KW1-13758 | 3 | 2023-12-20 | APPR | 2023-12-20 | Vishwanath, Shet -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-24 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
8 | 2023-12-13 | 30 | BU23-0371 | Install Electrical Outlet Z4 DFAC1 | 8674667 | 5970-01-013-9369 | TAPE, INSULATION, ELECTRICAL, RED, 3/4 X 792 INCHES | 49472 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | RL | 1 | 11.2 | 11.2 | 19857 | CLOSE | 2023-12-17 | 2023-12-17 | KW1-13758 | 4 | 2023-12-20 | APPR | 2023-12-20 | Vishwanath, Shet -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-24 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 6145-60-V00-0118 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 16 MM² | 49587 | 2023-12-13 | 2023-12-15 | CLOSE | 6 | MR | 100 | 21.57 | 2157 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 26 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-30 | 100.00 |  | BU | BU table | December | 2023 | MM_BU
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5975-60-V00-0511 | GLAND, ELECTRICAL CONDUIT, BRASS, BW, w/ EARTH TAG, 25 MM | 49587 | 2023-12-13 | 2023-12-15 | CLOSE | 5 | EA | 4 | 9.49 | 37.96 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 25 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5940-60-V00-0122 | TERMINAL, LUG, COPPER TUBE, STUD HOLE, 16MM² X M10 | 49587 | 2023-12-13 | 2023-12-15 | CLOSE | 4 | EA | 20 | 67.28 | 67.28 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 24 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 49589 | 2023-12-13 | 2023-12-15 | CLOSE | 5 | EA | 1 | 352.98 | 352.98 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 19 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 49589 | 2023-12-13 | 2023-12-15 | CLOSE | 4 | EA | 1 | 61.27 | 61.27 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 18 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5975-60-V00-0794 | CONDUIT, METAL, FLEXIBLE, STEEL, GRAY, GALVANIZED, 1-1/2 INCHES X 50 FEET | 49590 | 2023-12-13 | 2023-12-22 | CLOSE | 1 | EA | 1 | 452.77 | 452.77 | 19902 | CLOSE | 2023-12-22 | 2023-12-21 | KW1-13866 | 2 | 2023-12-22 | APPR | 2023-12-22 | Kannoth, Shajee -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-17 07:00 | COMP | 2024-01-10 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 6145-60-V00-0139 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 6 MM ² | 49587 | 2023-12-13 | 2023-12-15 | CLOSE | 3 | RL | 1 | 28.47 | 28.47 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 23 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2024-01-04 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5975-60-V00-0421 | LUG, TERMINAL, ROUND TYPE, ONE-HOLE, 6MM² X 6MM | 49589 | 2023-12-13 | 2023-12-15 | CLOSE | 3 | PG | 1 | 51.82 | 51.82 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 17 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5975-60-V00-0029 | CLAMP, GROUNDING, 5/8 INCH | 49587 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | EA | 1 | 44.12 | 44.12 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 22 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2023-12-29 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5975-00-074-2072 | STRAP, TIEDOWN, ELECTRICAL COMPONENT, PLASTIC, NATURAL, 6-3/10 INCHES | 49589 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | HD | 1 | 16.83 | 16.83 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 16 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5975-01-223-8533 | STRAP, TIE DOWN, ELECTRICAL COMPONENTS, PLASTIC POLYAMIDE, 0.1 X 8 INCHES | 49589 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | PG | 1 | 66.48 | 66.48 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 15 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 4240-60-V00-0122 | TAPE, WARNING, CAUTION BURIED ELECTRICAL CABLE BELOW, YELLOW 6 INCHES X 1000 FEET | 49587 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | RL | 1 | 176.82 | 176.82 | 19860 | SENT | 2023-12-26 | 2023-12-21 | KW1-13913 | 21 | 2023-12-26 | APPR | 2023-12-26 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-13 | COMP | 2024-01-04 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
9 | 2023-12-13 | 30 | BU24-0022 | Connect Electrical Z5 T5049 | 8389717 | 5610-60-V00-0014 | SAND, CONSTRUCTION, BEACH | 49588 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | CZ | 30 | 40.55 | 1216.5 | 19825 | CLOSE | 2023-12-20 | 2023-12-18 | KW1-13828 | 3 | 2023-12-20 | APPR | 2023-12-20 | Reghunath, Rajesh -Vectrus -GSD -No Export | GULF PIONEER COMPANY LLC | 2023-12-27 | COMP | 2023-12-23 | 30.00 |  | BU | BU table | December | 2023 | MM_BU
10 | 2023-12-03 | 30 | BU24-0087 | Install Circuit Breakers Z8 TT803 | 8565458 | 5975-60-V00-0531 | PROTECTOR, ELECTRICAL CABLE, PVC, WHITE, 1 INCH X 9 FEET | 48795 | 2023-12-03 | 2023-12-07 | CLOSE | 3 | EA | 8 | 16.19 | 129.52 | 19578 | CLOSE | 2023-12-11 | 2023-12-10 | KW1-13609 | 7 | 2023-12-13 | APPR | 2023-12-13 | Thomas, Vinu - Vectrus -No Export | COMMERCIAL UNITED GINCO EST. | 2023-12-20 | COMP | 2023-12-16 | 8.00 |  | BU | BU table | December | 2023 | MM_BU
10 | 2023-12-03 | 30 | BU24-0087 | Install Circuit Breakers Z8 TT803 | 8565458 | 5975-60-V00-0161 | RACEWAY, NON-METALLIC (CABLE TRUNKING), UPVC, WHITE, 50 X 50MM X 3 METER | 48795 | 2023-12-03 | 2023-12-07 | CLOSE | 2 | EA | 8 | 36.14 | 289.12 | 19578 | CLOSE | 2023-12-11 | 2023-12-10 | KW1-13609 | 6 | 2023-12-13 | APPR | 2023-12-13 | Thomas, Vinu - Vectrus -No Export | COMMERCIAL UNITED GINCO EST. | 2023-12-20 | COMP | 2023-12-16 | 8.00 |  | BU | BU table | December | 2023 | MM_BU
10 | 2023-12-03 | 30 | BU24-0087 | Install Circuit Breakers Z8 TT803 | 8565458 | 6145-60-V00-0163 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORE, 4 MM² | 48797 | 2023-12-03 | 2023-12-06 | CLOSE | 2 | RO | 3 | 249 | 747 |  |  |  |  | KW1-13557 | 2 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-13 | COMP | 2023-12-11 | 3.00 |  | BU | BU table | December | 2023 | MM_BU
10 | 2023-12-03 | 30 | BU24-0087 | Install Circuit Breakers Z8 TT803 | 8565458 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 48795 | 2023-12-03 | 2023-12-07 | CLOSE | 1 | EA | 16 | 3.43 | 54.88 | 19578 | CLOSE | 2023-12-11 | 2023-12-10 | KW1-13609 | 5 | 2023-12-13 | APPR | 2023-12-13 | Thomas, Vinu - Vectrus -No Export | COMMERCIAL UNITED GINCO EST. | 2023-12-20 | COMP | 2023-12-16 | 16.00 |  | BU | BU table | December | 2023 | MM_BU
10 | 2023-12-03 | 30 | BU24-0087 | Install Circuit Breakers Z8 TT803 | 8565458 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 48797 | 2023-12-03 | 2023-12-06 | CLOSE | 1 | EA | 6 | 12.4 | 74.4 |  |  |  |  | KW1-13557 | 1 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-29 | COMP | 2023-12-11 | 6.00 |  | BU | BU table | December | 2023 | MM_BU
10 | 2023-12-03 | 30 | BU24-0087 | Install Circuit Breakers Z8 TT803 | 8565458 | 5305-60-V00-0182 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATE, #8 X 1-1/4 INCHES | 48796 | 2023-12-03 | 2023-12-06 | CLOSE | 1 | BX | 2 | 29.54 | 59.08 |  |  |  |  | KW1-13558 | 1 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-13 | COMP | 2023-12-12 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5975-60-V00-0066 | CONDUIT, METAL, RIGID, GALVANIZED STEEL, 1/2 INCH X 10 FEET | 49486 | 2023-12-13 | 2023-12-15 | CLOSE | 5 | EA | 3 | 214.79 | 644.37 | 19827 | CLOSE | 2023-12-18 |  | KW1-13776 | 1 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-10 | COMP | 2023-12-23 | 3.00 |  | BU | BU table | December | 2023 | MM_BU
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5975-60-V00-0461 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, GALVANIZED STEEL, ½ INCH | 49487 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | EA | 10 | 1.6 | 16 | 19869 | CLOSE | 2023-12-27 | 2023-12-20 | KW1-13955 | 5 | 2023-12-27 | CLOSE | 2024-02-06 | Vishwanath, Shet -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-14 | COMP | 2023-12-30 | 10.00 |  | BU | BU table | December | 2023 | MM_BU
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5975-60-V00-0374 | COUPLING, ELECTRICAL CONDUIT, ZINC PLATED STEEL, 1/2 INCH | 49489 | 2023-12-13 | 2023-12-15 | CLOSE | 3 | PG | 1 | 129.1 | 129.1 | 19869 | CLOSE | 2023-12-27 | 2023-12-20 | KW1-13955 | 7 | 2023-12-27 | CLOSE | 2024-02-06 | Vishwanath, Shet -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-14 | COMP | 2023-12-30 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5975-00-578-3643 | BOX CONNECTOR, ELECTRICAL, ANGLE, LIQUIDTIGHT, IRON MALLEABLE, 1/2 INCH | 49490 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | EA | 5 | 12.54 | 62.7 | 19826 | CLOSE | 2023-12-22 | 2023-12-18 | KW1-13875 | 5 | 2023-12-22 | APPR | 2023-12-23 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-02 | COMP | 2024-01-21 | 5.00 |  | BU | BU table | December | 2023 | MM_BU
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5935-60-V00-0153 | BOX CONNECTOR, ELECTRICAL, ZINC PLATED STEEL, 1/2 INCH | 49486 | 2023-12-13 | 2023-12-15 | CLOSE | 4 | PG | 1 | 84.08 | 84.08 | 19826 | CLOSE | 2023-12-22 | 2023-12-18 | KW1-13875 | 4 | 2023-12-22 | APPR | 2023-12-23 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-31 | COMP | 2023-12-26 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 49486 | 2023-12-13 | 2023-12-15 | CLOSE | 3 | EA | 2 | 27.31 | 54.62 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 11 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5930-60-V00-0243 | LIGHT-SWITCH, METAL, 2 WAY, 1 GANG, 250V, 10A | 49486 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | EA | 2 | 33.3 | 66.6 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 10 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 6145-60-V00-0158 | WIRE, ELECTRICAL, RED, 1 CORE, 2.5 MM² | 49486 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | RO | 1 | 60.94 | 60.94 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 9 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-22 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5975-60-V00-0042 | BOX CONNECTOR, ELECTRICAL, STRAIGHT, LIQUID TIGHT CONDUIT, NICKEL PLATED BRASS, 1/2 INCH | 49489 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | EA | 10 | 23.7 | 237 | 19857 | CLOSE | 2023-12-17 | 2023-12-17 | KW1-13758 | 7 | 2023-12-20 | APPR | 2023-12-20 | Vishwanath, Shet -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-24 | COMP | 2023-12-21 | 10.00 |  | BU | BU table | December | 2023 | MM_BU
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5305-60-V00-0001 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 49488 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | BX | 1 | 18.9 | 18.9 | 19857 | CLOSE | 2023-12-17 | 2023-12-17 | KW1-13758 | 5 | 2023-12-20 | APPR | 2023-12-20 | Vishwanath, Shet -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-24 | COMP | 2023-12-27 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
11 | 2023-12-13 | 30 | BU24-0089 | Install Ceiling Light Switch Z5 TT503 | 8565290 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 49489 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | PG | 2 | 26.93 | 53.86 | 19857 | CLOSE | 2023-12-17 | 2023-12-17 | KW1-13758 | 6 | 2023-12-20 | APPR | 2023-12-20 | Vishwanath, Shet -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-24 | COMP | 2023-12-21 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
12 | 2023-12-13 | 30 | BU24-0097 | Install Exit Lights Z2 B211 | 8564897 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 48798 | 2023-12-13 | 2023-12-06 | CLOSE | 4 | EA | 2 | 160.23 | 320.46 |  |  |  |  | KW1-13557 | 6 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-13 | COMP | 2023-12-13 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
12 | 2023-12-13 | 30 | BU24-0097 | Install Exit Lights Z2 B211 | 8564897 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 48799 | 2023-12-13 | 2023-12-05 | CLOSE | 1 | RO | 1 | 163.35 | 163.35 |  |  |  |  | KW1-13518 | 5 | 2023-12-06 | APPR | 2023-12-06 | Kandankara, Thomas -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-18 | COMP | 2023-12-09 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
12 | 2023-12-13 | 30 | BU24-0097 | Install Exit Lights Z2 B211 | 8564897 | 5975-60-V00-0462 | TIE, CABLE, BLACK, 8 INCHES X 4.8 MILLIMETER | 48798 | 2023-12-13 | 2023-12-06 | CLOSE | 3 | PG | 1 | 24.03 | 24.03 |  |  |  |  | KW1-13557 | 5 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-13 | COMP | 2023-12-11 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
12 | 2023-12-13 | 30 | BU24-0097 | Install Exit Lights Z2 B211 | 8564897 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 48798 | 2023-12-13 | 2023-12-06 | CLOSE | 2 | RO | 1 | 120.45 | 120.45 |  |  |  |  | KW1-13557 | 4 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-13 | COMP | 2023-12-12 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
12 | 2023-12-13 | 30 | BU24-0097 | Install Exit Lights Z2 B211 | 8564897 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 48798 | 2023-12-13 | 2023-12-06 | CLOSE | 1 | EA | 5 | 4.25 | 21.25 |  |  |  |  | KW1-13558 | 3 | 2023-12-08 | APPR | 2023-12-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2023-12-13 | COMP | 2023-12-12 | 5.00 |  | BU | BU table | December | 2023 | MM_BU
13 | 2023-12-13 | 30 | BU24-0098 | Install Exit Signs Basewide | 8570569 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 49511 | 2023-12-13 | 2023-12-16 | CLOSE | 2 | EA | 8 | 3.26 | 26.08 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 21 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 8.00 |  | BU | BU table | December | 2023 | MM_BU
13 | 2023-12-13 | 30 | BU24-0098 | Install Exit Signs Basewide | 8570569 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 49514 | 2023-12-13 | 2023-12-16 | CLOSE | 3 | EA | 2 | 146.47 | 292.94 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 25 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
13 | 2023-12-13 | 30 | BU24-0098 | Install Exit Signs Basewide | 8570569 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 49514 | 2023-12-13 | 2023-12-16 | CLOSE | 2 | RO | 1 | 145 | 145 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 24 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
13 | 2023-12-13 | 30 | BU24-0098 | Install Exit Signs Basewide | 8570569 | 5305-60-V00-0205 | SCREW, PHILLIPS, FLAT HEAD, STEEL, #8 X 1 INCH | 49513 | 2023-12-13 | 2023-12-16 | CLOSE | 1 | HD | 1 | 28.97 | 28.97 | 19827 | CLOSE | 2023-12-18 |  | KW1-13776 | 5 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
13 | 2023-12-13 | 30 | BU24-0098 | Install Exit Signs Basewide | 8570569 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 49512 | 2023-12-13 | 2023-12-16 | CLOSE | 1 | RO | 1 | 21.65 | 21.65 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 22 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
13 | 2023-12-13 | 30 | BU24-0098 | Install Exit Signs Basewide | 8570569 | 5975-60-V00-0531 | PROTECTOR, ELECTRICAL CABLE, PVC, WHITE, 1 INCH X 9 FEET | 49511 | 2023-12-13 | 2023-12-16 | CLOSE | 1 | EA | 4 | 16.48 | 65.92 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 20 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-23 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
13 | 2023-12-13 | 30 | BU24-0098 | Install Exit Signs Basewide | 8570569 | 5975-60-V00-0480 | JUNCTION BOX, w/ BLANK SIDE, 100 X 100 X 50 MM | 49514 | 2023-12-13 | 2023-12-16 | CLOSE | 1 | EA | 1 | 12.14 | 12.14 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 23 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
14 | 2023-12-13 | 30 | BU24-0107 | Install Electrical Outlet FBF T008 | 8674569 | 5935-60-V00-0164 | SOCKET OUTLET, PLUG-IN, SWITCHED, 2 POLE, 2 GANG, 250V, 13A | 49517 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | EA | 2 | 56 | 112 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 14 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
14 | 2023-12-13 | 30 | BU24-0107 | Install Electrical Outlet FBF T008 | 8674569 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 49517 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | RO | 1 | 163 | 163 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 13 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-21 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
14 | 2023-12-13 | 30 | BU24-0107 | Install Electrical Outlet FBF T008 | 8674569 | 5925-60-V00-0264 | CIRCUIT BREAKER, (MCB), 3 POLE, 230-400 V, 20A | 49515 | 2023-12-13 | 2023-12-15 | CLOSE | 2 | EA | 1 | 32.47 | 32.47 | 19826 | CLOSE | 2023-12-22 | 2023-12-18 | KW1-13875 | 6 | 2023-12-22 | APPR | 2023-12-23 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-31 | COMP | 2023-12-27 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
14 | 2023-12-13 | 30 | BU24-0107 | Install Electrical Outlet FBF T008 | 8674569 | 5925-60-V00-0129 | CIRCUIT BREAKER, MCB, 1 POLE, 240/415V, 16A | 49518 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | EA | 1 | 24 | 24 | 19872 | CLOSE | 2024-02-23 | 2023-12-21 | KW1-14010 | 1 | 2023-12-30 | CLOSE | 2024-01-09 | Vishwanath, Shet -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-07 | COMP | 2024-01-04 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
14 | 2023-12-13 | 30 | BU24-0107 | Install Electrical Outlet FBF T008 | 8674569 | 4730-60-V00-0045 | ADAPTER, ELECTRICAL CONDUIT, w/BUSH, FEMALE, PVC, WHITE, 20 MM | 49516 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | EA | 6 | 6.2 | 37.2 |  |  |  |  | KW1-13754 | 1 | 2023-12-18 | APPR | 2023-12-18 | Kandankara, Thomas -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-04 | COMP | 2023-12-21 | 6.00 |  | BU | BU table | December | 2023 | MM_BU
14 | 2023-12-13 | 30 | BU24-0107 | Install Electrical Outlet FBF T008 | 8674569 | 5975-60-V00-0083 | CONDUIT, NONMETALLIC, HEAVY GAUGE, UPVC, WHITE, 20 MM X 3M | 49515 | 2023-12-13 | 2023-12-15 | CLOSE | 1 | EA | 4 | 10.99 | 43.96 | 19827 | CLOSE | 2023-12-18 |  | KW1-13775 | 12 | 2023-12-18 | APPR | 2023-12-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-23 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
15 | 2023-12-16 | 30 | BU24-0073 | Install Covers Ring 4 Power Plant | 8530135 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 49762 | 2023-12-16 | 2023-12-16 | CLOSE | 1 | EA | 15 | 61.27 | 919.05 | 19909 | CLOSE | 2023-12-26 | 2023-12-21 | KW1-13925 | 10 | 2023-12-26 | APPR | 2023-12-26 | Reghunath, Rajesh -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-06 | COMP | 2023-12-30 | 15.00 |  | BU | BU table | December | 2023 | MM_BU
16 | 2023-12-16 | 30 | BU24-0095 | Install Vestibule Doors Z5 Pad21 TT14 | 8563372 | 9905-60-V00-0004 | SIGNS, ADVERTISING DISPLAYS, AND IDENTIFICATION PLATES (CUSTOMIZED). | 49784 | 2023-12-16 | 2023-12-19 | CLOSE | 1 | PK | 2 | 58.35 | 116.7 | 19954 | CLOSE | 2023-12-24 |  | KW1-13903 | 8 | 2023-12-24 | APPR | 2023-12-24 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-01-21 | COMP | 2024-01-10 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
17 | 2023-12-16 | 30 | BU24-0096 | Install Vestibule Doors Z5 Pad21 TT09 | 8564095 | 9905-60-V00-0004 | SIGNS, ADVERTISING DISPLAYS, AND IDENTIFICATION PLATES (CUSTOMIZED). | 49785 | 2023-12-16 | 2023-12-19 | CLOSE | 1 | PK | 2 | 58.35 | 116.7 | 19954 | CLOSE | 2023-12-24 |  | KW1-13903 | 9 | 2023-12-24 | APPR | 2023-12-24 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-01-21 | COMP | 2024-01-10 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 49844 | 2023-12-17 | 2023-12-19 | CLOSE | 3 | EA | 1 | 349.8 | 349.8 |  |  |  |  | KW1-13827 | 4 | 2023-12-22 | APPR | 2023-12-22 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 | COMP | 2023-12-26 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 49840 | 2023-12-17 | 2023-12-19 | CLOSE | 1 | EA | 1 | 60.72 | 60.72 | 19959 | CLOSE | 2023-12-23 |  | KW1-13877 | 5 | 2023-12-23 | APPR | 2023-12-23 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-26 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 6145-60-V00-0112 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 95 MM² | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 11 | MR | 60 | 85.91 | 5154.6 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 52 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-30 | 60.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM ² | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 10 | YD | 25 | 267.6 | 267.6 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 51 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-25 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5940-60-V00-0016 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 16 MM² | 49828 | 2023-12-17 | 2023-12-19 | CLOSE | 1 | EA | 8 | 1.8 | 14.4 | 19959 | CLOSE | 2023-12-23 |  | KW1-13877 | 4 | 2023-12-23 | APPR | 2023-12-23 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-26 | 8.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5975-60-V00-0515 | STUFFING TUBE (CABLE GLAND), BRASS, BW, 50 MM | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 9 | EA | 2 | 29.8 | 59.6 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 50 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-25 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5940-60-V00-0025 | TERMINAL, LUG, TIN-PLATED, M12, 95MM², 3 X 24.5 X 60.5 INCHES | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 8 | EA | 8 | 28.84 | 230.72 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 49 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-25 | 8.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 4240-60-V00-0122 | TAPE, WARNING, CAUTION BURIED ELECTRICAL CABLE BELOW, YELLOW 6 INCHES X 1000 FEET | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 7 | RL | 1 | 176.82 | 176.82 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 48 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-27 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 6145-60-V00-0047 | WIRE, ELECTRICAL, GREEN/YELLOW, 1 CORE, 50MM ² | 49844 | 2023-12-17 | 2023-12-19 | CLOSE | 2 | MR | 60 | 10.3 | 618 |  |  |  |  | KW1-13827 | 3 | 2023-12-22 | APPR | 2023-12-22 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 | COMP | 2023-12-29 | 60.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5940-60-V00-0086 | LUG, TERMINAL, ROUND TYPE, ONE-HOLE, 50MM² X 10MM | 49827 | 2023-12-17 | 2023-12-19 |  | 6 | PG | 1 | 74.93 | 74.93 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 47 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 | COMP | 2023-12-30 | 6 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5610-60-V00-0014 | SAND | 49841 | 2023-12-17 | 2023-12-19 | CLOSE | 1 | CZ | 30 | 41.25 | 1237.5 | 19943 | CLOSE | 2023-12-26 | 2023-12-21 | KW1-13930 | 1 | 2023-12-26 | APPR | 2023-12-26 | Reghunath, Rajesh -Vectrus -GSD -No Export | GULF PIONEER COMPANY LLC | 2024-01-06 | COMP | 2023-12-27 | 30.00 | Catalog changed | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5620-60-V00-0006 | CONCRETE MASONRY UNIT, SOLID, 15 X 15 X 15 INCHES | 49842 | 2023-12-17 | 2023-12-19 | CLOSE | 1 | EA | 4 | 102.27 | 409.08 | 19939 | CLOSE | 2024-01-13 | 2023-12-23 | KW1-13992 | 7 | 2023-12-29 | APPR | 2024-01-03 | Reghuraman, Karthik -Vectrus -GSD -No Export | COMMERCIAL UNITED GINCO EST. | 2024-01-06 07:00 | COMP | 2024-01-13 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5306-60-V00-0005 | BOLT, CONCRETE ANCHOR, w/NUT & WASHER, M16 X 6 INCHES | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 5 | EA | 10 | 3.33 | 33.3 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 46 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-27 | 10.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5975-60-V00-0521 | CLAMP, GROUNDING, 5/8 INCH | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 4 | EA | 10 | 24.98 | 249.8 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 45 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-25 | 10.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5970-01-013-9369 | TAPE, INSULATION ELECTRICAL, 3M, 792", RED | 49843 | 2023-12-17 | 2023-12-19 | CLOSE | 2 | RO | 1 | 11.2 | 11.2 | 19959 | CLOSE | 2023-12-23 |  | KW1-13877 | 7 | 2023-12-23 | APPR | 2023-12-23 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-26 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5970-01-174-5651 | TAPE, INSULATION ELECTRICAL, 3M, 792", YELLOW | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 3 | RO | 1 | 10.1 | 10.1 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 44 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-25 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5970-01-015-5060 | TAPE, INSULATION ELECTRICAL, 3M, 792", BLUE | 49843 | 2023-12-17 | 2023-12-19 | CLOSE | 1 | RO | 1 | 10.23 | 10.23 | 19959 | CLOSE | 2023-12-23 |  | KW1-13877 | 6 | 2023-12-23 | APPR | 2023-12-23 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-10 | COMP | 2023-12-26 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5970-00-685-9059 | TAPE, INSULATION ELECTRICAL, 3M, 792", BLOCK | 49844 | 2023-12-17 | 2023-12-19 | CLOSE | 1 | RO | 1 | 39.58 | 39.58 |  |  |  |  | KW1-13827 | 2 | 2023-12-22 | APPR | 2023-12-22 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 | COMP | 2023-12-26 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5970-60-V00-0032 | TAPE, INSULATION ELECTRICAL, 3M, 792", YELLOW & GREEN | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 2 | RO | 1 | 16.98 | 16.98 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 43 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-25 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5975-60-V00-0504 | UNION, ELECTRICAL CONDUIT, NYLON POLYAMIDE, WHITE, 5-10 MM | 49827 | 2023-12-17 | 2023-12-19 | CLOSE | 1 | EA | 5 | 3.33 | 16.65 | 19938 | CLOSE | 2023-12-23 | 2023-12-23 | KW1-13886 | 42 | 2023-12-23 | APPR | 2023-12-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2023-12-30 07:00 | COMP | 2023-12-25 | 5.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 |  | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5975-60-V00-0498 | SPLICING KIT, CABLE JOINT, 25MM | [5 empty] | EA | 0 | [17 empty] | Not Required | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 | 30 | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5975-60-V00-0395 | STRAP, TIE DOWN, WHITE, 12 INCHES | 49845 | 2023-12-17 | 2023-12-19 | CLOSE | 1 | PG | 1 | 12.38 | 12.38 | 19986 | SENT | 2023-12-27 | 2023-12-24 | KW1-13963 | 1 | 2023-12-27 | APPR | 2023-12-27 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-10 | COMP | 2024-01-02 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
18 | 2023-12-17 |  | BU23-0366 | CONSOLIDATE POWER SERVING TT516 | 8528982 | 5940-60-V00-0091 | SPLICE, CONDUCTOR, BUTT, STANDARD BARREL, COPPER, BLUE, 16 MM | [5 empty] | PG | 0 | [17 empty] | Not Required | BU | BU table | December | 2023 | MM_BU
19 | 2023-12-21 | 30 | BU24-0027 | Service HVAC Units Z1 B1999 | 8236954 | 4130-60-V00-0484 | FILTER ELEMENT, AIR CONDITIONING, WASHABLE, ALUMINUM, 19.5 X 19.5 X 1.75 INCHES | 50183 | 2023-12-21 | 2023-12-23 | CLOSE | 1 | EA | 4 | 60.21 | 240.84 | 20126 | SENT | 2024-01-11 | 2024-01-05 | KW1-14093 | 1 | 2024-01-07 | APPR | 2024-01-07 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-01-25 | COMP | 2024-01-16 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
20 | 2023-12-21 | 30 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 8135-60-V00-0003 | PLASTIC SHEET, POLYETHYLENE, CLEAR, 6 MIL, 32 X 100 FEET | 50298 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | RO | 1 | 442.89 | 442.89 | 20210 | SENT | 2024-01-09 |  | KW1-14124 | 11 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
20 | 2023-12-21 | 30 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 5510-60-V00-0004 | LUMBER, SOFTWOOD, DIMENSION, 4 X 4 INCHES X 13 FEET | 50300 | 2023-12-23 | 2023-12-23 | CLOSE | 2 | EA | 60 | 37.46 | 2247.6 | 20018 | CLOSE | 2023-12-26 |  | KW1-13937 | 2 | 2023-12-26 | APPR | 2023-12-27 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-06 | COMP | 2023-12-30 | 60.00 |  | BU | BU table | December | 2023 | MM_BU
20 | 2023-12-21 | 30 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 5510-01-433-1244 | LUMBER, SMOOTH THREATED, 4 INCH X 16 FEET | 50525 | 2023-12-23 | 2023-12-25 | CLOSE | 1 | EA | 10 | 30.36 | 303.6 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 29 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 10.00 |  | BU | BU table | December | 2023 | MM_BU
20 | 2023-12-21 | 30 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 5530-00-618-8073 | PLYWOOD, CONSTRUCTION, 3/4 INCH X 4 X 8 FEET | 50299 | 2023-12-23 | 2023-12-23 | CLOSE | 2 | SH | 30 | 47.45 | 1423.5 | 20123 | CLOSE | 2024-01-04 |  | KW1-14040 | 1 | 2024-01-04 | APPR | 2024-01-04 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-15 | COMP | 2024-01-07 | 30.00 |  | BU | BU table | December | 2023 | MM_BU
20 | 2023-12-21 | 30 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 5530-60-V00-0010 | PLYWOOD, CONSTRUCTION, BLACK, 3/4 INCH X 4 X 8 FEET | 50299 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 25 | 61.61 | 1540.25 | 20102 | CLOSE | 2024-01-07 | 2024-01-04 | KW1-14079 | 10 | 2024-01-07 | APPR | 2024-01-07 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-21 | COMP | 2024-01-11 | 25.00 |  | BU | BU table | December | 2023 | MM_BU
20 | 2023-12-21 | 30 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 5305-60-V00-0147 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #7 X 2 INCHES | 50302 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | BX | 4 | 29.7 | 118.8 | 20206 | CLOSE | 2024-02-17 | 2024-01-10 | KW1-14188 | 10 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-20 | COMP | 2024-01-17 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
20 | 2023-12-21 | 30 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 5305-60-V00-0169 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 3 INCHES | 50300 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | BX | 3 | 30.97 | 92.91 | 20018 | CLOSE | 2023-12-26 |  | KW1-13937 | 1 | 2023-12-26 | APPR | 2023-12-27 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-20 | COMP | 2023-12-30 | 3.00 |  | BU | BU table | December | 2023 | MM_BU
20 | 2023-12-21 | 30 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 5510-01-433-1244 | LUMBER, SOFTWOOD, 2 X 4 INCHES X 16 FEET | 50607 | 2023-12-23 | 2023-12-26 | CLOSE | 1 | EA | 6 | 30.55 | 183.3 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 34 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 6.00 |  | BU | BU table | December | 2023 | MM_BU
20 | 2023-12-21 | 30 | BU24-0092 | Repair Floor Z5 TT507 | 8562496 | 5530-00-129-7777 | PLYWOOD, CONSTRUCTION, EXTERIOR, 1/2 INCH X 8 X 4 FEET | 50301 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 2 | 36.4 | 72.8 | 20206 | CLOSE | 2024-02-17 | 2024-01-10 | KW1-14188 | 14 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-26 | COMP | 2024-01-17 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 5530-00-618-8073 | PLYWOOD, CONSTRUCTION, 3/4 INCH X 4 X 8 FEET | 50426 | 2023-12-23 | 2023-12-24 | CLOSE | 3 | SH | 25 | 46.4 | 1160 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 15 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 25.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 5510-01-433-1244 | LUMBER, SMOOTH THREATED, 4 INCH X 16 FEET | 50424 | 2023-12-23 | 2023-12-24 | CLOSE | 1 | EA | 10 | 29.97 | 299.7 | 20210 | SENT | 2024-01-09 |  | KW1-14124 | 29 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-23 | COMP | 2024-01-14 | 10.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 5510-60-V00-0004 | LUMBER, SOFTWOOD, DIMENSION, 4 X 4 INCHES X 13 FEET | 50427 | 2023-12-23 | 2023-12-24 | CLOSE | 3 | EA | 10 | 36.63 | 366.3 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 18 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 10.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 5510-01-433-1371 | LUMBER, SOFTWOOD, 2 X 6 INCHES X 16 FEET | 50421 | 2023-12-23 | 2024-01-13 | CLOSE | 1 | EA | 25 | 17.75 | 443.75 | 20334 | CLOSE | 2024-01-13 | 2024-01-10 | KW1-14211 | 1 | 2024-01-13 | CLOSE | 2024-01-30 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-24 | 25.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 5305-60-V00-0147 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #7 X 2 INCHES | 50430 | 2023-12-23 | 2023-12-24 | CLOSE | 1 | BX | 1 | 29.7 | 29.7 | 20206 | CLOSE | 2024-02-17 | 2024-01-10 | KW1-14188 | 36 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-26 | COMP | 2024-01-17 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 5305-60-V00-0151 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, COARSE THREAD, #10 X 3-1/2 INCHES | 50426 | 2023-12-23 | 2023-12-24 | CLOSE | 2 | BX | 1 | 65.12 | 65.12 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 14 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 7210-60-V00-0059 | FLOOR COVERING, VINYL RESIN, 3 MM X 40 FEET | 50428 | 2023-12-23 | 2023-12-24 | CLOSE | 1 | RO | 1 | 716.1 | 716.1 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 19 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-24 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 8040-00-273-8713 | ADHESIVE, FLOORING, WHITE, | 50429 | 2023-12-23 | 2023-12-24 | CLOSE | 1 | GL | 3 | 185.7 | 557.1 | 20225 | CLOSE | 2024-01-10 | 2024-01-10 | KW1-14138 | 1 | 2024-01-11 | APPR | 2024-01-11 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 3.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 5640-60-V00-0038 | STRIP, ALUMINIUM, 3MM X 1-1/2 INCHES X 12FEET | 50426 | 2023-12-23 | 2023-12-24 | CLOSE | 1 | EA | 5 | 43.96 | 219.8 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 13 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 5.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 50423 | 2023-12-23 | 2023-12-24 | CLOSE | 3 | EA | 15 | 44.61 | 669.15 | 20214 | CLOSE | 2024-01-09 |  | KW1-14130 | 21 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 15.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 8030-01-075-1156 | CAULKING COMPOUND, LATEX, WHITE, 10.3 OZ | 50427 | 2023-12-23 | 2023-12-24 | CLOSE | 2 | EA | 12 | 14.65 | 175.8 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 17 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 12.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 8010-60-V00-0122 | PAINT, LATEX, MATT, WHITE, 16 LT | 50622 | 2023-12-23 | 2023-12-27 | CLOSE |  | CN | 2 | 66.14 | 132.28 | 20206 | CLOSE | 2024-02-17 | 2024-01-10 | KW1-14188 | 56 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-26 | COMP | 2024-01-25 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 50423 | 2023-12-23 | 2023-12-24 | CLOSE | 2 | CN | 1 | 36.63 | 36.63 | 20242 | CLOSE | 2024-01-10 |  | KW1-14159 | 1 | 2024-01-10 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-20 | COMP | 2024-01-13 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 50425 | 2023-12-23 | 2023-12-24 | CLOSE | 2 | EA | 3 | 28.65 | 85.95 |  |  |  |  | KW1-14173 | 2 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 3.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 50425 | 2023-12-23 | 2023-12-24 | CLOSE | 1 | EA | 10 | 13.67 | 136.7 |  |  |  |  | KW1-14173 | 1 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 10.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 50428 | 2023-12-23 | 2023-12-24 | CLOSE | 3 | EA | 3 | 14.6 | 43.8 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 21 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 3.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 8010-60-V00-0089 | PRIMER, COATING, WHITE, 4 - 5 LITERS | 50423 | 2023-12-23 | 2023-12-24 | CLOSE | 1 | CN | 3 | 40.5 | 121.5 | 20214 | CLOSE | 2024-01-09 |  | KW1-14130 | 20 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 3.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 6515-60-V00-0015 | GLOVES, EXAM, DISPOSABLE, NITRILE, PURPLE, X-LARGE | 50422 | 2023-12-23 | 2023-12-24 | CLOSE | 1 | EA | 1 | 48.84 | 48.84 | 20206 | CLOSE | 2024-02-17 | 2024-01-10 | KW1-14188 | 30 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-20 | COMP | 2024-01-21 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 5120-60-V00-0295 | CAULKING GUN, RATCHET ROD, PLASTIC, YELLOW/BLACK, 10 OZ | 50427 | 2023-12-23 | 2023-12-24 | CLOSE | 1 | EA | 1 | 163.61 | 163.61 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 16 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
21 | 2023-12-21 | 30 | BU240110 | Repair Floor Ceiling Z4 Pad9 B92 | 8674622 | 7510-00-266-6710 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 50428 | 2023-12-23 | 2023-12-24 | CLOSE | 2 | RO | 5 | 8 | 40 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 20 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 5.00 |  | BU | BU table | December | 2023 | MM_BU
22 | 2023-12-23 | 30 | BU24-0119 | Install Electrical Outlet Z2 T2072 | 8789414 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 50469 | 2023-12-24 | 2023-12-24 | CLOSE | 5 | EA | 3 | 10.1 | 30.3 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 26 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 3.00 |  | BU | BU table | December | 2023 | MM_BU
22 | 2023-12-23 | 30 | BU24-0119 | Install Electrical Outlet Z2 T2072 | 8789414 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 50469 | 2023-12-24 | 2023-12-24 | CLOSE | 4 | RO | 1 | 163 | 163 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 25 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
22 | 2023-12-23 | 30 | BU24-0119 | Install Electrical Outlet Z2 T2072 | 8789414 | 5975-60-V00-0652 | CONDUIT, EMT, STANDARD, GALVANIZED, GRAY, STEEL, 10 FEET X 3/4 INCHES | 50469 | 2023-12-24 | 2023-12-24 | CLOSE | 3 | EA | 4 | 158.18 | 632.72 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 24 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
22 | 2023-12-23 | 30 | BU24-0119 | Install Electrical Outlet Z2 T2072 | 8789414 | 5975-01-252-3611 | HANGER, CABLE, EMT, 1-HOLE PUSH-ON STRAP, STEEL, 3/4 X 1.99 INCHES | 50469 | 2023-12-24 | 2023-12-24 | CLOSE | 2 | EA | 15 | 6.49 | 97.35 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 23 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 15.00 |  | BU | BU table | December | 2023 | MM_BU
22 | 2023-12-23 | 30 | BU24-0119 | Install Electrical Outlet Z2 T2072 | 8789414 | 5975-09-V00-0137 | ADAPTER, ELECTRICAL CONDUIT, EMT, SET SCREW, ZINC PLATED STEEL, GRAY/YELLOW, 3/4 X 1-15/32 INCH | 50471 | 2023-12-24 | 2023-12-24 | CLOSE | 1 | EA | 8 | 1.18 | 9.44 | 20343 | CLOSE | 2024-01-23 | 2024-01-15 | KW1-14388 | 5 | 2024-01-23 | APPR | 2024-01-23 | Visakh, Ajith - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-23 | COMP | 2024-02-22 | 8.00 |  | BU | BU table | December | 2023 | MM_BU
22 | 2023-12-23 | 30 | BU24-0119 | Install Electrical Outlet Z2 T2072 | 8789414 | 5305-60-V00-0205 | SCREW, PHILLIPS, FLAT HEAD, STEEL, #8 X 1 INCH | 50470 | 2023-12-24 | 2023-12-24 | CLOSE | 1 | PG | 1 | 28.4 | 28.4 | 20210 | SENT | 2024-01-09 |  | KW1-14124 | 35 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-23 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
22 | 2023-12-23 | 30 | BU24-0119 | Install Electrical Outlet Z2 T2072 | 8789414 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50469 | 2023-12-24 | 2023-12-24 | CLOSE | 1 | EA | 4 | 3.7 | 14.8 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 22 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
23 | 2023-12-28 | 40 | BU-24-0098 | BUH-Z3-00-TRLR3020 | 7286430 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50798 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EA | 8 | 3.5 | 28 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 16 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 8.00 |  | BU | BU table | December | 2023 | MM_BU
23 | 2023-12-28 | 40 | BU-24-0098 | BUH-Z3-00-TRLR3020 | 7286430 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50800 | 2023-12-29 | 2023-12-30 | CLOSE | 2 | EA | 1 | 146.47 | 146.47 |  |  |  |  | KW1-14173 | 19 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
23 | 2023-12-28 | 40 | BU-24-0098 | BUH-Z3-00-TRLR3020 | 7286430 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 50798 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | RO | 1 | 146.52 | 146.52 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 15 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
23 | 2023-12-28 | 40 | BU-24-0098 | BUH-Z3-00-TRLR3020 | 7286430 | 5305-60-V00-0205 | SCREW, PHILLIPS, FLAT HEAD, STEEL, #8 X 1 INCH | 50799 | 2023-12-29 | 2023-12-30 | CLOSE | 1 | HD | 1 | 28.4 | 28.4 | 20213 | SENT | 2024-01-10 |  | KW1-14128 | 7 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-23 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
23 | 2023-12-28 | 40 | BU-24-0098 | BUH-Z3-00-TRLR3020 | 7286430 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 50800 | 2023-12-29 | 2023-12-30 | CLOSE | 1 | RO | 1 | 21.11 | 21.11 |  |  |  |  | KW1-14173 | 18 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
24 | 2023-12-28 | 50 | BU-24-0098 | BUH-00-ECP1-TRLR2000-00-00 | 5839058 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 50806 | 2023-12-29 | 2023-12-31 | CLOSE | 4 | ROLL | 1 | 146.52 | 146.52 | 20262 | CLOSE | 2024-01-19 | 2024-01-15 | KW1-14302 | 26 | 2024-01-19 | APPR | 2024-01-19 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-01-27 07:00 | COMP | 2024-01-23 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
24 | 2023-12-28 | 50 | BU-24-0098 | BUH-00-ECP1-TRLR2000-00-00 | 5839058 | 5975-60-V00-0533 | RACEWAY, CABLE, PVC, WHITE, 1-1/2 INCH X 10 FEET | 50806 | 2023-12-29 | 2023-12-31 | CLOSE | 3 | EACH | 7 | 1.64 | 11.49 | 20262 | CLOSE | 2024-01-19 | 2024-01-15 | KW1-14302 | 25 | 2024-01-19 | APPR | 2024-01-19 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-01-27 07:00 | COMP | 2024-01-23 | 7.00 |  | BU | BU table | December | 2023 | MM_BU
24 | 2023-12-28 | 50 | BU-24-0098 | BUH-00-ECP1-TRLR2000-00-00 | 5839058 | 6220-60-V00-0165 | LIGHT UNIT, EMERGENCY, EXIT SIGN, SELF-TEST, GREEN, 220-240V AC, 50/60 HZ, 3W | 50808 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | EACH | 2 | 147.3 | 294.6 |  |  |  |  | KW1-14173 | 20 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
24 | 2023-12-28 | 50 | BU-24-0098 | BUH-00-ECP1-TRLR2000-00-00 | 5839058 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50806 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EACH | 10 | 3.5 | 35 | 20262 | CLOSE | 2024-01-19 | 2024-01-15 | KW1-14302 | 24 | 2024-01-19 | APPR | 2024-01-19 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-01-27 07:00 | COMP | 2024-01-23 | 10.00 |  | BU | BU table | December | 2023 | MM_BU
24 | 2023-12-28 | 50 | BU-24-0098 | BUH-00-ECP1-TRLR2000-00-00 | 5839058 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 50806 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | PG | 3 | 27.31 | 81.93 | 20262 | CLOSE | 2024-01-19 | 2024-01-15 | KW1-14302 | 23 | 2024-01-19 | APPR | 2024-01-19 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-01-27 07:00 | COMP | 2024-01-23 | 3.00 |  | BU | BU table | December | 2023 | MM_BU
24 | 2023-12-28 | 50 | BU-24-0098 | BUH-00-ECP1-TRLR2000-00-00 | 5839058 | 5305-60-V00-0180 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #6 X 1 INCHES | 50807 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | BX | 1 | 25.8 | 25.8 |  |  |  |  | KW1-14180 | 12 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
25 | 2023-12-28 | 60 | BU-24-0098 | BUH-ECP1-TRLR2001-00 | 5930537 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50809 | 2023-12-29 | 2023-12-31 | CLOSE | 3 | EA | 10 | 3.5 | 35 |  |  |  |  | KW1-14173 | 23 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 10.00 |  | BU | BU table | December | 2023 | MM_BU
25 | 2023-12-28 | 60 | BU-24-0098 | BUH-ECP1-TRLR2001-00 | 5930537 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50810 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | EA | 3 | 146.47 | 439.41 |  |  |  |  | KW1-14173 | 24 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 3.00 |  | BU | BU table | December | 2023 | MM_BU
25 | 2023-12-28 | 60 | BU-24-0098 | BUH-ECP1-TRLR2001-00 | 5930537 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 50809 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | RO | 1 | 146.52 | 146.52 |  |  |  |  | KW1-14173 | 22 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
25 | 2023-12-28 | 60 | BU-24-0098 | BUH-ECP1-TRLR2001-00 | 5930537 | 5975-60-V00-0532 | PROTECTOR, ELECTRICAL CABLE, PVC, WHITE, 1/2 INCH X 10 FEET | 50811 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | EA | 4 | 8.82 | 35.28 | 20262 | CLOSE | 2024-01-19 | 2024-01-15 | KW1-14302 | 27 | 2024-01-19 | APPR | 2024-01-19 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-01-27 07:00 | COMP | 2024-01-23 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
25 | 2023-12-28 | 60 | BU-24-0098 | BUH-ECP1-TRLR2001-00 | 5930537 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 50809 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | PG | 2 | 27.31 | 54.62 |  |  |  |  | KW1-14173 | 21 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
26 | 2023-12-28 | 70 | BU-24-0098 | ECP2-TRLR-T003-00 | 5930556 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50814 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EACH | 2 | 146.47 | 292.94 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 18 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
26 | 2023-12-28 | 70 | BU-24-0098 | ECP2-TRLR-T003-00 | 5930556 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 50812 | 2023-12-29 | 2023-12-31 | CLOSE | 3 | ROLL | 1 | 146.52 | 146.52 |  |  |  |  | KW1-14173 | 27 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
26 | 2023-12-28 | 70 | BU-24-0098 | ECP2-TRLR-T003-00 | 5930556 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50812 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EACH | 6 | 3.5 | 21 |  |  |  |  | KW1-14173 | 26 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 6.00 |  | BU | BU table | December | 2023 | MM_BU
26 | 2023-12-28 | 70 | BU-24-0098 | ECP2-TRLR-T003-00 | 5930556 | 5975-60-V00-0531 | PROTECTOR, ELECTRICAL CABLE, PVC, WHITE, 1 INCH X 9 FEET | 50812 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | EACH | 4 | 16.48 | 65.92 |  |  |  |  | KW1-14173 | 25 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
26 | 2023-12-28 | 70 | BU-24-0098 | ECP2-TRLR-T003-00 | 5930556 | 5305-60-V00-0180 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #6 X 1 INCHES | 50813 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | BOX | 1 | 25.8 | 25.8 |  |  |  |  | KW1-14180 | 13 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
26 | 2023-12-28 | 70 | BU-24-0098 | ECP2-TRLR-T003-00 | 5930556 | 5975-60-V00-0480 | JUNCTION BOX, w/ BLANK SIDE, 100 X 100 X 50 MM | 50814 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | EACH | 1 | 12 | 12 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 17 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
27 | 2023-12-28 | 80 | BU-24-0098 | BUH-Z1-00-TT106 | 6779272 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50815 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EA | 8 | 3.5 | 28 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 20 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 8.00 |  | BU | BU table | December | 2023 | MM_BU
27 | 2023-12-28 | 80 | BU-24-0098 | BUH-Z1-00-TT106 | 6779272 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50818 | 2023-12-29 | 2023-12-31 | CLOSE | 5 | EA | 2 | 146.47 | 292.94 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 25 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
27 | 2023-12-28 | 80 | BU-24-0098 | BUH-Z1-00-TT106 | 6779272 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 50818 | 2023-12-29 | 2023-12-31 | CLOSE | 4 | RO | 1 | 163 | 163 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 24 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
27 | 2023-12-28 | 80 | BU-24-0098 | BUH-Z1-00-TT106 | 6779272 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 50817 | 2023-12-29 | 2023-12-30 | CLOSE | 1 | BX | 1 | 51.5 | 51.5 | 20213 | SENT | 2024-01-10 |  | KW1-14128 | 10 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-23 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
27 | 2023-12-28 | 80 | BU-24-0098 | BUH-Z1-00-TT106 | 6779272 | 5930-60-V00-0240 | SWITCH, 1 WAY, 1 GANG, 10 AMPS | 50816 | 2023-12-29 | 2024-01-10 | CLOSE | 1 | EA | 2 | 17.3 | 34.6 | 20242 | CLOSE | 2024-01-10 |  | KW1-14158 | 1 | 2024-01-10 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-20 | COMP | 2024-01-14 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
27 | 2023-12-28 | 80 | BU-24-0098 | BUH-Z1-00-TT106 | 6779272 | 5975-60-V00-0272 | SWITCH BOX, SURFACE, PVC, WHITE, 3 X 3 INCHES | 50818 | 2023-12-29 | 2023-12-31 | CLOSE | 3 | EA | 2 | 12.24 | 24.48 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 23 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
27 | 2023-12-28 | 80 | BU-24-0098 | BUH-Z1-00-TT106 | 6779272 | 5975-60-V00-0187 | PLATE, WALL, ELECTRICAL, BLANK, 1 GANG, WHITE, 86 X 86 MM | 50818 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | BX | 1 | 13.46 | 13.46 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 22 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-20 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
27 | 2023-12-28 | 80 | BU-24-0098 | BUH-Z1-00-TT106 | 6779272 | 5975-00-156-3253 | STRAP, TIE DOWN, ELECTRICAL COMPONE, 13-7/20 INCHES | 50815 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | HD | 2 | 26.64 | 53.28 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 19 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
27 | 2023-12-28 | 80 | BU-24-0098 | BUH-Z1-00-TT106 | 6779272 | 5975-60-V00-0740 | CONDUIT, HIGHLY FLEXIBLE, CORE, GALVANIZED STEEL, BLACK, 20 MM X 25 M | 50818 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | RO | 1 | 92.57 | 92.57 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 21 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
28 | 2023-12-28 | 90 | BU-24-0098 | BUH-Z3-00-TRLR3000 | 7227578 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50819 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EA | 8 | 3.5 | 28 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 27 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 8.00 |  | BU | BU table | December | 2023 | MM_BU
28 | 2023-12-28 | 90 | BU-24-0098 | BUH-Z3-00-TRLR3000 | 7227578 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50821 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EA | 1 | 146.47 | 146.47 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 32 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
28 | 2023-12-28 | 90 | BU-24-0098 | BUH-Z3-00-TRLR3000 | 7227578 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 50819 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | RO | 1 | 146.52 | 146.52 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 26 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
28 | 2023-12-28 | 90 | BU-24-0098 | BUH-Z3-00-TRLR3000 | 7227578 | 5305-60-V00-0205 | SCREW, PHILLIPS, FLAT HEAD, STEEL, #8 X 1 INCH | 50820 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | HD | 1 | 28.4 | 28.4 | 20213 | SENT | 2024-01-10 |  | KW1-14128 | 11 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-23 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
28 | 2023-12-28 | 90 | BU-24-0098 | BUH-Z3-00-TRLR3000 | 7227578 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 50821 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | RO | 1 | 21.11 | 21.11 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 31 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
29 | 2023-12-28 | 100 | BU-24-0098 | BUH-Z6-00-TRLR3013 | 7227613 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50908 | 2023-12-30 | 2023-12-31 | CLOSE | 2 | EA | 1 | 146.47 | 146.47 |  |  |  |  | KW1-14173 | 48 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
29 | 2023-12-28 | 100 | BU-24-0098 | BUH-Z6-00-TRLR3013 | 7227613 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 50908 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | RO | 1 | 145 | 145 |  |  |  |  | KW1-14173 | 47 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
29 | 2023-12-28 | 100 | BU-24-0098 | BUH-Z6-00-TRLR3013 | 7227613 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 50907 | 2023-12-30 | 2023-12-31 | CLOSE | 2 | BX | 1 | 170.5 | 170.5 | 20261 | CLOSE | 2024-01-11 | 2024-01-11 | KW1-14183 | 2 | 2024-01-11 | APPR | 2024-01-11 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
29 | 2023-12-28 | 100 | BU-24-0098 | BUH-Z6-00-TRLR3013 | 7227613 | 5975-60-V00-0091 | CONDUIT, NONMETALLIC, RIGID, PVC, WHITE, 20 MM X 1.5 METERS | 50905 | 2023-12-30 | 2023-12-31 | CLOSE | 2 | EA | 5 | 9.32 | 46.6 |  |  |  |  | KW1-14173 | 45 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 5.00 | Requested catalog not Active | BU | BU table | December | 2023 | MM_BU
29 | 2023-12-28 | 100 | BU-24-0098 | BUH-Z6-00-TRLR3013 | 7227613 | 4730-60-V00-0045 | ADAPTER, ELECTRICAL CONDUIT, w/BUSH, FEMALE, PVC, WHITE, 20 MM | 50907 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | EA | 5 | 6.2 | 31 | 20261 | CLOSE | 2024-01-11 | 2024-01-11 | KW1-14183 | 1 | 2024-01-11 | APPR | 2024-01-11 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-16 | 5.00 |  | BU | BU table | December | 2023 | MM_BU
29 | 2023-12-28 | 100 | BU-24-0098 | BUH-Z6-00-TRLR3013 | 7227613 | 5365-60-V00-0026 | SADDLE, SPACER BAR, CONDUIT, PVC, WHITE, 20 MM | 50906 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | EA | 10 | 3.16 | 31.6 |  |  |  |  | KW1-14173 | 46 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 10.00 |  | BU | BU table | December | 2023 | MM_BU
29 | 2023-12-28 | 100 | BU-24-0098 | BUH-Z6-00-TRLR3013 | 7227613 | 5975-60-V00-0372 | COUPLING, ELECTRICAL CONDUIT, PVC, WHITE, 20 MM | 50905 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | EA | 10 | 4.66 | 46.6 |  |  |  |  | KW1-14173 | 44 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 10.00 |  | BU | BU table | December | 2023 | MM_BU
29 | 2023-12-28 | 100 | BU-24-0098 | BUH-Z6-00-TRLR3013 | 7227613 | 5975-60-V00-0085 | ELBOW ,CONDUIT , PVC, WHITE, 20 MILLIMETERS | 50903 | 2023-12-30 | 2023-12-30 | CLOSE | 1 | EA | 10 | 13.99 | 139.9 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 56 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 10.00 |  | BU | BU table | December | 2023 | MM_BU
30 | 2023-12-28 | 110 | BU-24-0098 | BUH-Z3-00-TRLR3017 | 7286407 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50822 | 2023-12-29 | 2023-12-31 | CLOSE | 3 | EA | 4 | 3.5 | 14 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 30 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
30 | 2023-12-28 | 110 | BU-24-0098 | BUH-Z3-00-TRLR3017 | 7286407 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50824 | 2023-12-29 | 2023-12-31 | CLOSE | 3 | EA | 1 | 146.47 | 146.47 |  |  |  |  | KW1-14173 | 30 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
30 | 2023-12-28 | 110 | BU-24-0098 | BUH-Z3-00-TRLR3017 | 7286407 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 50822 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | RO | 1 | 146.52 | 146.52 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 29 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
30 | 2023-12-28 | 110 | BU-24-0098 | BUH-Z3-00-TRLR3017 | 7286407 | 5305-60-V00-0205 | SCREW, PHILLIPS, FLAT HEAD, STEEL, #8 X 1 INCH | 50823 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | HD | 1 | 28.4 | 28.4 | 20213 | SENT | 2024-01-10 |  | KW1-14128 | 8 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-23 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
30 | 2023-12-28 | 110 | BU-24-0098 | BUH-Z3-00-TRLR3017 | 7286407 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 50824 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | RO | 1 | 21.11 | 21.11 |  |  |  |  | KW1-14173 | 29 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
30 | 2023-12-28 | 110 | BU-24-0098 | BUH-Z3-00-TRLR3017 | 7286407 | 5975-60-V00-0531 | PROTECTOR, ELECTRICAL CABLE, PVC, WHITE, 1 INCH X 9 FEET | 50822 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | EA | 4 | 16.48 | 65.92 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 28 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
30 | 2023-12-28 | 110 | BU-24-0098 | BUH-Z3-00-TRLR3017 | 7286407 | 5975-60-V00-0480 | JUNCTION BOX, w/ BLANK SIDE, 100 X 100 X 50 MM | 50824 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | EA | 1 | 12 | 12 |  |  |  |  | KW1-14173 | 28 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
31 | 2023-12-28 | 120 | BU-24-0098 | BUH-Z3-00-TRLR3021 | 7286435 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50822 | 2023-12-29 | 2023-12-31 | CLOSE | 3 | EA | 8 | 3.5 | 14 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 30 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
31 | 2023-12-28 | 120 | BU-24-0098 | BUH-Z3-00-TRLR3021 | 7286435 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50824 | 2023-12-29 | 2023-12-31 | CLOSE | 3 | EA | 1 | 146.47 | 146.47 |  |  |  |  | KW1-14173 | 30 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
31 | 2023-12-28 | 120 | BU-24-0098 | BUH-Z3-00-TRLR3021 | 7286435 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 50822 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | RO | 1 | 146.52 | 146.52 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 29 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
31 | 2023-12-28 | 120 | BU-24-0098 | BUH-Z3-00-TRLR3021 | 7286435 | 5305-60-V00-0205 | SCREW, PHILLIPS, FLAT HEAD, STEEL, #8 X 1 INCH | 50823 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | HD | 1 | 28.4 | 28.4 | 20213 | SENT | 2024-01-10 |  | KW1-14128 | 8 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-23 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
31 | 2023-12-28 | 120 | BU-24-0098 | BUH-Z3-00-TRLR3021 | 7286435 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 50824 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | RO | 1 | 21.11 | 21.11 |  |  |  |  | KW1-14173 | 29 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
32 | 2023-12-28 | 130 | BU-24-0098 | UD-AF-9602-00 | 7372091 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50830 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EA | 2 | 146.47 | 292.94 |  |  |  |  | KW1-14173 | 38 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
32 | 2023-12-28 | 130 | BU-24-0098 | UD-AF-9602-00 | 7372091 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 50830 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | RO | 1 | 163 | 163 |  |  |  |  | KW1-14173 | 37 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
32 | 2023-12-28 | 130 | BU-24-0098 | UD-AF-9602-00 | 7372091 | 5975-60-V00-0531 | PROTECTOR, ELECTRICAL CABLE, PVC, WHITE, 1 INCH X 9 FEET | 50828 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EA | 8 | 16.48 | 131.84 |  |  |  |  | KW1-14173 | 36 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 8.00 |  | BU | BU table | December | 2023 | MM_BU
32 | 2023-12-28 | 130 | BU-24-0098 | UD-AF-9602-00 | 7372091 | 5975-60-V00-0506 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, WHITE, PG29, 18-25MM | 50828 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | EA | 5 | 28.31 | 141.55 |  |  |  |  | KW1-14173 | 35 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 5.00 |  | BU | BU table | December | 2023 | MM_BU
32 | 2023-12-28 | 130 | BU-24-0098 | UD-AF-9602-00 | 7372091 | 5305-60-V00-0187 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATE, #6 X 1 INCH | 50829 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | BX | 1 | 14.82 | 14.82 |  |  |  |  | KW1-14180 | 15 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
33 | 2023-12-28 | 140 | BU-24-0098 | UD-AF-9206-00 | 7372568 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50837 | 2023-12-29 | 2023-12-30 | CLOSE | 2 | EA | 2 | 161.7 | 323.4 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 38 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
33 | 2023-12-28 | 140 | BU-24-0098 | UD-AF-9206-00 | 7372568 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 50837 | 2023-12-29 | 2023-12-30 | CLOSE | 1 | RO | 1 | 163.35 | 163.35 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 37 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
33 | 2023-12-28 | 140 | BU-24-0098 | UD-AF-9206-00 | 7372568 | 5975-60-V00-0531 | PROTECTOR, ELECTRICAL CABLE, PVC, WHITE, 1 INCH X 9 FEET | 50835 | 2023-12-29 | 2023-12-30 | CLOSE | 2 | EA | 2 | 16.12 | 32.24 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 36 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
33 | 2023-12-28 | 140 | BU-24-0098 | UD-AF-9206-00 | 7372568 | 5975-60-V00-0506 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, WHITE, PG29, 18-25MM | 50835 | 2023-12-29 | 2023-12-30 | CLOSE | 1 | EA | 5 | 28 | 140 | 20215 | SENT | 2024-01-10 |  | KW1-14132 | 35 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 5.00 |  | BU | BU table | December | 2023 | MM_BU
33 | 2023-12-28 | 140 | BU-24-0098 | UD-AF-9206-00 | 7372568 | 5305-60-V00-0187 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATE, #6 X 1 INCH | 50836 | 2023-12-29 | 2023-12-30 | CLOSE | 1 | BX | 1 | 14.69 | 14.69 | 20213 | SENT | 2024-01-10 |  | KW1-14128 | 12 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-23 | COMP | 2024-01-14 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
34 | 2023-12-28 | 150 | BU-24-0098 | UD-AF-9410-00 | 7372576 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 50833 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EA | 2 | 146.47 | 292.94 |  |  |  |  | KW1-14173 | 43 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
34 | 2023-12-28 | 150 | BU-24-0098 | UD-AF-9410-00 | 7372576 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 50833 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | RO | 1 | 163 | 163 |  |  |  |  | KW1-14173 | 42 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
34 | 2023-12-28 | 150 | BU-24-0098 | UD-AF-9410-00 | 7372576 | 5975-60-V00-0531 | PROTECTOR, ELECTRICAL CABLE, PVC, WHITE, 1 INCH X 9 FEET | 50831 | 2023-12-29 | 2023-12-31 | CLOSE | 3 | EA | 2 | 16.48 | 32.96 |  |  |  |  | KW1-14173 | 41 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
34 | 2023-12-28 | 150 | BU-24-0098 | UD-AF-9410-00 | 7372576 | 5975-60-V00-0534 | PROTECTOR, CABLE, PVC, WHITE, 2 INCHES X 10 FEET | 50831 | 2023-12-29 | 2023-12-31 | CLOSE | 2 | EA | 2 | 167.83 | 335.66 |  |  |  |  | KW1-14173 | 40 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-25 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
34 | 2023-12-28 | 150 | BU-24-0098 | UD-AF-9410-00 | 7372576 | 5975-60-V00-0506 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, WHITE, PG29, 18-25MM | 50831 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | EA | 6 | 28.31 | 169.86 |  |  |  |  | KW1-14173 | 39 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 6.00 |  | BU | BU table | December | 2023 | MM_BU
34 | 2023-12-28 | 150 | BU-24-0098 | UD-AF-9410-00 | 7372576 | 5305-60-V00-0187 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATE, #6 X 1 INCH | 50832 | 2023-12-29 | 2023-12-31 | CLOSE | 1 | BX | 1 | 14.82 | 14.82 |  |  |  |  | KW1-14180 | 16 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 14 | EA | 13 | 9.9 | 128.7 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 33 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 13.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5935-60-V00-0172 | SOCKET, ELECTRICAL, FEMALE, 3 PIN, 220V, 32A | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 14 | EA | 1 | 35.82 | 35.82 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 19 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5935-60-V00-0173 | CONNECTOR, PLUG, ELECTRICAL, MALE, 3 PIN, 32A | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 13 | EA | 1 | 11.07 | 11.07 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 18 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 |  | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 6145-60-V00-0163 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORE, 4 MM² |  | 2023-12-30 |  |  |  | RO | 3 | [17 empty] | As per the BOM this items are not required | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 |  | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V01-0053 | RACEWAY, METALLIC, (CABLE TRUNKING), GALVANIZED STEEL, 3 X 3 INCHES X 10 FEET |  | 2023-12-30 |  |  |  | EA | 30 | [17 empty] | As per the BOM this items are not required | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0504 | UNION, ELECTRICAL CONDUIT, NYLON POLYAMIDE, LONG THREAD, 5-10 MM | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 12 | EA | 4 | 3.26 | 13.04 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 17 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 6145-60-V00-0038 | CABLE, POWER, ELECTRICAL, CU/PVC/PVC, WHITE, 3 CORE, 6 MM² | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 11 | MR | 80 | 8.47 | 677.6 | 20300 | SENT | 2024-02-15 | 2024-01-14 | KW1-14272 | 11 | 2024-01-18 | APPR | 2024-01-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-23 | 80.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5935-60-V00-0169 | CONNECTOR, WIRE, ORANGE, 18-14 AWG | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 13 | PG | 2 | 25.3 | 50.6 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 32 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 |  | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5305-60-V00-0148 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES |  | 2023-12-30 |  |  |  | BX | 1 | [17 empty] | As per the BOM this items are not required | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 12 | RO | 1 | 92 | 92 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 31 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-17 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 |  | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5305-60-V00-0205 | SCREW, PHILLIPS, FLAT HEAD, STEEL, #8 X 1 INCH |  | 2023-12-30 |  |  |  | BX | 1 | [17 empty] | As per the BOM this items are not required | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5970-60-V00-0040 | TAPE, INSULATION, RED, 3/4 INCH X 25 METER | 50934 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | RO | 1 | 19 | 38 | 20305 | INPRG | 2024-02-03 |  | KW1-14209 | 6 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 2 | RO | 1 | 16.83 | 33.66 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 22 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 |  | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-00-178-1217 | CONDUIT, METAL, RIGID, STEEL, 3/4 INCH X 10 FEET |  | 2023-12-30 |  |  |  | LG | 10 | [17 empty] | As per the BOM this items are not required | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0379 | CLAMP, ELECTRICAL, CONDUIT, 2 HOLE, GALVANIZED STEEL, 3/4 INCH | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 10 | EA | 15 | 2.6 | 39 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 16 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 15.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0017 | COUPLING, ELECTRICAL CONDUIT, ZINC PLATED STEEL, 3/4 INCH | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 9 | PG | 1 | 87.75 | 87.75 | 20300 | SENT | 2024-02-15 | 2024-01-14 | KW1-14272 | 10 | 2024-01-18 | APPR | 2024-01-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-23 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5925-60-V00-0145 | CIRCUIT BREAKER, MINIATURE, 1 POLE, 230VAC, 32A | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 11 | EA | 1 | 7.29 | 7.29 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 30 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 6145-60-V00-0143 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4 MM² | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 10 | RO | 3 | 90.56 | 271.68 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 29 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 3.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 6145-60-V00-0154 | WIRE, ELECTRICAL, BLACK, 1 CORE, 4 MM ² | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 8 | RO | 3 | 89.38 | 268.14 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 15 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-17 | 3.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 6145-60-V00-0159 | WIRE, ELECTRICAL, BLUE, 1 CORE, 4 MM ² | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 9 | RO | 3 | 90.56 | 271.68 | 20305 | INPRG | 2024-02-03 |  | KW1-14207 | 2 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-02-29 | COMP | 2024-01-16 | 3.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 6145-60-V00-0136 | WIRE, ELECTRICAL, RED, 1 CORE, 4 MM ² | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 8 | RO | 3 | 90.7 | 272.1 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 28 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 3.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 6145-60-V00-0157 | WIRE, ELECTRICAL, YELLOW, 1 CORE, 4MM ² | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 7 | MR | 270 | 1.4 | 378 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 27 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-20 | 270.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5935-60-V00-0167 | CONNECTOR, WIRE, RED, 18 -10 AWG | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 7 | PG | 3 | 25.07 | 75.21 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 14 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 3.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0528 | CONDUIT, RIGID, EMT, GALVANIZED STEEL, 1/2 INCH X 10 FEET | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 6 | EA | 35 | 24.3 | 850.5 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 26 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-17 | 35.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0197 | ELBOW, ELECTRICAL CONDUIT, ½ INCH | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 6 | EA | 6 | 12.54 | 75.24 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 13 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 6.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0487 | COUPLING, ELECTRICAL CONDUIT, w/ SCREW, ½ INCH | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 5 | EA | 50 | 4.23 | 211.5 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 12 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-10 | COMP | 2024-01-16 | 47.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0381 | CLAMP, ELECTRICAL, CONDUIT, 2 HOLE, STEEL, 1/2 INCH | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | EA | 50 | 3.91 | 195.5 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 9 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-17 | 11.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0026 | BOX CONNECTOR, ELECTRICAL, LIQUID-TIGHT, ZINC, 1/2 INCH | 50936 | 2023-12-30 | 2023-12-31 | CLOSE | 2 | BX | 2 | 115.5 | 231 | 20300 | SENT | 2024-02-15 | 2024-01-14 | KW1-14272 | 13 | 2024-01-18 | APPR | 2024-01-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-23 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0413 | ANCHOR, PLASTIC, BUTTERFLY, WHITE, 6MM | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 5 | BX | 1 | 33.7 | 33.7 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 25 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-20 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0284 | JUNCTION BOX, w/ KNOCKOUT, STEEL, 73 X 73 X 40 MM | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 4 | EA | 5 | 6.61 | 33.05 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 11 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 5.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0254 | COVER, JUNCTION BOX, BLANKING PLATE, STEEL, 1 GANG, GRAY, 79 X 79 X 42 MM | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 4 | EA | 5 | 6.27 | 31.35 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 24 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 5.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 3 | RO | 2 | 21.11 | 42.22 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 23 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 2 | RO | 1 | 16.83 | 33.66 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 22 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5970-60-V00-0040 | TAPE, INSULATION, RED, 3/4 INCH X 25 METER | 50934 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | RO | 1 | 19 | 38 | 20305 | INPRG | 2024-02-03 |  | KW1-14209 | 6 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 50933 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | BX | 2 | 29.27 | 58.54 | 20305 | INPRG | 2024-02-03 |  | KW1-14209 | 5 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 3 | EA | 4 | 3.42 | 13.68 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 10 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5305-60-V00-0150 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, TWIN FAST THREAD, #10 X 1-1/2 INCHES | 50936 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | BX | 1 | 27.85 | 27.85 | 20300 | SENT | 2024-02-15 | 2024-01-14 | KW1-14272 | 12 | 2024-01-18 | APPR | 2024-01-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-23 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5975-00-178-1217 | CONDUIT, METAL, RIGID, STEEL, 3/4 INCH X 10 FEET | 50935 | 2023-12-30 | 2023-12-31 | CLOSE | 1 | EA | 2 | 13.6 | 27.2 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 21 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-17 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
35 | 2023-12-30 | 30 | BU24-0086 | Install Outlets Z4 TT4053 | 8887890 | 5935-60-V00-0154 | BOX CONNECTOR, ELECTRICAL, CONCRETE-TIGHT CONDUIT, STEEL, 3/4 INCH | 50932 | 2023-12-30 | 2023-12-31 | CLOSE | 2 | PG | 1 | 98.77 | 98.77 | 20748 | CLOSE | 2024-02-03 |  | KW1-14620 | 1 | 2024-02-03 | CLOSE | 2024-02-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-30 | 40 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 5510-00-220-6242 | LUMBER, SOFTWOOD, DIMENSION, 4 X 2 INCHES X 10 FEET | 51196 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 4 | 21.65 | 86.6 | 20305 | INPRG | 2024-02-03 |  | KW1-14209 | 17 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 | COMP | 2024-01-16 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-30 | 40 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 5530-60-V00-0011 | PLYWOOD, CONSTRUCTION, INTERIOR, 3/4 INCH X 8 X 4 FEET | 51198 | 2024-01-04 | 2024-01-06 | CLOSE | 2 | EA | 3 | 57.25 | 171.75 | 20263 | CLOSE | 2024-01-20 | 2024-01-15 | KW1-14320 | 6 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-03 07:00 | COMP | 2024-01-24 | 3.00 |  | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-30 | 40 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 9330-60-V00-0016 | SHEET, ACRYLIC, WHITE, 48 X 96 X 0.250 INCHES | 51195 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 1 | 183.15 | 183.15 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 48 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-17 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-30 | 40 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 5305-60-V00-0149 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, TWIN FAST THREAD, #8 X 2-1/2 INCHES | 51197 | 2024-01-04 | 2024-01-06 | CLOSE | 2 | PG | 1 | 38.8 | 38.8 |  |  |  |  | KW1-14180 | 26 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-30 | 40 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 8010-00-297-0584 | PAINT, ENAMEL, SEMIGLOSS, WHITE, 1 GL | 51199 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | GL | 1 | 41.53 | 41.53 | 20263 | CLOSE | 2024-01-20 | 2024-01-15 | KW1-14320 | 7 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-03 07:00 | COMP | 2024-01-28 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-30 | 40 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 8020-00-205-6500 | BRUSH, PAINT, BRISTLES, CHISELED, 3 INCHES | 51197 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 4 | 21.9 | 87.6 |  |  |  |  | KW1-14173 | 70 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-30 | 40 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 8010-60-V00-0003 | PRIMER COATING, WOOD, ALKYD, WHITE, 16 LITER | 51230 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | CN | 1 | 162.1 | 162.1 | 20302 | CLOSE | 2024-01-21 | 2024-01-14 | KW1-14335 | 3 | 2024-01-21 | APPR | 2024-01-21 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-11 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-30 | 40 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GALLON | 51198 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | CN | 1 | 228.7 | 228.7 |  |  |  |  | KW1-14173 | 71 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-18 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0966 | ELBOW, SEWER AND DRAIN FITTINGS, PVC, STANDARD, 87.5 °, SPIGOT X SOCKET, SCH- 40, GREY, 50 MM | 50320 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 4 | 10.81 | 43.24 | 20209 | CLOSE | 2024-01-25 | 2024-01-11 | KW1-14294 | 21 | 2024-01-19 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-27 | 4.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0335 | COUPLING, PIPE, w/ RUBBER SEAL, SOCKET X SOCKET, UPVC, GRAY, 50 MM | 50317 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 4 | 10.8 | 43.2 |  |  |  |  | KW1-14123 | 7 | 2024-01-09 | APPR | 2024-01-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-30 07:00 | COMP | 2024-01-14 | 4.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 9150-60-V00-0050 | LUBRICANT, PIPE JOINT, 32 FL OUNCES | 50312 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | CN | 1 | 21.98 | 21.98 | 20210 | SENT | 2024-01-09 |  | KW1-14124 | 13 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-25 | COMP | 2024-01-14 | 1.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 8030-00-889-3535 | TAPE, ANTISEIZING, POLYTETRAFLUOROETHYLENE, ½ X 260 INCHES | 50318 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 10 | 7 | 70 | 20209 | CLOSE | 2024-01-25 | 2024-01-11 | KW1-14294 | 18 | 2024-01-19 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-27 | 10.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 50315 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | BX | 6 | 143.19 | 859.14 | 20214 | CLOSE | 2024-01-09 |  | KW1-14130 | 6 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 6.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 8040-60-V00-0040 | CEMENT, HEAVY BODIED, CPVC, ORANGE, 16 OZ | 50315 | 2023-12-23 | 2023-12-23 | CLOSE | 2 | CN | 1 | 18.32 | 18.32 | 20214 | CLOSE | 2024-01-09 |  | KW1-14130 | 7 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 1.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4510-60-V00-0077 | DRAIN, SINK, STAINLESS STEEL | 50313 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 2 | 27.47 | 54.94 | 20223 | CLOSE | 2024-01-10 |  | KW1-14135 | 1 | 2024-01-10 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-02-29 | COMP | 2024-01-14 | 2.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 7105-60-V00-0019 | MIRROR, GLASS, ROUND, WALL MOUNTED, WHITE, 50 CM | 50318 | 2023-12-23 | 2023-12-23 | CLOSE | 2 | EA | 2 | 21 | 42 | 20209 | CLOSE | 2024-01-25 | 2024-01-11 | KW1-14294 | 19 | 2024-01-19 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-27 | 2.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4820-60-V00-0127 | VALVE, BALL, THREADED, w/ HANDLE, BRASS, PN32, 3/4 INCH | 50316 | 2023-12-23 | 2023-12-23 | CLOSE | 2 | EA | 4 | 18.32 | 73.28 |  |  |  |  | KW1-14053 | 2 | 2024-01-04 | APPR | 2024-01-04 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-18 07:00 | COMP | 2024-01-10 | 4.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0940 | TEE, PIPE, SOCKET X SOCKET X SOCKET, CPVC, OFF-WHITE, SCH 40, 25 MM | 50527 | 2023-12-23 | 2023-12-25 | CLOSE | 1 | EA | 6 | 7.26 | 43.56 |  |  |  |  | KW1-14180 | 4 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 6.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0754 | ADAPTER, PRESSURE FITTINGS, MALE, CPVC, STANDARD, SOCKET X MIPT, PN16, OFF-WHITE, 25 MM | 50316 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 10 | 3.33 | 33.3 |  |  |  |  | KW1-14053 | 1 | 2024-01-04 | APPR | 2024-01-04 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-18 07:00 | COMP | 2024-01-10 | 10.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0448 | ELBOW, PIPE, SOCKET X SPIGOT, 45°, UPVC, GRAY, 50MM | 50314 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 8 | 13.99 | 111.92 | 20210 | SENT | 2024-01-09 |  | KW1-14124 | 14 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-23 | COMP | 2024-01-14 | 8.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0930 | TEE, PIPE, SOCKET X SOCKET X SOCKET, PVC, GRAY, SCH 40, 50 MM | 50317 | 2023-12-23 | 2023-12-23 | CLOSE | 2 | EA | 2 | 17.17 | 34.34 |  |  |  |  | KW1-14123 | 8 | 2024-01-09 | APPR | 2024-01-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-30 07:00 | COMP | 2024-01-14 | 2.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0734 | WYE, TRUE, PIPE, BRANCH, UPVC, 45 DEG, 50 MM | 50319 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 4 | 12.15 | 48.6 | 20209 | CLOSE | 2024-01-25 | 2024-01-11 | KW1-14294 | 20 | 2024-01-19 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-27 | 4.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0863 | ELBOW, PRESSURE FITTINGS, CPVC, BRASS, REDUCTION, 90 °, SOCKET X FIPT, SCH- 40, OFF-WHITE, 25 x 20 MM | 50317 | 2023-12-23 | 2023-12-23 | CLOSE | 3 | EA | 6 | 14.8 | 88.8 |  |  |  |  | KW1-14123 | 9 | 2024-01-09 | APPR | 2024-01-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-30 07:00 | COMP | 2024-01-14 | 6.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0927 | TEE, PIPE, SOCKET X SOCKET X FIPT, SCH-80, CPVC, OFF-WHITE, 25 MM X 1/2 INCH | 50317 | 2023-12-23 | 2023-12-23 | CLOSE | 4 | EA | 4 | 17 | 68 |  |  |  |  | KW1-14123 | 10 | 2024-01-09 | APPR | 2024-01-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-30 07:00 | COMP | 2024-01-14 | 4.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4730-60-V00-0834 | COUPLING, CPVC, SCH-40, TAN, 25 MM | 50316 | 2023-12-23 | 2023-12-23 | CLOSE | 3 | EA | 4 | 5.16 | 20.64 |  |  |  |  | KW1-14053 | 3 | 2024-01-04 | APPR | 2024-01-04 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-18 07:00 | COMP | 2024-01-10 | 4.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4720-60-V00-0268 | HOSE, METALLIC, FLEXIBLE, SINGLE NUT, STAINLESS STEEL BRAIDED, 1/2 X 1-1/2 FEET | 50316 | 2023-12-23 | 2023-12-23 | CLOSE | 4 | EA | 4 | 11.99 | 47.96 |  |  |  |  | KW1-14053 | 4 | 2024-01-04 | APPR | 2024-01-04 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-18 07:00 | COMP | 2024-01-10 | 4.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4820-60-V00-0227 | VALVE, ANGLE, 1/2 X 1/2 INCHES | 50316 | 2023-12-23 | 2023-12-23 | CLOSE | 5 | EA | 4 | 17.65 | 70.6 |  |  |  |  | KW1-14053 | 5 | 2024-01-04 | APPR | 2024-01-04 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-18 07:00 | COMP | 2024-01-10 | 4.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4510-60-V00-0096 | TRAP, BOTTLE, ADJUSTABLE INLET, w/FLEXIBLE HOSE, 1-1/2 INCHES | 50313 | 2023-12-23 | 2023-12-23 | CLOSE | 2 | EA | 2 | 21.31 | 42.62 | 20214 | CLOSE | 2024-01-09 |  | KW1-14130 | 8 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 | COMP | 2024-01-14 | 2.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4510-60-V00-0124 | FAUCET, LEVER, SINGLE, CHROME, BRASS, WASH BASIN MIXER | 50317 | 2023-12-23 | 2023-12-23 | CLOSE | 5 | EA | 2 | 65.63 | 131.26 |  |  |  |  | KW1-14121 | 41 | 2024-01-09 | APPR | 2024-01-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-16 07:00 | COMP | 2024-01-14 | 2.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
36 | 2023-12-23 | 30 | BU24-0085 | Install Sinks Z5 B5054 | 8887384 | 4510-60-V00-0071 | BASIN, WASH, CERAMIC, OVAL, WHITE, 570 X 490 MM | 50311 | 2023-12-23 | 2023-12-23 | CLOSE | 1 | EA | 2 | 241.43 | 482.86 | 20210 | SENT | 2024-01-09 |  | KW1-14124 | 12 | 2024-01-09 | APPR | 2024-01-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-25 | COMP | 2024-01-18 | 2.00 | O&M Order | BU | BU table | December | 2023 | MM_BU
37 | 2023-12-30 | 30 | BU24-0112 | Install Bollards Ring 4 | 8920496 | 4240-60-V00-0132 | BOLLARD, SAFETY, PROTECTIVE, STEEL, BLACK/YELLOW, 100 X 1450 MM | 50950 | 2023-12-31 | 2024-01-02 | CLOSE | 1 | EA | 24 | 366.3 | 8791.2 | 20132 | CLOSE | 2024-01-10 | 2024-01-06 | KW1-14163 | 15 | 2024-01-10 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-07 | COMP | 2024-01-16 | 3.00 | Pending Remaining items | BU | BU table | December | 2023 | MM_BU
37 | 2023-12-30 | 30 | BU24-0112 | Install Bollards Ring 4 | 8920496 | 5610-60-V00-0010 | GATCH AND GRAVEL, MIXED, CUBIC METER | 50951 | 2023-12-31 | 2023-12-31 | CLOSE | 1 | CZ | 1 | 58.28 | 58.28 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 60 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-21 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
37 | 2023-12-30 | 30 | BU24-0112 | Install Bollards Ring 4 | 8920496 | 9905-01-282-2285 | TAPE, FLAGGING, CAUTION DO NOT ENTER, POLYETHYLENE, BLACK ON YELLOW, 3 INCHES X 200 FEET | 50952 | 2023-12-31 | 2023-12-31 | CLOSE | 1 | RO | 1 | 90.91 | 90.91 | 20301 | CLOSE | 2024-01-18 | 2024-01-14 | KW1-14277 | 2 | 2024-01-18 | APPR | 2024-01-18 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-23 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
38 | 2023-12-30 | 30 | BU24-0018 | Install Generator Z2 PWD Yard - C to TDP | 8894903 | 6115-60-V00-0039 | GENERATOR SET, DIESEL ENGINE, 1500 RPM, 400V, 3PH, 50HZ, 135KVA | 51194 | 2024-01-04 | 2024-01-07 | CLOSE | 1 | EA | 1 | 28591.5 | 28591.5 | 20273 | CLOSE | 2024-01-15 | 2024-01-14 | KW1-14241 | 1 | 2024-01-16 | APPR | 2024-01-16 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 |  |  |  | ON-HOLD | BU | BU table | December | 2023 | MM_BU
38 | 2023-12-30 | 30 | BU24-0018 | Install Generator Z2 PWD Yard - C to TDP | 8894903 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 51193 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 2 | 302.94 | 605.88 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 47 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
38 | 2023-12-30 | 30 | BU24-0018 | Install Generator Z2 PWD Yard - C to TDP | 8894903 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM ² | 51192 | 2024-01-04 | 2024-01-06 | CLOSE | 2 | RL | 1 | 244.76 | 244.76 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 46 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
38 | 2023-12-30 | 30 | BU24-0018 | Install Generator Z2 PWD Yard - C to TDP | 8894903 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 51192 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 2 | 61.27 | 122.54 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 45 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 5305-60-V00-0170 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATE, # 8 X 3 INCHES | 51120 | 2024-01-03 | 2024-01-04 | CLOSE | 5 | BX | 7 | 35 | 245 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 80 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 7.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 51120 | 2024-01-03 | 2024-01-04 | CLOSE | 4 | BX | 7 | 19.6 | 137.2 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 79 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 7.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 5510-60-V00-0003 | LUMBER, SOFTWOOD, DIMENSION, 2 X 4 INCHES X 13 FEET | 51114 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | EA | 10 | 29.97 | 299.7 |  |  |  |  | KW1-14180 | 23 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 5510-60-V00-0024 | LUMBER, SOFTWOOD, 2 X 2 INCHES X 14 FEET | 51112 | 2024-01-03 | 2024-01-04 | CLOSE | 3 | EA | 10 | 27.47 | 274.7 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 71 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8010-60-V00-0028 | PAINT, ENAMEL, GLOSS, DESERT SAND, 3.6 LITER | 51118 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | CN | 34 | 39.6 | 1346.4 | 20136 | CLOSE | 2024-01-04 |  | KW1-14058 | 1 | 2024-01-04 | APPR | 2024-01-05 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-09 | 34.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8105-01-517-1363 | BAG, PLASTIC, CLEAR, 24 X 24 INCHES, 10 GALLONS | 51119 | 2024-01-03 | 2024-01-04 | CLOSE | 3 | BX | 1 | 91.1 | 91.1 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 75 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8340-00-068-7908 | DROP CLOTH, PAINTER'S, 9 FT X 12 FT | 51115 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | EA | 4 | 28.97 | 115.88 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 72 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 51116 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | BX | 4 | 19.65 | 78.6 |  |  |  |  | KW1-14179 | 5 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-01-25 07:00 | COMP | 2024-01-15 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8020-00-245-4519 | BRUSH, PAINT, BRISTLES, FLAT, 4 INCHES | 51117 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | EA | 8 | 16.48 | 131.84 |  |  |  |  | KW1-14173 | 59 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 8.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 51119 | 2024-01-03 | 2024-01-04 | CLOSE | 2 | EA | 6 | 14.6 | 87.6 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 74 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 51121 | 2024-01-03 | 2024-01-04 | CLOSE | 3 | EA | 8 | 12.4 | 99.2 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 42 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 8.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 51121 | 2024-01-03 | 2024-01-04 | CLOSE | 2 | EA | 4 | 13.9 | 55.6 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 41 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 5350-60-V00-0004 | PAPER, ABRASIVE (SANDPAPER), 80 GRIT, 9 X 11 INCHES | 51120 | 2024-01-03 | 2024-01-04 | CLOSE | 3 | PK | 5 | 34.2 | 171 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 78 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 5.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 5350-60-V00-0011 | PAPER, ABRASIVE (SANDPAPER), 220 GRIT, 9 X 11 INCHES | 51113 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | SH | 40 | 3.33 | 133.2 |  |  |  |  | KW1-14180 | 22 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 40.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8010-60-V00-0089 | PRIMER, COATING, WHITE, 4 - 5 LITERS | 51114 | 2024-01-03 | 2024-01-04 | CLOSE | 2 | CN | 12 | 41.63 | 499.56 |  |  |  |  | KW1-14173 | 58 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 12.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 51121 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | EA | 10 | 29 | 290 | 20305 | INPRG | 2024-02-03 |  | KW1-14212 | 40 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-27 | COMP | 2024-01-16 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 5530-00-618-8073 | PLYWOOD, MAPLE, PUREBOND, 3/4 IN x 4 FT x 8 FT | 51120 | 2024-01-03 | 2024-01-04 | CLOSE | 2 | EA | 11 | 47 | 517 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 77 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 11.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 5510-60-V00-0011 | LUMBER, HEAT TREATED, IPPC, 4 X 4 INCHES X 16 FEET | 51120 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | EA | 14 | 56.9 | 796.6 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 76 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-23 | 14.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 6350-60-V00-0102 | ALARM, SMOKE, AUTOMATIC, PLASTIC | 51112 | 2024-01-03 | 2024-01-04 | CLOSE | 2 | EA | 6 | 28.97 | 173.82 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 70 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 4210-60-V00-0189 | EXTINGUISHER, FIRE, DRY CHEMICAL, w/ BRASS VALVE, 10 LBS | 51119 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | EA | 4 | 244.8 | 979.2 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 73 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-11 | COMP | 2024-01-20 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
39 | 2024-01-03 | 30 | BU23-276 | SFF & HSR Shooting Platforms- Correct TI deficiencies to add to TE | 8529019 | 6210-60-V00-0112 | LIGHT UNIT, EMERGENCY, 230/240V AC, 50/60 HZ, 8W | 51112 | 2024-01-03 | 2024-01-04 | CLOSE | 1 | EA | 4 | 94.74 | 378.96 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 69 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
40 | 2024-01-03 | 30 | BU24-0103 | Fence Repair | 8873806 | 5660-60-V00-0074 | FENCE, CHAIN LINK, GALVANIZED STEEL, GREEN, 8 X 50 FEET | 51336 | 2024-01-06 | 2024-01-07 | CLOSE | 1 | RO | 10 | 249.52 | 2495.2 | 20195 | CLOSE | 2024-01-07 |  | KW1-14089 | 1 | 2024-01-07 | APPR | 2024-01-07 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-25 | COMP | 2024-01-14 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
40 | 2024-01-03 | 30 | BU24-0103 | Fence Repair | 8873806 | 5660-60-V00-0044 | FENCING, WIRE, (TENSION WIRE), PVC, GREEN, 16 GAGE, 100 METERS | 51337 | 2024-01-06 | 2024-01-07 | CLOSE | 1 | RO | 5 | 58.9 | 294.5 | 20305 | INPRG | 2024-02-03 |  | KW1-14209 | 19 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 | COMP | 2024-01-16 | 5.00 |  | BU | BU table | January | 2024 | MM_BU
40 | 2024-01-03 | 30 | BU24-0103 | Fence Repair | 8873806 | 5660-60-V00-0046 | FENCING, WIRE, PVC COATED, GREEN, 2.5 MM | 51338 | 2024-01-06 | 2024-01-07 | CLOSE | 1 | RO | 7 | 44.55 | 311.85 | 20302 | CLOSE | 2024-01-21 | 2024-01-14 | KW1-14335 | 9 | 2024-01-21 | APPR | 2024-01-21 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-04 | COMP | 2024-01-24 | 7.00 |  | BU | BU table | January | 2024 | MM_BU
40 | 2024-01-03 | 30 | BU24-0103 | Fence Repair | 8873806 | 5110-60-V00-0138 | CUTTER, BOLT, COMPACT, STEEL, 8 INCHES | 51339 | 2024-01-06 | 2024-01-07 | CLOSE | 3 | EA | 5 | 42.5 | 212.5 | 20263 | CLOSE | 2024-01-20 | 2024-01-15 | KW1-14320 | 11 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-19 | 5.00 |  | BU | BU table | January | 2024 | MM_BU
40 | 2024-01-03 | 30 | BU24-0103 | Fence Repair | 8873806 | 5120-60-V00-0504 | PULLER, FENCE, STANDARD, TYPE A, ALLOY STEEL, 3.5 X 48 INCHES | 51339 | 2024-01-06 | 2024-01-07 | CLOSE | 2 | EA | 6 | 136.17 | 817.02 | 20263 | CLOSE | 2024-01-20 | 2024-01-15 | KW1-14320 | 10 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 |  |  |  |  | BU | BU table | January | 2024 | MM_BU
40 | 2024-01-03 | 30 | BU24-0103 | Fence Repair | 8873806 | 5120-60-V00-0505 | PULLER, FENCE, REVERSED, TYPE A, ALLOY STEEL, 3.5 X 48 INCHES | 51339 | 2024-01-06 | 2024-01-07 | CLOSE | 1 | EA | 6 | 140.51 | 843.06 | 20263 | CLOSE | 2024-01-20 | 2024-01-15 | KW1-14320 | 9 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-12 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
40 | 2024-01-03 |  | BU24-0103 | Fence Repair | 8873806 | 5660-60-V00-0072 | TENSION BAND, CHAIN LINK FENCE, FLAT, GALVANIZED METAL, 1-5/8 INCH | [5 empty] | EA | 500 | [17 empty] | Not required | BU | BU table | January | 2024 | MM_BU
40 | 2024-01-03 | 40 | BU24-0103 | Fence Repair | 8873806 | 3950-60-V00-0033 | WINCH, WIRE ROPE (CABLE PULLER), HAND OPERATED, ALUMINIUM, 1600 KG | 51340 | 2024-01-06 | 2024-01-07 | CLOSE | 1 | EA | 2 | 531.81 | 1063.62 | 20263 | CLOSE | 2024-01-20 | 2024-01-15 | KW1-14320 | 12 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-05 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
40 | 2024-01-03 |  | BU24-0103 | Fence Repair | 8873806 | To be fabricated by welding | Pipe&Hook | [5 empty] | EA | 1 | [17 empty] | AJ Team will Fabricate | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 6145-60-V00-0112 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 95 MM² | 51161 | 2024-01-04 | 2024-01-04 | CLOSE | 8 | MR | 140 | 85.91 | 12027.4 | 20139 | CLOSE | 2024-01-08 | 2024-01-07 | KW1-14096 | 8 | 2024-01-08 | APPR | 2024-01-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-13 | 140.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5940-60-V00-0025 | TERMINAL, LUG, TIN-PLATED, M12, 95MM², 3 X 24.5 X 60.5 INCHES | 51161 | 2024-01-04 | 2024-01-04 | CLOSE | 7 | EA | 8 | 28.84 | 230.72 | 20139 | CLOSE | 2024-01-08 | 2024-01-07 | KW1-14096 | 7 | 2024-01-08 | APPR | 2024-01-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-11 | 8.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5975-60-V00-0515 | STUFFING TUBE (CABLE GLAND), BRASS, BW, 50 MM | 51161 | 2024-01-04 | 2024-01-04 | CLOSE | 6 | EA | 2 | 29.8 | 59.6 | 20139 | CLOSE | 2024-01-08 | 2024-01-07 | KW1-14096 | 6 | 2024-01-08 | APPR | 2024-01-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-11 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5975-00-074-2072 | STRAP, TIEDOWN, ELECTRICAL COMPONENT, PLASTIC, NATURAL, 6-3/10 INCHES | 51167 | 2024-01-04 | 2024-01-07 | CLOSE | 7 | HD | 2 | 16.83 | 33.66 |  |  |  |  | KW1-14173 | 69 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5975-01-223-8533 | STRAP, TIE DOWN, ELECTRICAL COMPONENTS, PLASTIC POLYAMIDE, 0.1 X 8 INCHES | 51161 | 2024-01-04 | 2024-01-04 | CLOSE | 5 | PG | 2 | 67.1 | 134.2 | 20139 | CLOSE | 2024-01-08 | 2024-01-07 | KW1-14096 | 5 | 2024-01-08 | APPR | 2024-01-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-11 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 4240-60-V00-0122 | TAPE, WARNING, CAUTION BURIED ELECTRICAL CABLE BELOW, YELLOW 6 INCHES X 1000 FEET | 51161 | 2024-01-04 | 2024-01-04 | CLOSE | 4 | RL | 1 | 176.82 | 176.82 | 20139 | CLOSE | 2024-01-08 | 2024-01-07 | KW1-14096 | 4 | 2024-01-08 | APPR | 2024-01-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-13 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5940-60-V00-0085 | LUG, TERMINAL, ROUND TYPE, COPPER, ONE-HOLE, 50 MM² X 6MM | 51161 | 2024-01-04 | 2024-01-04 | CLOSE | 1 | PG | 1 | 249.75 | 249.75 | 20139 | CLOSE | 2024-01-08 | 2024-01-07 | KW1-14096 | 1 | 2024-01-08 | APPR | 2024-01-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-11 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 6145-60-V00-0047 | WIRE, ELECTRICAL, GREEN/YELLOW, 1 CORE, 50MM ² | 51167 | 2024-01-04 | 2024-01-07 | CLOSE | 6 | MR | 130 | 10.3 | 1339 |  |  |  |  | KW1-14173 | 68 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-17 | 130.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5970-01-174-5651 | TAPE, INSULATION, ELECTRICAL, YELLOW, 3/4 X 792 INCHES | 51167 | 2024-01-04 | 2024-01-07 | CLOSE | 5 | EA | 1 | 10.1 | 10.1 |  |  |  |  | KW1-14173 | 67 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5970-01-015-5060 | TAPE, INSULATION, ELECTRICAL, BLUE, 3/4 X 792 INCHES | 51167 | 2024-01-04 | 2024-01-07 | CLOSE | 4 | RO | 1 | 10.1 | 10.1 |  |  |  |  | KW1-14173 | 66 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5970-01-013-9369 | TAPE, INSULATION, ELECTRICAL, RED, 3/4 X 792 INCHES | 51167 | 2024-01-04 | 2024-01-07 | CLOSE | 3 | RO | 1 | 10.1 | 10.1 |  |  |  |  | KW1-14173 | 65 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5970-01-013-9368 | TAPE, INSULATION, ELECTRICAL, GREEN, 3/4 X 792 INCHES | 51167 | 2024-01-04 | 2024-01-07 | CLOSE | 2 | RO | 1 | 16.83 | 16.83 |  |  |  |  | KW1-14173 | 64 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 51167 | 2024-01-04 | 2024-01-07 | CLOSE | 1 | RO | 1 | 21.11 | 21.11 |  |  |  |  | KW1-14173 | 63 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 | COMP | 2024-01-16 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5610-60-V00-0014 | SAND | 51163 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | TN | 40 | 34.13 | 1365.2 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 86 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-21 | 40.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5610-60-V00-0010 | GATCH AND GRAVEL, MIXED, CUBIC METER | 51231 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | CZ | 2 | 56.1 | 112.2 | 20302 | CLOSE | 2024-01-21 | 2024-01-14 | KW1-14335 | 4 | 2024-01-21 | APPR | 2024-01-21 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-04 | COMP | 2024-02-05 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5610-60-V00-0018 | CONCRETE MIX, GRAY, 4000 PSI, 80 LBS | 51165 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 30 | 42.5 | 1275 |  |  |  |  | KW1-14180 | 24 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 30.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 9510-60-V00-0013 | BAR, STEEL, REBAR, ROUND, 12 MM X 9 METER | 51164 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 8 | 33.3 | 266.4 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 87 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 8.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5660-60-V00-0045 | WIRE, STEEL, GALVANIZED, 28 GAGE, 100 FEET | 51162 | 2024-01-04 | 2024-01-06 | CLOSE | 3 | RO | 2 | 58.28 | 116.56 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 85 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 8135-60-V00-0003 | PLASTIC SHEET, POLYETHYLENE, CLEAR, 6 MIL, 32 X 100 FEET | 51162 | 2024-01-04 | 2024-01-06 | CLOSE | 2 | RO | 1 | 442.89 | 442.89 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 84 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 8030-60-V00-0005 | SEALING COMPOUND, TWO PART POLYSULPHIDE, GREY, 2 LITRES | 51161 | 2024-01-04 | 2024-01-04 | CLOSE | 3 | PG | 1 | 149.85 | 149.85 | 20139 | CLOSE | 2024-01-08 | 2024-01-07 | KW1-14096 | 3 | 2024-01-08 | APPR | 2024-01-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-12 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5620-60-V00-0012 | CONCRETE SPACER (COVER BLOCK), w/TIE-WIRE ATTACHMENT HOLE, 65/75 MM | 51161 | 2024-01-04 | 2024-01-04 | CLOSE | 2 | PG | 1 | 41.63 | 41.63 | 20139 | CLOSE | 2024-01-08 | 2024-01-07 | KW1-14096 | 2 | 2024-01-08 | APPR | 2024-01-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-13 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5640-60-V00-0026 | BACKER ROD, GAPS, CLOSED-CELL POLYETHYLENE, 3/8 INCH X 20 FEET | 51162 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 2 | 18.32 | 36.64 | 20260 | CLOSE | 2024-01-15 | 2024-01-13 | KW1-14244 | 83 | 2024-01-17 | APPR | 2024-01-17 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-22 | COMP | 2024-01-20 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 8430-60-V00-0001 | BOOTS, SLIP-ON, RUBBER, ROUND TOE, #10.5 | 51168 | 2024-01-04 | 2024-01-06 | CLOSE | 3 | PR | 2 | 38.61 | 77.22 | 20263 | CLOSE | 2024-01-20 | 2024-01-15 | KW1-14320 | 5 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-15 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5120-01-604-5657 | GLOVES, WELDING | 51166 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 4 | 60.6 | 242.4 |  |  |  |  | KW1-14180 | 25 | 2024-01-11 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 07:00 | COMP | 2024-01-15 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 5180-60-V00-0030 | TOOL KIT, MASON AND CONCRETE FINISHER'S, 7 COMPONENETS | 51168 | 2024-01-04 | 2024-01-06 | CLOSE | 2 | KT | 2 | 213.7 | 427.4 | 20263 | CLOSE | 2024-01-20 | 2024-01-15 | KW1-14320 | 4 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-05 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
41 | 2024-01-03 | 30 | BU24-0005 | Connect to MDP T004 & T005 | 8800694 | 3895-60-V00-0012 | BOARD, BITUMEN, 2400 X 75 X 9.5MM | 51168 | 2024-01-04 | 2024-01-06 | CLOSE | 1 | EA | 2 | 179.37 | 358.74 | 20263 | CLOSE | 2024-01-20 | 2024-01-15 | KW1-14320 | 3 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-17 07:00 | COMP | 2024-01-24 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
42 | 2024-01-06 | 30 | BU24-0081 | Replace Sandbags Bunkers Z5 BA2 | 8417604 | 5110-00-892-5071 | KNIFE, CRAFTSMAN'S, RETRACTABLE BLADE | 51318 | 2024-01-06 | 2024-01-07 | CLOSE | 1 | EA | 5 | 19.3 | 96.5 | 20305 | INPRG | 2024-02-03 |  | KW1-14209 | 18 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-31 | COMP | 2024-01-16 | 5.00 |  | BU | BU table | January | 2024 | MM_BU
42 | 2024-01-06 | 30 | BU24-0081 | Replace Sandbags Bunkers Z5 BA2 | 8417604 | 8105-01-331-3704 | BAG, SAND, TAN, PROTECTIVE, 26 INCHES | 51317 | 2024-01-06 | 2024-01-07 | CLOSE | 1 | HD | 110 | 699.3 | 76923 | 20190 | CLOSE | 2024-01-11 | 2024-01-08 | KW1-14171 | 1 | 2024-01-11 | APPR | 2024-01-11 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-02-22 | COMP | 2024-01-15 | 40.00 |  | BU | BU table | January | 2024 | MM_BU
43 | 2024-01-07 | 30 | BU24-0015 | Replace Generator Z2 Bldg. 209 -C To TDP | 8944274 | 6115-60-V00-0040 | GENERATOR SET, DIESEL ENGINE, 3-PHASE, 400V, 50HZ, 1500 RPM, 330 KVA/264 KWE | 51875 | 2024-01-16 | 2024-01-27 | CLOSE | 2 | EA | 1 | 57539.38 | 57539.38 | 20594 | CLOSE | 2024-02-11 | 2024-01-30 | KW1-14808 | 2 | 2024-02-11 | APPR | 2024-02-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-28 |  |  |  |  | BU | BU table | January | 2024 | MM_BU
43 | 2024-01-07 | 30 | BU24-0015 | Replace Generator Z2 Bldg. 209 -C To TDP | 8944274 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 51874 | 2024-01-16 | 2024-01-18 | CLOSE | 3 | EA | 4 | 348.15 | 1392.6 | 20446 | CLOSE | 2024-01-22 | 2024-01-22 | KW1-14376 | 8 | 2024-01-22 | APPR | 2024-01-28 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-05 | COMP | 2024-01-31 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
43 | 2024-01-07 | 30 | BU24-0015 | Replace Generator Z2 Bldg. 209 -C To TDP | 8944274 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM ² | 51874 | 2024-01-16 | 2024-01-18 | CLOSE | 2 | RL | 1 | 304.2 | 304.2 | 20446 | CLOSE | 2024-01-22 | 2024-01-22 | KW1-14376 | 7 | 2024-01-22 | APPR | 2024-01-28 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-05 | COMP | 2024-01-31 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
43 | 2024-01-07 | 30 | BU24-0015 | Replace Generator Z2 Bldg. 209 -C To TDP | 8944274 | 5975-60-V00-0418 | LUGS, CABLE, TUBE TERMINALS, COPPER, 16 X 8 MILLIMETERS | 51875 | 2024-01-16 | 2024-01-27 | CLOSE | 1 | EA | 4 | 1.05 | 4.2 | 20594 | CLOSE | 2024-02-11 | 2024-01-30 | KW1-14808 | 1 | 2024-02-11 | APPR | 2024-02-11 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 | COMP | 2024-02-14 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
43 | 2024-01-07 | 30 | BU24-0015 | Replace Generator Z2 Bldg. 209 -C To TDP | 8944274 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 51874 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | EA | 4 | 60.72 | 242.88 | 20446 | CLOSE | 2024-01-22 | 2024-01-22 | KW1-14376 | 6 | 2024-01-22 | APPR | 2024-01-28 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-05 | COMP | 2024-01-31 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5307-60-V00-0021 | STUD, DRYWALL FRAME, U-CHANNEL, GALVANIZED STEEL, 3 X 1-1/4 INCHES X 12 FEET | 51540 | 2024-01-10 | 2024-01-10 | CLOSE | 4 | EA | 200 | 6.34 | 1268 | 20372 | CLOSE | 2024-01-25 | 2024-01-20 | KW1-14437 | 13 | 2024-01-25 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-08 07:00 | COMP | 2024-02-01 | 200.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5650-60-V01-0003 | C-STUD RUNNER, GALVANIZED STEEL, 0.0366 X 1 1/4 X 3 INCHES X 12 FEET | 51540 | 2024-01-10 | 2024-01-10 | CLOSE | 3 | EA | 40 | 6.18 | 247.2 | 20372 | CLOSE | 2024-01-25 | 2024-01-20 | KW1-14437 | 12 | 2024-01-25 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-08 07:00 | COMP | 2024-02-01 | 40.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 40 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5305-05-V00-0025 | SCREW, PHILLIPS, TRUSS HEAD, STAINLESS STEEL, 10 X 3/4 INCHES 100pc / bx | 51576 | 2024-01-10 | 2024-01-13 | CLOSE | 2 | PG | 25 | 12.99 | 324.75 | 20372 | CLOSE | 2024-01-25 | 2024-01-20 | KW1-14437 | 15 | 2024-01-25 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-01 07:00 | COMP | 2024-01-30 | 25.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5305-60-V00-0022 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #10, 1-1/2 INCHES | 51530 | 2024-01-10 | 2024-01-10 | CLOSE | 2 | PG | 6 | 48.12 | 288.72 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 53 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-23 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 9520-60-V00-0044 | L CHANNEL GALVANIZE 3MM X 1 1/2" X 12' | 51540 | 2024-01-10 | 2024-01-10 | CLOSE | 2 | EA | 8 | 117 | 936 | 20372 | CLOSE | 2024-01-25 | 2024-01-20 | KW1-14437 | 11 | 2024-01-25 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-01 07:00 | COMP | 2024-01-30 | 8.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5640-60-V00-0048 | DRYWALL SHEET, (GYPSUM BOARD), 4 X 8 FEET X 1/2 INCH | 51533 | 2024-01-10 | 2024-01-10 | CLOSE | 2 | EA | 80 | 19.31 | 1544.8 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 57 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-23 | 80.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5305-60-V00-0157 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, COARSE THREAD, #7 X 1-3/8 INCHES 1000pc/box | 51536 | 2024-01-10 | 2024-01-13 | CLOSE | 8 | BX | 5 | 23.31 | 116.55 | 20370 | CLOSE | 2024-01-20 | 2024-01-18 | KW1-14329 | 44 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-27 | COMP | 2024-01-25 | 5.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5640-60-V00-0044 | TAPE, SELF ADHESIVE, DRYWALL JOINT, FIBERGLASS, 2 INCHES X 300 FEET | 51539 | 2024-01-10 | 2024-01-10 | CLOSE | 5 | EA | 2 | 18.5 | 37 | 20318 | CLOSE | 2024-01-22 | 2024-01-15 | KW1-14372 | 14 | 2024-01-22 | APPR | 2024-01-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-10 | COMP | 2024-01-27 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 51533 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | CN | 4 | 37.3 | 149.2 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 56 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-23 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 7510-00-680-2395 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 51536 | 2024-01-10 | 2024-01-13 | CLOSE | 7 | RO | 2 | 12.99 | 25.98 | 20370 | CLOSE | 2024-01-20 | 2024-01-18 | KW1-14329 | 43 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-27 | COMP | 2024-01-25 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5130-60-V00-0125 | DISK, ABRASIVE, SANDING, HOOK AND LOOP, 220 GRIT, 8 HOLE, 5 INCHES-DUSTLESS HOOK AND LOOP SANDING DISC | 51536 | 2024-01-10 | 2024-01-13 | CLOSE | 6 | PG | 3 | 49.28 | 147.84 | 20370 | CLOSE | 2024-01-20 | 2024-01-18 | KW1-14329 | 42 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-27 | COMP | 2024-01-25 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5680-60-V01-0002 | CORNER BEAD, STAINLESS STEEL, 25 MM X2.5 METER | 51536 | 2024-01-10 | 2024-01-13 | CLOSE | 5 | EA | 10 | 109.89 | 1098.9 | 20370 | CLOSE | 2024-01-20 | 2024-01-18 | KW1-14329 | 41 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-15 | COMP | 2024-02-05 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5350-60-V00-0007 | PAPER, ABRASIVE (SANDPAPER), 120 GRIT, 9 X 11 INCHES | 51536 | 2024-01-10 | 2024-01-13 | CLOSE | 4 | EA | 20 | 4.33 | 86.6 | 20370 | CLOSE | 2024-01-20 | 2024-01-18 | KW1-14329 | 40 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-27 | COMP | 2024-01-25 | 20.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 40 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8010-60-V00-0241 | PRIMER, PAINT, LATEX, INTERIOR, WATERBASED, WHITE, 5 GALLON | 51576 | 2024-01-10 | 2024-01-13 | CLOSE | 1 | CN | 2 | 55.08 | 110.16 | 20372 | CLOSE | 2024-01-25 | 2024-01-20 | KW1-14437 | 14 | 2024-01-25 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-08 07:00 | COMP | 2024-01-30 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8010-60-V00-0130 | PAINT, LATEX, MATT, WHITE, 1 GL (3.2 TO 3.6 LT) | 51536 | 2024-01-10 | 2024-01-13 | CLOSE | 3 | CN | 16 | 42.62 | 681.92 | 20370 | CLOSE | 2024-01-20 | 2024-01-18 | KW1-14329 | 39 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-27 | COMP | 2024-01-25 | 16.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 51537 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | EA | 6 | 14.6 | 87.6 | 20326 | CLOSE | 2024-01-13 |  | KW1-14200 | 5 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-02-29 | COMP | 2024-01-17 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 51539 | 2024-01-10 | 2024-01-10 | CLOSE | 4 | EA | 8 | 12.4 | 99.2 | 20327 | CLOSE | 2024-01-13 |  | KW1-14201 | 17 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-16 | 8.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 51539 | 2024-01-10 | 2024-01-10 | CLOSE | 3 | EA | 12 | 13.99 | 167.88 | 20327 | CLOSE | 2024-01-13 |  | KW1-14201 | 16 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-16 | 12.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUAR | 51539 | 2024-01-10 | 2024-01-10 | CLOSE | 2 | EA | 6 | 29.3 | 175.8 | 20327 | CLOSE | 2024-01-13 |  | KW1-14201 | 15 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-16 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8415-01-492-0179 | GLOVES, DISPOSABLE, LATEX FREE, NITRILE, MEDIUM | 51534 | 2024-01-10 | 2024-01-10 | CLOSE | 3 | BX | 2 | 18.65 | 37.3 | 20326 | CLOSE | 2024-01-13 |  | KW1-14199 | 4 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-02-29 | COMP | 2024-01-17 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5510-60-V00-0022 | BOARD, MDF, INTERIOR, BROWN, 12 X 1220 X 2440 MM | 51540 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | EA | 10 | 29.7 | 297 | 20372 | CLOSE | 2024-01-25 | 2024-01-20 | KW1-14437 | 10 | 2024-01-25 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-01 07:00 | COMP | 2024-01-30 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8010-60-V00-0050 | PAINT, ENAMEL, GLOSS, DARK BROWN, 3.2 AND 3.6 LITER | 51530 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | CN | 3 | 39.96 | 119.88 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 52 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-25 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8010-60-V00-0146 | PRIMER COATING, WOOD, WHITE, 5 GL | 51535 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | CN | 1 | 123.21 | 123.21 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 58 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-28 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GL | 51539 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | GL | 2 | 228.7 | 457.4 | 20327 | CLOSE | 2024-01-13 |  | KW1-14201 | 14 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-25 | COMP | 2024-01-18 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5340-00-116-2375 | CLOSER, HYDRAULIC DOOR, LIGHT DUTY | 51538 | 2024-01-10 | 2024-01-10 | CLOSE | 4 | EA | 2 | 97 | 194 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 63 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-23 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 50 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5340-09-V00-0029 | DOOR CLOSER, MANUAL HYDRAULIC, HEAVY-DUTY INTERIOR AND EXTERIOR, DARK BRONZE | 51577 | 2024-01-10 | 2024-01-13 | CLOSE | 1 | EA | 1 | 125.66 | 125.66 | 20373 | CLOSE | 2024-01-23 | 2024-01-20 | KW1-14389 | 1 | 2024-01-23 | APPR | 2024-01-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-02-29 07:00 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5340-60-V00-0492 | STOPPER, DOOR, DROP DOWN, METAL, 5" | 51531 | 2024-01-10 | 2024-01-10 | CLOSE | 2 | EA | 3 | 12.1 | 36.3 | 20325 | CLOSE | 2024-01-13 |  | KW1-14197 | 30 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-25 | COMP | 2024-01-16 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5340-60-V00-0141 | DOORSTOP, FLOOR MOUNT, BRASS, 1-3/4 X 1-1/4 INCHES | 51536 | 2024-01-10 | 2024-01-13 | CLOSE | 2 | EA | 3 | 9.66 | 28.98 | 20370 | CLOSE | 2024-01-20 | 2024-01-18 | KW1-14329 | 38 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-27 | COMP | 2024-01-25 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5640-60-V00-0035 | WEATHER STRIP, DOOR, W/BRUSH, 2 X 36 INCHES | 51534 | 2024-01-10 | 2024-01-10 | CLOSE | 2 | EA | 3 | 30.47 | 91.41 | 20318 | CLOSE | 2024-01-22 | 2024-01-15 | KW1-14372 | 12 | 2024-01-22 | APPR | 2024-01-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-10 | COMP | 2024-01-25 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8030-09-V01-0003 | SEALING COMPOUND, CAULK, ACRYLIC, WHITE, 5.5 OZ | 51535 | 2024-01-10 | 2024-01-10 | CLOSE | 2 | EA | 4 | 16.98 | 67.92 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 59 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-20 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5510-01-433-1244 | LUMBER, SOFTWOOD, 2 X 4 INCHES X 16 FEET | 51538 | 2024-01-10 | 2024-01-10 | CLOSE | 3 | EA | 6 | 30.8 | 184.8 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 62 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-30 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8030-60-V00-0050 | PUTTY, WOOD FILLER, MEDIUM OAK, 250 ML | 51531 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | CN | 2 | 68.27 | 136.54 | 20327 | CLOSE | 2024-01-13 |  | KW1-14201 | 13 | 2024-01-13 | APPR | 2024-01-13 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 | COMP | 2024-01-21 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5130-60-V00-0134 | BIT, SCREWDRIVER, (POWER BIT), PHILLIPS, STEEL, #2 X 2 INCHES | 51532 | 2024-01-10 | 2024-01-10 | CLOSE | 2 | PG | 1 | 14.99 | 14.99 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 55 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-23 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 40 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5130-60-V00-0123 | CUTTING WHEEL, METAL, ALUMINUM OXIDE, 4X0.05X5/8 INCHES | 51574 | 2024-01-10 | 2024-01-13 | CLOSE | 1 | EA | 6 | 14.99 | 89.94 |  |  |  |  | KW1-14446 | 12 | 2024-01-25 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-08 07:00 | COMP | 2024-01-30 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 8020-60-V00-0017 | EXTENSION POLE, PAINT ROLLER, ALUMINUM, YELLOW, 2 - 4 FEET | 51536 | 2024-01-10 | 2024-01-13 | CLOSE | 1 | EA | 2 | 43.29 | 86.58 | 20370 | CLOSE | 2024-01-20 | 2024-01-18 | KW1-14329 | 37 | 2024-01-20 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 40 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5120-60-V00-0418 | EXTENSION POLE, FIBER GLASS, 4 – 8 FT | 51575 | 2024-01-10 | 2024-01-13 | CLOSE | 1 | EA | 2 | 37.46 | 74.92 |  |  |  |  | KW1-14446 | 13 | 2024-01-25 | APPR | 2024-01-25 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-08 07:00 | COMP | 2024-01-30 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5120-60-V00-0267 | KNIFE, PUTTY, STAINLESS STEEL, BLACK/BLUE, 5 INCHES | 51534 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | EA | 5 | 16.48 | 82.4 | 20318 | CLOSE | 2024-01-22 | 2024-01-15 | KW1-14372 | 15 | 2024-01-22 | APPR | 2024-01-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-10 | COMP | 2024-02-03 | 5.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5110-60-V00-0077 | KNIFE, PUTTY, 3 INCHES | 51538 | 2024-01-10 | 2024-01-10 | CLOSE | 2 | EA | 5 | 11.5 | 57.5 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 61 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-23 | 5.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5210-60-V00-0005 | TAPE, MEASURING, STEEL, 26 FEET | 51532 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | EA | 3 | 36.63 | 109.89 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 54 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-23 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
44 | 2024-01-07 | 30 | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | 5110-00-892-5071 | KNIFE, CRAFTSMAN'S, RETRACTABLE BLADE | 51538 | 2024-01-10 | 2024-01-10 | CLOSE | 1 | EA | 3 | 19.3 | 57.9 | 20333 | CLOSE | 2024-01-20 | 2024-01-16 | KW1-14309 | 60 | 2024-01-19 | APPR | 2024-01-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-26 07:00 | COMP | 2024-01-23 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
45 | 2024-01-04 |  | BU24-0028 | Repair Runway Holes | 7894966 | 5610-60-V00-0029 | ASPHALT, COLD PATCH, READY TO USE, 50 LBS | [5 empty] | BG | 90 | [17 empty] | Allready received | BU | BU table | January | 2024 | MM_BU
45 | 2024-01-04 | 50 | BU24-0028 | Repair Runway Holes | 7894966 | 8010-60-V00-0244 | PRIMER, SOLVENT BASED, BITUMEN, BLACK, 20 LITERS | 51809 | 2024-01-15 | 2024-01-17 | CLOSE | 4 | CN | 3 | 81.3 | 243.9 | 20429 | CLOSE | 2024-01-24 | 2024-01-23 | KW1-14393 | 6 | 2024-01-23 | APPR | 2024-01-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL BAYADER INTER.GROUP COMPANY | 2024-02-20 07:00 | COMP | 2024-02-12 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
45 | 2024-01-04 |  | BU24-0028 | Repair Runway Holes | 7894966 | 5610-60-V00-0010 | GATCH AND GRAVEL, MIXED, CUBIC METER | [5 empty] | CZ | 4 | [17 empty] | Allready received | BU | BU table | January | 2024 | MM_BU
45 | 2024-01-04 | 50 | BU24-0028 | Repair Runway Holes | 7894966 | 7920-00-292-2365 | BROOM, PUSH, W/O HANDLE, 3 X 2-1/2 X 14 INCHES | 51809 | 2024-01-15 | 2024-01-17 | CLOSE | 3 | EA | 2 | 22.02 | 44.04 | 20429 | CLOSE | 2024-01-24 | 2024-01-23 | KW1-14393 | 5 | 2024-01-23 | APPR | 2024-01-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL BAYADER INTER.GROUP COMPANY | 2024-01-30 07:00 | COMP | 2024-01-28 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
45 | 2024-01-04 | 50 | BU24-0028 | Repair Runway Holes | 7894966 | 5130-05-V00-0043 | BLADE, CIRCULAR SAW, ASPHALT CUTTING, WET/DRY, DIAMOND, 5460 RPM, 14 X 0.125 INCHES | 51809 | 2024-01-15 | 2024-01-17 | CLOSE | 2 | EA | 1 | 291.68 | 291.68 | 20429 | CLOSE | 2024-01-24 | 2024-01-23 | KW1-14393 | 4 | 2024-01-23 | APPR | 2024-01-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL BAYADER INTER.GROUP COMPANY | 2024-02-29 07:00 | COMP | 2024-02-18 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
45 | 2024-01-04 | 50 | BU24-0028 | Repair Runway Holes | 7894966 | 7920-05-V00-0019 | SQUEEGEE, ASPHALT, NEOPRENE BLADE, 60 X 36 INCHES | 51809 | 2024-01-15 | 2024-01-17 | CLOSE | 1 | EA | 1 | 52.38 | 52.38 | 20429 | CLOSE | 2024-01-24 | 2024-01-23 | KW1-14393 | 3 | 2024-01-23 | APPR | 2024-01-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL BAYADER INTER.GROUP COMPANY | 2024-02-29 07:00 | COMP | 2024-02-05 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 8010-60-V00-0095 | PRIMER, COATING, RED OXIDE, LIQUID, 3.78 TO 4 LITERS | 51598 | 2024-01-11 | 2024-01-13 | CAN | 1 | CN | 5 | 25.71 | 128.55 | [15 empty] | Cancelled | BU | BU table | January | 2024 | MM_BU
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 8010-60-V00-0028 | PAINT, ENAMEL, GLOSS, DESERT SAND, 3.6 LITER | 51604 | 2024-01-11 |  | APPR | 3 | CN | 5 | [17 empty] | Cancelled | BU | BU table | January | 2024 | MM_BU
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 5345-60-V00-0019 | DISK, FLAP, ABRASIVE, 60 GRIT, ZIRCONIA, 4-1/2 X 7/8 INCHES | 51603 | 2024-01-11 | 2024-01-13 | CAN | 2 | EA | 8 | 12.99 | 103.92 | [15 empty] | Cancelled | BU | BU table | January | 2024 | MM_BU
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 51604 | 2024-01-11 | 2024-01-13 | CLOSE | 2 | EA | 5 | 29.3 | 146.5 | 20340 | CLOSE | 2024-01-14 |  | KW1-14226 | 2 | 2024-01-14 | APPR | 2024-01-14 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 |  |  |  | Cancelled | BU | BU table | January | 2024 | MM_BU
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 51604 | 2024-01-11 | 2024-01-13 | CLOSE | 1 | EA | 10 | 12.4 | 124 | 20340 | CLOSE | 2024-01-14 |  | KW1-14226 | 1 | 2024-01-14 | APPR | 2024-01-14 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-31 |  |  |  | Cancelled | BU | BU table | January | 2024 | MM_BU
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 51602 | 2024-01-11 | 2024-01-13 | CAN | 1 | EA | 5 | 14.6 | 73 | [15 empty] | Cancelled | BU | BU table | January | 2024 | MM_BU
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 6515-60-V00-0015 | GLOVES, EXAM, DISPOSABLE, NITRILE, PURPLE, X-LARGE | 51601 | 2024-01-11 | 2024-01-13 | CAN | 2 | EA | 1 | 49.95 | 49.95 | [15 empty] | Cancelled | BU | BU table | January | 2024 | MM_BU
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 4020-00-246-0688 | CORD, FIBROUS, POLYAMIDE NYLON, OLIVE DRAB, 47/250 INCH X 1200 FEET | 51599 | 2024-01-11 | 2024-01-13 | CAN | 1 | RO | 6 | 182.98 | 1097.88 | [15 empty] | Cancelled | BU | BU table | January | 2024 | MM_BU
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 5610-60-V00-0010 | GATCH AND GRAVEL, MIXED, CUBIC METER | 51600 | 2024-01-11 | 2024-01-13 | CAN | 1 | CZ | 10 | 58.28 | 582.8 | [15 empty] | Cancelled | BU | BU table | January | 2024 | MM_BU
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 8105-01-336-6163 | BAG, SAND, TAN, 26 INCHES | 51603 | 2024-01-11 | 2024-01-13 | CAN | 1 | HD | 1 | 727.27 | 727.27 | [15 empty] | Cancelled | BU | BU table | January | 2024 | MM_BU
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 9530-60-V00-0010 | BAR, METAL, FLAT, GALVANIZED MILD STEEL, 50 X 3 X 6000 MM | 51605 | 2024-01-11 | 2024-01-13 | CAN | 1 | EA | 6 | 58.37 | 350.22 | [15 empty] | Cancelled | BU | BU table | January | 2024 | MM_BU
46 | 2024-01-09 | 30 | BU24-0066 | SUNSHADE FRAME AND CANVAS NEED TO REPAIRS | 8293539 | 4020-60-V00-0006 | ROPE, NYLON DOUBLE-BRAIDED, (COILS TWISTED), 1/2 INCH X 50 FEET | 51601 | 2024-01-11 | 2024-01-13 | CAN | 1 | EA | 5 | 9.99 | 49.95 | [15 empty] | Cancelled | BU | BU table | January | 2024 | MM_BU
47 | 2024-01-10 | 40 | BU23-0352 | Z6 B6016 Door Soundproofing | 7562147 | 8030-60-V00-0087 | SEALING COMPOUND (GLUE NOISEPROOFING COMPOUND), GREEN, 28 OZ, 12 PIECES | 51588 | 2024-01-10 | 2024-01-13 | CLOSE | 1 | PG | 2 | 326.53 | 653.06 | 20373 | CLOSE | 2024-01-23 | 2024-01-20 | KW1-14389 | 3 | 2024-01-23 | APPR | 2024-01-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-15 | COMP | 2024-03-09 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5640-60-V00-0048 | DRYWALL SHEET, (GYPSUM BOARD), 4 X 8 FEET X 1/2 INCH | 51857 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | EA | 15 | 19.14 | 287.1 | 20467 | CLOSE | 2024-01-27 | 2024-01-25 | KW1-14455 | 1 | 2024-01-27 | APPR | 2024-01-27 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-11 | COMP | 2024-01-30 | 15.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5305-60-V00-0179 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 1-1/2 INCHES | 51853 | 2024-01-16 | 2024-01-18 | CLOSE | 2 | BX | 2 | 10.5 | 21 | 20441 | CLOSE | 2024-01-21 | 2024-01-21 | KW1-14365 | 2 | 2024-01-21 | APPR | 2024-01-22 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-05 | COMP | 2024-01-24 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 51853 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | BX | 2 | 19.6 | 39.2 | 20441 | CLOSE | 2024-01-21 | 2024-01-21 | KW1-14365 | 1 | 2024-01-21 | APPR | 2024-01-22 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-05 | COMP | 2024-01-24 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 51912 | 2024-01-16 | 2024-01-18 | CLOSE | 2 | CN | 1 | 39.6 | 39.6 | 20573 | CLOSE | 2024-01-27 |  | KW1-14460 | 1 | 2024-01-27 | APPR | 2024-01-27 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-11 | COMP | 2024-01-30 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5640-60-V00-0044 | TAPE, SELF ADHESIVE, DRYWALL JOINT, FIBERGLASS, 2 INCHES X 300 FEET | 51862 | 2024-01-16 | 2024-01-18 | CLOSE | 2 | EA | 2 | 18.5 | 37 | 20467 | CLOSE | 2024-01-27 | 2024-01-25 | KW1-14455 | 3 | 2024-01-27 | APPR | 2024-01-27 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-11 | COMP | 2024-01-30 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5350-60-V00-0004 | PAPER, ABRASIVE (SANDPAPER), 80 GRIT, 9 X 11 INCHES | 51848 | 2024-01-16 | 2024-01-17 | CLOSE | 1 | EA | 1 | 34.48 | 34.48 | 20409 | CLOSE | 2024-01-19 |  | KW1-14300 | 30 | 2024-01-23 | APPR | 2024-01-23 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-04 |  |  |  |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8010-60-V00-0006 | PAINT, LATEX, MATT, WHITE, 3.2 LT | 51854 | 2024-01-16 | 2024-01-18 | CLOSE | 4 | CN | 5 | 44 | 220 | 20446 | CLOSE | 2024-01-22 | 2024-01-22 | KW1-14376 | 4 | 2024-01-22 | APPR | 2024-01-28 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-05 | COMP | 2024-02-01 | 5.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8010-60-V00-0048 | PAINT, LATEX, MATT, ALMOND, 3.2 AND 3.6 LITERS | 51851 | 2024-01-16 | 2024-01-17 | CLOSE | 1 | CN | 6 | 41.14 | 246.84 | 20410 | CLOSE | 2024-01-19 |  | KW1-14305 | 32 | 2024-01-19 | APPR | 2024-01-19 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-11 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 51854 | 2024-01-16 | 2024-01-18 | CLOSE | 3 | EA | 3 | 29 | 87 | 20446 | CLOSE | 2024-01-22 | 2024-01-22 | KW1-14376 | 3 | 2024-01-22 | APPR | 2024-01-28 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-05 | COMP | 2024-01-31 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 51854 | 2024-01-16 | 2024-01-18 | CLOSE | 2 | EA | 6 | 13.9 | 83.4 | 20446 | CLOSE | 2024-01-22 | 2024-01-22 | KW1-14376 | 2 | 2024-01-22 | APPR | 2024-01-28 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-05 | COMP | 2024-01-31 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 51852 | 2024-01-16 | 2024-01-17 | CLOSE | 1 | EA | 5 | 14.6 | 73 | 20412 | CLOSE | 2024-01-19 |  | KW1-14306 | 4 | 2024-01-19 | APPR | 2024-01-19 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-02-29 | COMP | 2024-01-23 | 5.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 7510-00-266-6710 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 51860 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | RO | 5 | 8.25 | 41.25 | 20442 | CLOSE | 2024-01-21 | 2024-01-21 | KW1-14366 | 1 | 2024-01-21 | APPR | 2024-01-22 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-02-05 | COMP | 2024-01-24 | 5.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 6515-60-V00-0015 | GLOVES, EXAM, DISPOSABLE, NITRILE, PURPLE, X-LARGE | 51856 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | BX | 1 | 48.78 | 48.78 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 1 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 9520-60-V00-0035 | CHANNEL, CEILING, METAL, 3600 X 0.55 MM | 51859 | 2024-01-16 | 2024-01-18 | CLOSE | 5 | EA | 25 | 17.32 | 433 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 6 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 25.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 9520-60-V00-0034 | CHANNEL, CEILING, PRIMARY, METAL, 3600 X 0.80 MM | 51859 | 2024-01-16 | 2024-01-18 | CLOSE | 4 | EA | 35 | 14.85 | 519.75 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 5 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 35.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 9540-60-V00-0014 | CHANNEL, STRUCTURAL, PERIMETER, MF6A, GALVANISED STEEL, 30 MM X 27 MM X 3.6 METERS | 51863 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | EA | 10 | 4.1 | 41 | 20467 | CLOSE | 2024-01-27 | 2024-01-25 | KW1-14455 | 4 | 2024-01-27 | APPR | 2024-01-27 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-11 | COMP | 2024-02-05 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5305-60-V00-0197 | SCREW, PHILLIPS DRIVE, SELF-DRILLING, ZINC PLATED, TRUSS HEAD, # 8, 8 X 1/2 INCH | 51849 | 2024-01-16 | 2024-01-17 | CLOSE | 1 | BX | 5 | 29.04 | 145.2 | 20409 | CLOSE | 2024-01-19 |  | KW1-14300 | 32 | 2024-01-23 | APPR | 2024-01-23 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-04 |  |  |  |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8030-60-V00-0081 | PUTTY, MULTI PURPOSE, PLASTIC, GRAY, 1-QUART | 51859 | 2024-01-16 | 2024-01-18 | CLOSE | 3 | CN | 2 | 150.15 | 300.3 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 4 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8030-60-V00-0052 | PUTTY, ALL PURPOSE, LIGHT GRAY, 3.43 KG | 51862 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | CN | 2 | 124 | 248 | 20571 | CLOSE | 2024-01-27 |  | KW1-14457 | 1 | 2024-01-27 | APPR | 2024-01-27 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-11 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5510-60-V00-0027 | PLYWOOD, CONSTRUCTION, MELAMINE COATED, 4 MM X 8 X 4 FEET | 51858 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | EA | 2 | 55.44 | 110.88 | 20467 | CLOSE | 2024-01-27 | 2024-01-25 | KW1-14455 | 2 | 2024-01-27 | APPR | 2024-01-27 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-11 | COMP | 2024-01-30 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5315-60-V00-0058 | NAIL, FLAT, STAINLESS-STEEL, 2D X 1 INCH | 51850 | 2024-01-16 | 2024-01-17 | CLOSE | 1 | BX | 2 | 13.53 | 27.06 | 20409 | CLOSE | 2024-01-19 |  | KW1-14300 | 19 | 2024-01-23 | APPR | 2024-01-23 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-04 |  |  |  |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 5315-60-V00-0015 | NAIL, STRAIGHT, 16 GAGE, GALVANIZED, 3/4 INCHES | 51855 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | BX | 3 | 25.28 | 75.84 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 1 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-14 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8030-01-075-1156 | CAULKING COMPOUND, CARTRIDGE, WHITE, 10 OZ | 51859 | 2024-01-16 | 2024-01-18 | CLOSE | 2 | CQ | 12 | 14.85 | 178.2 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 3 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 | COMP | 2024-02-26 | 12.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8010-60-V00-0089 | PRIMER, COATING, WHITE, 4 - 5 LITERS | 51854 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | CN | 4 | 41.3 | 165.2 | 20446 | CLOSE | 2024-01-22 | 2024-01-22 | KW1-14376 | 1 | 2024-01-22 | APPR | 2024-01-28 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-05 | COMP | 2024-02-04 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8415-60-V00-0352 | COVERALLS, DISPOSABLE PROTECTIVE, TYVEK400, WHITE, XL | 51912 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | BX | 1 | 269.2 | 269.2 | 20467 | CLOSE | 2024-01-27 | 2024-01-25 | KW1-14455 | 5 | 2024-01-27 | APPR | 2024-01-27 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-29 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
48 | 2024-01-15 | 30 | BU24-0132 | Repair Ceiling Z3 T3020 | 8938044 | 8340-00-068-7908 | DROP CLOTH, PAINTER'S, 9 FT X 12 FT | 51859 | 2024-01-16 | 2024-01-18 | CLOSE | 1 | EA | 1 | 28.71 | 28.71 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 2 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
49 | 2023-11-27 | 30 | BU23-0310 | Install New Emergency Shower | 6872738 | 4230-60-V00-0001 | SHOWER ASSEMBLY, DECONTAMINATING, GALVANIZED STEEL, 350 LITERS, HDPE, WHITE, 60.6 X 34.6 X 128.1 INCHES | 42734 | 2023-09-19 | 2023-12-30 | CLOSE | 1 | EA | 1 | 11238.75 | 11238.75 | 20132 | CLOSE | 2024-01-10 | 2024-01-06 | KW1-14163 | 1 | 2024-01-10 | APPR | 2024-01-11 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-01-24 03:00 | COMP | 2024-01-15 | 1.00 |  | BU | BU table | November | 2023 | MM_BU
50 | 2024-01-16 | 30 | BU24-0048 | New Signs ASP Z8 T8000 | 8418200 | 8105-01-336-6163 | BAG, SAND, TAN, 26 INCHES | 51928 | 2024-01-17 | 2024-01-18 | CLOSE | 1 | HD | 3 | 742.5 | 2227.5 | 20441 | CLOSE | 2024-01-21 | 2024-01-21 | KW1-14365 | 6 | 2024-01-21 | APPR | 2024-01-22 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-05 | COMP | 2024-01-24 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5935-60-V00-0160 | SOCKET, OUTLET, WEATHERPROOF, 2 GANG, 2 POLES, 13 AMPS | 52341 | 2024-01-22 | 2024-01-27 | CLOSE | 7 | EA | 8 | 41.4 | 331.2 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 7 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 8.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 52337 | 2024-01-22 | 2024-01-27 | CLOSE | 5 | EA | 4 | 27.31 | 109.24 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 25 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0743 | BOX CONNECTOR, ELECTRICAL, CONDUIT, SET SCREW, STEEL, 3/4 INCH | 52338 | 2024-01-22 | 2024-01-27 | APPR | 4 | EA | 5 | 10.66 | 53.3 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 29 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-21 | COMP |  |  |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0376 | COUPLING, CONDUIT, w/ SET SCREW, STEEL, 3/4 INCH | 52337 | 2024-01-22 | 2024-01-27 | CLOSE | 4 | EA | 20 | 2 | 40 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 24 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 20.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-00-178-1217 | CONDUIT, RIGID, EMT, GALVANIZED STEEL, 3/4" INCH X 10 FEET | 52341 | 2024-01-22 | 2024-01-27 | CLOSE | 6 | EA | 20 | 13.6 | 272 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 6 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 20.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0066 | CONDUIT, METAL, RIGID, GALVANIZED STEEL, 1/2 INCH X 10 FEET | 52340 | 2024-01-22 | 2024-01-27 | CLOSE | 1 | EA | 20 | 212.9 | 4258 | 20622 | CLOSE | 2024-01-29 |  | KW1-14510 | 1 | 2024-01-29 | APPR | 2024-01-29 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-11 | COMP | 2024-02-01 | 20.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0483 | BOX CONNECTOR, ELECTRICAL, ZINC DIE CAST, 1/2 INCH | 52337 | 2024-01-22 | 2024-01-27 | CLOSE | 3 | EA | 10 | 4 | 40 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 23 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-21 | COMP | 2024-02-15 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0487 | COUPLING, ELECTRICAL CONDUIT, w/ SCREW, Â½ INCH | 52341 | 2024-01-22 | 2024-01-27 | CLOSE | 5 | EA | 10 | 5 | 50 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 5 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-10 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0043 | COUPLING, ELECTRICAL, CONDUIT, COMBINATION, EMT TO FMC, DIE CAST ZINC, 1/2 INCH | 52342 | 2024-01-22 | 2024-01-27 | CLOSE | 3 | EA | 8 | 9.24 | 73.92 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 8 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-14 | 8.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0042 | BOX CONNECTOR, ELECTRICAL, STRAIGHT, LIQUID TIGHT CONDUIT, NICKEL PLATED BRASS, 1/2 INCH | 52341 | 2024-01-22 | 2024-01-27 | CLOSE | 4 | EA | 16 | 24 | 384 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 4 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 16.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0395 | STRAP, TIE DOWN, WHITE, 12 INCHES | 52338 | 2024-01-22 | 2024-01-27 | CLOSE | 3 | PG | 2 | 13.99 | 27.98 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 28 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0460 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, GALVANIZED STEEL, ¾ INCH | 52337 | 2024-01-22 | 2024-01-27 | CLOSE | 2 | EA | 20 | 2.04 | 40.8 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 22 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 20.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0461 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, GALVANIZED STEEL, ½ INCH | 52338 | 2024-01-22 | 2024-01-27 | CLOSE | 2 | EA | 30 | 1.6 | 48 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 27 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 30.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 6145-60-V00-0136 | WIRE, ELECTRICAL, RED, 1 CORE, 4MM² | 52341 | 2024-01-22 | 2024-01-27 | CLOSE | 3 | RL | 1 | 90.56 | 90.56 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 3 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 6145-60-V00-0159 | WIRE, ELECTRICAL, BLUE, 1 CORE, 4 MM² | 52339 | 2024-01-22 | 2024-01-27 | CLOSE | 1 | RL | 1 | 90.4 | 90.4 | 20708 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14585 | 1 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-03-01 | COMP | 2024-02-05 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 6145-60-V00-0154 | WIRE, ELECTRICAL, BLACK, 1 CORE, 4MM² | 52341 | 2024-01-22 | 2024-01-27 | CLOSE | 2 | RL | 2 | 90.56 | 181.12 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 2 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 6145-60-V00-0142 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4MM² | 52337 | 2024-01-22 | 2024-01-27 | CLOSE | 1 | RL | 2 | 66.1 | 132.2 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 21 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5305-60-V00-0001 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 52338 | 2024-01-22 | 2024-01-27 | CLOSE | 1 | BX | 1 | 19.31 | 19.31 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 26 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5925-60-V00-0051 | CIRCUIT BREAKER, MINIATURE, 1 POLE, 230/400V, 20A | 52342 | 2024-01-22 | 2024-01-27 | CLOSE | 2 | EA | 4 | 49.5 | 198 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 7 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 52341 | 2024-01-22 | 2024-01-27 | CLOSE | 1 | BX | 1 | 92.02 | 92.02 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 1 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-12 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5110-60-V00-0066 | CUTTER, PIPE, HEAVY DUTY, 1/8- 2 INCHES | 52342 | 2024-01-22 | 2024-01-27 | CLOSE | 1 | EA | 1 | 188.5 | 188.5 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 6 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
51 | 2024-01-22 | 30 | BU24-0139 | Install Outlets Z6 B610 | 9227460 | 5110-01-367-7278 | CUTTER, CABLE, HAND OPERATED, FORGED STEEL, PLASTIC DIPPED, 9-1/2 INCHES | 52552 | 2024-01-25 | 2024-01-27 | CLOSE | 1 | EA | 1 | 66.6 | 66.6 | 20680 | CLOSE | 2024-01-31 | 2024-01-31 | KW1-14567 | 2 | 2024-01-31 | APPR | 2024-01-31 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-25 | COMP | 2024-02-17 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4730-60-V00-0754 | ADAPTER, PRESSURE FITTINGS, MALE, CPVC, STANDARD, SOCKET X MIPT, PN16, OFF-WHITE, 25 MM | 52617 | 2024-01-25 | 2024-01-29 | CLOSE | 8 | EA | 4 | 3.2 | 12.8 | 20699 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14578 | 12 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4730-60-V00-0897 | BUSHING, PIPE, REDUCER, SCH-40, CPVC, OFF-WHITE, 2 X 1 INCHES | 52603 | 2024-01-25 | 2024-01-29 | CLOSE | 2 | EA | 4 | 5.16 | 20.64 | 20680 | CLOSE | 2024-01-31 | 2024-01-31 | KW1-14567 | 17 | 2024-01-31 | APPR | 2024-01-31 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 8040-60-V00-0040 | CEMENT, HEAVY BODIED, CPVC, ORANGE, 16 OZ | 52605 | 2024-01-25 | 2024-01-29 | CLOSE | 2 | CN | 2 | 18.32 | 36.64 | 20666 | CLOSE | 2024-01-31 | 2024-01-31 | KW1-14559 | 16 | 2024-01-31 | APPR | 2024-01-31 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-10 | COMP | 2024-02-04 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4730-60-V00-0893 | BUSHING, PIPE, REDUCTION, SCH- 40, CPVC, OFF-WHITE, 1 X 3/4 INCHES | 52617 | 2024-01-25 | 2024-01-29 | CLOSE | 7 | EA | 4 | 5 | 20 | 20699 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14578 | 11 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4730-60-V00-0854 | ELBOW, CPVC, 90 DEGREE, SCH- 40, OFF-WHITE, 2 INCHES | 52603 | 2024-01-25 | 2024-01-29 | CLOSE | 1 | EA | 6 | 10.07 | 60.42 | 20680 | CLOSE | 2024-01-31 | 2024-01-31 | KW1-14567 | 16 | 2024-01-31 | APPR | 2024-01-31 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4730-60-V00-0850 | ELBOW, CPVC, SOCKET X SOCKET, SCH 40, OFF-WHITE, 25 MM | 52617 | 2024-01-25 | 2024-01-29 | CLOSE | 6 | EA | 4 | 3.6 | 14.4 | 20699 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14578 | 10 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4710-60-V00-0107 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 2 INCHES | 52617 | 2024-01-25 | 2024-01-29 | CLOSE | 5 | EA | 2 | 51.15 | 102.3 | 20699 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14578 | 9 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4710-60-V00-0111 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 1 INCH | 52617 | 2024-01-25 | 2024-01-29 | CLOSE | 4 | EA | 1 | 31.18 | 31.18 | 20699 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14578 | 8 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4710-60-V00-0108 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 52617 | 2024-01-25 | 2024-01-29 | CLOSE | 3 | EA | 1 | 18.81 | 18.81 | 20699 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14578 | 7 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 8030-60-V00-0051 | TAPE, ANTISEIZING, (TEFLON TAPE), 0.5 X 520 INCHES | 52605 | 2024-01-25 | 2024-01-29 | CLOSE | 1 | EA | 10 | 1.67 | 16.7 | 20666 | CLOSE | 2024-01-31 | 2024-01-31 | KW1-14559 | 15 | 2024-01-31 | APPR | 2024-01-31 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-10 | COMP | 2024-02-04 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4510-60-V00-0132 | STRAP, METAL | 52618 | 2024-01-25 | 2024-01-29 | CLOSE | 2 | EA | 1 | 73.9 | 73.9 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 48 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4230-60-V00-0001 | SHOWER ASSEMBLY, DECONTAMINATING, GALVANIZED STEEL, 350 LITERS, HDPE, WHITE, 60.6 X 34.6 X 128.1 INCHES | 52602 | 2024-01-25 | 2024-01-29 | CLOSE | 1 | EA | 2 | 11938.05 | 23876.1 | 20638 | CLOSE | 2024-02-08 | 2024-02-01 | KW1-14725 | 1 | 2024-02-08 | APPR | 2024-02-08 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-07-31 |  |  |  |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 5306-60-V00-0006 | BOLT, CONCRETE ANCHOR, w/ NUT & WASHER, M10 X 4 INCHES | 52617 | 2024-01-25 | 2024-01-29 | CLOSE | 2 | BX | 8 | 7.26 | 58.08 | 20699 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14578 | 6 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 8.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4820-60-V00-0115 | VALVE, CHECK, PVC, 2 INCHES | 52606 | 2024-01-25 | 2024-01-27 | CLOSE | 2 | EA | 2 | 67.27 | 134.54 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 14 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4820-60-V00-0229 | VALVE, BALL, BRASS, PN25, RED, 3/4 INCH | 52617 | 2024-01-25 | 2024-01-29 | CLOSE | 1 | EA | 2 | 15.84 | 31.68 | 20699 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14578 | 5 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4730-60-V00-0775 | ADAPTER, MALE, CPVC, STANDARD, SOCKET X MIPT, SCH- 40, OFF-WHITE, 63 MM | 52604 | 2024-01-25 | 2024-01-29 | CLOSE | 3 | EA | 4 | 45.79 | 183.16 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 12 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-19 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4730-60-V00-0760 | ADAPTER, FEMALE, CPVC & METAL, STANDARD, SOCKET X SR FIPT, SCH- 40, OFF WHITE, 32 MM | 52604 | 2024-01-25 | 2024-01-29 | CLOSE | 2 | EA | 6 | 12.99 | 77.94 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 11 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-19 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4730-60-V00-0765 | ADAPTER, PRESSURE FITTINGS, FEMALE, CPVC, STANDARD, SOCKET X FIPT, SCH- 40, OFF-WHITE, 25 MM | 52607 | 2024-01-25 | 2024-01-29 | CLOSE | 2 | EA | 4 | 13.1 | 52.4 | 20680 | CLOSE | 2024-01-31 | 2024-01-31 | KW1-14567 | 19 | 2024-01-31 | APPR | 2024-01-31 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 4730-60-V00-0788 | CAP, PIPE, UPVC, OCTAGON, FEMALE, SCH-40, GRAY, 63 MM | 52604 | 2024-01-25 | 2024-01-29 | CLOSE | 1 | EA | 2 | 9.16 | 18.32 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 10 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-19 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 5510-00-220-6242 | LUMBER, SOFTWOOD, DIMENSION, 4 X 2 INCHES X 10 FEET | 52607 | 2024-01-25 | 2024-01-29 | CLOSE | 1 | EA | 2 | 25.4 | 50.8 | 20680 | CLOSE | 2024-01-31 | 2024-01-31 | KW1-14567 | 18 | 2024-01-31 | APPR | 2024-01-31 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 5510-01-433-4221 | LUMBER, SOFTWOOD, 4 X 4 INCHES X 16 FEET | 52606 | 2024-01-25 | 2024-01-27 | CLOSE | 1 | EA | 2 | 37.46 | 74.92 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 13 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 5305-09-V00-0012 | SCREW, WOOD, DRYWALL, PHILLIPS, STEEL, 3 INCHES | 52619 | 2024-01-25 | 2024-01-29 | CLOSE | 1 | BX | 1 | 159.16 | 159.16 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 15 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
52 | 2024-01-24 | 30 | BU24-0071 | Install Emergency Shower H9100 SS9708 - C to TDP | 9117710 | 5133-60-V00-0020 | DRILL, MASONRY, ROTARY DRIVEN, (BIT), CONCRETE, SDS-PLUS, 1/2 X 8 INCHES | 52618 | 2024-01-25 | 2024-01-29 | CLOSE | 1 | EA | 2 | 10.73 | 21.46 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 47 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
53 | 2024-01-25 | 30 | BU24-0140 | Install Cypher Locks T9601 | 9223619 | 5340-60-V00-0425 | LOCK SET, MORTISE, MECHANICAL, PUSH BUTTON, RIGHT HAND, 2-3/4 INCHES | 52621 | 2024-01-25 | 2024-01-27 | CLOSE | 1 | EA | 2 | 690.03 | 1380.06 | 20699 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14578 | 13 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-10 | COMP | 2024-02-05 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6210-60-V00-0081 | LIGHT, PANEL, LED, COOL WHITE, 50/60 HZ, 40W | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 20 | EA | 2 | 274.38 | 548.76 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 25 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6210-60-V00-0082 | LIGHT, PANEL, LED, COOL WHITE, 50/60 HZ, 40W, w/ EMERGENCY BATTERY | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 19 | EA | 3 | 297.94 | 893.82 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 24 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6210-60-V00-0136 | EMERGENCY LIGHT, EXIT COMBO, LED | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 18 | EA | 1 | 130.86 | 130.86 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 23 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6210-60-V00-0040 | FIXTURE, LIGHTING, LED, WALL PACK, 5000K, 100-277 VAC, 30W | 53003 | 2024-01-30 | 2024-02-01 | CLOSE | 8 | EA | 1 | 127.05 | 127.05 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 27 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6130-60-V00-0097 | BATTERY, EMERGENCY LED DRIVER, 50/60HZ, 15W, 100-277V | 53003 | 2024-01-30 | 2024-02-01 | CLOSE | 7 | EA | 1 | 254.32 | 254.32 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 26 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6210-60-V00-0165 | LIGHT, LED FLOOD, W/EMERGENCY BATTERY,50W, 100-240 VAC, 50/60 Hz | 53003 | 2024-01-30 | 2024-02-01 | CLOSE | 6 | EA | 2 | 601.37 | 1202.74 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 25 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 17 | EA | 10 | 9.9 | 99 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 22 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-25 | COMP | 2024-02-07 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5930-60-V00-0387 | LIGHT-SWITCH, METAL, 1 WAY, 1 GANG, 250V, 10A | 53003 | 2024-01-30 | 2024-02-01 | CLOSE | 5 | EA | 3 | 17.63 | 52.89 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 24 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0118 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 16 MM² | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 1 | MT | 50 | 22 | 1100 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 6 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 50.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-60-V00-0511 | GLAND, ELECTRICAL CONDUIT, BRASS, BW, w/ EARTH TAG, 25 MM | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 16 | EA | 5 | 8 | 40 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 21 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 5.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5940-60-V00-0122 | TERMINAL, LUG, COPPER TUBE, STUD HOLE, 16MM² X M10 | 53003 | 2024-01-30 | 2024-02-01 | CLOSE | 4 | PK | 1 | 67.3 | 67.3 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 23 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 15 | RL | 1 | 242.58 | 242.58 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 20 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 07:00 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 14 | EA | 1 | 16.83 | 16.83 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 19 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5970-60-V00-0043 | TAPE, INSULATION, ELECTRICAL, SUPER 33 +,VINYL, BLACK, 3/4" X 66' | 53003 | 2024-01-30 | 2024-02-01 | CLOSE | 3 | EA | 2 | 13.99 | 27.98 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 22 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5970-01-013-9369 | TAPE, INSULATION ELECTRICAL, 3M, 792", RED | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 13 | EA | 1 | 10.1 | 10.1 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 18 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5970-01-174-5651 | TAPE, INSULATION ELECTRICAL, YELLOW | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 12 | EA | 1 | 10.1 | 10.1 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 17 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5970-01-015-5060 | TAPE, INSULATION ELECTRICAL BLUE | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 11 | EA | 1 | 10.1 | 10.1 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 16 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-01-559-8780 | STRAP, TIE DOWN,ELECTRICAL COMPONENT, BLACK, 50 PSI, 3 X 0.19 X 0.05 X 11.1 INCHES | 53006 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | PK | 2 | 2.48 | 4.96 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 16 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 53004 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 100 | 4.3 | 430 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 17 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 100.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 10 | BX | 1 | 92.02 | 92.02 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 15 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-12 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6110-60-V00-0104 | SWITCH, DISCONNECT (ISOLATOR), 4 POLES, 690V, 63A | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 9 | EA | 1 | 101.52 | 101.52 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 14 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-60-V00-0460 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, GALVANIZED STEEL, ¾ INCH | 53003 | 2024-01-30 | 2024-02-01 | CLOSE | 2 | PG | 10 | 2.11 | 84.4 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 21 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 40.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 9905-60-V00-0066 | SIGN, DANGER, 415 VOLTS , 5 X 3-3/4 INCHES | 53003 | 2024-01-30 | 2024-02-01 | CLOSE | 1 | PG | 2 | 17.08 | 34.16 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 20 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 8 | EA | 1 | 302.94 | 302.94 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 13 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 7 | EA | 1 | 58.91 | 58.91 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 12 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0158 | WIRE, ELECTRICAL, RED, 1 CORE, 2.5 MM² | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 6 | RO | 1 | 60.39 | 60.39 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 11 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0151 | WIRE, ELECTRICAL, BLACK 1 CORE, 2.5 MM² | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 5 | RO | 1 | 64.92 | 64.92 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 10 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 53004 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | RO | 1 | 64.5 | 64.5 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 16 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0154 | WIRE, ELECTRICAL, BLACK, 1 CORE, 4 MM ² | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 4 | RO | 1 | 90.56 | 90.56 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 9 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0143 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4 MM² | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 3 | RO | 1 | 90.56 | 90.56 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 8 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 60 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0136 | WIRE, ELECTRICAL, RED, 1 CORE, 4 MM ² | 53005 | 2024-01-30 | 2024-02-01 | CLOSE | 2 | RO | 1 | 90.56 | 90.56 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 7 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 70 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6110-60-V00-0166 | SENSOR, PHOTOCELL CONTROL, 15A, 50/60 HZ | 52975 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 1 | 63.36 | 63.36 | 20797 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14677 | 6 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 70 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4240-60-V00-0055 | TAPE, FLAGGING, CAUTION BURIED ELECTRIC LINE BELOW, ALUMINUM, RED, 6 INCHES X 1000 FEET | 52974 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | RO | 1 | 224.4 | 224.4 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 39 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 70 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 52975 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 2 | 51.81 | 103.62 | 20797 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14677 | 5 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-10 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 70 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 52972 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 10 | 26.67 | 266.7 | 20797 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14677 | 4 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-10 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 70 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5120-60-V00-0111 | SCREW DRIVER / NUT DRIVER, HEAVY DUTY, MULTI-BIT | 52973 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 2 | 41.25 | 82.5 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 14 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-30 | 70 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5180-39-V01-0007 | SCREW DRIVER SET , ELECTRONICS SLOTTED AND PHILLIPS , 4-PIECE. | 52974 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 2 | 51.48 | 102.96 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 38 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 | COMP | 2024-02-28 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4710-60-V00-0098 | TUBE, METALLIC, REFRIGERATION, COPPER, 5/8 INCH X 50 FEET | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 10 | RO | 1 | 100.5 | 100.5 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 41 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4710-60-V00-0097 | TUBE, METALLIC, REFRIGERATION, COPPER, 3/8 INCH X 50 FEET | 52816 | 2024-01-29 | 2024-01-30 | CLOSE | 3 | RO | 1 | 62.4 | 62.4 | 20708 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14585 | 11 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-03-01 | COMP | 2024-02-05 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5640-60-V00-0031 | INSULATION SLEEVING, THERMAL, 5/8 X 72 INCHES | 52817 | 2024-01-29 | 2024-01-30 | CLOSE | 4 | EA | 9 | 4 | 36 | 20831 | CLOSE | 2024-02-06 | 2024-02-06 | KW1-14688 | 4 | 2024-02-06 | APPR | 2024-02-06 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-11 | 9.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5640-60-V00-0030 | INSULATION SLEEVING, THERMAL, 3/8 X 72 INCHES | 52817 | 2024-01-29 | 2024-01-30 | CLOSE | 3 | EA | 9 | 2.6 | 23.4 | 20831 | CLOSE | 2024-02-06 | 2024-02-06 | KW1-14688 | 3 | 2024-02-06 | APPR | 2024-02-06 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-11 | 9.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4710-60-V00-0110 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 52816 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | EA | 1 | 17.5 | 17.5 | 20708 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14585 | 10 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-03-01 | COMP | 2024-02-05 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 9 | BX | 1 | 141.9 | 141.9 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 40 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4130-60-V00-0288 | TAPE, WRAP, INSULATION, 3 INCHES X 150 FEET | 52817 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | RO | 2 | 32 | 64 | 20831 | CLOSE | 2024-02-06 | 2024-02-06 | KW1-14688 | 2 | 2024-02-06 | APPR | 2024-02-06 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 8 | EA | 1 | 60 | 60 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 39 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4730-60-V00-0594 | C-CLAMP W/ RUBBER, GALVANIZED STEEL, 2 INCHES | 52816 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | EA | 4 | 9.4 | 37.6 | 20708 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14585 | 9 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-03-01 | COMP | 2024-02-05 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-60-V00-0505 | STUFFING TUBE (CABLE GLAND), PG16, POLYAMIDE, GRAY, 9 -14 MM | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 7 | EA | 4 | 3.2 | 12.8 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 38 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM ² | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 6 | RO | 1 | 163.2 | 163.2 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 37 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 52814 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | RO | 1 | 146.52 | 146.52 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 73 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5930-60-V00-0254 | SWITCH, DOUBLE POLE, METAL CLAD, 1 GANG, 32A | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 5 | EA | 1 | 70 | 70 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 36 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4130-60-V00-0353 | NUT, TUBE COUPLING, 3/8 INCH | 52812 | 2024-01-29 | 2024-01-29 | CLOSE | 2 | EA | 2 | 13.32 | 26.64 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 70 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5310-60-V00-0126 | NUT, TUBE COUPLING, 5/8 INCH | 52812 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | EA | 2 | 7.33 | 14.66 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 69 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4130-60-V00-0137 | MOUNTING BASE, AIR-CONDITIONER, POLYPROPYLENE, IVORY, 17 X 3 X 5.12 INCHES | 52813 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | PG | 1 | 68.6 | 68.6 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 71 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4120-60-V00-0018 | AIR CONDITIONER, SPLIT, INDOOR & OUTDOOR, 220-240V, 1 PH, 50/60 HZ, BTU 22000 | 52811 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | EA | 1 | 1098.9 | 1098.9 | 20723 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14732 | 3 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | CARRIER KUWAIT AIR CONDITIONING | 2024-04-01 |  |  |  |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4730-60-V00-0430 | ELBOW, PIPE, SOCKET X SOCKET, 45 DEGREE, CPVC, OFF WHITE, 25 MM | 52814 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | EA | 1 | 3.16 | 3.16 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 72 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4730-60-V00-0850 | ELBOW, CPVC, SOCKET X SOCKET, SCH 40, OFF-WHITE, 25 MM | 52817 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | EA | 1 | 3.6 | 3.6 | 20831 | CLOSE | 2024-02-06 | 2024-02-06 | KW1-14688 | 1 | 2024-02-06 | APPR | 2024-02-06 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-01-655-6053 | CONDUIT, METAL, FLEXIBLE, BLACK, 3/4 INCH X 100 FEET | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 4 | BX | 1 | 702.78 | 702.78 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 35 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 3 | RO | 1 | 242.58 | 242.58 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 34 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | RO | 1 | 21.11 | 21.11 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 33 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 52818 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | EA | 1 | 16.83 | 16.83 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 32 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5940-60-V00-0003 | LUG, TERMINAL, FORK, INSULATED, BLUE, 16-14 AWG | 52820 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | BG | 1 | 53.63 | 53.63 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 25 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5620-60-V00-0004 | CONCRETE MASONRY UNIT, SOLID, 10 X 10 X 2 INCHES | 52815 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | EA | 4 | 91.74 | 366.96 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 74 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-20 | COMP | 2024-02-19 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 50 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5975-60-V00-0502 | ROD, GROUNDING, KIT, WITH CLAMP, 5/8 INCH X 4 FEET | 52819 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | KT | 1 | 145 | 145 | 20711 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14593 | 9 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-10 | COMP | 2024-02-06 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 30 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 4210-60-V00-0189 | EXTINGUISHER, FIRE, ABC DRY CHEMICAL W/ WALL HOOK, 10 LBS | 52772 | 2024-01-28 | 2024-01-29 | CLOSE | 1 | EA | 1 | 277.22 | 277.22 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 67 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-21 |  |  |  |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 30 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6350-60-V00-0102 | ALARM, SMOKE, AUTOMATIC, PLASTIC | 52771 | 2024-01-28 | 2024-01-29 | CLOSE | 1 | EA | 3 | 28.97 | 86.91 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 66 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5640-60-V00-0012 | INSULATION BLANKET, THERMAL, GLASS WOOL, YELLOW, 4 FEET X 10 METER | 52801 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | RO | 1 | 214.45 | 214.45 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 6 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5620-60-V00-0015 | TILE, CEILING, LAMINATED, GYPSUM, 2 X 2 FEET | 52807 | 2024-01-29 | 2024-01-29 | CLOSE | 4 | EA | 60 | 37.46 | 299.68 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 12 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 8.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 10 | BX | 3 | 19.6 | 58.8 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 10 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-10 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5305-60-V00-0170 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATE, # 8 X 3 INCHES | 52807 | 2024-01-29 | 2024-01-29 | CLOSE | 3 | BX | 3 | 35.96 | 107.88 | 20743 | CLOSE | 2024-02-03 |  | KW1-14615 | 5 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-06 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 7210-60-V00-0059 | FLOOR COVERING, VINYL RESIN, 3 MM X 40 FEET | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 9 | RL | 1 | 716.1 | 716.1 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 9 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-15 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8040-00-273-8713 | ADHESIVE, FLOORING, WHITE, 1 GL | 52809 | 2024-01-29 | 2024-01-29 | CLOSE | 6 | GL | 4 | 185.7 | 742.8 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 30 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8010-60-V00-0130 | PAINT, LATEX, MATT, WHITE, 1 GL (3.2 TO 3.6 LT) | 52800 | 2024-01-29 | 2024-01-29 | CLOSE | 6 | CN | 8 | 42.62 | 340.96 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 10 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-06 | 8.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 52809 | 2024-01-29 | 2024-01-29 | CLOSE | 5 | EA | 10 | 13.9 | 139 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 29 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 52806 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | BX | 1 | 16.5 | 16.5 | 20781 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14652 | 4 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-03-15 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5350-60-V00-0010 | PAPER, ABRASIVE (SANDPAPER), 80 GRIT, 9 X 11 INCHES | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 8 | PG | 3 | 23 | 69 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 8 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-10 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8020-00-260-1302 | BRUSH, PAINT, BRISTLES, CHISELED, 2 INCHES | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 7 | EA | 10 | 15.2 | 152 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 7 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-10 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 52809 | 2024-01-29 | 2024-01-29 | CLOSE | 4 | EA | 8 | 29 | 232 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 28 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 8.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 6 | EA | 11 | 45.4 | 499.4 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 6 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-10 | 11.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8030-60-V00-0055 | SEALANT, SILICONE, WHITE, 300ml | 52809 | 2024-01-29 | 2024-01-29 | CLOSE | 3 | BX | 1 | 141.9 | 141.9 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 27 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8010-60-V00-0089 | PRIMER, COATING, WHITE, 4 - 5 LITERS | 52809 | 2024-01-29 | 2024-01-29 | CLOSE | 2 | CN | 3 | 41.3 | 123.9 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 26 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8010-60-V00-0013 | PAINT, ENAMEL, FLAT, WHITE, 3.20 LITER | 52800 | 2024-01-29 | 2024-01-29 | CLOSE | 5 | CN | 6 | 49.62 | 297.72 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 9 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-06 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 9515-60-V00-0016 | SHEET, METAL, ALUMINIUM, FLAT, 4 X 8 FEET X 1/16 INCH | 52807 | 2024-01-29 | 2024-01-29 | CLOSE | 2 | SH | 1 | 88.25 | 88.25 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 11 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5640-05-V00-0007 | CEMENT BOARD, WATER RESISTANT, 1/2 INCH X 4 X 8 FEET | 52810 | 2024-01-29 | 2024-01-29 | CLOSE | 3 | EA | 7 | 37.1 | 259.7 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 15 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 7.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5340-60-V00-0471 | CLOSER, DOOR, HYDRAULIC, ALUMINUM, NON-HOLD OPEN, 4 X 13 X 2-3/16 INCHES | 52807 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | EA | 1 | 599.4 | 599.4 | 20743 | CLOSE | 2024-02-03 |  | KW1-14615 | 3 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-06 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5340-60-V00-0220 | LATCH, SLIDING WINDOW, SPRING LOADED, PLASTIC, BLACK, 3 X 1-1/6 X 1-1/4 INCHES | 52810 | 2024-01-29 | 2024-01-29 | CLOSE | 2 | EA | 3 | 35.64 | 106.92 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 14 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-17 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5340-60-V01-0076 | LOCK, SLIDING WINDOW | 52981 | 2024-01-29 | 2024-01-31 | CLOSE | 1 | KT | 3 | 23.71 | 71.13 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 10 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-15 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5340-60-V00-0485 | HANDLE, SLIDING WINDOW, METAL, 5-3/4 INCHES | 52805 | 2024-01-29 | 2024-01-29 | CLOSE | 2 | EA | 3 | 19.65 | 58.95 | 20743 | CLOSE | 2024-02-03 |  | KW1-14615 | 4 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-06 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5640-60-V00-0044 | TAPE, SELF ADHESIVE, DRYWALL JOINT, FIBERGLASS, 2 INCHES X 300 FEET | 52805 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | EA | 1 | 18.65 | 18.65 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 10 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5340-60-V00-0481 | HINGE, DOOR, STAINLESS STEEL, 3 MM X 3-1/2 X 4 INCHES | 52802 | 2024-01-29 | 2024-01-29 | CLOSE | 2 | EA | 6 | 30.47 | 182.82 | 20780 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14649 | 8 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-15 | COMP | 2024-02-10 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8030-60-V00-0053 | FOAM, CONSTRUCTION, CREAM, 700ML | 52800 | 2024-01-29 | 2024-01-29 | CLOSE | 4 | EA | 5 | 19.5 | 97.5 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 8 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-06 | 5.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 5 | CN | 3 | 37 | 111 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 5 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-10 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 6850-60-V00-0005 | ADDITIVE, MILDEWCIDE, LIQUID, 50-GRAM | 52803 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | EA | 7 | 35.8 | 250.6 | 20708 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14585 | 8 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-03-01 | COMP | 2024-02-07 | 7.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5305-60-V00-0169 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 3 INCHES | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 4 | BX | 1 | 30.4 | 30.4 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 4 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5320-60-V00-0014 | RIVET, BLIND, ALUMINUM, 2 INCHES | 52802 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | BX | 1 | 20.98 | 20.98 | 20780 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14649 | 7 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-15 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5320-60-V00-0005 | RIVET, BLIND, STAINLESS STEEL, SILVER, 6.4 MM | 52804 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | PG | 1 | 67.93 | 67.93 | 20780 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14649 | 9 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-15 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 3230-60-V00-0024 | BLADE, CIRCULAR SAW, WOOD CUTTING, 36 TOOTH, 7-1/4 INCHES | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 3 | EA | 1 | 52 | 52 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 3 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5510-60-V00-0003 | LUMBER, SOFTWOOD, DIMENSION, 2 X 4 INCHES X 13 FEET | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 2 | EA | 4 | 35.3 | 141.2 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 2 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-10 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8040-60-V00-0027 | TAPE, ADHESIVE, POLY FOAM, OPEN CELL, BLACK, 12.7 X 19 MM X 5 METERS | 52809 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | RO | 2 | 19.8 | 39.6 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 25 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5640-60-V00-0032 | WEATHER STRIP, DOOR, W/RUBBER BOTTOM SWEEP, 39" | 52800 | 2024-01-29 | 2024-01-29 | CLOSE | 3 | EA | 2 | 16.62 | 33.24 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 9 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5640-60-V00-0035 | WEATHER STRIP, DOOR, W/BRUSH, 2 X 36 INCHES | 52800 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | EA | 2 | 30.47 | 60.94 | 20766 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14752 | 9 | 2024-02-09 | APPR | 2024-02-09 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-02-20 | COMP | 2024-02-13 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5640-60-V00-0034 | WEATHER STRIP, FLUTE TOPPED ALUMINUM THRESHOLD, 3' (L) X 4-1/4" (W) | 52800 | 2024-01-29 | 2024-01-29 | CLOSE | 2 | EA | 1 | 49.45 | 49.45 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 8 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 52808 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | BX | 2 | 29 | 58 | 20788 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14662 | 1 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-10 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
54 | 2024-01-27 | 40 | BU24-0059 | TI Deficiency Repairs Z8 T132 | 8528915 | 8010-60-V00-0245 | BRITISH GYPSUM GYPROC DRYWALL PRIMER 10L | 52810 | 2024-01-29 | 2024-01-29 | CLOSE | 1 | CN | 1 | 76.19 | 76.19 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 13 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-12 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5650-60-V01-0003 | C-STUD RUNNER, GALVANIZED STEEL, 0.0366 X 1 1/4 X 3 INCHES X 12 FEET | 52874 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | EA | 12 | 6.17 | 74.04 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 32 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-14 | 12.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5305-60-V00-0022 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #10, 1-1/2 INCHES | 52875 | 2024-01-29 | 2024-01-30 | CLOSE | 7 | BX | 1 | 46.95 | 46.95 | 20743 | CLOSE | 2024-02-03 |  | KW1-14615 | 18 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-06 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5305-60-V00-0220 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, STEEL, #6 X 2 INCHES | 52875 | 2024-01-29 | 2024-01-30 | CLOSE | 6 | BX | 1 | 52.02 | 52.02 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 34 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5305-60-V00-0157 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, COARSE THREAD, #7 X 1-3/8 INCHES 1000pc/box | 52875 | 2024-01-29 | 2024-01-30 | CLOSE | 5 | bx | 2 | 22.74 | 45.48 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 33 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 7510-00-680-2395 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 52875 | 2024-01-29 | 2024-01-30 | CLOSE | 4 | EA | 8 | 12.67 | 101.36 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 32 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 8.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5680-60-V01-0002 | CORNER BEAD, STAINLESS STEEL, 25 MM X2.5 METER | 52875 | 2024-01-29 | 2024-01-30 | CLOSE | 3 | EA | 4 | 52.08 | 208.32 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 31 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-12 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8010-60-V00-0003 | PRIMER COATING, WOOD, ALKYD, WHITE, 16 LITER | 52872 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | CN | 1 | 162.1 | 162.1 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 88 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-20 | COMP | 2024-02-17 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8010-60-V00-0141 | PAINT, LATEX, SEMI MATT, BEIGE, 1 GL (3.6 L) | 52878 | 2024-01-29 | 2024-01-30 | CLOSE | 3 | CN | 5 | 55.4 | 277 | 20793 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14670 | 13 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-19 | COMP | 2024-02-11 | 5.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 52876 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | EA | 10 | 14.6 | 146 | 20778 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14641 | 9 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-04-04 | COMP | 2024-02-07 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 52878 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | EA | 6 | 12.54 | 75.24 | 20793 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14670 | 12 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-19 | COMP | 2024-02-10 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUAR | 52878 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | EA | 6 | 29.04 | 174.24 | 20793 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14670 | 11 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-19 | COMP | 2024-02-10 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 9515-60-V00-0016 | SHEET, METAL, ALUMINIUM, FLAT, 4 X 8 FEET X 1/16 INCH | 52875 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | EA | 8 | 86.1 | 688.8 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 30 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 8.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5530-00-129-7777 | PLYWOOD, CONSTRUCTION, EXTERIOR, 1/2 INCH X 8 X 4 FEET | 52872 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | EA | 3 | 36.3 | 108.9 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 89 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5340-60-V00-0492 | STOPPER, DOOR, DROP DOWN, METAL, 5" | 52876 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | EA | 1 | 19.47 | 19.47 | 20778 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14642 | 13 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8030-09-V01-0003 | SEALING COMPOUND, CAULK, ACRYLIC, WHITE, 5.5 OZ | 52875 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | EA | 4 | 49.83 | 199.32 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 29 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-03-11 | COMP | 2024-02-20 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 70 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5510-01-433-1244 | LUMBER, SOFTWOOD, 2 X 4 INCHES X 16 FEET | 52877 | 2024-01-29 | 2024-01-30 | CLOSE | 2 | EA | 10 | 30.4 | 304 | 20831 | CLOSE | 2024-02-06 | 2024-02-06 | KW1-14688 | 21 | 2024-02-06 | APPR | 2024-02-06 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-11 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 40 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8010-60-V00-0241 | PRIMER COATING, PAINT, LATEX, INTERIOR, WATERBASED, WHITE, 16 LITERS | 52874 | 2024-01-29 | 2024-01-30 | CLOSE | 1 | CN | 1 | 55.07 | 55.07 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 31 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 52954 | 2024-01-30 | 2024-01-31 | CLOSE | 4 | RO | 2 | 92.02 | 184.04 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 35 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 52953 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 20 | 27.06 | 541.2 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 22 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 20.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5930-60-V00-0243 | LIGHT-SWITCH, METAL, 2 WAY, 1 GANG, 250V, 10A | 52954 | 2024-01-30 | 2024-01-31 | CLOSE | 3 | EA | 6 | 33.25 | 199.5 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 34 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 4010-60-V00-0023 | CHAIN, WELDED, LINK, STEEL, 4 X 19 MM | 52956 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | MR | 50 | 6.51 | 325.5 | 20778 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14641 | 13 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-04-04 | COMP | 2024-02-07 | 50.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5306-60-V00-0120 | BOLT AND NUT, HEX w/ WASHER, 2 INCHES X 10 MM | 52958 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | PG | 3 | 82.5 | 247.5 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 96 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5306-60-V00-0173 | BOLT, U, ZINC PLATED SQUARE, 1/2 X 2 X 3 1/2 INCHES, 5 COMPONENTS | 52960 | 2024-01-30 | 2024-01-31 | CLOSE | 3 | EA | 50 | 5.29 | 264.5 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 8 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-03-11 | COMP | 2024-02-12 | 50.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5305-05-V00-0057 | SCREW, PIN SHACKLE, CLAMPING WINCH CABLE, 3/8 X 0.375 INCHES | 52960 | 2024-01-30 | 2024-01-31 | APPR | 2 | EA | 40 | 15.11 | 604.4 | [16 empty] | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5306-60-V00-0174 | BOLT, EYE, UNWELDED, STAINLESS STEEL, 1/4 X 2-1/2 INCHES | 52960 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 50 | 1.94 | 97 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 6 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-03-11 | COMP | 2024-02-12 | 50.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 9520-60-V00-0005 | ANGLE, STRUCTURAL, STEEL, 4MM X 2 X 2 INCHES X 10 FEET | 52962 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 22 | 50.4 | 1108.8 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 9 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-12 | 22.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 6210-60-V00-0165 | LIGHT, LED FLOOD, W/EMERGENCY BATTERY,50W, 100-240 VAC, 50/60 Hz | 52953 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 2 | 631.95 | 1263.9 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 5 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 52959 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 50 | 4.3 | 215 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 11 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 50.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 4140-60-V00-0118 | FAN, VENTILATING, SQUARE, 220V, 12 INCHES | 52996 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 2 | 93.1 | 186.2 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 12 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 80 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5310-60-V00-0084 | WASHER, FLAT, STEEL, M8 | 52957 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 3 | 7.26 | 21.78 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 10 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0066 | CONDUIT, METAL, RIGID,EMT GALVANIZED STEEL, 1/2 INCH X 10 FEET | 52954 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 20 | 265 | 5300 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 24 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 20.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 6210-60-V00-0094 | FIXTURE, LIGHTING, LED, RETROFIT, POLYCARBONATE, PURE WHITE, 40W | 52954 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 20 | 242.35 | 4847 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 23 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 20.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 6145-60-V00-0098 | WIRE, ELECTRICAL, WHITE, 8 CORE, 18 AWG | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 10 | SL | 1 | 761.3 | 761.3 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 19 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 6685-60-V00-0166 | GUARD, THERMOSTAT, PLASTIC, CLEAR, 6-3/8 X 3-1/2 X 3-1/4 INCHES | 52997 | 2024-01-30 | 2024-02-01 | CLOSE | 9 | EA | 2 | 24.72 | 49.44 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 9 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 6685-60-V00-0163 | THERMOSTAT, DIGITAL, NON-PROGRAMMABLE | 52997 | 2024-01-30 | 2024-02-01 | CLOSE | 8 | EA | 2 | 91.07 | 182.14 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 8 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5306-60-V00-0001 | BOLT, CONCRETE ANCHOR, w/ NUT & WASHER, M10 X 3 INCHES | 52967 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | BX | 3 | 37 | 111 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 13 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0435 | PAD, ANTI VIBRATION, RUBBER/CORK, 4 X 4 X 1 INCHES | 53000 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 7 | 15.5 | 108.5 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 15 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 7.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 9520-60-V00-0005 | ANGLE, STRUCTURAL, STEEL, 4MM X 2 X 2 INCHES X 10 FEET | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 9 | EA | 5 | 50.4 | 252 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 18 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-14 | 5.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8010-60-V00-0143 | PAINT, ENAMEL, GLOSS, DESERT SAND, 1 GL (3.2 to 3.6 LITER) | 52966 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | CN | 1 | 49.1 | 49.1 | 20793 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14670 | 18 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-19 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8010-60-V00-0124 | PRIMER, RED OXIDE, OIL BASED, RED, 1 GL | 52968 | 2024-01-30 | 2024-01-31 | CLOSE | 3 | CN | 1 | 41.4 | 41.4 | 20797 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14677 | 3 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8020-00-205-6500 | BRUSH, PAINT, BRISTLES | 52969 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 4 | 21.8 | 87.2 | 20793 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14670 | 19 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-19 | COMP | 2024-02-10 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 52968 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 4 | 12.4 | 49.6 | 20797 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14677 | 2 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-10 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 8020-60-V00-0032 | TRAY, PAINT ROLLER, METAL, 13 INCHES, 3 QT. | 52968 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 3 | 10 | 30 | 20797 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14677 | 1 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-12 | 3.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-01-655-6053 | CONDUIT, METAL, FLEXIBLE, BLACK, 3/4 INCH X 100 FEET | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 8 | RO | 1 | 702.78 | 702.78 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 17 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0042 | BOX CONNECTOR, ELECTRICAL, STRAIGHT, LIQUID TIGHT CONDUIT, NICKEL PLATED BRASS, 1/2 INCH | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 7 | EA | 16 | 24 | 384 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 16 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 16.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 6 | RO | 1 | 242.58 | 242.58 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 15 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 6145-60-V00-0149 | WIRE, ELECTRICAL, RED, 1 CORE, 1.5 MM ² | 52997 | 2024-01-30 | 2024-02-01 | CLOSE | 7 | RO | 1 | 48.14 | 48.14 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 7 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 6145-60-V00-0050 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 1.5 MM ² | 52997 | 2024-01-30 | 2024-02-01 | CLOSE | 6 | RO | 1 | 41.14 | 41.14 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 6 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5940-60-V00-0016 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 16 MM ² | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 5 | EA | 10 | 5 | 50 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 14 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5935-60-V00-0225 | CONNECTOR, TWIST ON SPLICE, STRAIGHT, YELLOW, 18-12 AWG, 600V | 52998 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | PG | 1 | 132.83 | 132.83 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 38 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 | COMP | 2024-02-28 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0237 | JUNCTION BOX, w/ KNOCKOUT, GALVANIZED STEEL, SQUARE, 4 INCHES | 52997 | 2024-01-30 | 2024-02-01 | CLOSE | 5 | EA | 4 | 5.27 | 21.08 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 5 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-08 07:00 | COMP | 2024-02-13 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0629 | COVER, JUNCTION BOX, STEEL, SQUARE, FLAT, 0.063 X 4 X 4 INCHES | 52997 | 2024-01-30 | 2024-02-01 | CLOSE | 4 | EA | 4 | 4.29 | 17.16 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 4 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5305-60-V00-0001 | SCREW, SELF DRILLING, HEX WASHER HEAD, STEEL, 5/16 X 1 INCH | 52965 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | BX | 2 | 19.14 | 38.28 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 12 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5305-60-V00-0206 | SCREW, SELF DRILLING, HEX HEAD, METAL WASHER, #14 X 1 INCH | 52964 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | PG | 1 | 4.72 | 4.72 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 97 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5305-05-V01-0080 | SCREW, SELF DRILLING, HEX, WASHER HEAD, 1/4 X 3 INCHES | 52995 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | PG | 2 | 3 | 6 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 11 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0394 | STRAP, TIE DOWN, ELECTRICAL COMPONENTS, NYLON, BLACK OR WHITE, 6 INCHES | 52998 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | PG | 2 | 5.28 | 10.56 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 37 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0395 | STRAP, TIE DOWN, WHITE, 12 INCHES | 52999 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | PG | 2 | 13.66 | 27.32 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 13 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-00-178-1217 | CONDUIT, METAL, RIGID, STEEL, 3/4 INCH X 10 FEET | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 4 | EA | 10 | 13.6 | 136 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 13 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5975-60-V00-0460 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, GALVANIZED STEEL, ¾ INCH | 52997 | 2024-01-30 | 2024-02-01 | CLOSE | 3 | EA | 40 | 2.11 | 84.4 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 3 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 40.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5920-60-V00-0059 | FUSE, CARTRIDGE, 250V,2A | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 3 | EA | 6 | 9.79 | 58.74 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 12 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5940-60-V00-0067 | TERMINAL JUNCTION BLOCK, SECTIONAL (FUSE TERMINAL), SCREW CLAMP, GRAY, 800V, 6.3A | 52997 | 2024-01-30 | 2024-02-01 | CLOSE | 2 | EA | 4 | 1.63 | 6.52 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 2 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5920-60-V00-0031 | FUSE, CARTRIDGE, 240 V, 3 A | 53002 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 4 | 0.73 | 2.92 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 15 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5970-01-013-9369 | TAPE, INSULATION, ELECTRICAL, RED, 3/4 X 792 INCHES | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 2 | RO | 1 | 10.1 | 10.1 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 11 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 53001 | 2024-01-30 | 2024-02-01 | CLOSE | 1 | EA | 1 | 16.83 | 16.83 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 10 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5940-60-V00-0015 | TERMINAL, LUG, FORK, INSULATED, RED, 22-16 AWG | 53002 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | PG | 1 | 99 | 99 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 14 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
55 | 2024-01-27 | 90 | BU23-0193 | ASSESSMENT FOR TT2071/ Tent build-out | 6871039 | 5940-60-V00-0014 | TERMINAL, LUG, FORK, I | 52997 | 2024-01-30 | 2024-02-01 | CLOSE | 1 | PG | 1 | 99.82 | 99.82 | 20761 | CLOSE | 2024-02-09 | 2024-02-06 | KW1-14775 | 1 | 2024-02-09 | APPR | 2024-02-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 07:00 | COMP | 2024-02-13 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5110-60-V00-0077 | KNIFE, PUTTY, 3 INCHES | 52744 | 2024-01-27 | 2024-01-29 | CLOSE | 4 | EA | 4 | 11.38 | 45.52 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 63 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5640-60-V00-0048 | DRYWALL SHEET, (GYPSUM BOARD), 4 X 8 FEET X 1/2 INCH | 52741 | 2024-01-27 | 2024-01-29 | CLOSE | 4 | EA | 30 | 18.85 | 565.5 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 59 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 30.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 52738 | 2024-01-27 | 2024-01-29 | CLOSE | 2 | EA | 72 | 44.69 | 3217.68 | 20743 | CLOSE | 2024-02-03 |  | KW1-14615 | 2 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-06 | 72.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5640-60-V00-0045 | TAPE, JOINT, WALLBOARD, SELF-ADHESIVE, 50 MM X 90 METERS | 52741 | 2024-01-27 | 2024-01-29 | CLOSE | 3 | EA | 4 | 11.7 | 46.8 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 58 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8010-60-V00-0141 | PAINT, LATEX, SEMI MATT, BEIGE, 1 GL (3.6 L) | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 10 | CN | 43 | 55.4 | 2382.2 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 18 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-14 | 43.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 52746 | 2024-01-27 | 2024-01-29 | CLOSE | 5 | CN | 4 | 37 | 148 | 20778 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14642 | 8 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-07 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | EA | 10 | 29 | 290 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 9 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8020-00-682-6489 | COVER, PAINT ROLLER, ACRYLIC, 0.375 X 7 INCHES | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 9 | EA | 10 | 14.2 | 142 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 17 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 8 | EA | 6 | 13.9 | 83.4 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 16 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 52745 | 2024-01-27 | 2024-01-29 | CLOSE | 2 | EA | 10 | 14.6 | 146 | 20708 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14585 | 4 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-03-01 | COMP | 2024-02-05 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8010-00-286-7737 | PAINT, ENAMEL, GLOSS, BROWN, 1 GL | 52748 | 2024-01-27 | 2024-01-29 | CLOSE | 3 | CN | 4 | 29.02 | 116.08 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 24 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-17 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GALLON | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 7 | GL | 2 | 228.6 | 457.2 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 15 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8010-60-V00-0146 | PRIMER COATING, WOOD, WHITE, 5 GL | 52744 | 2024-01-27 | 2024-01-29 | CLOSE | 3 | CN | 1 | 120.27 | 120.27 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 62 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-20 | COMP | 2024-02-17 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 6850-60-V00-0005 | ADDITIVE, MILDEWCIDE, LIQUID, 50-GRAM | 52740 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | EA | 43 | 32.18 | 1383.74 | 20708 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14585 | 2 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-03-01 | COMP | 2024-02-07 | 6.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 52742 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | BX | 1 | 16.5 | 16.5 | 20781 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14652 | 2 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-03-15 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8105-01-517-1363 | BAG, PLASTIC, CLEAR, 24 X 24 INCHES, 10 GALLONS | 52739 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | BX | 2 | 93.29 | 186.58 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 4 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8340-00-068-7908 | DROP CLOTH, PAINTER'S, 9 FT X 12 FT | 52738 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | EA | 5 | 28.28 | 141.4 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 1 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 5.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 7510-00-266-6710 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 52745 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | EA | 15 | 8 | 120 | 20708 | CLOSE | 2024-02-01 | 2024-02-01 | KW1-14585 | 3 | 2024-02-01 | APPR | 2024-02-01 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-03-01 | COMP | 2024-02-05 | 15.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5305-60-V00-0157 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, COARSE THREAD, #7 X 1-3/8 INCHES 1000pc/box | 52744 | 2024-01-27 | 2024-01-29 | CLOSE | 2 | BX | 5 | 22.75 | 113.75 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 61 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 5.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5350-60-V00-0010 | PAPER, ABRASIVE (SANDPAPER), 80 GRIT, 9 X 11 INCHES | 52746 | 2024-01-27 | 2024-01-29 | CLOSE | 4 | PK | 5 | 23 | 115 | 20778 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14642 | 7 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-07 | 5.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5350-60-V00-0011 | PAPER, ABRASIVE (SANDPAPER), 220 GRIT, 9 X 11 INCHES | 52746 | 2024-01-27 | 2024-01-29 | CLOSE | 3 | SH | 30 | 3.2 | 96 | 20778 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14642 | 6 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-07 | 30.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8010-60-V00-0241 | PRIMER COATING, PAINT, LATEX, INTERIOR, WATERBASED, WHITE, 16 LITERS | 52743 | 2024-01-27 | 2024-01-29 | CLOSE | 2 | PA | 1 | 55.1 | 55.1 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 21 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 6 | BX | 4 | 142 | 568 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 14 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8010-60-V00-0028 | PAINT, ENAMEL, GLOSS, DESERT SAND, 3.6 LITER | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 5 | GAL | 1 | 39.6 | 39.6 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 13 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8030-60-V00-0052 | PUTTY, ALL PURPOSE, LIGHT GRAY, 3.43 KG | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 4 | CAN | 2 | 124 | 248 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 12 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5130-60-V00-0125 | DISK, ABRASIVE, SANDING, HOOK AND LOOP, 220 GRIT, 8 HOLE, 5 INCHES-DUSTLESS HOOK AND LOOP SANDING DISC | 52744 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | PG | 2 | 44.86 | 89.72 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 60 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5120-60-V00-0283 | ROLLER, HAND (BRAYER), SOFT RUBBER, BROWN, 2 INCHES | 52748 | 2024-01-27 | 2024-01-29 | CLOSE | 2 | EA | 2 | 44.55 | 89.1 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 23 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 | COMP | 2024-03-06 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 9540-60-V00-0001 | STUD, STRUCTURAL, DRYWALL, FRAMING, GALVANIZED STEEL, 20 GUAGE, 4 X 1-1/4 INCHES | 52748 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | EA | 10 | 14.19 | 141.9 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 22 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 | COMP | 2024-02-17 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5305-05-V00-0025 | SCREW, PHILLIPS, TRUSS HEAD, STAINLESS STEEL, 10 X 3/4 INCHES 100pc / bx | 52743 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | BX | 4 | 13 | 52 | 20726 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14748 | 20 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-14 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5130-60-V00-0122 | CUTTING WHEEL, METAL, ALUMINUM OXIDE, 4X0.05X5/8 INCHES | 52741 | 2024-01-27 | 2024-01-29 | CLOSE | 2 | EA | 4 | 19.5 | 78 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 57 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-21 | COMP | 2024-02-14 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5110-60-V00-0028 | CHISEL SET, WOOD, STEEL, 9 PIECES | 52741 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | set | 1 | 196.65 | 196.65 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 56 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8030-01-075-1156 | CAULKING COMPOUND, CARTRIDGE, WHITE, 10 OZ | 52782 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | EA | 24 | 14.85 | 356.4 | 20703 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14661 | 5 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-03-11 | COMP | 2024-02-24 | 24.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5110-01-273-5951 | SAW, JAB, 6 INCHES | 52746 | 2024-01-27 | 2024-01-29 | CLOSE | 2 | ea | 2 | 35.1 | 70.2 | 20778 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14641 | 4 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MARATHON INC TRADING LLC | 2024-04-04 | COMP | 2024-02-07 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 3 | EA | 4 | 12.4 | 49.6 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 11 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 4.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 8020-01-317-2854 | COVER, PAINT ROLLER, POLYESTER FIBER, 3 INCHES | 52747 | 2024-01-27 | 2024-01-29 | CLOSE | 2 | EA | 8 | 14.2 | 113.6 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 10 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 8.00 |  | BU | BU table | January | 2024 | MM_BU
56 | 2024-01-27 | 30 | BU24-0072 | Repair Walls Z8 TT803 | 9243520 | 5120-60-V00-0295 | DISPENSER, SEALANT (CAULKING GUN), CAST STEEL, 12.8 OZ | 52746 | 2024-01-27 | 2024-01-29 | CLOSE | 1 | EA | 2 | 164 | 328 | 20778 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14642 | 5 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-20 | COMP | 2024-02-07 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 5975-60-V00-0083 | CONDUIT, NONMETALLIC, HEAVY GAUGE, UPVC, WHITE, 20 MM X 3M | 52781 | 2024-01-28 | 2024-01-29 | CLOSE | 4 | EA | 2 | 9.9 | 19.8 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 23 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-12 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 5975-60-V00-0276 | JUNCTION BOX, THREE WAY, RIGID PVC, WHITE, 20 MM | 52777 | 2024-01-28 | 2024-01-29 | CLOSE | 2 | EA | 2 | 9.9 | 19.8 | 20789 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14665 | 3 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-30 | COMP | 2024-02-11 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 52781 | 2024-01-28 | 2024-01-29 | CLOSE | 3 | EA | 2 | 146.47 | 292.94 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 22 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 2.00 |  | BU | BU table | December | 2023 | MM_BU
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 52779 | 2024-01-28 | 2024-01-29 | CLOSE | 1 | RO | 1 | 145.2 | 145.2 | 20779 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14645 | 3 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 5975-60-V00-0269 | COVER, JUNCTION BOX, CIRCULAR, PLASTIC, WHITE, 20 MM | 52776 | 2024-01-28 | 2024-01-29 | CLOSE | 1 | EA | 4 | 5.77 | 23.08 | 20724 | CLOSE | 2024-02-08 | 2024-02-05 | KW1-14739 | 68 | 2024-02-08 | APPR | 2024-02-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-15 | COMP | 2024-02-14 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 5975-60-V00-0573 | TEE, ELECTRICAL CONDUIT, INSPECTION, PVC, WHITE, 20 MM | 52777 | 2024-01-28 | 2024-01-29 | CLOSE | 1 | EA | 4 | 11.55 | 46.2 | 20789 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14666 | 6 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-10 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 4730-60-V00-0045 | .ADAPTER, ELECTRICAL CONDUIT, w/BUSH, FEMALE, PVC, WHITE, 20 MM | 52780 | 2024-01-28 | 2024-01-29 | CLOSE | 2 | EA | 4 | 6.2 | 24.8 | 20789 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14666 | 7 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-10 | 4.00 |  | BU | BU table | December | 2023 | MM_BU
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 5975-60-V00-0377 | CLAMP, ELECTRICAL, CONDUIT, PVC, WHITE, 20 MM | 52780 | 2024-01-28 | 2024-01-29 | CLOSE | 1 | EA | 10 | 3.63 | 36.3 | 20789 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14665 | 4 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-30 | COMP | 2024-02-11 | 10.00 |  | BU | BU table | December | 2023 | MM_BU
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 5975-60-V00-0372 | COUPLING, ELECTRICAL CONDUIT, PVC, WHITE, 20 MM | 52781 | 2024-01-28 | 2024-01-29 | CLOSE | 2 | EA | 6 | 4.54 | 27.24 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 21 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 6.00 |  | BU | BU table | December | 2023 | MM_BU
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 52781 | 2024-01-28 | 2024-01-29 | CLOSE | 1 | EA | 1 | 3.5 | 3.5 | 20775 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14638 | 20 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-07 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
57 | 2023-12-28 | 180 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 52783 | 2024-01-28 | 2024-01-29 | CLOSE | 1 | EA | 5 | 3.5 | 17.5 | 20779 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14645 | 4 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-15 | COMP | 2024-02-07 | 5.00 |  | BU | BU table | December | 2023 | MM_BU
57 | 2023-12-28 | 170 | BU-24-0098 | BUH-Z1-00-TRLR108-B | 8570569 | 5305-60-V00-0178 | SCREW, PHILLIPS, FLAT HEAD, STAINLESS STEEL, #8 X 3/4 INCHES | 52778 | 2024-01-28 | 2024-01-29 | CLOSE | 1 | BX | 1 | 12.68 | 12.68 | 20780 | CLOSE | 2024-02-04 | 2024-02-04 | KW1-14649 | 3 | 2024-02-04 | APPR | 2024-02-04 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-15 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | December | 2023 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 6210-60-V00-0099 | FIXTURE, LIGHTING, LED, FLOOD, 5000K, 50/60HZ, 90W | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 10 | EA | 2 | 656.37 | 1312.74 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 30 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 9 | EA | 2 | 260.02 | 520.04 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 29 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 52940 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 5 | 27.06 | 135.3 | 20793 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14670 | 16 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-19 | COMP | 2024-02-10 | 5.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 8 | PK | 2 | 28.9 | 57.8 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 28 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5975-60-V00-0461 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, GALVANIZED STEEL, ½ INCH | 52941 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 50 | 1.58 | 79 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 6 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 50.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5975-60-V00-0066 | CONDUIT, METAL, RIGID, GALVANIZED STEEL, 1/2 INCH X 10 FEET | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 7 | EA | 15 | 265 | 3975 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 27 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 15.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 6 | BX | 1 | 92.02 | 92.02 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 26 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5975-60-V00-0335 | STRAP, TIE DOWN, ELECTRICAL, COMPON (CABLE TIE), BLACK, 50 LBS, 4.6 MM X 11.02 INCHES | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 5 | PK | 1 | 15 | 15 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 25 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5970-60-V00-0043 | TAPE, INSULATION, ELECTRICAL, SUPER 33 +,VINYL, BLACK, 3/4" X 66' | 52940 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 1 | 14.19 | 14.19 | 20793 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14670 | 15 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-19 | COMP | 2024-02-10 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 52942 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 50 | 4.3 | 215 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 8 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 50.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5975-60-V00-0043 | COUPLING, ELECTRICAL, CONDUIT, COMBINATION, EMT TO FMC, DIE CAST ZINC, 1/2 INCH | 52944 | 2024-01-30 | 2024-01-31 | CLOSE | 4 | EA | 10 | 9.24 | 92.4 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 4 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-02-20 | COMP | 2024-02-11 | 10.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5975-60-V00-0487 | COUPLING, ELECTRICAL CONDUIT, w/ SCREW, Â½ INCH | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 4 | EA | 15 | 5 | 75 | 20771 | CLOSE | 2024-02-04 |  | KW1-14634 | 5 | 2024-02-04 | APPR | 2024-02-04 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-18 | COMP | 2024-02-10 | 15.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 6145-60-V00-0158 | WIRE, ELECTRICAL, RED, 1 CORE, 2.5 MM² | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 3 | RO | 1 | 57 | 57 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 20 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 6145-60-V00-0151 | WIRE, ELECTRICAL, BLACK 1 CORE, 2.5 MM² | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | RO | 1 | 64.92 | 64.92 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 19 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 52942 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | RO | 1 | 65.01 | 65.01 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 7 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5305-60-V00-0001 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 52941 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | BX | 1 | 19.14 | 19.14 | 20803 | CLOSE | 2024-02-05 | 2024-02-05 | KW1-14685 | 5 | 2024-02-05 | APPR | 2024-02-05 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 6110-60-V00-0166 | SENSOR, PHOTOCELL CONTROL, 15A, 50/60 HZ | 52943 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 1 | 74.8 | 74.8 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 18 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-20 | COMP | 2024-02-06 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5925-60-V00-0128 | CIRCUIT BREAKER, MCB, 1 POLE, 240/415V, 10A | 52944 | 2024-01-30 | 2024-01-31 | CLOSE | 3 | EA | 1 | 16 | 16 | 20742 | CLOSE | 2024-02-03 |  | KW1-14614 | 21 | 2024-02-03 | APPR | 2024-02-03 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-11 | 1.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5110-60-V00-0022 | CUTTER, TUBE, STEEL, 1/4 TO 7/8 X 4-1/2 INCHES | 52944 | 2024-01-30 | 2024-01-31 | CLOSE | 2 | EA | 2 | 22.63 | 45.26 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 3 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-03-11 | COMP | 2024-02-12 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
58 | 2024-01-29 | 30 | BU24-0141 | Installation of Flood Lights and Ceiling Lights | 9333709 | 5110-60-V00-0045 | CUTTER, WIRE, HAND, SHEAR CUT, STEEL, BLACK VINYL COVERED, 7 INCHES | 52944 | 2024-01-30 | 2024-01-31 | CLOSE | 1 | EA | 2 | 36.3 | 72.6 | 20787 | CLOSE | 2024-02-05 | 2024-02-03 | KW1-14660 | 2 | 2024-02-05 | APPR | 2024-02-05 | Santhumayor, Santhosh - Vectrus - No Export | FLORIDA FOUNDATION GLOBAL ELECTRICAL TOOLS & CONTRACTING EST | 2024-03-11 | COMP | 2024-02-19 | 2.00 |  | BU | BU table | January | 2024 | MM_BU
59 | 2024-02-07 | 30 | BU24-0147 | T-2028 New Cipher Lock | 9522604 | 5340-60-V00-0172 | LOCK SET, RIM, PUSHBUTTON, RHR, 5 INCHES | 53597 | 2024-02-07 | 2024-02-10 | CLOSE | 2 | EA | 1 | 656.4 | 656.4 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 47 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
59 | 2024-02-07 | 30 | BU24-0147 | T-2028 New Cipher Lock | 9522604 | 5340-60-V00-0169 | LOCK SET, MORTISE, RIM EXIT DEVICE, KEY OUTSIDE UNLOCKS/LOCKS TRIM | 53597 | 2024-02-07 | 2024-02-10 | CLOSE | 1 | EA | 1 | 2227.5 | 2227.5 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 46 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5307-60-V00-0021 | STUD, DRYWALL FRAME, U-CHANNEL, GALVANIZED STEEL, 3 X 1-1/4 INCHES X 12 FEET | 53647 | 2024-02-08 | 2024-02-10 | CLOSE | 6 | EA | 600 | 6.34 | 3804 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 26 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 600.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5650-60-V01-0003 | C-STUD RUNNER, STEEL, 0.0366IN X 1¼" X 3" X 12FT | 53647 | 2024-02-08 | 2024-02-10 | CLOSE | 5 | EA | 100 | 6.27 | 627 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 25 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 100.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5305-05-V00-0025 | SCREW, PHILLIPS, TRUSS HEAD, STAINLESS STEEL, 10 X 3/4 INCHES 100pc / bx | 53647 | 2024-02-08 | 2024-02-10 | CLOSE | 4 | PK | 35 | 21.15 | 740.25 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 24 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 35.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5305-60-V00-0022 | MATERIAL: STAINLESS STEELSIZE: #10SCREW LENGTH: 1-1/2 INCHESHEAD STYLE: TRUSS HEADDRIVE TYPE: PHILLIPSUNIT OF MEASURE: PACKAGE (CONTAINS 100 EACH) | 53650 | 2024-02-08 | 2024-02-10 | CLOSE | 9 | PG | 18 | 44.9 | 808.2 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 38 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 18.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5305-60-V00-0220 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, STEEL, #6 X 2 INCHES | 53645 | 2024-02-08 | 2024-02-10 | CLOSE | 7 | BX | 2 | 51.99 | 103.98 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 28 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-25 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5640-60-V00-0048 | DRYWALL SHEET, (GYPSUM BOARD), 4 X 8 FEET X 1/2 INCH | 53644 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 190 | 19.14 | 3636.6 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 29 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 190.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5305-60-V00-0157 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, COARSE THREAD, #7 X 1-3/8 INCHES 1000pc/box | 53645 | 2024-02-08 | 2024-02-10 | CLOSE | 6 | BX | 12 | 23.1 | 277.2 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 27 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-25 | 12.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5640-60-V00-0044 | TAPE, SELF ADHESIVE, DRYWALL JOINT, FIBERGLASS, 2 INCHES X 300 FEET | 53645 | 2024-02-08 | 2024-02-10 | CLOSE | 5 | EA | 6 | 18.48 | 110.88 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 43 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 53650 | 2024-02-08 | 2024-02-10 | CLOSE | 8 | CN | 8 | 37 | 296 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 37 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 8.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 7510-00-680-2395 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 53645 | 2024-02-08 | 2024-02-10 | CLOSE | 4 | ROLL | 6 | 12.69 | 76.14 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 26 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-25 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5130-60-V00-0125 | DISK, ABRASIVE, SANDING, HOOK AND LOOP, 220 GRIT, 8 HOLE, 5 INCHES-DUSTLESS HOOK AND LOOP SANDING DISC | 53648 | 2024-02-08 | 2024-02-10 | CLOSE | 5 | PG | 5 | 45.54 | 227.7 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 40 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 5.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5680-60-V01-0002 | CORNER BEAD, STAINLESS STEEL, 25 MM X2.5 METER | 53645 | 2024-02-08 | 2024-02-10 | CLOSE | 3 | EA | 70 | 108.9 | 7623 | 21348 | CLOSE | 2024-02-22 | 2024-02-16 | KW1-15106 | 3 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-10 | COMP | 2024-02-26 | 70.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5350-60-V00-0007 | PAPER, ABRASIVE (SANDPAPER), 120 GRIT, 9 X 11 INCHES | 53650 | 2024-02-08 | 2024-02-10 | CLOSE | 7 | EA | 40 | 4.2 | 168 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 36 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 40.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8010-60-V00-0241 | PRIMER COATING, PAINT, LATEX, INTERIOR, WATERBASED, WHITE, 16 LITERS | 53647 | 2024-02-08 | 2024-02-10 | CLOSE | 3 | CN | 1 | 55.08 | 55.08 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 23 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-07 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8010-60-V00-0050 | PAINT, ENAMEL, GLOSS, DARK BROWN, 3.2 AND 3.6 LITER( require vendor visit to match wall sample) | 53648 | 2024-02-08 | 2024-02-10 | CLOSE | 4 | CN | 8 | 39.6 | 316.8 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 25 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 |  |  |  | Need sample approval | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8010-60-V00-0146 | PRIMER COATING, WOOD, WHITE, 5 GL | 53648 | 2024-02-08 | 2024-02-10 | CLOSE | 3 | CN | 1 | 122.1 | 122.1 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 24 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-28 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8010-60-V00-0006 | PAINT, LATEX, MATT, OFF-WHITE, 3.2 LITER | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 10 | CN | 45 | 44 | 1980 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 28 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8010-60-V00-0095 | PRIMER, COATING, RED OXIDE, LIQUID, 3.78 TO 4 LITERS | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 9 | CN | 2 | 41.3 | 82.6 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 27 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8010-60-V00-0010 | PAINT, LATEX, GLOSS, WHITE, 3.6 LITERS | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 8 | GAL | 3 | 44.55 | 133.65 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 26 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 53649 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 12 | 14.6 | 175.2 | 21181 | CLOSE | 2024-02-17 |  | KW1-14961 | 4 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-03-23 | COMP | 2024-02-20 | 12.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 7 | EA | 4 | 12.4 | 49.6 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 25 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8020-60-V00-0045 | COVER, PAINT ROLLER, 3 INCHES | 53653 | 2024-02-08 | 2024-02-10 | CLOSE | 6 | EA | 10 | 8.2 | 82 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 12 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-31 | COMP | 2024-03-09 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 6 | EA | 15 | 13.9 | 208.5 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 24 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 5 | EA | 8 | 29 | 232 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 23 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 53646 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | BX | 3 | 16.5 | 49.5 | 21187 | CLOSE | 2024-02-17 |  | KW1-14969 | 5 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-03-23 | COMP | 2024-02-19 | 3.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5510-60-V00-0022 | BOARD, MDF, INTERIOR, BROWN, 12 X 1220 X 2440 MM | 53647 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | EA | 18 | 32.67 | 588.06 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 22 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 18.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GL | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 4 | GL | 5 | 220.5 | 1102.5 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 22 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5340-00-116-2375 | CLOSER, HYDRAULIC DOOR, LIGHT DUTY | 53650 | 2024-02-08 | 2024-02-10 | CLOSE | 6 | EA | 10 | 97.35 | 973.5 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 35 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5340-60-V00-0492 | STOPPER, DOOR, DROP DOWN, METAL, 5" | 53650 | 2024-02-08 | 2024-02-10 | CLOSE | 5 | EA | 10 | 18 | 180 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 34 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5340-60-V00-0141 | DOORSTOP, FLOOR MOUNT, BRASS, 1-3/4 X 1-1/4 INCHES | 53648 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | EA | 10 | 9.57 | 95.7 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 23 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-25 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5640-60-V00-0035 | WEATHER STRIP, DOOR, W/BRUSH, 2 X 36 INCHES | 53643 | 2024-02-08 | 2024-02-10 | CLOSE | 3 | EA | 10 | 30.19 | 301.9 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 29 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-25 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8030-01-075-1156 | CAULKING COMPOUND, CARTRIDGE, WHITE, 10 OZ | 53645 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | EA | 24 | 14.85 | 356.4 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 42 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 24.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5510-01-433-1244 | LUMBER, SOFTWOOD, 2 X 4 INCHES X 16 FEET | 53650 | 2024-02-08 | 2024-02-10 | CLOSE | 4 | EA | 35 | 30.4 | 1064 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 33 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 35.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8030-60-V00-0050 | PUTTY, WOOD FILLER, MEDIUM OAK, 250 ML | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 3 | CN | 4 | 85.19 | 340.76 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 21 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 | COMP | 2024-02-22 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5120-60-V00-0080 | BIT, SCREWDRIVER, PH2, STEEL, 50 MM | 53645 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | BX | 2 | 204.6 | 409.2 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 41 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5130-60-V00-0123 | WHEEL, ABRASIVE, ALUMINUM OXIDE, 12,225 RPM, 5 X 1/16 X 7/8 INCHES | 53650 | 2024-02-08 | 2024-02-10 | CLOSE | 3 | EA | 10 | 14.8 | 148 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 32 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-14 | COMP | 2024-02-19 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5335-60-V00-0001 | WIRE MESH, GALVANIZED STEEL, 21 GAGE, 4 X 50 FEET | 53652 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | RO | 7 | 41.9 | 293.3 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 28 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 7.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5660-60-V00-0033 | FENCE, GALVANIZED STEEL, CHAIN LINK MESH, 50 x 10 FEET (1 rool 50ft x 10ft) | 53643 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | RO | 3 | 422.4 | 1267.2 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 45 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-07 | COMP | 2024-02-19 | 3.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5340-01-306-9992 | LOCK SET, MORTISE, PUSH BUTTON, MECHANICAL, w/KNOB, SATIN CHROME, 2-3/4 INCHES, FACTORY LEFT; FIELD REVERSIBLE | 53650 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | EA | 5 | 607.7 | 3038.5 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 31 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-21 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5340-60-V00-0429 | LOCK SET, MECHANICAL, PUSH BUTTON, RIGHT HAND, 2-3/4 INCHES | 53648 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 5 | 602.6 | 3013 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 39 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 5.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8010-60-V00-0124 | PRIMER, RED OXIDE, OIL BASED, RED, 1 GL | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | CN | 2 | 41.4 | 82.8 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 20 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 90 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 4710-05-V00-0007 | TUBE, RECTANGULAR, STEEL, 3 X 1-1/2 X 1/8 INCHES x 20ft | 53677 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 28 | 70 | 1960 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 18 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-21 | COMP | 2024-03-02 | 28.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5306-60-V00-0100 | BOLT, CARRIAGE w/HEX NUT, STEEL, ZINC PLATED, 10M X 4-1/2 INCHES | 53653 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 300 | 3.14 | 942 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 7 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-25 | 300.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5315-00-060-9315 | STAPLE, STEEL, 1/2 INCH | 53653 | 2024-02-08 | 2024-02-10 | CLOSE | 5 | BX | 5 | 11.29 | 56.45 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 11 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-31 | COMP | 2024-03-09 | 5.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5120-00-889-1796 | TACKER, GUN, STAPLE, 1/2 INCH | 53653 | 2024-02-08 | 2024-02-10 | CLOSE | 4 | EA | 1 | 25.66 | 25.66 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 10 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-31 | COMP | 2024-03-09 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5133-60-V00-0003 | DRILL, TWIST, (BIT), HIGH SPEED STEEL, 8 X 117 MM | 53653 | 2024-02-08 | 2024-02-10 | CLOSE | 3 | EA | 10 | 18.15 | 181.5 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 9 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-21 | COMP | 2024-02-25 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 8030-60-V00-0052 | PUTTY, ALL PURPOSE, LIGHT GRAY, 3.43 KG | 53651 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 2 | 123.8 | 495.2 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 19 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5305-60-V00-0167 | SCREW, HEX WASHER HEAD, STEEL, #14 X 3 INCHES | 53652 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | BX | 3 | 37.9 | 113.7 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 27 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 3.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 9520-60-V00-0044 | ANGLE, STRUCTURAL, GALVANIZED STEEL, 1-1/2 X 1-1/2 X 1/8 INCH X 20 FEET | 53647 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 25 | 118.8 | 2970 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 21 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 25.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5130-60-V00-0127 | DISK, ABRASIVE, METAL CUTTING, ALUMINUM OXIDE, 1 X 0.10 X 12 INCHES | 53650 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | ea | 4 | 8 | 32 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 30 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 4240-60-V00-0043 | MASK, N95, PARTICULATE RESPIRATOR, 10EA/BOX, WHITE | 53653 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | BX | 2 | 81.76 | 163.52 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 8 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-21 | COMP | 2024-02-25 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 70 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5133-60-V00-0070 | BIT, SPADE, WOOD BORING, STEEL, 8 PIECES | 53643 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | set | 1 | 82.17 | 82.17 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 44 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-15 | COMP | 2024-03-06 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 80 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 9520-60-V00-0005 | ANGLE, STRUCTURAL, STEEL, 4MM X 2 X 2 INCHES X 10 FEET | 53655 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | EA | 10 | 45.54 | 455.4 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 22 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-03-02 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 80 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5305-60-V00-0001 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 53656 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | BX | 2 | 18.9 | 37.8 | 21091 | CLOSE | 2024-02-15 |  | KW1-14886 | 20 | 2024-02-15 | APPR | 2024-02-15 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 80 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5935-60-V00-0167 | CONNECTOR, WIRE, RED, 18 -10 AWG | 53657 | 2024-02-08 | 2024-02-10 | CLOSE | 3 | PG | 20 | 26.8 | 536 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 17 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 80 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5975-60-V00-0066 | CONDUIT, METAL, RIGID, EMT, GALVANIZED STEEL, 1/2 INCH X 10 FEET | 53657 | 2024-02-08 | 2024-02-10 | CLOSE | 2 | EA | 10 | 265 | 2650 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 16 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 80 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5975-60-V00-0491 | BOX CONNECTOR, ELECTRICAL, COMPRESSION, RAIN TIGHT, STEEL, EMT, 1/2 INCH | 53658 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 40 | 8.25 | 330 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 18 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 80 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 53657 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 2 | 260.02 | 520.04 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 15 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 80 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5345-60-V00-0017 | WHEEL, ABRASIVE (CUTTING DISK), METAL CUTTING, 180 X 22.23 X 3 MM | 53659 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 10 | 3.61 | 36.1 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 19 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-31 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 80 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 6625-60-V00-0093 | TESTER, SOCKET, W/ BEEPER, RCD, 250 V, 50 HZ | 53655 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 1 | 74.25 | 74.25 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 21 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-03-03 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 80 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5120-60-V00-0117 | SCREW DRIVER, INSULATED VINYL GRIP, SET, 10 PIECES | 53654 | 2024-02-08 | 2024-02-10 | CLOSE | 1 | EA | 2 | 51.56 | 103.12 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 20 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-31 | COMP | 2024-03-09 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
60 | 2024-02-07 | 50 | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | 5340-60-V00-0736 | LOCK, MORTISE, INTERCHANGEABLE CORE, 6-PIN, SATIN CHROME | 53777 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | EA | 1 | 178.16 | 890.8 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 5 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 5.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 9520-60-V00-0030 | STUD, FRAMING, GALVANIZED STEEL, 10 FEET | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 14 | EA | 44 | 10.2 | 448.8 |  |  |  |  | KW1-14917 | 14 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 44.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5650-60-V00-0004 | CHANNEL, STRUCTURAL, C-SHAPE, STEEL, 1-5/8 X 3-5/8 INCHES X 10 FEET | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 13 | EA | 40 | 9.7 | 388 |  |  |  |  | KW1-14917 | 13 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-15 | COMP | 2024-02-20 | 40.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5305-60-V00-0198 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATED, #6 X 2 INCHES | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 12 | EA | 400 | 0.3 | 120 |  |  |  |  | KW1-14917 | 12 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 400.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5530-60-V00-0010 | PLYWOOD, CONSTRUCTION, MARINE GRADE, 3/4 INCH X 8 X 4 FEET | 53878 | 2024-02-10 | 2024-02-12 | CLOSE | 5 | SH | 6 | 60.09 | 360.54 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 108 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5530-00-618-8073 | PLYWOOD, MAPLE, PUREBOND, 3/4 IN x 4 FT x 8 FT | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 11 | SH | 20 | 47 | 940 |  |  |  |  | KW1-14917 | 11 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 20.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5510-01-433-4221 | LUMBER, SOFTWOOD, 4 X 4 INCHES X 16 FEET | 53878 | 2024-02-10 | 2024-02-12 | CLOSE | 4 | EA | 10 | 50 | 500 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 107 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 10 | BX | 8 | 29.4 | 235.2 |  |  |  |  | KW1-14917 | 10 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 8.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 9 | BX | 8 | 19.6 | 156.8 |  |  |  |  | KW1-14917 | 9 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 8.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5305-60-V00-0169 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 3 INCHES | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 8 | BX | 4 | 30.4 | 121.6 |  |  |  |  | KW1-14917 | 8 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-15 | COMP | 2024-02-20 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8135-60-V00-0003 | PLASTIC SHEET, POLYETHYLENE, CLEAR, 6 MIL, 32 X 100 FEET | 53878 | 2024-02-10 | 2024-02-12 | CLOSE | 3 | RO | 1 | 475.17 | 475.17 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 106 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8010-60-V00-0084 | PAINT, FIRE RETARDANT, GRAY, 1 GALLON | 53873 | 2024-02-10 | 2024-02-12 | CLOSE | 3 | CN | 4 | 84.51 | 338.04 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15056 | 3 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-24 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 9540-60-V00-0009 | ANGLE, STRUCTURAL, ALUMINUM, CREAM, 2 X 2 INCH X 20 FEET | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 7 | EA | 2 | 51.2 | 102.4 |  |  |  |  | KW1-14917 | 7 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 53879 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | EA | 4 | 18.2 | 72.8 |  |  |  |  | KW1-14913 | 7 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 53876 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | BX | 1 | 16.5 | 16.5 |  |  |  |  | KW1-14908 | 1 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-03-15 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8020-00-260-1302 | BRUSH, PAINT, BRISTLES, CHISELED, 2 INCHES | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 6 | EA | 4 | 15.2 | 60.8 |  |  |  |  | KW1-14917 | 6 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 53879 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 4 | 30.6 | 122.4 |  |  |  |  | KW1-14913 | 6 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8030-60-V00-0055 | SEALANT, SILICONE, WHITE, 300ml | 53881 | 2024-02-10 | 2024-02-12 | CLOSE | 3 | BX | 1 | 141.9 | 141.9 |  |  |  |  | KW1-14913 | 11 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5320-60-V00-0014 | RIVET, BLIND, ALUMINUM, 2 INCHES | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 5 | BX | 6 | 20 | 120 |  |  |  |  | KW1-14917 | 5 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5320-60-V00-0005 | RIVET, BLIND, STAINLESS STEEL, SILVER, 6.4 MM | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 4 | PG | 6 | 60.5 | 363 |  |  |  |  | KW1-14917 | 4 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 3230-60-V00-0024 | BLADE, CIRCULAR SAW, WOOD CUTTING, 36 TOOTH, 7-1/4 INCHES | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 3 | EA | 1 | 52 | 52 |  |  |  |  | KW1-14917 | 3 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-10 | COMP | 2024-03-03 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8040-60-V00-0027 | TAPE, ADHESIVE, POLY FOAM, OPEN CELL, BLACK, 12.7 X 19 MM X 5 METERS | 53881 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | RO | 2 | 19.8 | 39.6 |  |  |  |  | KW1-14913 | 10 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5640-60-V00-0032 | WEATHER STRIP, DOOR, W/RUBBER BOTTOM SWEEP, 39" | 53882 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 2 | 17.4 | 34.8 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 109 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5640-60-V00-0035 | WEATHER STRIP, DOOR, W/BRUSH, 2 X 36 INCHES | 53874 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 2 | 29.72 | 59.44 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 101 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | BX | 6 | 29.4 | 176.4 |  |  |  |  | KW1-14917 | 2 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5340-60-V00-0505 | RAIN GUARD, DOOR, ALUMINUM, 236.22 X 4 INCHES | 53878 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | EA | 2 | 52.78 | 105.56 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 105 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8040-60-V00-0008 | ADHESIVE, GRIPFILL, MULTIPUROPSE, BUFF, C20, 310 ML | 53875 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | BX | 1 | 133.16 | 133.16 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 7 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 53878 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | BX | 6 | 51.15 | 306.9 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 104 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8010-60-V00-0146 | PRIMER COATING, WOOD, WHITE, 5 GL | 53877 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | CN | 1 | 120.17 | 120.17 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 103 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GALLON | 53882 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | GL | 2 | 220.5 | 441 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 110 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5670-05-V00-0001 | GRATING BAR, SERRATED, GALVANIZED STEEL, 240 X 24 X 1 INCHES | 53883 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 1 | 941.34 | 941.34 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 8 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-04-03 07:00 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 9905-01-282-2285 | TAPE, FLAGGING, CAUTION DO NOT ENTER, POLYETHYLENE, BLACK ON YELLOW, 3 INCHES X 200 FEET | 53877 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | RO | 1 | 88.67 | 88.67 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 102 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8105-01-336-6163 | BAG, SAND, TAN, 26 INCHES | 53880 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | HD | 1 | 742.5 | 742.5 |  |  |  |  | KW1-14917 | 1 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 7220-60-V00-0056 | CARPET, FLOOR, NYLON, GRAY, 20 X 20 INCHES | 53873 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | EA | 24 | 11.85 | 284.4 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 6 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 24.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 8040-00-273-8713 | ADHESIVE, FLOORING, WHITE, 1 GL | 53881 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | GL | 1 | 185.7 | 185.7 |  |  |  |  | KW1-14913 | 9 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 30 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5610-60-V00-0010 | GATCH AND GRAVEL, MIXED, CUBIC METER | 53873 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | CZ | 1 | 55.21 | 55.21 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 5 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-03 | COMP | 2024-03-02 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 53871 | 2024-02-10 | 2024-02-12 | CLOSE | 4 | EA | 2 | 260.02 | 520.04 |  |  |  |  | KW1-14913 | 4 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 |  | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5975-00-178-1217 | CONDUIT, METAL, RIGID, STEEL, 3/4 INCH X 10 FEET | [5 empty] | LG | [18 empty] | Not Required | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 53871 | 2024-02-10 | 2024-02-12 | CLOSE | 3 | RL | 1 | 92.02 | 92.02 |  |  |  |  | KW1-14913 | 3 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 |  | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5975-60-V00-0017 | COUPLING, ELECTRICAL CONDUIT, ZINC PLATED STEEL, 3/4 INCH | [5 empty] | PG | [18 empty] | Not Required | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 53870 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | EA | 10 | 4.3 | 43 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 100 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 |  | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5975-60-V00-0405 | ADAPTER, ELECTRICAL CONDUIT, ZINC, 3/4 INCH | [5 empty] | EA | [18 empty] | Not Required | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 |  | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5975-60-V00-0379 | CLAMP, ELECTRICAL, CONDUIT, 2 HOLE, GALVANIZED STEEL, 3/4 INCH | [5 empty] | EA | [18 empty] | Not Required | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5975-60-V00-0460 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, GALVANIZED STEEL, ¾ INCH | 53869 | 2024-02-10 | 2024-02-12 | CLOSE | 3 | PG | 10 | 2.11 | 21.1 | 21124 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14905 | 2 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 53871 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | RL | 1 | 163.2 | 163.2 |  |  |  |  | KW1-14913 | 2 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5305-60-V00-0001 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 53869 | 2024-02-10 | 2024-02-12 | CLOSE | 2 | PG | 1 | 18.84 | 18.84 | 21124 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14904 | 1 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-22 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5120-05-V00-0014 | CUTTER, CABLE/WIRE, HAND OPERATED, ALLOY STEEL, 140MM | 53870 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 2 | 64.3 | 128.6 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 99 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-31 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5110-60-V00-0080 | STRIPPER, WIRE, 10-20 AWG | 53872 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 2 | 20.41 | 40.82 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 4 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-04-03 07:00 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 53871 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 1 | 28.9 | 28.9 |  |  |  |  | KW1-14913 | 1 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
61 | 2024-02-07 | 40 | BU24-0051 | ARTC TT615 Vestibule | 9487373 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 53869 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 1 | 26.63 | 26.63 | 21124 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14905 | 1 | 2024-02-15 | APPR | 2024-02-15 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-22 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 9520-60-V00-0030 | STUD, FRAMING, GALVANIZED STEEL, 10 FEET | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 14 | EA | 44 | 10.2 | 448.8 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 29 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 44.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5650-60-V00-0004 | CHANNEL, STRUCTURAL, C-SHAPE, STEEL, 1-5/8 X 3-5/8 INCHES X 10 FEET | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 13 | EA | 40 | 9.7 | 388 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 28 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 40.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5305-60-V00-0198 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATED, #6 X 2 INCHES | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 12 | EA | 400 | 0.3 | 120 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 27 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 400.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5530-60-V00-0010 | PLYWOOD, CONSTRUCTION, MARINE GRADE, 3/4 INCH X 8 X 4 FEET | 53783 | 2024-02-10 | 2024-02-10 | CLOSE | 5 | SH | 6 | 61.61 | 369.66 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 13 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5530-00-618-8073 | PLYWOOD, MAPLE, PUREBOND, 3/4 IN x 4 FT x 8 FT | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 11 | SH | 20 | 47 | 940 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 26 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 20.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5510-01-433-4221 | LUMBER, SOFTWOOD, 4 X 4 INCHES X 16 FEET | 53783 | 2024-02-10 | 2024-02-10 | CLOSE | 4 | EA | 10 | 50 | 500 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 12 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 10 | BX | 8 | 29.4 | 235.2 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 25 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 8.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 9 | BX | 8 | 19.6 | 156.8 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 24 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 8.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5305-60-V00-0169 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 3 INCHES | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 8 | BX | 4 | 30.4 | 121.6 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 23 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8135-60-V00-0003 | PLASTIC SHEET, POLYETHYLENE, CLEAR, 6 MIL, 32 X 100 FEET | 53783 | 2024-02-10 | 2024-02-10 | CLOSE | 3 | RO | 1 | 487.18 | 487.18 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 11 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8010-60-V00-0084 | PAINT, FIRE RETARDANT, GRAY, 1 GALLON | 53778 | 2024-02-10 | 2024-02-10 | CLOSE | 3 | CN | 4 | 274.73 | 1098.92 | 21096 | CLOSE | 2024-02-15 |  | KW1-14889 | 7 | 2024-02-20 | APPR | 2024-02-20 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 9540-60-V00-0009 | ANGLE, STRUCTURAL, ALUMINUM, CREAM, 2 X 2 INCH X 20 FEET | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 7 | EA | 2 | 51.2 | 102.4 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 22 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 53784 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | EA | 4 | 18.2 | 72.8 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 15 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 53781 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | BX | 1 | 16.5 | 16.5 | 21187 | CLOSE | 2024-02-17 |  | KW1-14969 | 3 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-03-23 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8020-00-260-1302 | BRUSH, PAINT, BRISTLES, CHISELED, 2 INCHES | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 6 | EA | 4 | 15.2 | 60.8 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 21 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 53784 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | EA | 4 | 30.6 | 122.4 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 14 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8030-60-V00-0055 | SEALANT, SILICONE, WHITE, 300ml | 53786 | 2024-02-10 | 2024-02-10 | CLOSE | 3 | BX | 1 | 141.9 | 141.9 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 32 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5320-60-V00-0014 | RIVET, BLIND, ALUMINUM, 2 INCHES | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 5 | BX | 6 | 20 | 120 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 20 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5320-60-V00-0005 | RIVET, BLIND, STAINLESS STEEL, SILVER, 6.4 MM | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 4 | PG | 6 | 60.5 | 363 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 19 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 3230-60-V00-0024 | BLADE, CIRCULAR SAW, WOOD CUTTING, 36 TOOTH, 7-1/4 INCHES | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 3 | EA | 1 | 52 | 52 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 18 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-09 | COMP | 2024-03-07 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8040-60-V00-0027 | TAPE, ADHESIVE, POLY FOAM, OPEN CELL, BLACK, 12.7 X 19 MM X 5 METERS | 53786 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | RO | 2 | 19.8 | 39.6 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 31 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5640-60-V00-0032 | WEATHER STRIP, DOOR, W/RUBBER BOTTOM SWEEP, 39" | 53787 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | EA | 2 | 17.4 | 34.8 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 34 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5640-60-V00-0035 | WEATHER STRIP, DOOR, W/BRUSH, 2 X 36 INCHES | 53779 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | EA | 2 | 30.47 | 60.94 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 6 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | BX | 6 | 29.4 | 176.4 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 17 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5340-60-V00-0505 | RAIN GUARD, DOOR, ALUMINUM, 236.22 X 4 INCHES | 53783 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | EA | 2 | 54.11 | 108.22 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 10 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8040-60-V00-0008 | ADHESIVE, GRIPFILL, MULTIPUROPSE, BUFF, C20, 310 ML | 53780 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | BX | 1 | 227.27 | 227.27 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 1 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-26 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 53783 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | BX | 6 | 52.45 | 314.7 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 9 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8010-60-V00-0146 | PRIMER COATING, WOOD, WHITE, 5 GL | 53782 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | CN | 1 | 123.21 | 123.21 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 8 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GALLON | 53787 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | GL | 2 | 220.5 | 441 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 33 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5670-05-V00-0001 | GRATING BAR, SERRATED, GALVANIZED STEEL, 240 X 24 X 1 INCHES | 53788 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | EA | 1 | 941.34 | 941.34 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 2 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-04-03 07:00 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 9905-01-282-2285 | TAPE, FLAGGING, CAUTION DO NOT ENTER, POLYETHYLENE, BLACK ON YELLOW, 3 INCHES X 200 FEET | 53782 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | RO | 1 | 90.91 | 90.91 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 7 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8105-01-336-6163 | BAG, SAND, TAN, 26 INCHES | 53785 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | HD | 1 | 742.5 | 742.5 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 16 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 7220-60-V00-0056 | CARPET, FLOOR, NYLON, GRAY, 20 X 20 INCHES | 53778 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | EA | 24 | 12.15 | 291.6 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 3 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-25 | 24.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 8040-00-273-8713 | ADHESIVE, FLOORING, WHITE, 1 GL | 53786 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | GL | 1 | 185.7 | 185.7 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 30 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5610-60-V00-0010 | GATCH AND GRAVEL, MIXED, CUBIC METER | 53778 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | CZ | 1 | 56.61 | 56.61 | 21097 | INPRG | 2024-03-03 | 2024-02-16 | KW1-15099 | 2 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-03-02 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 30 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 53820 | 2024-02-10 | 2024-02-10 | CLOSE | 4 | EA | 2 | 260.02 | 520.04 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 44 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 |  | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5975-00-178-1217 | CONDUIT, METAL, RIGID, STEEL, 3/4 INCH X 10 FEET | [5 empty] | LG | [18 empty] | Not Required | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 40 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 53820 | 2024-02-10 | 2024-02-10 | CLOSE | 3 | RL | 1 | 92.02 | 92.02 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 43 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 |  | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5975-60-V00-0017 | COUPLING, ELECTRICAL CONDUIT, ZINC PLATED STEEL, 3/4 INCH | [5 empty] | PG | [18 empty] | Not Required | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 40 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 53819 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | EA | 10 | 4.3 | 43 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 40 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 |  | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5975-60-V00-0405 | ADAPTER, ELECTRICAL CONDUIT, ZINC, 3/4 INCH | [5 empty] | EA | [18 empty] | Not Required | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 |  | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5975-60-V00-0379 | CLAMP, ELECTRICAL, CONDUIT, 2 HOLE, GALVANIZED STEEL, 3/4 INCH | [5 empty] | EA | [18 empty] | Not Required | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 40 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5975-60-V00-0460 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, GALVANIZED STEEL, ¾ INCH | 53817 | 2024-02-10 | 2024-02-10 | CLOSE | 3 | PG | 10 | 2.13 | 21.3 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 37 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 40 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 53820 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | RL | 1 | 163.2 | 163.2 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 42 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 40 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5305-60-V00-0001 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 53817 | 2024-02-10 | 2024-02-10 | CLOSE | 2 | PG | 1 | 19.31 | 19.31 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 36 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 40 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5110-60-V00-0012 | FILE SET, HAND, CARBON-STEEL, 16 PIECES | 53818 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | EA | 2 | 54.1 | 108.2 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 38 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-31 | COMP | 2024-02-29 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 40 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5120-60-V00-0076 | SCREW DRIVER, PHILIPS, SET, 5 PIECES | 53819 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | EA | 2 | 76 | 152 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 39 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-31 | COMP | 2024-02-29 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 40 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 53820 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | EA | 1 | 28.9 | 28.9 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 41 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
62 | 2024-02-07 | 40 | BU24-0050 | ARTC TT614 Vestibule | 9487106 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 53817 | 2024-02-10 | 2024-02-10 | CLOSE | 1 | EA | 1 | 27.31 | 27.31 | 21058 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14924 | 35 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-24 07:00 | COMP | 2024-02-21 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
63 | 2024-02-10 | 90 | BU23-0083 | Correct TI Deficiencies for FMR Tower | 5083138 | 5340-60-V00-0904 | SADDLE, CONDUCTOR, HEAVY DUTY, EARTHING PROTECTION, BRASS, NATURAL, 50 MM² | 53865 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 37 | 9.57 | 354.09 | 21344 | CLOSE | 2024-02-22 | 2024-02-16 | KW1-15089 | 9 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-26 | 37.00 |  | BU | BU table | February | 2024 | MM_BU
64 | 2024-02-10 | 60 | BU23-0031 | Correct TI Deficiencies for UDR 5 ISBC Tower | 5069515 | 5340-60-V00-0904 | SADDLE, CONDUCTOR, HEAVY DUTY, EARTHING PROTECTION, BRASS, NATURAL, 50 MM² | 53867 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 37 | 9.57 | 354.09 | 21344 | CLOSE | 2024-02-22 | 2024-02-16 | KW1-15089 | 10 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-26 | 37.00 |  | BU | BU table | February | 2024 | MM_BU
65 | 2024-02-10 | 90 | BU23-0082 | Correct TI Deficiencies for HSR Tower | 5083153 | 5340-60-V00-0904 | SADDLE, CONDUCTOR, HEAVY DUTY, EARTHING PROTECTION, BRASS, NATURAL, 50 MM² | 53868 | 2024-02-10 | 2024-02-12 | CLOSE | 1 | EA | 37 | 0.58 | 21.46 | 21344 | CLOSE | 2024-02-22 | 2024-02-16 | KW1-15089 | 11 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-03-07 | COMP | 2024-02-26 | 37.00 |  | BU | BU table | February | 2024 | MM_BU
66 | 2024-02-12 | 30 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 | 6210-60-V00-0021 | FIXTURE, LIGHTING, LED, SAFETY AND EXIT SIGN, SINGLE SIDED, GREEN, 230V AC, 136 X 303 X 62 MM |  | 2024-02-12 |  |  |  | EACH | 0 | [17 empty] | From DPW | BU | BU table | February | 2024 | MM_BU
66 | 2024-02-12 | 30 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 | 5975-60-V00-0480 | JUNCTION BOX, w/ BLANK SIDE, 100 X 100 X 50 MM | 53938 | 2024-02-12 | 2024-02-14 | CLOSE | 3 | EACH | 3 | 12 | 36 | 21117 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14897 | 4 | 2024-02-15 | APPR | 2024-02-15 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 | COMP | 2024-02-19 | 3.00 |  | BU | BU table | February | 2024 | MM_BU
66 | 2024-02-12 | 30 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 53938 | 2024-02-12 | 2024-02-14 | CLOSE | 2 | ROLL | 1 | 92.02 | 92.02 | 21117 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14897 | 3 | 2024-02-15 | APPR | 2024-02-15 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
66 | 2024-02-12 | 30 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 53937 | 2024-02-12 | 2024-02-14 | CLOSE | 1 | EACH | 20 | 4.3 | 86 | 21110 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14895 | 4 | 2024-02-15 | APPR | 2024-02-15 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 20.00 |  | BU | BU table | February | 2024 | MM_BU
66 | 2024-02-12 | 30 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 | 5180-60-V00-0075 | NUT DRIVER SET, SAE, 3/16 – 9/16 INCH, 8 PIECES | 53934 | 2024-02-12 | 2024-02-14 | CLOSE | 1 | EACH | 2 | 139.86 | 279.72 | 21110 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14895 | 2 | 2024-02-15 | APPR | 2024-02-15 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-15 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
66 | 2024-02-12 | 30 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 | 5975-60-V00-0382 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, STEEL, 20MM | 53936 | 2024-02-12 | 2024-02-14 | CLOSE | 1 | EACH | 50 | 1.9 | 95 | 21117 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14897 | 1 | 2024-02-15 | APPR | 2024-02-15 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 | COMP | 2024-02-19 | 50.00 |  | BU | BU table | February | 2024 | MM_BU
66 | 2024-02-12 | 30 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 53935 | 2024-02-12 | 2024-02-14 | CLOSE | 1 | BX | 1 | 52.45 | 52.45 | 21110 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14895 | 3 | 2024-02-15 | APPR | 2024-02-15 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
66 | 2024-02-12 | 30 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 | 5120-60-V00-0237 | TAPE, FISH, STEEL & POLYPROPYLENE, 1/8 X .045 INCH X 50 FEET | 53939 | 2024-02-12 | 2024-02-14 | CLOSE | 1 | EACH | 1 | 51.15 | 51.15 | 21095 | CLOSE | 2024-02-18 | 2024-02-18 | KW1-15000 | 1 | 2024-02-18 | APPR | 2024-02-18 | Visakh, Ajith - No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-31 | COMP | 2024-02-22 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
66 | 2024-02-12 | 30 | BU24-0144 | ASSEMENT TO FIX THE EXIT LIGHT -T4002 | 9423630 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 53938 | 2024-02-12 | 2024-02-14 | CLOSE | 1 | ROLL | 1 | 145 | 145 | 21117 | CLOSE | 2024-02-15 | 2024-02-15 | KW1-14897 | 2 | 2024-02-15 | APPR | 2024-02-15 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 | COMP | 2024-02-19 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 4120-60-V00-0009 | AIR CONDITIONER, WINDOW, EXPLOSION PROOF, 208/230 V, 60 HZ, R-410A, BTU 24,000 | 54193 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 2 | 9373.95 | 18747.9 | 21122 | CLOSE | 2024-02-16 | 2024-02-15 | KW1-14944 | 1 | 2024-02-16 | APPR | 2024-02-16 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-22 |  |  |  | Catalog completed 14 Feb 24 | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5930-60-V00-0254 | SWITCH, DOUBLE POLE, METAL CLAD, 1 GANG, 32A | 54197 | 2024-02-14 | 2024-02-15 | CLOSE | 5 | EA | 2 | 70.38 | 140.76 |  |  |  |  | KW1-14950 | 24 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-60-V00-0528 | CONDUIT, RIGID, EMT, GALVANIZED STEEL, 1/2 INCH X 10 FEET | 54195 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 2 | 27 | 54 |  |  |  |  | KW1-14950 | 19 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-60-V00-0197 | ELBOW, ELECTRICAL CONDUIT, ½ INCH | 54197 | 2024-02-14 | 2024-02-15 | CLOSE | 4 | EA | 4 | 15.8 | 63.2 |  |  |  |  | KW1-14950 | 23 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-60-V00-0021 | BOX CONNECTOR, ELECTRICAL, RAINTIGHT, STEEL, 1/2 INCH | 54197 | 2024-02-14 | 2024-02-15 | CLOSE | 3 | EA | 10 | 5.2 | 52 |  |  |  |  | KW1-14950 | 22 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-21 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-60-V00-0382 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, STEEL, 20MM | 54197 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 10 | 2.3 | 23 |  |  |  |  | KW1-14950 | 20 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-60-V00-0237 | JUNCTION BOX, w/ KNOCKOUT, GALVANIZED STEEL, SQUARE, 4 INCHES | 54194 | 2024-02-14 | 2024-02-15 | CLOSE | 4 | EA | 2 | 24.14 | 48.28 |  |  |  |  | KW1-15098 | 3 | 2024-02-22 | APPR | 2024-02-22 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-25 07:00 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-60-V00-0629 | COVER, JUNCTION BOX, STEEL, SQUARE, FLAT, 0.063 X 4 X 4 INCHES | 54194 | 2024-02-14 | 2024-02-15 | CLOSE | 3 | EA | 2 | 6.66 | 13.32 |  |  |  |  | KW1-15100 | 20 | 2024-02-22 | APPR | 2024-02-22 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-26 07:00 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 54194 | 2024-02-14 | 2024-02-15 | CLOSE | 2 | EA | 1 | 16.98 | 16.98 |  |  |  |  | KW1-15098 | 2 | 2024-02-22 | APPR | 2024-02-22 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-25 07:00 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 54197 | 2024-02-14 | 2024-02-15 | CLOSE | 2 | EA | 1 | 21.11 | 21.11 |  |  |  |  | KW1-14950 | 21 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5970-01-013-9369 | TAPE, INSULATION, ELECTRICAL, RED, 3/4 X 792 INCHES | 54194 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 1 | 10.32 | 10.32 |  |  |  |  | KW1-15098 | 1 | 2024-02-22 | APPR | 2024-02-22 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-25 07:00 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 54196 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | BX | 1 | 29.4 | 29.4 |  |  |  |  | KW1-14954 | 11 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 07:00 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-05-V01-0071 | GLAND, CABLE PLASTIC, NYLON, WHITE, PG 13.5 | 54198 | 2024-02-14 | 2024-02-15 | CLOSE | 2 | EA | 2 | 0.69 | 1.38 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 14 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 30 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-60-V00-0809 | STUFFING TUBE (CABLE GLAND), POLYAMIDE, BLACK, M16 X 5-10 MM | 54198 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 2 | 3.3 | 6.6 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 13 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-04-03 07:00 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 50 | BU24-0058 | T6050 Add to TE | 9330911 | 5640-60-V00-0032 | WEATHER STRIP, DOOR, W/RUBBER BOTTOM SWEEP, 39" | 54208 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 2 | 17.4 | 34.8 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 21 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 50 | BU24-0058 | T6050 Add to TE | 9330911 | 5640-60-V00-0035 | WEATHER STRIP, DOOR, W/BRUSH, 2 X 36 INCHES | 54205 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 2 | 30.47 | 60.94 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 20 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 50 | BU24-0058 | T6050 Add to TE | 9330911 | 8040-60-V00-0027 | TAPE, ADHESIVE, POLY FOAM, OPEN CELL, BLACK, 12.7 X 19 MM X 5 METERS | 54207 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | RO | 3 | 19.8 | 59.4 |  |  |  |  | KW1-14950 | 31 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 3.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 50 | BU24-0058 | T6050 Add to TE | 9330911 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 54206 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | BX | 1 | 29.4 | 29.4 |  |  |  |  | KW1-14954 | 12 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 07:00 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 50 | BU24-0058 | T6050 Add to TE | 9330911 | 5640-60-V00-0028 | WEATHER STRIP, ADHESIVE, POLY FOAM, BLACK, 19 MM X 5 METERS | 54209 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 1 | 15 | 15 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 22 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 6210-60-V00-0094 | FIXTURE, LIGHTING, LED, RETROFIT, POLYCARBONATE, PURE WHITE, 40W | 54203 | 2024-02-14 | 2024-02-15 | CLOSE | 6 | EA | 16 | 242.35 | 3877.6 |  |  |  |  | KW1-14950 | 30 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 16.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 54203 | 2024-02-14 | 2024-02-15 | CLOSE | 5 | EA | 2 | 302.94 | 605.88 |  |  |  |  | KW1-14950 | 29 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 54203 | 2024-02-14 | 2024-02-15 | CLOSE | 4 | EA | 2 | 58.91 | 117.82 |  |  |  |  | KW1-14950 | 28 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM² | 54200 | 2024-02-14 | 2024-02-15 | CLOSE | 4 | RO | 1 | 244.76 | 244.76 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15056 | 6 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-25 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 9905-60-V00-0065 | SIGN, DANGER HIGH VOLTAGE, ADHESIVE, CUSTOMIZED (Length 9X8 Width Inches) | 54199 | 2024-02-14 | 2024-02-15 | CLOSE | 2 | EA | 2 | 9.99 | 19.98 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 16 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 9905-60-V00-0066 | SIGN, DANGER, 415 VOLTS , 5 X 3-3/4 INCHES | 54200 | 2024-02-14 | 2024-02-15 | CLOSE | 3 | PG | 1 | 17.48 | 17.48 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 18 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 5930-60-V00-0254 | SWITCH, DOUBLE POLE, METAL CLAD, 1 GANG, 32A | 54203 | 2024-02-14 | 2024-02-15 | CLOSE | 3 | EA | 2 | 70.38 | 140.76 |  |  |  |  | KW1-14950 | 27 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 6210-60-V00-0115 | LIGHT UNIT, EMERGENCY, EXIT, 60 HZ, 3 WATT | 54204 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 1 | 186.03 | 186.03 |  |  |  |  | KW1-15019 | 2 | 2024-02-20 | APPR | 2024-02-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 6850-60-V00-0025 | CLEANING COMPOUND,SOLVENT, CONTACT, COLORLESS, 11OZ | 54201 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 2 | 90.91 | 181.82 |  |  |  |  | KW1-15019 | 1 | 2024-02-20 | APPR | 2024-02-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 54203 | 2024-02-14 | 2024-02-15 | CLOSE | 2 | EA | 4 | 260.02 | 1040.08 |  |  |  |  | KW1-14950 | 26 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 5120-05-V00-0014 | CUTTER, CABLE/WIRE, HAND OPERATED, ALLOY STEEL, 140MM | 54202 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 2 | 64.3 | 128.6 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 19 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-04-04 07:00 | COMP | 2024-03-07 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 6625-60-V00-0093 | SCREW DRIVER / NUT DRIVER, HEAVY DUTY, MULTI-BIT | 54199 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 2 | 74.93 | 149.86 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 15 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 8020-00-245-4519 | BRUSH, PAINT, BRISTLES, FLAT, 4 INCHES | 54203 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 2 | 14.9 | 29.8 |  |  |  |  | KW1-14950 | 25 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-22 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 5305-60-V00-0001 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 54200 | 2024-02-14 | 2024-02-15 | CLOSE | 2 | BX | 1 | 19.31 | 19.31 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15057 | 4 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
67 | 2024-02-12 | 40 | BU24-0058 | T6050 Add to TE | 9330911 | 6350-60-V00-0102 | ALARM, SMOKE, AUTOMATIC, PLASTIC | 54200 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 4 | 28.97 | 115.88 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 17 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 54230 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EACH | 3 | 27.31 | 81.93 | 21184 | CLOSE | 2024-02-17 |  | KW1-14967 | 56 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-02 | COMP | 2024-02-20 | 3.00 |  | BU | BU table | February | 2024 | MM_BU
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 54233 | 2024-02-14 | 2024-02-15 | CLOSE | 4 | ROLL | 1 | 92.02 | 92.02 | 21184 | CLOSE | 2024-02-17 |  | KW1-14967 | 60 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-02 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
68 | 2024-02-14 | 40 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 54242 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EACH | 6 | 4.3 | 25.8 | 21182 | CLOSE | 2024-02-17 |  | KW1-14963 | 28 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-20 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
68 | 2024-02-14 | 40 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 5975-60-V00-0382 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, STEEL, 20MM | 54243 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EACH | 12 | 2.3 | 27.6 |  |  |  |  | KW1-15019 | 3 | 2024-02-20 | APPR | 2024-02-20 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-24 | 12.00 |  | BU | BU table | February | 2024 | MM_BU
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 54288 | 2024-02-14 | 2024-02-19 | CLOSE | 1 | EACH | 14 | 4.3 | 60.2 | 21337 | CLOSE | 2024-02-22 |  | KW1-15079 | 11 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 | COMP | 2024-02-24 | 14.00 |  | BU | BU table | February | 2024 | MM_BU
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 5975-60-V00-0382 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, STEEL, 20MM | 54289 | 2024-02-14 | 2024-02-19 | CLOSE | 1 | EACH | 38 | 2.3 | 87.4 | 21341 | CLOSE | 2024-02-22 |  | KW1-15084 | 21 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-02-24 | 38.00 |  | BU | BU table | February | 2024 | MM_BU
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 5210-01-626-3065 | DISTANCE MEASURER, LASER, STANLEY, 100’ RANGE, TLM99 | 54234 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EACH | 1 | 127.75 | 127.75 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 24 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-04-04 07:00 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 5305-60-V00-0207 | SCREW, HEX, STEEL, w/ RUBBER WASHER, #14 X 1-1/2 INCHES | 54231 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | BX | 1 | 52.45 | 52.45 | 21182 | CLOSE | 2024-02-17 |  | KW1-14963 | 27 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 6145-60-V00-0158 | WIRE, ELECTRICAL, RED, 1 CORE, 2.5 MM² | 54233 | 2024-02-14 | 2024-02-15 | CLOSE | 3 | ROLL | 1 | 57 | 57 | 21184 | CLOSE | 2024-02-17 |  | KW1-14967 | 59 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-02 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 6145-60-V00-0151 | WIRE, ELECTRICAL, BLACK 1 CORE, 2.5 MM² | 54233 | 2024-02-14 | 2024-02-15 | CLOSE | 2 | ROLL | 1 | 65 | 65 | 21184 | CLOSE | 2024-02-17 |  | KW1-14967 | 58 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-02 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 54232 | 2024-02-14 | 2024-02-15 | CLOSE | 2 | ROLL | 1 | 64.5 | 64.5 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15057 | 5 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 07:00 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 5120-60-V00-0110 | SCREW DRIVER, BLACK, SET, 7 PIECES | 54232 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EACH | 2 | 144.3 | 288.6 | 21114 | CLOSE | 2024-02-21 | 2024-02-18 | KW1-15059 | 23 | 2024-02-21 | APPR | 2024-02-21 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-04-04 07:00 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
68 | 2024-02-14 | 30 | BU24-0148 | Install Exit Signs Z4 T4001 | 9486667 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 54233 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | PG | 1 | 26.93 | 26.93 | 21184 | CLOSE | 2024-02-17 |  | KW1-14967 | 57 | 2024-02-17 | APPR | 2024-02-17 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-02 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W |  | 2024-02-14 |  |  |  | EA | 2 | [17 empty] | From DPW | BU | BU table | February | 2024 | MM_BU
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 6145-60-V00-0158 | WIRE, ELECTRICAL, RED, 1 CORE, 2.5 MM² | 54269 | 2024-02-14 | 2024-02-19 | CLOSE | 5 | RO | 1 | 57 | 57 | 21341 | CLOSE | 2024-02-22 |  | KW1-15084 | 20 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 6145-60-V00-0151 | WIRE, ELECTRICAL, BLACK 1 CORE, 2.5 MM² | 54269 | 2024-02-14 | 2024-02-19 | CLOSE | 4 | RO | 1 | 65 | 65 | 21341 | CLOSE | 2024-02-22 |  | KW1-15084 | 19 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 6145-60-V00-0007 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 2.5 MM² | 54268 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | RO | 1 | 64.5 | 64.5 |  |  |  |  | KW1-14954 | 14 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 07:00 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 54267 | 2024-02-14 | 2024-02-15 | CLOSE | 3 | EA | 2 | 26.62 | 53.24 |  |  |  |  | KW1-14950 | 34 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5975-60-V00-0487 | COUPLING, ELECTRICAL CONDUIT, w/ SCREW, Â½ INCH | 54269 | 2024-02-14 | 2024-02-19 | CLOSE | 3 | EA | 20 | 5 | 100 | 21341 | CLOSE | 2024-02-22 |  | KW1-15084 | 18 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-02-24 | 20.00 |  | BU | BU table | February | 2024 | MM_BU
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5975-60-V00-0483 | BOX CONNECTOR, ELECTRICAL, ZINC DIE CAST, 1/2 INCH | 54267 | 2024-02-14 | 2024-02-15 | CLOSE | 2 | EA | 10 | 3.9 | 39 |  |  |  |  | KW1-14950 | 33 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5345-60-V00-0017 | WHEEL, ABRASIVE (CUTTING DISK), METAL CUTTING, 180 X 22.23 X 3 MM | 54270 | 2024-02-14 | 2024-02-19 | CLOSE | 4 | EA | 10 | 3.61 | 36.1 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 23 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-04-11 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5975-60-V00-0467 | STRAP, TIE DOWN, ELECTRICAL COMPONENT, NYLON 6.6, BLACK, 12.2 X 0.374 INCHES | 54265 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | PG | 1 | 232.11 | 232.11 |  |  |  |  | KW1-14950 | 32 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 07:00 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5305-60-V00-0001 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 54267 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | PG | 1 | 18.83 | 18.83 |  |  |  |  | KW1-14954 | 13 | 2024-02-16 | APPR | 2024-02-16 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 07:00 | COMP | 2024-02-20 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5975-60-V00-0066 | CONDUIT, METAL, RIGID, GALVANIZED STEEL, 1/2 INCH X 10 FEET | 54269 | 2024-02-14 | 2024-02-19 | CLOSE | 2 | EA | 20 | 11.77 | 235.4 | 21341 | CLOSE | 2024-02-22 |  | KW1-15084 | 17 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-02-24 | 20.00 |  | BU | BU table | February | 2024 | MM_BU
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5925-60-V00-0105 | CIRCUIT BREAKER, MCB, 240 V, 10 A | 54270 | 2024-02-14 | 2024-02-19 | CLOSE | 3 | EA | 1 | 14 | 14 | 21782 | CLOSE | 2024-03-01 | 2024-02-24 | KW1-15326 | 1 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-06 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5120-60-V00-0158 | BIT, SCREWDRIVER, STEEL, #2 PHILLIPS, 1 INCH, 30 PIECES | 54270 | 2024-02-14 | 2024-02-19 | CLOSE | 2 | PG | 1 | 25.58 | 25.58 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 27 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-28 | COMP | 2024-03-05 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5120-60-V00-0159 | HOLDER, SCREWDRIVER BIT, HEX, STEEL, 1/4 X 3 INCHES | 54266 | 2024-02-14 | 2024-02-15 | CLOSE | 1 | EA | 10 | 27.27 | 272.7 | 21292 | CLOSE | 2024-02-23 | 2024-02-21 | KW1-15138 | 7 | 2024-02-23 | APPR | 2024-02-23 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL-IRTEKAZ NATIONAL GEN.TRDG.C | 2024-03-22 07:00 | COMP | 2024-02-29 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5935-60-V00-0168 | CONNECTOR, WIRE, ROUND, YELLOW | 54269 | 2024-02-14 | 2024-02-19 | CLOSE | 1 | PG | 1 | 26.93 | 26.93 | 21341 | CLOSE | 2024-02-22 |  | KW1-15084 | 16 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
69 | 2024-02-14 | 30 | BU24-0151 | Install Exit Signs Z5 Pad16 TT23 | 9522584 | 5120-60-V00-0238 | TAPE, FISH, STEEL & PLASTIC, 1/8 X 12 INCHES X 250 FEET | 54270 | 2024-02-14 | 2024-02-19 | CLOSE | 1 | EA | 1 | 151.29 | 151.29 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 26 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-04-11 | COMP | 2024-03-10 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4710-60-V00-0055 | PIPE, PLASTIC, DRAINAGE, ORANGE, SINGLE SOCKET, 110 MM X 6 METERS | 54414 | 2024-02-17 | 2024-02-19 | CLOSE | 6 | EA | 3 | 47.85 | 143.55 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 16 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-05 | 3.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0964 | COUPLING, SEWAGE, w/RUBBER GASKET, PVC, ORANGE, 4 INCHES | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 20 | EA | 7 | 13.1 | 91.7 |  |  |  |  | KW1-15107 | 19 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 7.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4510-60-V00-0096 | TRAP, BOTTLE, ADJUSTABLE INLET, w/FLEXIBLE HOSE, 1-1/2 INCHES | 54412 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 2 | 21.1 | 42.2 | 21312 | CLOSE | 2024-02-21 | 2024-02-21 | KW1-15049 | 2 | 2024-02-21 | APPR | 2024-02-21 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-05 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0458 | ELBOW, PIPE, SOCKET X SPIGOT, 45°, PVC, ORANGE, 110MM | 54404 | 2024-02-17 |  |  | 4 | EA | 2 | [18 empty] | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0970 | ELBOW, PRESSURE FITTINGS, PVC, STANDARD, 90 °, SPIGOT X SOCKET, ORANGE, 110 MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 19 | EA | 3 | 12.4 | 37.2 |  |  |  |  | KW1-15107 | 18 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 3.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0644 | REDUCER, PIPE, PVC, ORANGE, 50 X 110MM | 54407 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 2 | 9.16 | 18.32 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 25 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4820-60-V00-0227 | VALVE, ANGLE, 1/2 X 1/2 INCHES | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 18 | EA | 4 | 17.3 | 69.2 |  |  |  |  | KW1-15107 | 17 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4820-60-V00-0229 | VALVE, BALL, BRASS, PN25, RED, 3/4 INCH | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 17 | EA | 2 | 15.6 | 31.2 |  |  |  |  | KW1-15107 | 16 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0973 | TEE, PIPE, SEWER AND DRAIN FITTINGS, PVC, SCH-80, ORANGE, 110 MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 16 | EA | 1 | 49.3 | 49.3 |  |  |  |  | KW1-15107 | 15 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-26 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0847 | WYE, PIPE, SEWAGE, 45 °, UPVC, ORANGE, 110MM | 54410 | 2024-02-17 | 2024-02-19 | CLOSE | 3 | EA | 2 | 11.4 | 22.8 | 21336 | CLOSE | 2024-02-22 |  | KW1-15077 | 12 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-03-31 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0943 | UNION, PIPE, SOCKET X SOCKET, SCH 40, CPVC, OFF-WHITE, 25 MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 15 | EA | 2 | 10 | 20 |  |  |  |  | KW1-15107 | 14 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4510-60-V00-0211 | SINK, COMMERCIAL, TWO COMPARTMENT, W/LEGS AND DRAINBOARD, STAINLESS STEEL, 17 X 17 X 12 INCHES | 54414 | 2024-02-17 | 2024-02-19 | CLOSE | 5 | EA | 1 | 665.73 | 665.73 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 15 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-28 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0929 | TEE, PIPE, SOCKET X SOCKET X SOCKET, SCH-80, CPVC, OFF-WHITE, 25 MM | 54408 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 5 | 7.83 | 39.15 | 21336 | CLOSE | 2024-02-22 |  | KW1-15077 | 13 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-03-31 | COMP | 2024-02-24 | 5.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4410-60-V00-0003 | HEATER, WATER, ELECTRIC, 8 BAR, 220-240V, 2000W, 50 LITERS | 54404 | 2024-02-17 |  |  | 1 | EA | 1 | [18 empty] | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4510-60-V00-0028 | COWL, VENTILATION, UPVC, GRAY, 50MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 14 | EA | 1 | 16.2 | 16.2 |  |  |  |  | KW1-15107 | 13 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0819 | COUPLING, WASTE, SINK, PLASTIC, 1-1/2 INCHES | 54407 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | EA | 6 | 17.32 | 103.92 | 21337 | CLOSE | 2024-02-22 |  | KW1-15079 | 12 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 | COMP | 2024-02-24 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4710-60-V00-0164 | PIPE, PLASTIC, PVC, GRAY, 1-1/2 INCHES X 6 METERS | 54409 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 2 | 42.46 | 84.92 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 19 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4510-60-V00-0040 | FAUCET, SINGLE, SWIVEL TUBULAR, WALL MOUNTED, CHROME, 1/2 INCH | 54410 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 1 | 231.7 | 231.7 | 21336 | CLOSE | 2024-02-22 |  | KW1-15077 | 11 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-03-31 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0754 | ADAPTER, PRESSURE FITTINGS, MALE, CPVC, STANDARD, SOCKET X MIPT, PN16, OFF-WHITE, 25 MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 13 | EA | 4 | 3.2 | 12.8 |  |  |  |  | KW1-15107 | 12 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0850 | ELBOW, CPVC, SOCKET X SOCKET, SCH 40, OFF-WHITE, 25 MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 12 | EA | 14 | 3.6 | 50.4 |  |  |  |  | KW1-15107 | 11 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 14.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4720-60-V00-0266 | HOSE, METALLIC, FLEXIBLE, DOUBLE NUT, STAINLESS STEEL BRAIDED, 1/2 INCH X 1-1/2 FEET |  | 2024-02-17 |  |  |  | EA | 4 | [18 empty] | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 9150-60-V00-0050 | LUBRICANT, PIPE JOINT, 32 FL OUNCES | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 11 | EA | 1 | 43.6 | 43.6 |  |  |  |  | KW1-15107 | 10 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 8040-60-V00-0040 | CEMENT, HEAVY BODIED, CPVC, ORANGE, 16 OZ | 54412 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | CN | 1 | 18.2 | 18.2 | 21312 | CLOSE | 2024-02-21 | 2024-02-21 | KW1-15049 | 1 | 2024-02-21 | APPR | 2024-02-21 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-05 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 8040-01-307-0504 | ADHESIVE, CEMENT, PVC, MEDIUM BODIED, CLEAR, 16 OZ | 54414 | 2024-02-17 | 2024-02-19 | CLOSE | 4 | CN | 1 | 36.62 | 36.62 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 8 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-04-11 | COMP | 2024-03-05 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 50 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-05-V01-0706 | ELBOW, PIPE, 90 DEGREE, UPVC, SOCKET, 50MM |  | 2024-02-17 |  |  |  | EA | 4 | [18 empty] | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0871 | ELBOW, PVC, 45 DEGREE, SCH-40, GRAY, 1-1/2 INCH | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 10 | EA | 3 | 9.81 | 29.43 |  |  |  |  | KW1-15107 | 9 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 3.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0829 | COUPLING, UPVC, SCH-40, GRAY, 50 MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 9 | EA | 4 | 9.5 | 38 |  |  |  |  | KW1-15107 | 8 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 7105-60-V00-0019 | MIRROR, GLASS, ROUND, WALL MOUNTED, WHITE, 50 CM | 54405 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 1 | 19.65 | 19.65 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 22 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-05 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4710-60-V00-0108 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 8 | EA | 10 | 18.6 | 186 |  |  |  |  | KW1-15107 | 7 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0810 | CLAMP, PIPE, CPVC, BEIGE, 25 MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 7 | EA | 20 | 0.9 | 18 |  |  |  |  | KW1-15107 | 6 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 20.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4720-60-V00-0266 | HOSE, METALLIC, FLEXIBLE, DOUBLE NUT, STAINLESS STEEL BRAIDED, 1/2 INCH X 1-1/2 FEET |  | 2024-02-17 |  |  |  | EA | 4 | [18 empty] | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0863 | ELBOW, PRESSURE FITTINGS, CPVC, BRASS, REDUCTION, 90 °, SOCKET X FIPT, SCH- 40, OFF-WHITE, 25 x 20 MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 6 | EA | 4 | 14.8 | 59.2 |  |  |  |  | KW1-15107 | 5 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0763 | ADAPTER, PRESSURE FITTINGS, FEMALE, CPVC, REDUCTION, SOCKET X FIPT, SCH- 40, OFF-WHITE, 3/4 X 1/2 INCH | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 5 | EA | 4 | 24.2 | 96.8 |  |  |  |  | KW1-15107 | 4 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0834 | COUPLING, CPVC, SCH-40, TAN, 25 MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 4 | EA | 6 | 5 | 30 |  |  |  |  | KW1-15107 | 3 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 8030-09-V00-0010 | TAPE, ANTISEIZING, (TEFLON), PTFE, WHITE, 43 FEET X 1/2 INCHES | 54414 | 2024-02-17 | 2024-02-19 | CLOSE | 3 | EA | 5 | 1.34 | 6.7 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 14 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-28 | COMP | 2024-03-05 | 5.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5130-60-V00-0135 | BLADE, HOLE SAW, BI-METAL, 3/4 INCH | 54414 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 1 | 38.94 | 38.94 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 13 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-28 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5130-60-V00-0139 | BLADE, HOLE SAW, BI-METAL, 1 INCHES | 54406 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | EA | 1 | 26.31 | 26.31 | 21337 | CLOSE | 2024-02-22 |  | KW1-15079 | 9 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5306-60-V00-0073 | BOLT, MACHINE, HEX HEAD, COARSE THREAD, STEEL, 1/2 X 5 INCHES | 54404 | 2024-02-17 | 2024-02-19 | CLOSE | 3 | EA | 10 | 3.16 | 31.6 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 20 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-05 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-01-241-8789 | TRAP, DRAINAGE PIPE, SOCKET, PLASTIC, 1-1/2 INCHES | 54413 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | EA | 2 | 58.5 | 117 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15027 | 1 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-03 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4510-60-V00-0029 | DRAIN, FLOOR, COVER, UPVC, BEIGE, 160/110MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 3 | EA | 1 | 11.19 | 11.19 |  |  |  |  | KW1-15105 | 1 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-02-29 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0734 | WYE, TRUE, PIPE, BRANCH, UPVC, 45 DEG, 50 MM | 54404 | 2024-02-17 |  |  | 2 | EA | 1 | [18 empty] | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4510-60-V00-0027 | DRAIN, FLOOR, TRAP, MINI, 2 WAY, UPVC, GRAY, 4 X 2 INCHES | 54410 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | EA | 1 | 23.2 | 23.2 | 21336 | CLOSE | 2024-02-22 |  | KW1-15077 | 10 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-03-31 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4240-60-V00-0150 | TAPE, WARNING, UNDERGROUND, CAUTION BURIED WATER LINE BELOW, BLUE & BLACK, 6 INCHES X 1000 FEET | 54409 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | RO | 1 | 230.1 | 230.1 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 18 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 9905-60-V00-0064 | TAPE, BARRICADE, "CAUTION BURIED SEWER LINE BELOW", GREEN, 3 INCHES | 54414 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | RO | 1 | 254.1 | 254.1 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 12 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-04-11 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 9905-01-282-2285 | TAPE, FLAGGING (BARRICADE TAPE), CAUTION DO NOT ENTER, POLYETHYLENE, YELLOW, 3 INCH X 1000 FEET | 54408 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | RO | 1 | 90.91 | 90.91 | 21337 | CLOSE | 2024-02-22 |  | KW1-15079 | 10 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5620-60-V00-0013 | CONCRETE BLOCK, READYMADE, AAC, WHITE, 600 X 200 X 100 MM | 54405 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | EA | 30 | 12.82 | 384.6 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 21 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-05 | 30.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0917 | BUSHING, PIPE, REDUCER, SPIGOT X SOCKET, UPVC, GRAY, 2 X 1-1/2 INCHES | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 1 | 4.5 | 4.5 |  |  |  |  | KW1-15107 | 2 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 30 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-0106 | PLUG, PIPE, PVC, ORANGE, 110MM | 54411 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | EA | 1 | 13.1 | 13.1 |  |  |  |  | KW1-15107 | 1 | 2024-02-22 | APPR | 2024-02-22 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-29 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 6145-60-V00-0163 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORE, 4 MM² | 54421 | 2024-02-17 | 2024-02-19 | CLOSE | 4 | RO | 1 | 249 | 249 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 8 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 54421 | 2024-02-17 | 2024-02-19 | CLOSE | 3 | EA | 1 | 52 | 52 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 7 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5930-60-V00-0254 | SWITCH, DOUBLE POLE, METAL CLAD, 1 GANG, 32A | 54421 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 1 | 70.38 | 70.38 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 6 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5925-60-V00-0051 | CIRCUIT BREAKER, MINIATURE, 1 POLE, 230/400V, 20A | 54418 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | EA | 1 | 139.69 | 139.69 | 21341 | CLOSE | 2024-02-22 |  | KW1-15084 | 15 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-31 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5975-60-V00-0097 | CONDUIT, METAL, RIGID, STEEL, ZINC, 3/4 INCH X 3 MTR | 54416 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | EA | 6 | 22.2 | 133.2 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 10 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-05 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5975-60-V00-0009 | BOX CONNECTOR, ELECTRICAL, LIQUID-TIGHT CONDUIT, ZINC, 3/4 INCH | 54415 | 2024-02-17 | 2024-02-19 | CLOSE | 4 | EA | 4 | 153.18 | 612.72 | 21341 | CLOSE | 2024-02-22 |  | KW1-15084 | 14 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-02-24 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5975-60-V00-0090 | COUPLING, ELECTRICAL CONDUIT, COMPRESSION, ZINC DIE CAST, 3/4 INCH | 54415 | 2024-02-17 | 2024-02-19 | CLOSE | 3 | EA | 10 | 19.98 | 199.8 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 9 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-05 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5975-60-V00-0203 | ELBOW, ELECTRICAL CONDUIT, ZINC PLATED, 3/4 INCH | 54415 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | EA | 6 | 30.64 | 183.84 | 21341 | CLOSE | 2024-02-22 |  | KW1-15084 | 13 | 2024-02-22 | APPR | 2024-02-22 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-02-24 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 54421 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | RO | 2 | 21.11 | 42.22 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 5 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5970-01-013-9369 | TAPE, INSULATION, ELECTRICAL, RED, 3/4 X 792 INCHES | 54419 | 2024-02-17 | 2024-02-19 | CLOSE | 3 | RO | 2 | 10.1 | 20.2 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 3 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5970-60-V00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 54419 | 2024-02-17 | 2024-02-19 | CLOSE | 2 | RO | 3 | 16.83 | 50.49 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 2 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 3.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5975-60-V00-0079 | CLAMP, ELECTRICAL, CONDUIT, w/ BOLT, STEEL, 3/4 INCH | 54415 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | PG | 1 | 115.38 | 115.38 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 17 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-10 | COMP | 2024-03-05 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5975-60-V00-0379 | CLAMP, ELECTRICAL, CONDUIT, 2 HOLE, GALVANIZED STEEL, 3/4 INCH | 54419 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | EA | 10 | 2.5 | 25 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 1 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5305-60-V00-0002 | SCREW, SELF DRILLING, PHILIPS, MODIFIED TRUSS HEAD, #8 X 1-1/2 INCHES | 54417 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | BX | 1 | 29.97 | 29.97 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15027 | 2 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-05 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 5305-60-V00-0182 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, BLACK PHOSPHATE, #8 X 1-1/4 INCHES | 54420 | 2024-02-17 | 2024-02-19 | CLOSE | 1 | BX | 1 | 29.2 | 29.2 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15027 | 3 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-05 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
70 | 2024-02-15 | 40 | BU23-270 | Install Sink for Food Inspector T5019 | 9653102 | 4730-60-V00-1750 | TRAP, DRAINAGE PIPE (P-TRAP), POLYPROPYLENE, WHITE, 1-1/2 INCHES |  | 2024-02-29 |  |  |  | EA | 5 | [18 empty] | BU | BU table | February | 2024 | MM_BU
71 | 2024-02-12 |  | BU24-0076 | Replace floor in female shower trailer 16A |  |  |  | PRINPRG | [23 empty] | Project Cancelled | BU | BU table | February | 2024 | MM_BU
72 | 2024-02-18 | 30 | BU24-0167 | Install Security Bars Z2 Trailer2028 | 9653621 | 5306-60-V00-0100 | BOLT, CARRIAGE w/HEX NUT, STEEL, ZINC PLATED, 10M X 4-1/2 INCHES | 54781 | 2024-02-20 | 2024-02-24 | CLOSE | 1 | EA | 16 | 3.14 | 50.24 | 21739 | CLOSE | 2024-03-02 | 2024-03-02 | KW1-15364 | 7 | 2024-03-02 | APPR | 2024-03-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-03-16 | COMP | 2024-03-05 | 16.00 |  | BU | BU table | February | 2024 | MM_BU
72 | 2024-02-18 | 30 | BU24-0167 | Install Security Bars Z2 Trailer2028 | 9653621 | 5133-60-V00-0072 | DRILL, TWIST, (BIT), METAL, 10MM | 54780 | 2024-02-20 | 2024-02-24 | CLOSE | 1 | EA | 2 | 8.12 | 16.24 | 21739 | CLOSE | 2024-03-02 | 2024-03-02 | KW1-15364 | 6 | 2024-03-02 | APPR | 2024-03-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-03-16 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
73 | 1900-03-18 | 30 | BU24-0165 | Emplace Gravel Z8 PAT Site9 | 9722236 | 5610-60-V00-0009 | GRAVEL (CUSTOMIZED) | 54615 | 2024-02-18 |  | CAN | 1 | CZ | 120 | 96.57 | 11588.4 | [15 empty] | CANCELLED | BU | BU table | March | 1900 | MM_BU
73 | 2024-02-18 | 30 | BU24-0165 | Emplace Gravel Z8 PAT Site9 | 9722236 | 5610-60-V00-0010 | GATCH AND GRAVEL, MIXED, CUBIC METER | 54547 | 2024-02-18 |  | CAN | 1 | CZ | 91 | 56.5 | 5141.5 | [15 empty] | CANCELLED | BU | BU table | February | 2024 | MM_BU
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5935-60-V00-0101 | SOCKET, SWITCH, METAL CLAD, 2 GANG, GRAY, 13A, 142 X 79 X 42 MM | 54532 | 2024-02-18 | 2024-02-20 | CLOSE | 4 | EA | 2 | 10.1 | 20.2 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 13 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 4730-60-V00-0979 | ADAPTOR, W/LOCK NUT AND SCREW, MALE, BRASS, 3/4 INCH | 54531 | 2024-02-18 | 2024-02-19 | CLOSE | 3 | EA | 10 | 4.3 | 43 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15027 | 8 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-05 | COMP | 2024-02-24 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 6145-60-V00-0136 | WIRE, ELECTRICAL, RED, 1 CORE, 4MM² | 54530 | 2024-02-18 | 2024-02-19 | CLOSE | 6 | RO | 1 | 91.58 | 91.58 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15028 | 5 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-05 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 6145-60-V00-0154 | WIRE, ELECTRICAL, BLACK, 1 CORE, 4MM² | 54530 | 2024-02-18 | 2024-02-19 | CLOSE | 5 | RO | 1 | 91.58 | 91.58 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15028 | 4 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-05 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 6145-60-V00-0143 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4MM² | 54530 | 2024-02-18 | 2024-02-19 | CLOSE | 4 | RO | 1 | 91.58 | 91.58 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15028 | 3 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-05 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5345-60-V00-0017 | WHEEL, ABRASIVE (CUTTING DISK), METAL CUTTING, 180 X 22.23 X 3 MM | 54533 | 2024-02-18 | 2024-02-19 | CLOSE | 2 | EA | 10 | 3.61 | 36.1 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 7 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-03-28 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5935-60-V00-0167 | CONNECTOR, WIRE, RED, 18 -10 AWG | 54532 | 2024-02-18 | 2024-02-20 | CLOSE | 3 | PG | 1 | 23.3 | 23.3 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 12 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5975-60-V00-0460 | CLAMP, ELECTRICAL, CONDUIT, ONE HOLE, GALVANIZED STEEL, 3/4 INCHES | 54530 | 2024-02-18 | 2024-02-19 | CLOSE | 3 | PG | 10 | 2.16 | 21.6 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15028 | 2 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-05 | COMP | 2024-02-24 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5305-60-V00-0001 | SCREW, PHILLIPS, HEX HEAD, STEEL, #10-16 X 1 INCH | 54530 | 2024-02-18 | 2024-02-19 | CLOSE | 2 | PG | 1 | 19.31 | 19.31 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15027 | 5 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-05 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 54532 | 2024-02-18 | 2024-02-20 | CLOSE | 2 | BX | 1 | 92 | 92 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 11 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 54532 | 2024-02-18 | 2024-02-20 | CLOSE | 1 | EA | 2 | 27 | 54 | 21302 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15034 | 10 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5970-60-V00-0043 | TAPE, INSULATION, ELECTRICAL, SUPER 33 +,VINYL, BLACK, 3/4" X 66' | 54530 | 2024-02-18 | 2024-02-19 | CLOSE | 1 | EA | 1 | 14.32 | 14.32 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15028 | 1 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-05 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5120-60-V00-0105 | BIT, SCREWDRIVER, HEXAGONAL, PHILLIPS, #2 X 1/4 X 1 INCHES | 54533 | 2024-02-18 | 2024-02-19 | CLOSE | 1 | PG | 2 | 8 | 16 | 21334 | CLOSE | 2024-03-04 | 2024-02-24 | KW1-15278 | 6 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | CREDENCE TRADING EST. | 2024-04-11 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5130-01-473-9387 | HOLDER, SCREWDRIVER BIT, STEEL, 6 INCHES | 54529 | 2024-02-18 | 2024-02-19 | CLOSE | 1 | EA | 2 | 35.9 | 71.8 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15027 | 4 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-05 | COMP | 2024-02-24 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5120-60-V00-0111 | SCREW DRIVER / NUT DRIVER, HEAVY DUTY, MULTI-BIT | 54531 | 2024-02-18 | 2024-02-19 | CLOSE | 2 | EA | 1 | 24.7 | 24.7 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15027 | 7 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-05 | COMP | 2024-02-24 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
74 | 2024-02-18 | 30 | BU24-0171 | (BUH-Z6-CDP-BLDG601-00) Need New two outlets in warehouse. | 9671402 | 5120-60-V00-0193 | NUTDRIVER SET, HEX SOCKET, MAGNETIC, CHROME VANADIUM STEEL, 4 PIECES | 54531 | 2024-02-18 | 2024-02-19 | CLOSE | 1 | SE | 2 | 24.7 | 49.4 | 21300 | CLOSE | 2024-02-20 | 2024-02-20 | KW1-15027 | 6 | 2024-02-20 | APPR | 2024-02-20 | Visakh, Ajith - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-05 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 5530-00-618-8073 | PLYWOOD, CONSTRUCTION, 3/4 INCH X 4 X 8 FEET | 54793 | 2024-02-21 | 2024-02-24 | CLOSE | 7 | SH | 15 | 47 | 705 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 15 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-10 | COMP | 2024-02-27 | 15.00 |  | BU | BU table | February | 2024 | MM_BU
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 5530-60-V00-0010 | PLYWOOD, CONSTRUCTION, MARINE GRADE, 3/4 INCH X 8 X 4 FEET | 54793 | 2024-02-21 | 2024-02-24 | CLOSE | 6 | SH | 15 | 61.61 | 924.15 | 21455 | CLOSE | 2024-02-29 | 2024-02-27 | KW1-15285 | 2 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-10 | COMP | 2024-03-04 | 15.00 |  | BU | BU table | February | 2024 | MM_BU
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 5510-60-V00-0011 | LUMBER, HEAT TREATED, IPPC, 4 X 4 INCHES X 16 FEET | 54794 | 2024-02-21 |  |  | 1 | EA | 35 | [18 empty] | BU | BU table | February | 2024 | MM_BU
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 5510-60-V00-0013 | LUMBER, HEAT TREATED, IPPC, 2 X 4 INCHES, 16 FEET | 54791 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 10 | 27.64 | 276.4 | 21739 | CLOSE | 2024-03-02 | 2024-03-02 | KW1-15364 | 9 | 2024-03-02 | APPR | 2024-03-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-03-16 | COMP | 2024-03-05 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 5510-01-433-1371 | LUMBER, SOFTWOOD, 2 X 6 INCHES X 16 FEET | 54789 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 15 | 30.64 | 459.6 | 21739 | CLOSE | 2024-03-02 | 2024-03-02 | KW1-15364 | 8 | 2024-03-02 | APPR | 2024-03-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-03-16 | COMP | 2024-03-05 | 15.00 |  | BU | BU table | February | 2024 | MM_BU
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 54793 | 2024-02-21 | 2024-02-24 | CLOSE | 5 | BX | 20 | 19.81 | 396.2 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 14 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-10 | COMP | 2024-02-27 | 20.00 |  | BU | BU table | February | 2024 | MM_BU
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 5305-60-V00-0169 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 3 INCHES | 54793 | 2024-02-21 | 2024-02-24 | CLOSE | 4 | BX | 8 | 30.97 | 247.76 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 13 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-17 | COMP | 2024-02-27 | 8.00 |  | BU | BU table | February | 2024 | MM_BU
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 7210-60-V00-0059 | FLOOR COVERING, VINYL RESIN, 3 MM X 40 FEET | 54793 | 2024-02-21 | 2024-02-24 | CLOSE | 3 | RO | 1 | 722.61 | 722.61 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 12 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-10 | COMP | 2024-03-06 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 8040-00-273-8713 | ADHESIVE, FLOORING, WHITE, 1 GL | 54795 | 2024-02-21 | 2024-02-24 | CLOSE | 3 | GL | 3 | 185.7 | 557.1 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 16 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 3.00 |  | BU | BU table | February | 2024 | MM_BU
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 5640-60-V00-0038 | STRIP, ALUMINIUM, 3MM X 1-1/2 INCHES X 12FEET | 54793 | 2024-02-21 | 2024-02-24 | CLOSE | 2 | EA | 5 | 44.96 | 224.8 | 21455 | CLOSE | 2024-02-29 | 2024-02-27 | KW1-15285 | 1 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-10 | COMP | 2024-03-04 | 5.00 |  | BU | BU table | February | 2024 | MM_BU
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 54793 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 15 | 45.4 | 681 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 11 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-10 | COMP | 2024-02-27 | 15.00 |  | BU | BU table | February | 2024 | MM_BU
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 54795 | 2024-02-21 | 2024-02-24 | CLOSE | 2 | BX | 1 | 143.19 | 143.19 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 15 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-29 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 54795 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 5 | 13.9 | 69.5 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 14 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 5.00 |  | BU | BU table | February | 2024 | MM_BU
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 6515-60-V00-0015 | GLOVES, EXAM, DISPOSABLE, NITRILE, PURPLE, X-LARGE | 54790 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 1 | 49.95 | 49.95 | 21736 | CLOSE | 2024-02-29 |  | KW1-15290 | 4 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-15 | COMP | 2024-03-03 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
75 | 2024-02-21 | 30 | BU24-0168 | Repair Floor Z4 Pad9 Bldg2 RM111 | 9653682 | 3405-60-V00-0008 | BLADE, RECIPROCATING SAW, METAL, STRAIGHT, 14/18 TPI, 8 X 1 INCHES | 54792 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 3 | 33.3 | 99.9 | 21739 | CLOSE | 2024-03-02 | 2024-03-02 | KW1-15364 | 2 | 2024-03-02 | APPR | 2024-03-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-03-30 | COMP | 2024-03-05 | 3.00 |  | BU | BU table | February | 2024 | MM_BU
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 5530-00-618-8073 | PLYWOOD, CONSTRUCTION, 3/4 INCH X 4 X 8 FEET | 54815 | 2024-02-21 | 2024-02-24 | CLOSE | 7 | SH | 15 | 47.45 | 711.75 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 10 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-10 | COMP | 2024-02-27 | 15.00 |  | BU | BU table | February | 2024 | MM_BU
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 5530-60-V00-0010 | PLYWOOD, CONSTRUCTION, MARINE GRADE, 3/4 INCH X 8 X 4 FEET | 54815 | 2024-02-21 | 2024-02-24 | CLOSE | 6 | SH | 15 | 61.61 | 924.15 | 21455 | CLOSE | 2024-02-29 | 2024-02-27 | KW1-15285 | 4 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-10 | COMP | 2024-03-04 | 15.00 |  | BU | BU table | February | 2024 | MM_BU
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 5510-60-V00-0011 | LUMBER, HEAT TREATED, IPPC, 4 X 4 INCHES X 16 FEET | 54816 | 2024-02-21 |  |  | 1 | EA | 35 | [18 empty] | BU | BU table | February | 2024 | MM_BU
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 5510-60-V00-0013 | LUMBER, HEAT TREATED, IPPC, 2 X 4 INCHES, 16 FEET | 54813 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 10 | 27.64 | 276.4 | 21739 | CLOSE | 2024-03-02 | 2024-03-02 | KW1-15364 | 11 | 2024-03-02 | APPR | 2024-03-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-03-16 | COMP | 2024-03-05 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 5510-01-433-1371 | LUMBER, SOFTWOOD, 2 X 6 INCHES X 16 FEET | 54811 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 15 | 30.64 | 459.6 | 21739 | CLOSE | 2024-03-02 | 2024-03-02 | KW1-15364 | 10 | 2024-03-02 | APPR | 2024-03-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-03-16 | COMP | 2024-03-05 | 15.00 |  | BU | BU table | February | 2024 | MM_BU
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 54815 | 2024-02-21 | 2024-02-24 | CLOSE | 5 | BX | 20 | 19.81 | 396.2 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 9 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-10 | COMP | 2024-02-27 | 20.00 |  | BU | BU table | February | 2024 | MM_BU
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 5305-60-V00-0169 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 3 INCHES-( | 54815 | 2024-02-21 | 2024-02-24 | CLOSE | 4 | BX | 8 | 30.97 | 247.76 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 8 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-17 | COMP | 2024-02-27 | 8.00 |  | BU | BU table | February | 2024 | MM_BU
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 7210-60-V00-0059 | FLOOR COVERING, VINYL RESIN, 3 MM X 40 FEET | 54815 | 2024-02-21 | 2024-02-24 | CLOSE | 3 | RO | 1 | 722.61 | 722.61 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 7 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-10 | COMP | 2024-03-06 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 8040-00-273-8713 | ADHESIVE, FLOORING, WHITE,( | 54817 | 2024-02-21 | 2024-02-24 | CLOSE | 3 | GL | 3 | 185.7 | 557.1 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 13 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 3.00 |  | BU | BU table | February | 2024 | MM_BU
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 5640-60-V00-0038 | STRIP, ALUMINIUM, 3MM X 1-1/2 INCHES X 12FEET | 54815 | 2024-02-21 | 2024-02-24 | CLOSE | 2 | EA | 5 | 44.96 | 224.8 | 21455 | CLOSE | 2024-02-29 | 2024-02-27 | KW1-15285 | 3 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-10 | COMP | 2024-03-04 | 5.00 |  | BU | BU table | February | 2024 | MM_BU
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 54815 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 15 | 45.4 | 681 | 21453 | CLOSE | 2024-02-25 |  | KW1-15168 | 6 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-10 | COMP | 2024-02-27 | 15.00 |  | BU | BU table | February | 2024 | MM_BU
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 54817 | 2024-02-21 | 2024-02-24 | CLOSE | 2 | BX | 1 | 142 | 142 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 12 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-29 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 54817 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 5 | 13.9 | 69.5 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 11 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 5.00 |  | BU | BU table | February | 2024 | MM_BU
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 6515-60-V00-0015 | GLOVES, EXAM, DISPOSABLE, NITRILE, PURPLE, X-LARGE | 54812 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 1 | 49.95 | 49.95 | 21736 | CLOSE | 2024-02-29 |  | KW1-15290 | 5 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-15 | COMP | 2024-03-03 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
76 | 2024-02-21 | 30 | BU24-0169 | Repair Floor Z4 Pad9 Bldg3 RM103 | 9653523 | 3405-60-V00-0008 | BLADE, RECIPROCATING SAW, METAL, STRAIGHT, 14/18 TPI, 8 X 1 INCHES | 54814 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 3 | 33.3 | 99.9 | 21739 | CLOSE | 2024-03-02 | 2024-03-02 | KW1-15364 | 12 | 2024-03-02 | APPR | 2024-03-02 | Santhumayor, Santhosh - Vectrus - No Export | COMMERCIAL UNITED GINCO EST. | 2024-03-30 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
77 | 2024-02-21 | 30 | BU24-0175 | Paint Floor Lines Z3 VLAM005 | 9790969 | 8010-60-V00-0067 | PAINT, TRAFFIC, GLOSS, YELLOW, 16 LITERS | 54832 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | CN | 6 | 188.84 | 1133.04 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 10 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
77 | 2024-02-21 | 30 | BU24-0175 | Paint Floor Lines Z3 VLAM005 | 9790969 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 54834 | 2024-02-21 | 2024-02-24 | CLOSE | 3 | EA | 10 | 29 | 290 | 21463 | CLOSE | 2024-02-25 |  | KW1-15178 | 4 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
77 | 2024-02-21 | 30 | BU24-0175 | Paint Floor Lines Z3 VLAM005 | 9790969 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 54834 | 2024-02-21 | 2024-02-24 | CLOSE | 2 | EA | 5 | 13.9 | 69.5 | 21463 | CLOSE | 2024-02-25 |  | KW1-15178 | 3 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 5.00 |  | BU | BU table | February | 2024 | MM_BU
77 | 2024-02-21 | 30 | BU24-0175 | Paint Floor Lines Z3 VLAM005 | 9790969 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 54834 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 10 | 2.4 | 24 | 21463 | CLOSE | 2024-02-25 |  | KW1-15178 | 2 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
77 | 2024-02-21 | 30 | BU24-0175 | Paint Floor Lines Z3 VLAM005 | 9790969 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 54833 | 2024-02-21 | 2024-02-24 | CLOSE | 2 | EA | 10 | 14.6 | 146 |  |  |  |  | KW1-15232 | 2 | 2024-02-27 | APPR | 2024-02-27 | Reghuraman, Karthik -Vectrus -GSD -No Export | MARATHON INC TRADING LLC | 2024-03-31 07:00 | COMP | 2024-02-29 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
77 | 2024-02-21 | 30 | BU24-0175 | Paint Floor Lines Z3 VLAM005 | 9790969 | 7510-00-266-6710 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 54833 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 20 | 8 | 160 |  |  |  |  | KW1-15232 | 1 | 2024-02-27 | APPR | 2024-02-27 | Reghuraman, Karthik -Vectrus -GSD -No Export | MARATHON INC TRADING LLC | 2024-03-12 07:00 | COMP | 2024-02-29 | 20.00 |  | BU | BU table | February | 2024 | MM_BU
77 | 2024-02-21 | 30 | BU24-0175 | Paint Floor Lines Z3 VLAM005 | 9790969 | 6515-60-V00-0015 | GLOVES, EXAM, DISPOSABLE, NITRILE, PURPLE, X-LARGE | 54831 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | BX | 1 | 49.95 | 49.95 | 21736 | CLOSE | 2024-02-29 |  | KW1-15290 | 6 | 2024-02-29 | APPR | 2024-02-29 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-15 | COMP | 2024-03-03 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
78 | 2024-02-21 | 30 | BU24-0143 | Install Overhead Lights B9501AB | 9360741 | 5925-60-V00-0267 | CIRCUIT BREAKER, MINIATURE, 1 POLE, 230-400V, 10A | 54838 | 2024-02-21 | 2024-02-24 | CLOSE | 3 | EA | 2 | 11.63 | 23.26 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 9 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
78 | 2024-02-21 | 30 | BU24-0143 | Install Overhead Lights B9501AB | 9360741 | 6210-60-V00-0094 | FIXTURE, LIGHTING, LED, RETROFIT, POLYCARBONATE, PURE WHITE, 40W | 54838 | 2024-02-21 | 2024-02-24 | CLOSE | 2 | EA | 9 | 242.35 | 2181.15 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 8 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 9.00 |  | BU | BU table | February | 2024 | MM_BU
78 | 2024-02-21 | 30 | BU24-0143 | Install Overhead Lights B9501AB | 9360741 | 6145-60-V00-0145 | CABLE, POWER, ELECTRICAL, WHITE, 3 CORES, 1.5MM ² | 54838 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | ROLL | 1 | 145.35 | 145.35 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 7 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
79 | 2024-02-21 | 30 | BU24-0172 | (TT404) NEED TO FIX DAMAGE FLOOR | 9790884 | 8010-00-597-7856 | VARNISH, OIL, GLOSS, CLEAR, 1 GL | 54841 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | CN | 6 | 247.6 | 1485.6 | 21451 | CLOSE | 2024-03-08 |  | KW1-15166 | 6 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
79 | 2024-02-21 | 30 | BU24-0172 | (TT404) NEED TO FIX DAMAGE FLOOR | 9790884 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 54842 | 2024-02-21 | 2024-02-24 | CLOSE | 3 | EA | 6 | 29 | 174 | 21463 | CLOSE | 2024-02-25 |  | KW1-15178 | 7 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
79 | 2024-02-21 | 30 | BU24-0172 | (TT404) NEED TO FIX DAMAGE FLOOR | 9790884 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 54842 | 2024-02-21 | 2024-02-24 | CLOSE | 2 | EA | 10 | 13.99 | 139.9 | 21463 | CLOSE | 2024-02-25 |  | KW1-15178 | 6 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
79 | 2024-02-21 | 30 | BU24-0172 | (TT404) NEED TO FIX DAMAGE FLOOR | 9790884 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 54842 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 10 | 2.4 | 24 | 21463 | CLOSE | 2024-02-25 |  | KW1-15178 | 5 | 2024-02-25 | APPR | 2024-02-25 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-10 | COMP | 2024-02-27 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
79 | 2024-02-21 | 30 | BU24-0172 | (TT404) NEED TO FIX DAMAGE FLOOR | 9790884 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 54840 | 2024-02-21 | 2024-02-24 | CLOSE | 2 | EA | 10 | 14.6 | 146 |  |  |  |  | KW1-15232 | 4 | 2024-02-27 | APPR | 2024-02-27 | Reghuraman, Karthik -Vectrus -GSD -No Export | MARATHON INC TRADING LLC | 2024-03-31 07:00 | COMP | 2024-02-29 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
79 | 2024-02-21 | 30 | BU24-0172 | (TT404) NEED TO FIX DAMAGE FLOOR | 9790884 | 7510-00-266-6710 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 54840 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | EA | 20 | 8 | 160 |  |  |  |  | KW1-15232 | 3 | 2024-02-27 | APPR | 2024-02-27 | Reghuraman, Karthik -Vectrus -GSD -No Export | MARATHON INC TRADING LLC | 2024-03-12 07:00 | COMP | 2024-02-29 | 20.00 |  | BU | BU table | February | 2024 | MM_BU
79 | 2024-02-21 | 30 | BU24-0172 | (TT404) NEED TO FIX DAMAGE FLOOR | 9790884 | 6515-60-V00-0015 | GLOVES, EXAM, DISPOSABLE, NITRILE, PURPLE, X-LARGE | 54839 | 2024-02-21 | 2024-02-24 | CLOSE | 1 | BX | 1 | 49.95 | 49.95 | 21579 | CLOSE | 2024-03-01 |  | KW1-15331 | 1 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | EMCOR INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-09 07:00 | COMP | 2024-03-05 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5340-60-V00-0505 | RAIN GUARD, DOOR, ALUMINUM, 236.22 X 4 INCHES | 55566 | 2024-02-28 | 2024-02-29 | CLOSE | 3 | EA | 2 | 53.63 | 107.26 | 21797 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15336 | 2 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MARATHON INC TRADING LLC | 2024-04-12 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 55565 | 2024-02-28 | 2024-02-29 | CLOSE | 2 | BX | 1 | 29.37 | 29.37 |  |  |  |  | KW1-15346 | 5 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5610-60-V00-0001 | CEMENT, MASONRY, (MORTAR MIX), TYPE- N, 60 LB | 55565 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | BG | 1 | 26.4 | 26.4 |  |  |  |  | KW1-15346 | 4 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5340-60-V00-0481 | HINGE, DOOR, STAINLESS STEEL, 3 MM X 3-1/2 X 4 INCHES | 55568 | 2024-02-28 | 2024-02-29 | CLOSE | 4 | EA | 1 | 29.9 | 29.9 |  |  |  |  | KW1-15346 | 9 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5620-60-V00-0043 | CONCRETE SPLASH BLOCK | 55568 | 2024-02-28 | 2024-02-29 | CLOSE | 3 | EA | 4 | 79.2 | 316.8 |  |  |  |  | KW1-15346 | 8 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 55569 | 2024-02-28 | 2024-02-29 | CLOSE | 4 | BX | 1 | 142 | 142 |  |  |  |  | KW1-15340 | 12 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-22 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 8010-60-V00-0095 | PRIMER, COATING, RED OXIDE, LIQUID, 3.78 TO 4 LITERS | 55569 | 2024-02-28 | 2024-02-29 | CLOSE | 3 | CN | 1 | 41.3 | 41.3 |  |  |  |  | KW1-15340 | 10 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 8010-60-V00-0028 | PAINT, ENAMEL, GLOSS, DESERT SAND, 3.6 LITER | 55569 | 2024-02-28 | 2024-02-29 | CLOSE | 5 | CN | 1 | 39.6 | 39.6 |  |  |  |  | KW1-15340 | 9 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 55567 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | EA | 2 | 14.6 | 29.2 | 21797 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15336 | 3 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MARATHON INC TRADING LLC | 2024-04-20 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 55569 | 2024-02-28 | 2024-02-29 | CLOSE | 2 | EA | 2 | 29 | 58 |  |  |  |  | KW1-15340 | 11 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 7210-60-V00-0059 | FLOOR COVERING, VINYL RESIN, 3 MM X 40 FEET | 55568 | 2024-02-28 | 2024-02-29 | CLOSE | 2 | RL | 1 | 716.1 | 716.1 |  |  |  |  | KW1-15346 | 7 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 55568 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | EA | 12 | 45.4 | 544.8 |  |  |  |  | KW1-15346 | 6 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 12.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 8040-60-V00-0027 | TAPE, ADHESIVE, POLY FOAM, OPEN CELL, BLACK, 12.7 X 19 MM X 5 METERS | 55566 | 2024-02-28 | 2024-02-29 | CLOSE | 2 | RO | 2 | 19.8 | 39.6 | 21802 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15339 | 1 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5640-60-V00-0032 | WEATHER STRIP, DOOR, W/RUBBER BOTTOM SWEEP, 39" | 55564 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | EA | 2 | 16.17 | 32.34 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 13 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-09 07:00 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5640-60-V00-0035 | WEATHER STRIP, DOOR, W/BRUSH, 2 X 36 INCHES | 55563 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | EA | 2 | 53.3 | 106.6 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 12 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-09 07:00 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 8040-00-273-8713 | ADHESIVE, FLOORING, WHITE, 1 GL | 55569 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | GL | 4 | 185.7 | 742.8 |  |  |  |  | KW1-15340 | 13 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 30 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5110-60-V00-0077 | KNIFE, PUTTY, 3 INCHES | 55566 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | EA | 3 | 11.55 | 34.65 |  |  |  |  | KW1-15338 | 1 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 3.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 40 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 4730-60-V00-0869 | ELBOW, PIPE, SCH-40, SOCKET X SOCKET, 90°, PVC, GRAY, 63 MM | 55573 | 2024-02-28 | 2024-02-29 | CLOSE | 3 | EA | 8 | 4.3 | 34.4 |  |  |  |  | KW1-15346 | 12 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 8.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 40 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 4710-60-V00-0103 | PIPE, PLASTIC, SCH-40, UPVC, GRAY, 2 INCHES | 55573 | 2024-02-28 | 2024-02-29 | CLOSE | 2 | EA | 1 | 31.4 | 31.4 |  |  |  |  | KW1-15346 | 11 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 40 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 4730-60-V00-0428 | ELBOW, PIPE, SOCKET X SOCKET, 45 °, PVC, GRAY, 63 MM | 55573 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | EA | 4 | 24.6 | 98.4 |  |  |  |  | KW1-15346 | 10 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 4.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 40 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 8040-60-V00-0040 | CEMENT, HEAVY BODIED, CPVC, ORANGE, 16 OZ | 55574 | 2024-02-28 | 2024-02-29 | CLOSE | 2 | EA | 1 | 18.2 | 18.2 |  |  |  |  | KW1-15340 | 14 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 40 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 7930-60-V00-0046 | CLEANER, PVC/CPVC, CLEAR, 8 FL OUNCES | 55572 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | EA | 1 | 21.65 | 21.65 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 14 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-09 07:00 | COMP | 2024-03-05 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 40 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 4510-60-V00-0132 | STRAP, METAL | 55574 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | EA | 1 | 73.9 | 73.9 |  |  |  |  | KW1-15340 | 1 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 40 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5610-60-V00-0009 | GRAVEL (CUSTOMIZED) | 55654 | 2024-02-28 | 2024-03-03 | CLOSE | 1 | CZ | 1 | 94.25 | 94.25 | 22027 | CLOSE | 2024-03-08 | 2024-03-06 | KW1-15482 | 10 | 2024-03-08 | APPR | 2024-03-08 | Reghuraman, Karthik -Vectrus -GSD -No Export | RAMOOZ AL QIMMAH GENERAL TRADING & CONTRACTING CO | 2024-03-15 07:00 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 6145-60-V00-0142 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4 MM ² | 55593 | 2024-02-28 | 2024-03-01 | CLOSE | 3 | MT | 25 | 65.51 | 1637.75 |  |  |  |  | KW1-15347 | 5 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-09 07:00 | COMP | 2024-03-04 | 25.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 6145-60-V00-0139 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 6 MM ² | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 10 | YD | 25 | 28.1 | 702.5 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 11 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 25.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0421 | LUG, TERMINAL, ROUND TYPE, ONE-HOLE, 6MM² X 6MM | 55595 | 2024-02-28 | 2024-03-01 | CLOSE | 3 | PG | 1 | 70 | 70 |  |  |  |  | KW1-15352 | 3 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0425 | LUG, TERMINAL, ROUND TYPE, ONE-HOLE, 10MM X M6 | 55592 | 2024-02-28 | 2024-03-01 | CLOSE | 1 | EA | 10 | 6.93 | 69.3 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 1 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-04-12 | COMP | 2024-03-04 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-00-727-5153 | STRAP, TIE DOWN, ELECTRICAL COMPONENTS, 3.9 INCHES | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 9 | HD | 1 | 81.2 | 81.2 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 10 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-01-223-8533 | STRAP, TIE DOWN, ELECTRICAL COMPONENTS, PLASTIC POLYAMIDE, 0.1 X 8 INCHES | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 8 | PG | 1 | 66.48 | 66.48 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 9 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 7510-01-490-7265 | TAPE, LABELING, BLACK ON WHITE, 1/2 INCH X 26 FEET | 55595 | 2024-02-28 | 2024-03-01 | CLOSE | 2 | EA | 1 | 29.7 | 29.7 |  |  |  |  | KW1-15354 | 1 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MARATHON INC TRADING LLC | 2024-03-15 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 7 | EA | 10 | 3.5 | 35 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 8 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0511 | GLAND, ELECTRICAL CONDUIT, BRASS, BW, w/ EARTH TAG, 25 MM | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 6 | EA | 2 | 8 | 16 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 7 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0128 | TRAY, CABLE, STRAIGHT, MEDIUM DUTY, GALVANIZED STEEL, 450 MM X 3 METERS | 55597 | 2024-02-28 | 2024-03-01 | APPR | 2 | MT | 4 | 77.55 | 310.2 | 21808 | SENT | 2024-03-08 | 2024-03-03 | [12 empty] | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0108 | RACEWAY, METALLIC, GALVANISED STEEL, 150 X 100 MM, 10 FEET | 55591 | 2024-02-28 | 2024-02-29 | CLOSE | 2 | EA | 3 | 503.25 | 1509.75 |  |  |  |  | KW1-15347 | 4 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-04-30 07:00 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5940-60-V00-0077 | TERMINAL STRIP, GROUNDING, 12 WAY, PLASTIC, WHITE, 16 MM ², 30A | 55594 | 2024-02-28 | 2024-03-01 | CLOSE | 1 | EA | 5 | 23.1 | 115.5 |  |  |  |  | KW1-15352 | 1 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-22 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0480 | JUNCTION BOX, w/ BLANK SIDE, 100 X 100 X 50 MM | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 5 | EA | 3 | 12 | 36 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 6 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 3.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0477 | JUNCTION BOX, CIRCULAR, 3-WAY, GALVANIZED MALLEABLE IRON, 20 X 20 X 25 MM | 55591 | 2024-02-28 | 2024-02-29 | CLOSE | 1 | EA | 3 | 44.55 | 133.65 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 15 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-09 07:00 | COMP | 2024-03-09 | 3.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5970-01-013-9369 | TAPE, INSULATION, ELECTRICAL, RED, 3/4 X 792 INCHES | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 4 | RL | 2 | 10.1 | 20.2 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 5 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5970-00-419-4291 | TAPE, INSULATION, ELECTRICAL, BLACK, 3/4 X 1296 INCHES | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 3 | RL | 2 | 21.11 | 42.22 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 4 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5970-60-v00-0032 | TAPE, INSULATION, ELECTRICAL, YELLOW-GREEN, 19 MM X 20 METER | 55595 | 2024-02-28 | 2024-03-01 | CLOSE | 1 | RO | 2 | 16.5 | 33 |  |  |  |  | KW1-15352 | 2 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 4240-60-V00-0054 | TAPE, BARRICADE, "CAUTION BURIED ELECTRIC LINE BELOW", 3 INCHES X 1000 FEET | 55593 | 2024-02-28 | 2024-03-01 | CLOSE | 2 | RO | 2 | 239.75 | 479.5 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 17 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-09 07:00 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0209 | RACEWAY, METALLIC, GALVANIZED STEEL, 2 X 2 INCHES X 10 FEET | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 2 | EA | 2 | 56.21 | 112.42 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 3 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 5975-60-V00-0161 | RACEWAY, NON-METALLIC (CABLE TRUNKING), UPVC, WHITE, 50 X 50MM X 3 METER 12 | 55596 | 2024-02-28 | 2024-03-01 | CLOSE | 1 | EA | 2 | 25.25 | 50.5 | 21805 | CLOSE | 2024-03-01 |  | KW1-15342 | 2 | 2024-03-01 | APPR | 2024-03-01 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-15 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 4210-60-V00-0189 | EXTINGUISHER, FIRE, ABC DRY CHEMICAL W/ WALL HOOK, 10 LBS | 55593 | 2024-02-28 | 2024-03-01 | CLOSE | 1 | EA | 1 | 274.73 | 274.73 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 16 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-04-30 07:00 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
80 | 2024-02-21 | 50 | BU23-0226 | Deficiency Repair_initial_signed | 9791053 | 7125-09-V00-0027 | CABINET, FIRE EXTINGUISHER, SURFACE MOUNT, POLYSTYRENE, ACRYLIC, 20 LBS | 55597 | 2024-02-28 | 2024-03-01 | APPR | 1 | EA | 2 | 93.83 | 187.66 | 21808 | SENT | 2024-03-08 | 2024-03-03 | KW1-15472 | 1 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | AL BAYADER INTER.GROUP COMPANY | 2024-04-19 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5975-60-V00-0391 | SOCKET, PLUG-IN ELECTRONIC COMPONENT, OUTLET, SHUTTERED, 2 GANG, 15A, 127V | 55476 | 2024-02-27 | 2024-02-29 | CLOSE | 3 | EA | 6 | 42.5 | 255 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 8 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-15 07:00 | COMP | 2024-03-05 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5975-60-V00-0208 | BOX, METAL CLAD, SURFACE MOUNT, 2 GANG, 20MM | 55480 | 2024-02-27 | 2024-02-29 | CLOSE | 7 | EA | 6 | 11.02 | 66.12 |  |  |  |  | KW1-15340 | 4 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 6.00 |  | BU | BU table | February | 2024 | MM_BU
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5975-60-V00-0254 | COVER, JUNCTION BOX, BLANKING PLATE, STEEL, 1 GANG, GRAY, 79 X 79 X 42 MM | 55480 | 2024-02-27 | 2024-02-29 | CLOSE | 6 | EA | 10 | 6.27 | 62.7 |  |  |  |  | KW1-15340 | 5 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 6145-60-V00-0136 | WIRE, ELECTRICAL, RED, 1 CORE, 4MM² | 55480 | 2024-02-27 | 2024-02-29 | CLOSE | 5 | RO | 1 | 90.56 | 90.56 |  |  |  |  | KW1-15340 | 6 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 6145-60-V00-0154 | WIRE, ELECTRICAL, BLACK, 1 CORE, 4MM² | 55480 | 2024-02-27 | 2024-02-29 | CLOSE | 4 | RO | 1 | 90.56 | 90.56 |  |  |  |  | KW1-15340 | 7 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 6145-60-V00-0143 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 4MM² | 55478 | 2024-02-27 | 2024-02-29 | CLOSE | 2 | RO | 1 | 90 | 90 | 21792 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15330 | 2 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5975-60-V00-0743 | BOX CONNECTOR, ELECTRICAL, CONDUIT, SET SCREW, STEEL, 3/4 INCH | 55476 | 2024-02-27 | 2024-02-29 | CLOSE | 2 | EA | 30 | 17.16 | 514.8 |  |  |  |  | KW1-15347 | 2 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 07:00 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5975-60-V00-0376 | COUPLING, CONDUIT, w/ SET SCREW, STEEL, 3/4 INCH | 55476 | 2024-02-27 | 2024-02-29 | CLOSE | 1 | EA | 5 | 1.95 | 9.75 |  |  |  |  | KW1-15347 | 1 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-22 07:00 | COMP | 2024-03-04 | 5.00 |  | BU | BU table | February | 2024 | MM_BU
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5975-00-178-1217 | CONDUIT, RIGID, EMT, GALVANIZED STEEL, 3/4" INCH X 10 FEET | 55478 | 2024-02-27 | 2024-02-29 | CLOSE | 1 | EA | 10 | 14.9 | 149 | 21792 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15330 | 1 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-03-04 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5133-60-V00-0002 | DRILL, MULTI-STEP, (BIT), TITANIUM, 4 PIECES | 55477 | 2024-02-27 | 2024-02-29 | CLOSE | 2 | SE | 2 | 287.1 | 574.2 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15419 | 1 | 2024-03-05 | APPR | 2024-03-05 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-12 07:00 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 8040-01-024-6988 | SUPER GLUE, INSTANT ADHESIVE, 3500PSI, CLEAR, 20G | 55477 | 2024-02-27 | 2024-02-29 | CLOSE | 1 | EA | 5 | 108.57 | 542.85 |  |  |  |  | KW1-15347 | 3 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-04-30 07:00 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5935-60-V00-0167 | CONNECTOR, WIRE, RED, 18 -10 AWG | 55480 | 2024-02-27 | 2024-02-29 | CLOSE | 3 | PG | 2 | 25.3 | 50.6 |  |  |  |  | KW1-15340 | 2 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5975-00-111-3208 | STRAP, TIE DOWN, ELECTRICAL COMPONENTS, PLASTIC, NATURAL, 0.146 X 0.055 X 4.680 INCHES | 55480 | 2024-02-27 | 2024-02-29 | CLOSE | 2 | HD | 20 | 1.31 | 26.2 |  |  |  |  | KW1-15340 | 3 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 20.00 |  | BU | BU table | February | 2024 | MM_BU
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 6150-60-V00-0012 | REEL, CABLE, 4 WAY, 50 METERS, 13A | 55480 | 2024-02-27 | 2024-02-29 | CLOSE | 1 | EA | 2 | 230.62 | 461.24 |  |  |  |  | KW1-15340 | 8 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-08 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
81 | 2024-02-22 | 30 | BU24-0170 | Zone 2 T-T2059 | 9671349 | 5305-60-V00-0002 | SCREW, SELF DRILLING, PHILIPS, MODIFIED TRUSS HEAD, #8 X 1-1/2 INCHES | 55479 | 2024-02-27 | 2024-02-29 | CLOSE | 1 | BX | 1 | 29.5 | 29.5 |  |  |  |  | KW1-15346 | 2 | 2024-03-01 | APPR | 2024-03-01 | Govind, Binu - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 5307-60-V00-0021 | STUD, DRYWALL FRAME, U-CHANNEL, GALVANIZED STEEL, 3 X 1-1/4 INCHES X 12 FEET | 55474 | 2024-02-27 | 2024-02-29 | CLOSE | 5 | EA | 2 | 6.34 | 12.68 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 7 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-09 07:00 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 5305-60-V00-0220 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, STEEL, #6 X 2 INCHES | 55469 | 2024-02-27 | 2024-02-28 | CLOSE | 3 | BX | 1 | 52 | 52 | 21682 | CLOSE | 2024-03-01 | 2024-02-29 | KW1-15335 | 8 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2024-03-09 07:00 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 5640-60-V00-0048 | DRYWALL SHEET, (GYPSUM BOARD), 4 X 8 FEET X 1/2 INCH | 55474 | 2024-02-27 | 2024-02-29 | CLOSE | 4 | EA | 2 | 19.1 | 38.2 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 6 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-03-09 07:00 | COMP | 2024-03-05 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 5305-60-V00-0157 | SCREW, DRYWALL, BUGLE HEAD, PHILLIPS, COARSE THREAD, #7 X 1-3/8 INCHES 1000pc/box | 55469 | 2024-02-27 | 2024-02-28 | CLOSE | 2 | BX | 1 | 23.1 | 23.1 | 21682 | CLOSE | 2024-03-01 | 2024-02-29 | KW1-15335 | 7 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2024-03-09 07:00 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 5640-60-V00-0044 | TAPE, SELF ADHESIVE, DRYWALL JOINT, FIBERGLASS, 2 INCHES X 300 FEET | 55470 | 2024-02-27 | 2024-02-28 | CLOSE | 1 | EA | 1 | 18.2 | 18.2 | 21682 | CLOSE | 2024-03-01 | 2024-02-29 | KW1-15335 | 9 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2024-03-09 07:00 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 55474 | 2024-02-27 | 2024-02-29 | CLOSE | 3 | CN | 1 | 37 | 37 |  |  |  |  | KW1-15349 | 3 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 07:00 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 7510-00-680-2395 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 55469 | 2024-02-27 | 2024-02-28 | CLOSE | 1 | RO | 1 | 12.67 | 12.67 | 21682 | CLOSE | 2024-03-01 | 2024-02-29 | KW1-15335 | 6 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | AL-NUKHBHA AL-REBAEYA GENERAL TRADING CO | 2024-03-09 07:00 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 5350-60-V00-0007 | PAPER, ABRASIVE (SANDPAPER), 120 GRIT, 9 X 11 INCHES | 55474 | 2024-02-27 | 2024-02-29 | CLOSE | 2 | EA | 10 | 4.2 | 42 |  |  |  |  | KW1-15349 | 2 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-08 07:00 | COMP | 2024-03-04 | 10.00 |  | BU | BU table | February | 2024 | MM_BU
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 8010-60-V00-0241 | PRIMER, PAINT, LATEX, INTERIOR, WATERBASED, WHITE, 5 GALLON | 55474 | 2024-02-27 | 2024-02-29 | CLOSE | 1 | CN | 1 | 55.08 | 55.08 |  |  |  |  | KW1-15349 | 1 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-23 07:00 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 8010-60-V00-0130 | PAINT, LATEX, MATT, WHITE, 1 GL (3.2 TO 3.6 LT) | 55475 | 2024-02-27 | 2024-02-29 | CLOSE | 4 | CN | 1 | 42.2 | 42.2 | 21790 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15329 | 4 | 2024-03-02 | APPR | 2024-03-02 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-03-07 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 8010-60-V00-0028 | PAINT, ENAMEL, GLOSS, DESERT SAND, 3.6 LITER | 55475 | 2024-02-27 | 2024-02-29 | CLOSE | 3 | CN | 1 | 39.6 | 39.6 | 21790 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15329 | 3 | 2024-03-02 | APPR | 2024-03-02 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-03-04 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 55473 | 2024-02-27 | 2024-02-29 | CLOSE | 1 | EA | 2 | 14.6 | 29.2 | 21797 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15336 | 1 | 2024-03-01 | APPR | 2024-03-01 | Narayana Kutty Pillai, Nisha - No Export | MARATHON INC TRADING LLC | 2024-04-20 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 55475 | 2024-02-27 | 2024-02-29 | CLOSE | 2 | EA | 2 | 13.9 | 27.8 | 21790 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15329 | 2 | 2024-03-02 | APPR | 2024-03-02 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUAR | 55475 | 2024-02-27 | 2024-02-29 | CLOSE | 1 | EA | 2 | 29 | 58 | 21790 | CLOSE | 2024-03-01 | 2024-03-01 | KW1-15329 | 1 | 2024-03-02 | APPR | 2024-03-02 | Narayana Kutty Pillai, Nisha - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-07 | COMP | 2024-03-04 | 2.00 |  | BU | BU table | February | 2024 | MM_BU
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 5680-09-V00-0001 | CORNER BEAD, QUICKSILVER, METAL, 8 FEET X 1-1/4 INCHES | 55472 | 2024-02-27 | 2024-02-29 | CLOSE | 1 | ea | 2 | 8.42 | 16.84 | 21809 | CLOSE | 2024-03-05 | 2024-03-04 | KW1-15356 | 5 | 2024-03-01 | APPR | 2024-03-01 | Reghuraman, Karthik -Vectrus -GSD -No Export | CREDENCE TRADING EST. | 2024-04-30 07:00 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
82 | 2024-02-23 | 30 | BU24-0173 | Remove Wall Z5 Pad23 TT11 | 9808603 | 8415-01-492-0179 | GLOVES, DISPOSABLE, LATEX FREE, NITRILE, MEDIUM | 55471 | 2024-02-27 | 2024-02-28 | CLOSE | 1 | BX | 1 | 18.48 | 18.48 |  |  |  |  | KW1-15265 | 1 | 2024-02-28 | APPR | 2024-02-28 | Narayana Kutty Pillai, Nisha - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-05-31 | COMP | 2024-03-02 | 1.00 |  | BU | BU table | February | 2024 | MM_BU
83 | 2024-02-24 |  | BU24-0177 | Replace Electrical Cable Z1 B103 |  |  |  | PRINPRG | [23 empty] | CATALOG INPRG | BU | BU table | February | 2024 | MM_BU
84 | 2024-02-29 | 50 | BU23-223 | TI Deficiency Repairs Zone6 TT6078 - C to TDP | 7562117 | 5340-60-V00-0213 | VERTICAL ROD EXIT DEVICE, SURFACE, 1-1/2 HOUR FIRE-LISTED, SATIN STAINLESS STEEL, LHR | 55705 | 2024-02-29 | 2024-03-03 | CLOSE | 1 | EA | 1 | 2046 | 2046 | 21896 | SENT | 2024-03-08 | 2024-03-05 | KW1-15486 | 3 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-04-30 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
84 | 2024-02-29 | 70 | BU23-223 | TI Deficiency Repairs Zone6 TT6078 - C to TDP | 7562117 | 5340-60-V00-0213 | VERTICAL ROD EXIT DEVICE, SURFACE, 1-1/2 HOUR FIRE-LISTED, SATIN STAINLESS STEEL, LHR | 55697 | 2024-02-29 | 2024-03-03 | CLOSE | 1 | EA | 1 | 2046 | 2046 | 21896 | SENT | 2024-03-08 | 2024-03-05 | KW1-15486 | 1 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-04-30 |  |  |  |  | BU | BU table | February | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5660-60-V00-0033 | FENCE, GALVANIZED STEEL, CHAIN LINK MESH, 50 x 10 FEET | 56039 | 2024-03-04 | 2024-03-07 | APPR | 13 | RL | 1 | 500.6 | 500.6 |  |  |  |  | KW1-15459 | 16 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5650-60-V01-0003 | C-STUD RUNNER, STEEL, 0.0366IN X 1¼" X 3" X 12FT | 56039 | 2024-03-04 | 2024-03-07 | APPR | 12 | EA | 14 | 6.3 | 88.2 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5307-60-V00-0021 | STUD, DRYWALL FRAME, U-CHANNEL, GALVANIZED STEEL, 3 X 1-1/4 INCHES X 12 FEET | 56034 | 2024-03-04 | 2024-03-07 | APPR | 2 | EA | 14 | 6.27 | 87.78 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5640-60-V00-0048 | DRYWALL SHEET, (GYPSUM BOARD), 4 X 8 FEET X 1/2 INCH | 56034 | 2024-03-04 | 2024-03-07 | APPR | 1 | EA | 15 | 19.1 | 286.5 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5340-05-V00-0095 | HINGE, BUTT, CABINET, PIANO, STEEL, 1-1/2 X 12 INCHES | 56041 | 2024-03-04 | 2024-03-07 | APPR | 5 | EA | 2 | 14.79 | 29.58 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5305-60-V00-0171 | SCREW, PHILLIPS, BUGLE HEAD, STEEL, #8 X 2 INCHES | 56039 | 2024-03-04 | 2024-03-07 | APPR | 11 | BX | 2 | 19.6 | 39.2 |  |  |  |  | KW1-15459 | 15 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 2.00 |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STAINLESS STEEL, 10 X 3/4 INCHES 100pc / bx | 56039 | 2024-03-04 | 2024-03-07 | APPR | 1 | BX | 3 | 29.4 | 88.2 |  |  |  |  | KW1-15459 | 6 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 3.00 |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5640-60-V00-0051 | JOINT COMPOUND, WALLBOARD, 28 KG | 56039 | 2024-03-04 | 2024-03-07 | APPR | 10 | CN | 1 | 37 | 37 |  |  |  |  | KW1-15459 | 14 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 1.00 |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5640-60-V00-0044 | TAPE, SELF ADHESIVE, DRYWALL JOINT, FIBERGLASS, 2 INCHES X 300 FEET | 56035 | 2024-03-04 | 2024-03-07 | APPR | 1 | EA | 2 | 18.48 | 36.96 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8010-60-V00-0006 | PAINT, LATEX, MATT, OFF-WHITE, 3.2 LITER | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 10 | CN | 2 | 44 | 88 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 9 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 9 | EA | 4 | 29 | 116 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 8 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8020-00-753-4914 | ROLLER, PAINT, POLYESTER, 7 INCHES | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 8 | EA | 2 | 13.9 | 27.8 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 7 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8020-00-682-6489 | COVER, PAINT ROLLER, ACRYLIC, 0.375 X 7 INCHES | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 7 | EA | 3 | 14.2 | 42.6 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 6 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-04-30 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 56038 | 2024-03-04 | 2024-03-07 | CLOSE | 2 | EA | 4 | 14.6 | 58.4 | 22161 | CLOSE | 2024-03-07 |  | KW1-15460 | 2 | 2024-03-07 | APPR | 2024-03-07 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-04-18 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 7510-00-266-6710 | TAPE, PRESSURE SENSITIVE ADHESIVE, PAPER, TAN, 2 INCHES X 60 YARDS | 56038 | 2024-03-04 | 2024-03-07 | CLOSE | 1 | EA | 2 | 8 | 16 | 22161 | CLOSE | 2024-03-07 |  | KW1-15460 | 1 | 2024-03-07 | APPR | 2024-03-07 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 7220-60-V00-0041 | BASEBOARD, WALL PLASTIC, PVC FOAM SKIRTING,100MM X 3M X 0.3MM, G100-3.5 | 56039 | 2024-03-04 | 2024-03-07 | APPR | 9 | ea | 8 | 45.4 | 363.2 |  |  |  |  | KW1-15459 | 13 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 8.00 |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8030-01-075-1156 | CAULKING COMPOUND, CARTRIDGE, WHITE, 10 OZ | 56039 | 2024-03-04 | 2024-03-07 | APPR | 8 | ea | 10 | 14.9 | 149 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5335-60-V00-0001 | WIRE MESH, GALVANIZED STEEL, 21 GAGE, 4 X 50 FEET | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 6 | rool | 1 | 39.7 | 39.7 | 22149 | CLOSE | 2024-03-07 |  | KW1-15453 | 2 | 2024-03-07 | APPR | 2024-03-07 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 56037 | 2024-03-04 | 2024-03-07 | CLOSE | 1 | bx | 1 | 19.47 | 19.47 | 22164 | CLOSE | 2024-03-07 |  | KW1-15462 | 1 | 2024-03-09 | APPR | 2024-03-09 | Santhumayor, Santhosh - Vectrus - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-04-30 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8010-60-V00-0089 | PRIMER COATING, WHITE, 1 GL | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 5 | gal | 2 | 41.3 | 82.6 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 5 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5130-60-V00-0123 | WHEEL, ABRASIVE, ALUMINUM OXIDE, 12,225 RPM, 5 X 1/16 X 7/8 INCHES | 56039 | 2024-03-04 | 2024-03-07 | APPR | 7 | EA | 6 | 15 | 90 |  |  |  |  | KW1-15459 | 12 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 6.00 |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5130-60-V00-0134 | BIT, SCREWDRIVER, (POWER BIT), PHILLIPS, STEEL, #2 X 2 INCHES | 56039 | 2024-03-04 | 2024-03-07 | APPR | 6 | pg | 1 | 14.8 | 14.8 |  |  |  |  | KW1-15459 | 11 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 1.00 |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5350-60-V00-0007 | PAPER, ABRASIVE (SANDPAPER), 120 GRIT, 9 X 11 INCHES | 56039 | 2024-03-04 | 2024-03-07 | APPR | 5 | ea | 10 | 4.2 | 42 |  |  |  |  | KW1-15459 | 10 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 10.00 |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5680-60-V01-0002 | CORNER BEAD, STAINLESS STEEL, 25 MM X2.5 METER | 56033 | 2024-03-04 | 2024-03-07 | APPR | 3 | ea | 10 | 108.9 | 1089 | 22173 | SENT | 2024-03-07 | 2024-03-10 | [12 empty] | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5130-60-V00-0125 | DISK, ABRASIVE, SANDING, HOOK AND LOOP, 220 GRIT, 8 HOLE, 5 INCHES-DUSTLESS HOOK AND LOOP SANDING DISC | 56039 | 2024-03-04 | 2024-03-07 | APPR | 4 | bx | 1 | 45.7 | 45.7 |  |  |  |  | KW1-15459 | 9 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 1.00 |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 4710-05-V00-0007 | TUBE, RECTANGULAR, STEEL, 3 X 1-1/2 X 1/8 INCHES x 20ft | 56033 | 2024-03-04 | 2024-03-07 | APPR | 2 | ea | 4 | 41.25 | 165 | 22173 | SENT | 2024-03-07 | 2024-03-10 | [12 empty] | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5306-60-V00-0100 | CARRIAGE BOLT 8M X 4 1/4" WITH NUT AND WASHER SQUARE NECK | 56036 | 2024-03-04 | 2024-03-07 | APPR | 1 | ea | 20 | 3.63 | 72.6 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5340-60-V00-0116 | LOCK, FLUSH, CABINET AND DRAWER, STEEL, GOLD, 1.8 X 1.3 INCHES | 56041 | 2024-03-04 | 2024-03-07 | APPR | 4 | ea | 1 | 13.2 | 13.2 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8010-00-242-2089 | THINNER, PAINT PRODUCTS, 1 GL | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 4 | GAL | 1 | 54.6 | 54.6 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 4 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8010-00-297-0584 | PAINT, ENAMEL, SEMIPAINT, ENAMEL, SEMIGLOSPAINT, ENAMEL, SEMIGLOSS, WHITE, 1 GLS, WHITE, 1 GLGLOSS, WHITE, 1 GL | 56062 | 2024-03-04 | 2024-03-07 | APPR | 1 | GAL | 1 | 41.53 | 41.53 | 22172 | SENT | 2024-03-07 | 2024-03-10 | [12 empty] | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8010-60-V00-0124 | PRIMER, RED OXIDE, OIL BASED, RED, 1 GL | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 3 | gal | 1 | 41.4 | 41.4 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 3 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 2 | EA | 3 | 12.4 | 37.2 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 2 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 8020-01-317-2854 | COVER, PAINT ROLLER, POLYESTER FIBER, 3 INCHES | 56040 | 2024-03-04 | 2024-03-07 | CLOSE | 1 | EA | 3 | 6.6 | 19.8 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 1 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5305-05-V00-0020 | SCREW, SELF DRILLING, HEX HEAD, w/NEOPRENE WASHER, STAINLESS STEEL, #10 X 1-1/2 INCHES | 56041 | 2024-03-04 | 2024-03-07 | APPR | 2 | EA | 50 | 0.7 | 35 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5305-60-V00-0167 | SCREW, HEX WASHER HEAD, STEEL, #14 X 3 INCHES | 56039 | 2024-03-04 | 2024-03-07 | APPR | 3 | bx | 32 | 35.6 | 1139.2 |  |  |  |  | KW1-15459 | 8 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 32.00 |  | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5133-05-V01-0089 | DRILL BIT, CARBIDE, TIPPED, SAND BLAST, 12 MM | 56041 | 2024-03-04 | 2024-03-07 | APPR | 1 | EA | 2 | 22.1 | 44.2 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 4240-60-V00-0043 | MASK, N95, PARTICULATE RESPIRATOR, 10EA/BOX, WHITE | 56033 | 2024-03-04 | 2024-03-07 | APPR | 1 | bx | 1 | 53.46 | 53.46 | 22173 | SENT | 2024-03-07 | 2024-03-10 | [12 empty] | BU | BU table | March | 2024 | MM_BU
85 | 2024-03-02 | 30 | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS | 9869144 | 5305-60-V00-0022 | MATERIAL: STAINLESS STEELSIZE: #10SCREW LENGTH: 1-1/2 INCHESHEAD STYLE: TRUSS HEADDRIVE TYPE: PHILLIPSUNIT OF MEASURE: PACKAGE (CONTAINS 100 EACH) | 56039 | 2024-03-04 | 2024-03-07 | APPR | 2 | pg | 1 | 44.9 | 44.9 |  |  |  |  | KW1-15459 | 7 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 1.00 |  | BU | BU table | March | 2024 | MM_BU
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 5130-60-V00-0122 | WHEEL ABRASIVE, ALUMINIUM OXIDE, 4 X 1/16 X 5/8 INCHES | 56045 | 2024-03-04 | 2024-03-07 | APPR | 1 | EA | 10 | 19.8 | 198 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [11 empty] | CATALOG INPRG | BU | BU table | March | 2024 | MM_BU
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 5345-60-V00-0019 | DISK, FLAP, ABRASIVE, 60 GRIT, ZIRCONIA, 4-1/2 X 7/8 INCHES | 56047 | 2024-03-04 | 2024-03-07 | CLOSE | 2 | EA | 15 | 12.8 | 192 |  |  |  |  | KW1-15459 | 20 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 15.00 |  | BU | BU table | March | 2024 | MM_BU
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 9150-01-418-9008 | LUBRICATING OIL, UTILITY, 11 OZ. | 56046 | 2024-03-04 | 2024-03-07 | APPR | 3 | EA | 3 | 23.3 | 69.9 | 22172 | SENT | 2024-03-07 | 2024-03-10 | [12 empty] | BU | BU table | March | 2024 | MM_BU
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 8010-60-V00-0095 | PRIMER, COATING, RED OXIDE, LIQUID, 3.78 TO 4 LITERS | 56048 | 2024-03-04 | 2024-03-07 | CLOSE | 5 | GL | 6 | 41.3 | 247.8 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 14 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 8010-60-V00-0028 | PAINT, ENAMEL, GLOSS, DESERT SAND, 3.6 LITER | 56048 | 2024-03-04 | 2024-03-07 | CLOSE | 4 | EA | 10 | 39.6 | 396 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 13 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 8415-01-492-0178 | GLOVES, DISPOSABLE, NITRILE, LARGE, 9-1/2 X 0-1/250 INCHES | 56044 | 2024-03-04 | 2024-03-07 | CLOSE | 1 | bx | 2 | 19.47 | 38.94 | 22164 | CLOSE | 2024-03-07 |  | KW1-15462 | 3 | 2024-03-09 | APPR | 2024-03-09 | Santhumayor, Santhosh - Vectrus - No Export | TRADEX INTERNATIONAL TRADING LLC | 2024-04-30 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 8020-01-421-6849 | BRUSH, PAINT, CHISELED, 2 INCHES | 56046 | 2024-03-04 | 2024-03-07 | APPR | 2 | EA | 8 | 14.6 | 116.8 | 22161 | CLOSE | 2024-03-07 |  | KW1-15460 | 4 | 2024-03-07 | APPR | 2024-03-07 | Santhumayor, Santhosh - Vectrus - No Export | MARATHON INC TRADING LLC | 2024-04-18 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 5120-60-V00-0328 | NUTDRIVER SET, MAGNETIC, 3 PIECES | 56047 | 2024-03-04 | 2024-03-07 | CLOSE | 1 | ea | 4 | 24.1 | 96.4 |  |  |  |  | KW1-15459 | 19 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 4.00 |  | BU | BU table | March | 2024 | MM_BU
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 5305-60-V00-0090 | SCREW, SELF-DRILLING, STEEL, w/ RUBBER WASHER, #14 X 1 INCH | 56046 | 2024-03-04 | 2024-03-07 | APPR | 1 | PK | 15 | 23.5 | 352.5 | 22172 | SENT | 2024-03-07 | 2024-03-10 | [12 empty] | BU | BU table | March | 2024 | MM_BU
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 8020-01-317-2800 | ROLLER, PAINT, 3 INCHES | 56048 | 2024-03-04 | 2024-03-07 | CLOSE | 3 | EA | 4 | 12.4 | 49.6 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 12 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 8020-01-317-2854 | COVER, PAINT ROLLER, POLYESTER FIBER, 3 INCHES | 56048 | 2024-03-04 | 2024-03-07 | CLOSE | 2 | EA | 12 | 6.6 | 79.2 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 11 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 8020-00-753-4911 | TRAY, PAINT ROLLER, METAL, 1 QUART | 56048 | 2024-03-04 | 2024-03-07 | CLOSE | 1 | EA | 4 | 29 | 116 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 10 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 8030-60-V00-0008 | SEALING COMPOUND, GUTTER & SEAM, WHITE, 10 OZ. | 56043 | 2024-03-04 | 2024-03-07 | CLOSE | 2 | ea | 12 | 23.1 | 277.2 |  |  |  |  | KW1-15459 | 18 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 12.00 |  | BU | BU table | March | 2024 | MM_BU
86 | 2024-03-04 | 40 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 5130-60-V00-0101 | GRINDER, ELECTRIC, PORTABLE, ANGLE, RPM 800, 20 V | 56043 | 2024-03-04 | 2024-03-07 | CLOSE | 1 | EA | 1 | 1205.49 | 1205.49 |  |  |  |  | KW1-15459 | 17 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-04-04 07:00 | COMP | 2024-03-10 | 1.00 |  | BU | BU table | March | 2024 | MM_BU
86 | 2024-03-04 | 50 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 9515-60-V00-0008 | SHEET, METAL, CORRUGATED, 4 X 14 FEET | 56069 | 2024-03-04 | 2024-03-07 | APPR | 1 | EA | 33 | 37.95 | 1252.35 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
86 | 2024-03-04 | 50 | BU24-0040 | Convert to Sunshade Z7 TT700 | 8675135 | 9515-60-V00-0004 | SHEET, METAL, CORRUGATED, 1 X 3 METER | 56070 | 2024-03-04 | 2024-03-07 | APPR | 1 | EA | 24 | 21.47 | 515.28 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 6115-60-V00-0037 | GENERATOR SET, DIESEL ENGINE, 4-CYCLE, 400V, 24 KW, 50HZ | 56512 | 2024-03-09 |  | PREFIN | 1 | EA | 2 | 14597.59 | 29195.18 | [15 empty] | Waiting Submittal approval | BU | BU table | February | 2024 | MM_BU
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 56514 | 2024-03-09 |  | WDOAPPR | 8 | EA | 4 | 302.94 | 1211.76 | [16 empty] | BU | BU table | February | 2024 | MM_BU
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 56514 | 2024-03-09 |  | WDOAPPR | 7 | EA | 4 | 58.91 | 235.64 | [16 empty] | BU | BU table | February | 2024 | MM_BU
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 6145-60-V00-0119 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 25 MM² | 56514 | 2024-03-09 |  | WDOAPPR | 6 | MR | 30 | 26.5 | 795 | [16 empty] | BU | BU table | February | 2024 | MM_BU
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM ² | 56514 | 2024-03-09 |  | WDOAPPR | 5 | YD | 35 | 242.58 | 242.58 | [16 empty] | BU | BU table | February | 2024 | MM_BU
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 5940-60-V00-0016 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 16 MM² | 56513 | 2024-03-09 |  | WDOAPPR | 1 | EA | 10 | 5 | 50 | [16 empty] | BU | BU table | February | 2024 | MM_BU
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 5975-60-V00-0512 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, CW, BRASS, 32 MM | 56514 | 2024-03-09 |  | WDOAPPR | 4 | KT | 2 | 25.5 | 51 | [16 empty] | BU | BU table | February | 2024 | MM_BU
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 5940-60-V00-0017 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 25 MM² | 56514 | 2024-03-09 |  | WDOAPPR | 3 | EA | 10 | 5 | 50 | [16 empty] | BU | BU table | February | 2024 | MM_BU
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 56514 | 2024-03-09 |  | WDOAPPR | 2 | YD | 35 | 163 | 163 | [16 empty] | BU | BU table | February | 2024 | MM_BU
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 5975-60-V00-0209 | RACEWAY, METALLIC, GALVANIZED STEEL, 2 X 2 INCHES X 10 FEET | 56514 | 2024-03-09 |  | WDOAPPR | 1 | EA | 1 | 56.21 | 56.21 | [16 empty] | BU | BU table | February | 2024 | MM_BU
87 | 2024-02-20 | 30 | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | 5975-60-V00-0793 | TRAY, CABLE, STRAIGHT, MEDIUM DUTY, GALVANIZED STEEL, 450 MM X 3 METERS | 56511 | 2024-03-09 |  | WDOAPPR | 1 | EA | 1 | 55.09 | 55.09 | [16 empty] | BU | BU table | February | 2024 | MM_BU
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 6115-60-V00-0037 | GENERATOR SET, DIESEL ENGINE, 4-CYCLE, 400V, 24 KW, 50HZ | 56508 | 2024-03-09 |  | PREFIN | 1 | EA | 2 | 14597.6 | 29195.2 | [16 empty] | BU | BU table | February | 2024 | MM_BU
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 56510 | 2024-03-09 |  | WDOAPPR | 8 | EA | 4 | 302.94 | 1211.76 | [16 empty] | BU | BU table | February | 2024 | MM_BU
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 56510 | 2024-03-09 |  | WDOAPPR | 7 | EA | 4 | 58.91 | 235.64 | [16 empty] | BU | BU table | February | 2024 | MM_BU
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 6145-60-V00-0119 | CABLE, POWER, ELECTRICAL, XLPE, BLACK, 4 CORE, 25 MM² | 56510 | 2024-03-09 |  | WDOAPPR | 6 | MR | 30 | 26.5 | 795 | [16 empty] | BU | BU table | February | 2024 | MM_BU
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 6145-60-V00-0148 | WIRE, ELECTRICAL, 1 CORE, YELLOW & GREEN, 16 MM ² | 56510 | 2024-03-09 |  | WDOAPPR | 5 | YD | 35 | 242.58 | 242.58 | [16 empty] | BU | BU table | February | 2024 | MM_BU
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 5940-60-V00-0016 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 16 MM² | 56509 | 2024-03-09 |  | WDOAPPR | 1 | EA | 10 | 5 | 50 | [16 empty] | BU | BU table | February | 2024 | MM_BU
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 5975-60-V00-0512 | STUFFING TUBE (CABLE GLAND), w/EARTH TAG, CW, BRASS, 32 MM | 56510 | 2024-03-09 |  | WDOAPPR | 4 | KT | 2 | 25.5 | 51 | [16 empty] | BU | BU table | February | 2024 | MM_BU
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 5940-60-V00-0017 | TERMINAL, LUG, ONE HOLE, COPPER, 8.4 MM X 25 MM² | 56510 | 2024-03-09 |  | WDOAPPR | 3 | EA | 10 | 5 | 50 | [16 empty] | BU | BU table | February | 2024 | MM_BU
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 56510 | 2024-03-09 |  | WDOAPPR | 2 | YD | 35 | 163 | 163 | [16 empty] | BU | BU table | February | 2024 | MM_BU
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 5975-60-V00-0209 | RACEWAY, METALLIC, GALVANIZED STEEL, 2 X 2 INCHES X 10 FEET | 56510 | 2024-03-09 |  | WDOAPPR | 1 | EA | 1 | 56.21 | 56.21 | [16 empty] | BU | BU table | February | 2024 | MM_BU
88 | 2024-02-20 | 30 | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | 5975-60-V00-0793 | RACEWAY, METALLIC, (CABLE TRAY), MEDIUM DUTY, HOT-DIP GALVANIZED, 1.20 X 50 X 3000 X 450 MM | 56507 | 2024-03-09 |  | WDOAPPR | 1 | EA | 1 | 55.09 | 55.09 | [16 empty] | BU | BU table | February | 2024 | MM_BU
89 | 2024-03-04 | 30 | BU24-0179 | 4 New Cipher Locks TT301 | 9966783 | 5340-60-V00-0429 | LOCK SET, MECHANICAL, PUSH BUTTON, RIGHT HAND, 2-3/4 INCHES | 56124 | 2024-03-05 | 2024-03-07 | CLOSE | 3 | EA | 2 | 602.6 | 1205.2 | 22149 | CLOSE | 2024-03-07 |  | KW1-15453 | 5 | 2024-03-07 | APPR | 2024-03-07 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-21 | COMP | 2024-03-10 | 2.00 |  | BU | BU table | March | 2024 | MM_BU
89 | 2024-03-04 | 30 | BU24-0179 | 4 New Cipher Locks TT301 | 9966783 | 5340-60-V00-0171 | LOCK SET, RIM, PUSHBUTTON, LHR, 5 INCHES | 56124 | 2024-03-05 | 2024-03-07 | CLOSE | 2 | EA | 2 | 751.4 | 1502.8 | 22149 | CLOSE | 2024-03-07 |  | KW1-15453 | 4 | 2024-03-07 | APPR | 2024-03-07 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-21 | COMP | 2024-03-10 | 2.00 |  | BU | BU table | March | 2024 | MM_BU
89 | 2024-03-04 | 30 | BU24-0179 | 4 New Cipher Locks TT301 | 9966783 | 5340-60-V00-0169 | LOCK SET, MORTISE, RIM EXIT DEVICE, KEY OUTSIDE UNLOCKS/LOCKS TRIM | 56124 | 2024-03-05 | 2024-03-07 | CLOSE | 1 | EA | 2 | 2227.5 | 4455 | 22149 | CLOSE | 2024-03-07 |  | KW1-15453 | 3 | 2024-03-07 | APPR | 2024-03-07 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-21 | COMP | 2024-03-10 | 2.00 |  | BU | BU table | March | 2024 | MM_BU
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 9905-60-V00-0065 | SIGN, DANGER HIGH VOLTAGE, ADHESIVE, CUSTOMIZED (Length 9X8 Width Inches) | 56188 | 2024-03-05 | 2024-03-07 | APPR | 1 | EA | 1 | 9.75 | 9.75 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 9905-60-V00-0066 | SIGN, DANGER, 415 VOLTS , 5 X 3-3/4 INCHES | 56156 | 2024-03-05 | 2024-03-07 | APPR | 1 | PG | 1 | 17.06 | 17.06 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 11 | EA | 1 | 302.94 | 302.94 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 25 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 10 | EA | 1 | 58.91 | 58.91 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 24 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6210-60-V00-0114 | LIGHT UNIT, EMERGENCY, (EXIT SIGN), WHITE, 230/240V, 8W | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 9 | EA | 1 | 146.47 | 146.47 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 23 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 56144 | 2024-03-05 |  |  | 8 | RO | 2 | [18 empty] | BU | BU table | March | 2024 | MM_BU
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 7 | EA | 6 | 3.26 | 19.56 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 21 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 6 | RO | 1 | 92.02 | 92.02 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 20 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 | COMP | 2024-03-10 | 1.00 |  | BU | BU table | March | 2024 | MM_BU
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 5975-60-V00-0480 | JUNCTION BOX, w/ BLANK SIDE, 100 X 100 X 50 MM | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 5 | EA | 1 | 12 | 12 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 19 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6145-60-V00-0101 | CABLE, POWER, ELECTRICAL, H07RN-F, BLACK, 3 CORE, 4 MM² | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 4 | MR | 20 | 13.5 | 270 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 18 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6145-60-V00-0128 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 10 MM ² | 56143 | 2024-03-05 | 2024-03-07 | CLOSE | 1 | RL | 1 | 26 | 26 |  |  |  |  | KW1-15455 | 2 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | MARATHON INC TRADING LLC | 2024-03-31 07:00 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 5975-60-V00-0299 | PLATE, ELECTRICAL GROUNDING (BUS BAR), 20 HOLES, COPPER, TIN-PLATED, 19-3/8 X 1 X 3/16 INCHES | 56141 | 2024-03-05 | 2024-03-07 | CLOSE | 1 | KT | 1 | 273.24 | 273.24 |  |  |  |  | KW1-15457 | 1 | 2024-03-07 | APPR | 2024-03-07 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-14 07:00 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 3 | EA | 1 | 260.02 | 260.02 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 17 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6210-60-V00-0094 | FIXTURE, LIGHTING, LED, RETROFIT, POLYCARBONATE, PURE WHITE, 40W | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 2 | EA | 2 | 242.35 | 484.7 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 16 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6210-60-V00-0040 | FIXTURE, LIGHTING, LED, WALL PACK, 5000K, 100-277 VAC, 30W | 56144 | 2024-03-05 | 2024-03-07 | CLOSE | 1 | EA | 1 | 142.6 | 142.6 | 22152 | CLOSE | 2024-03-07 |  | KW1-15456 | 15 | 2024-03-08 | APPR | 2024-03-08 | Santhumayor, Santhosh - Vectrus - No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-21 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6130-60-V00-0097 | BATTERY, EMERGENCY LED DRIVER, 50/60HZ, 15W, 100-277V | 56142 | 2024-03-05 | 2024-03-07 | APPR | 1 | EA | 1 | 117.81 | 117.81 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6625-60-V00-0093 | TESTER, SOCKET, THREE, FLAT, PRONG, 220V, 13A | 56155 | 2024-03-05 | 2024-03-07 | APPR | 1 | EA | 1 | 211.79 | 211.79 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
90 | 2024-03-05 | 30 | BU24-0160 | Correct TI deficiencies water reclamation system | 8851969 | 6625-60-V00-0049 | TESTER, VOLTAGE, W/FLASHLIGHT, 12-1000V | 56154 | 2024-03-05 | 2024-03-07 | APPR | 1 | EA | 1 | 169.99 | 169.99 | 22160 | SENT | 2024-03-09 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 30 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 8030-60-V00-0008 | SEALING COMPOUND, GUTTER & SEAM, WHITE, 10 OZ. | 56364 | 2024-03-07 | 2024-03-09 | CLOSE | 1 | CS | 24 | 23.1 | 554.4 | 22249 | CLOSE | 2024-03-10 |  | KW1-15519 | 6 | 2024-03-10 | APPR | 2024-03-10 | Santhumayor, Santhosh - Vectrus - No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-24 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 30 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 8030-60-V00-0055 | SEALING COMPOUND, SILICONE, WHITE, 10.1 OZ | 56366 | 2024-03-09 | 2024-03-09 | CLOSE | 3 | BX | 1 | 141.9 | 141.9 |  |  |  |  | KW1-15508 | 3 | 2024-03-09 | APPR | 2024-03-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-16 07:00 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 30 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 9330-60-V00-0016 | SHEET, ACRYLIC, WHITE, 48 X 96 X 0.250 INCHES | 56366 | 2024-03-09 | 2024-03-09 | CLOSE | 2 | SH | 1 | 181.5 | 181.5 |  |  |  |  | KW1-15508 | 2 | 2024-03-09 | APPR | 2024-03-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-16 07:00 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 30 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 8010-01-331-6107 | PAINT, ENAMEL, GLOSS, SPRAY, BLACK, 11 OZ | 56366 | 2024-03-09 | 2024-03-09 | CLOSE | 1 | PT | 3 | 57.5 | 172.5 |  |  |  |  | KW1-15508 | 1 | 2024-03-09 | APPR | 2024-03-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | MERIT INTERNATIONAL GENERAL TRADING CO WLL | 2024-03-16 07:00 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 30 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5305-60-V00-0005 | SCREW, PHILLIPS, TRUSS HEAD, STEEL, #8 X 1 INCH | 56365 | 2024-03-09 | 2024-03-09 | CLOSE | 1 | BX | 1 | 29.4 | 29.4 |  |  |  |  | KW1-15509 | 5 | 2024-03-09 | APPR | 2024-03-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-16 07:00 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 9905-60-V00-0065 | SIGN, DANGER HIGH VOLTAGE, ADHESIVE, CUSTOMIZED (Length 9X8 Width Inches) | 56459 | 2024-03-09 | 2024-03-09 | APPR | 1 | EA | 1 | 9.9 | 9.9 | 22252 | SENT | 2024-03-10 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 9905-60-V00-0066 | SIGN, DANGER, 415 VOLTS , 5 X 3-3/4 INCHES | 56462 | 2024-03-09 |  | WDOAPPR | 1 | PG | 1 | 17.33 | 17.33 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5975-00-878-3791 | ROD, GROUNDING, 108 INCHES | 56464 | 2024-03-09 |  | WDOAPPR | 9 | EA | 1 | 302.94 | 302.94 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5975-60-V00-0469 | EARTH PIT, CONCRETE, 6 X 12 X 12 INCHES | 56464 | 2024-03-09 |  | WDOAPPR | 8 | EA | 1 | 58.91 | 58.91 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 |  | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 6625-60-V01-0056 | TESTER, SOCKET, 230V, 50Hz, RCD 30mA, SM300 |  | 2024-03-09 |  |  |  | EA | 1 | [17 empty] | Waiting AHJ approval | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5975-60-V00-0531 | PROTECTOR, ELECTRICAL CABLE, PVC, WHITE, 1 INCH X 9 FEET | 56464 | 2024-03-09 |  | WDOAPPR | 7 | EA | 5 | 11.83 | 59.15 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 56464 | 2024-03-09 |  | WDOAPPR | 6 | EA | 1 | 260.02 | 260.02 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 6145-60-V00-0134 | CABLE, POWER, ELECTRICAL, 3 CORES, WHITE, 2.5 MM² | 56464 | 2024-03-09 |  |  | 5 | RO | 1 | [18 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5975-60-V00-0503 | UNION, ELECTRICAL CONDUIT, POLYAMIDE, LONG THREAD, 6-12 MM | 56464 | 2024-03-09 |  | WDOAPPR | 4 | EA | 6 | 3.7 | 22.2 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5120-01-428-8497 | SCREWDRIVER SET, FLAT TIP AND CROSS TIP, 8 PIECES | 56461 | 2024-03-09 | 2024-03-09 | CLOSE | 1 | SE | 1 | 94.71 | 94.71 |  |  |  |  | KW1-15509 | 11 | 2024-03-09 | APPR | 2024-03-09 | Reghuraman, Karthik -Vectrus -GSD -No Export | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-16 07:00 |  |  |  |  | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 6625-60-V00-0093 | TESTER, SOCKET, W/ BEEPER, RCD, 250 V, 50 HZ | 56460 | 2024-03-09 | 2024-03-09 | APPR | 1 | EA | 3 | 74.25 | 222.75 | 22252 | SENT | 2024-03-10 | 2024-03-12 | [12 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5975-60-V00-0480 | JUNCTION BOX, w/ BLANK SIDE, 100 X 100 X 50 MM | 56464 | 2024-03-09 |  | WDOAPPR | 3 | EA | 3 | 13.1 | 39.3 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 6145-60-V00-0101 | CABLE, POWER, ELECTRICAL, H07RN-F, BLACK, 3 CORE, 4 MM² | 56464 | 2024-03-09 |  | WDOAPPR | 2 | MR | 20 | 12.75 | 255 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 6145-60-V00-0128 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 10 MM ² | 56463 | 2024-03-09 |  | WDOAPPR | 1 | RL | 1 | 26 | 26 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 40 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 6210-60-V00-0021 | FIXTURE, LIGHTING, LED, SAFETY AND EXIT SIGN, SINGLE SIDED, GREEN, 230V AC, 136 X 303 X 62 MM | 56464 | 2024-03-09 |  | WDOAPPR | 1 | EA | 1 | 639.54 | 639.54 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 4130-60-V00-0288 | TAPE, WRAP, INSULATION, 3 INCHES X 150 FEET | 56471 | 2024-03-09 |  | WDOAPPR | 2 | RO | 1 | 32 | 32 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5970-60-V00-0037 | TAPE, INSULATION, ELECTRICAL, WHITE, 19MM X 20M | 56468 | 2024-03-09 |  | WDOAPPR | 1 | RO | 1 | 21.45 | 21.45 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5975-60-V00-0529 | CONDUIT, FLEXIBLE, CORRUGATED, GALVANIZED, 3/4 INCH | 56472 | 2024-03-09 |  | WDOAPPR | 6 | RO | 1 | 92 | 92 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 6145-60-V00-0139 | WIRE, ELECTRICAL, YELLOW & GREEN, 1 CORE, 6 MM ² | 56472 | 2024-03-09 |  | WDOAPPR | 5 | RO | 1 | 28.1 | 28.1 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5975-60-V00-0421 | LUG, TERMINAL, ROUND TYPE, ONE-HOLE, 6 X 6 MM | 56472 | 2024-03-09 |  | WDOAPPR | 4 | PG | 1 | 51.82 | 51.82 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 |  | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5306-35-V00-0001 | ASSORTMENT KIT, BOLTS AND NUTS, 375PCS |  | 2024-03-09 |  |  |  | KT | 1 | [17 empty] | Waiting catalog | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5930-60-V00-0255 | ISOLATOR, WALL MOUNT WEATHERPROOF, 3 POLE, 32A | 56472 | 2024-03-09 |  | WDOAPPR | 3 | EA | 1 | 52 | 52 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 5975-60-V00-0505 | STUFFING TUBE (CABLE GLAND), PG16, POLYAMIDE, GRAY, 9 -14 MM | 56472 | 2024-03-09 |  | WDOAPPR | 2 | EA | 4 | 2.96 | 11.84 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 4730-60-V00-0594 | C-CLAMP W/ RUBBER, GALVANIZED STEEL, 2 INCHES | 56470 | 2024-03-09 |  | WDOAPPR | 2 | EA | 4 | 9.4 | 37.6 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 4710-60-V00-0110 | PIPE, PLASTIC, SCH-80, CPVC, OFF-WHITE, 3/4 INCH | 56470 | 2024-03-09 |  | WDOAPPR | 1 | EA | 1 | 17.5 | 17.5 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 4130-60-V00-0137 | MOUNTING BASE, AIR-CONDITIONER, POLYPROPYLENE, IVORY, 17 X 3 X 5.12 INCHES | 56471 | 2024-03-09 |  | WDOAPPR | 1 | PG | 1 | 68 | 68 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 8030-60-V00-0053 | FOAM, CONSTRUCTION, CREAM, 700ML | 56472 | 2024-03-09 |  | WDOAPPR | 1 | EA | 1 | 19.5 | 19.5 | [16 empty] | BU | BU table | March | 2024 | MM_BU
91 | 2024-03-07 | 50 | BU24-0174 | Correct TI deficiencies ECP1 Breakroom | 9978852 | 6350-60-V00-0102 | ALARM, SMOKE, AUTOMATIC, PLASTIC | 56469 | 2024-03-09 |  | WDOAPPR | 1 | EA | 1 | 28.71 | 28.71 | [16 empty] | BU | BU table | March | 2024 | MM_BU
92 | 2024-03-09 | 40 | BU24-0143 | Install Overhead Lights B9501AB | 9360741 | 6210-60-V00-0095 | FIXTURE, LIGHTING, w/ EMERGENCY BATTERY, LED, RETROFIT, PURE WHITE, 200-240V, 40W | 56500 | 2024-03-09 |  | WDOAPPR | 2 | EA | 3 | 260.02 | 780.06 | [15 empty] | Additional material request | BU | BU table | March | 2024 | MM_BU
92 | 2024-03-09 | 40 | BU24-0143 | Install Overhead Lights B9501AB | 9360741 | 5306-60-V00-0117 | BOLT, TOGGLE, ROUND HEAD, BRASS, 3/16 X 2-1/2 INCHES | 56501 | 2024-03-09 |  | WDOAPPR | 1 | EA | 30 | 1.49 | 44.7 | [16 empty] | BU | BU table | March | 2024 | MM_BU
92 | 2024-03-09 | 40 | BU24-0143 | Install Overhead Lights B9501AB | 9360741 | 5975-60-V00-0475 | JUNCTION BOX, IRON, 4 X 4 INCHES | 56500 | 2024-03-09 |  | WDOAPPR | 1 | EA | 10 | 27 | 270 | [16 empty] | BU | BU table | March | 2024 | MM_BU
93 | 2024-03-10 |  | BU24-0129 | Relocate Retention Pond RP6002 |  |  |  | PRINPRG | [24 empty] | BU | BU table | March | 2024 | MM_BU
1 | 2022-05-13 |  | AJ21-0177 | BLDG 540 Hanel Lean-Lift Power Panel and Equipment Installation | 1194736 | FABRICATION | FABRICATION POWER DFISTRIBUTION PANEL 12 way | 32165 | 2022-05-13 | 2022-05-13 |  | 1 | EA | 1 | [6 empty] | LCVKW0302S | 1 | [5 empty] | 2022-08-17 | COMP | 2022-08-21 | 1 | Vendor Submittal approved 5 July 22 | AJ | Fab table | May | 2022 | AJ_Fabrication
2 | 2022-05-16 |  | AJ22-0074 | MP23LM2 | 1234123 | FABRICATION | FABRICATION PANEL, POWER DISTRIBUTION , 8WAY , 415V, 63AMPS, 3PHASE | 32198 | 2022-05-16 | 2022-05-16 |  | 2 | EA | 1 | [6 empty] | LCVKW0313S | 2 | [5 empty] | 2022-07-15 | COMP | 2022-07-21 | 1 |  | AJ | Fab table | May | 2022 | AJ_Fabrication
3 | 2022-05-26 |  | AJ22-0081 | RLB T6044 Relocation and Modification | 1368335 | FABRICATION | FABRICATION PANEL WITH DISCONNECT SWITCH | 32698 | 2022-05-26 | 2022-05-26 |  | 2 | AY | 2 | [6 empty] | LCVKW0312S | N/A | [5 empty] | 2022-07-15 | COMP | 2022-07-22 | 2 |  | AJ | Fab table | May | 2022 | AJ_Fabrication
3 | 2022-06-01 |  | AJ22-0081 | RLB T6044 Relocation and Modification | 1368335 | FABRICATION | FABRICATION DOOR WITH FRAME | 32848 | 2022-06-01 | 2022-06-01 |  | 1 | AY | 11 | [6 empty] | LCVKW0320S | N/A | [5 empty] | 2022-07-28 | COMP | 2022-08-01 | 11 | Materials Recived | AJ | Fab table | June | 2022 | AJ_Fabrication
4 | 2022-06-23 |  | AJ22-0044 | Replace 65 Street Light Heads | 2238765 | FABRICATION | FABRICATION OF LIGHT POLE BRACKET ASPER THE DRAWING, SOUTH ABRAMS, FABRICATION OF BRACKET ASPER THE DRAWING, | 33968 | 2022-06-23 | 2022-06-23 |  | 1 | EA | 63 | [6 empty] | LCVKW0341S | 1 | [5 empty] | 2022-10-15 | COMP | 2022-10-15 | 63 |  | AJ | Fab table | June | 2022 | AJ_Fabrication
5 | 2022-07-07 |  | AJ22-0067 | T725 Power Outlets and Equipment Install | 2141547 | FABRICATION | FABRICATION PANEL (INDOOR PANEL), 32A 1POLE RCBO-1EA, 25A 1 POLE RCBO -3EA, 20A 1 POLE RCBO-6EA,16A 1 POLE RCBO-2EA | 34654 | 2022-07-07 | 2022-07-08 |  | 1 | AY | 1 | [6 empty] | LCVKW0350S | 1 | [5 empty] | 2022-09-16 | COMP | 2022-09-16 | 1 | Vendor Submittal approved 20 Aug 22 | AJ | Fab table | July | 2022 | AJ_Fabrication
6 | 2022-07-28 |  | AJ22-0265 | Joint Portal Shield Biological Detection Sensor | 2671164 | FABRICATION | FABRICATION, OUTDOOR PANEL AND 40A MCCB 3 POLE BREAKER WITH STAND | 35777 | 2022-07-28 | 2022-08-04 |  | 1 | AY | 3 | [6 empty] | LCVKW0357S | 1 | [5 empty] | 2022-09-30 | COMP | 2022-09-30 | 3 |  | AJ | Fab table | July | 2022 | AJ_Fabrication
7 | 2022-08-31 |  | AJ22-0105 | T340 Security Features Install | 2621467 | FABRICATION | SINGLE WOODEN DOOR, SOLID WOODEN DOOR THICKNESS IS 1-3/4” (3'X7') WITH GYPSUM BOARD METAL FRAME(FABRICATION SERVICES) | 37171 | 2022-08-31 | 2022-09-10 |  | 1 | EA | 8 | [6 empty] | LCVKW0390S | 1 | [5 empty] | 2022-10-18 |  |  |  |  | AJ | Fab table | August | 2022 | AJ_Fabrication
7 | 2022-08-31 |  | AJ22-0105 | T340 Security Features Install | 2621467 | FABRICATION | DOUBLE DOOR, SOLID WOODEN DOOR THICKNESS IS 1-3/4”(6'X7') (WOODEN) WITH GYPSUM BOARD METAL FRAME(FABRICATION SERVICES) | 37171 | 2022-08-31 | 2022-09-10 |  | 2 | EA | 1 | [6 empty] | LCVKW0390S | 2 | [5 empty] | 2022-10-18 |  |  |  |  | AJ | Fab table | August | 2022 | AJ_Fabrication
7 | 2022-08-31 |  | AJ22-0105 | T340 Security Features Install | 2621467 | FABRICATION | WINDOWS SECURITY ALUMINIUM BAR FOR EXTERNAL WINDOWS(4'X3'5.5") (FABRICATION SERVICES) | 37171 | 2022-08-31 | 2022-09-10 |  | 3 | EA | 22 | [6 empty] | LCVKW0390S | 3 | [5 empty] | 2022-10-18 |  |  |  |  | AJ | Fab table | August | 2022 | AJ_Fabrication
7 | 2022-08-31 |  | AJ22-0105 | T340 Security Features Install | 2621467 | FABRICATION | WINDOWS SECURITY ALUMINIUM BAR FOR EXTERNAL DOOR WINDOWS WITH FLEXI GLASS (1'X1'4") (FABRICATION SERVICES) | 37171 | 2022-08-31 | 2022-09-10 |  | 4 | EA | 5 | [6 empty] | LCVKW0390S | 4 | [5 empty] | 2022-10-18 |  |  |  |  | AJ | Fab table | August | 2022 | AJ_Fabrication
8 | 2022-09-18 |  | AJ22-0137 | Vectrus Tent 1 Relocation | 2238613 | FABRICATION | FABRICATION OF 2 NEW 90-DEGREE ELBOW TRANSITION DUCTS | 37556 | 2022-09-18 | 2022-09-21 |  | 1 | AY | 2 | [6 empty] | LCKW0404S | [6 empty] | 2022-10-11 | COMP | 2022-10-30 | 2 |  | AJ | Fab table | September | 2022 | AJ_Fabrication
9 | 2022-09-18 |  | AJ22-0138 | Vectrus Tent 2 Relocation | 2238650 | FABRICATION | FABRICATION OF 2 NEW 90-DEGREE ELBOW TRANSITION DUCTS | 37558 | 2022-09-18 | 2022-09-21 |  | 1 | EA | 2 | [6 empty] | LCKW0404S | [6 empty] | 2022-10-11 | COMP | 2022-10-30 | 2 | 2 | AJ | Fab table | September | 2022 | AJ_Fabrication
10 | 2022-09-18 |  | AJ22-0139 | Vectrus Tent 3 Relocation | 2238605 | FABRICATION | FABRICATION OF 2 NEW 90-DEGREE ELBOW TRANSITION DUCTS | 37559 | 2022-09-18 | 2022-09-21 |  | 1 | EA | 2 | [6 empty] | LCKW0404S | [6 empty] | 2022-10-11 | COMP | 2022-10-01 | 2 |  | AJ | Fab table | September | 2022 | AJ_Fabrication
11 | 2022-09-18 |  | AJ22-0140 | Vectrus Tent 4 Relocation | 2238683 | FABRICATION | FABRICATION OF 2 NEW 90-DEGREE ELBOW TRANSITION DUCTS | 37560 | 2022-09-18 | 2022-09-21 |  | 1 | EA | 2 | [6 empty] | LCKW0404S | [6 empty] | 2022-10-11 | COMP | 2022-10-01 | 2 |  | AJ | Fab table | September | 2022 | AJ_Fabrication
12 | 2022-09-18 |  | AJ22-0141 | Vectrus Tent 5 Relocation | 2238643 | FABRICATION | FABRICATION OF 2 NEW 90-DEGREE ELBOW TRANSITION DUCTS | 37561 | 2022-09-18 | 2022-09-21 |  | 1 | EA | 2 | [6 empty] | LCKW0404S | [6 empty] | 2022-10-11 | COMP | 2022-10-11 | 2 |  | AJ | Fab table | September | 2022 | AJ_Fabrication
13 | 2022-09-18 |  | AJ22-0142 | Vectrus Tent 6 Relocation | 2238633 | FABRICATION | FABRICATION OF 2 NEW 90-DEGREE ELBOW TRANSITION DUCTS | 37554 | 2022-09-18 | 2022-09-21 |  | 1 | EA | 2 | [6 empty] | LCKW0404S | [6 empty] | 2022-10-11 | COMP | 2022-10-11 | 2 |  | AJ | Fab table | September | 2022 | AJ_Fabrication
14 | 2022-09-18 |  | AJ22-0143 | Vectrus Tent 7 Relocation | 2539656 | FABRICATION | FABRICATION OF 2 NEW 90-DEGREE ELBOW TRANSITION DUCTS | 37555 | 2022-09-18 | 2022-09-21 |  | 1 | EA | 2 | [6 empty] | LCKW0404S | [6 empty] | 2022-10-11 | COMP | 2022-10-11 | 2 |  | AJ | Fab table | September | 2022 | AJ_Fabrication
15 | 2022-09-29 |  | AJ22-0145 | Z7 Utility Infrastructure-Power Generation | 2219753 | FABRICATION | MDP (OUTDOOR): AIR CIRCUIT BREAKERS(ACB) 1250A, BRANCH: 3Px160A, 6EA , 3Px 300A, 1EA, 3Px 63A, 1EA, SPARE BLANK 2EA, W/ STAND | 45822 | 2022-09-29 | CANCELLED |  |  | EA | 1 | [18 empty] | AJ | Fab table | September | 2022 | AJ_Fabrication
15 | 2022-09-29 |  | AJ22-0145 | Z7 Utility Infrastructure-Power Generation | 2219753 | FABRICATION | DISCONNECT SWITCH(OUTDOOR): 4Px100A W/ STAND | 45822 | 2022-09-29 | 2023-05-10 |  | 1 | EA | 4 | [6 empty] | LCVKW0637S | [11 empty] | AJ | Fab table | September | 2022 | AJ_Fabrication
15 | 2022-09-29 |  | AJ22-0145 | Z7 Utility Infrastructure-Power Generation | 2219753 | FABRICATION | DISCONNECT SWITCH(OUTDOOR): 4Px63A W/ STAND | 45822 | 2022-09-29 | 2023-05-10 |  | 2 | EA | 1 | [6 empty] | LCVKW0637S | [11 empty] | AJ | Fab table | September | 2022 | AJ_Fabrication
15 | 2022-09-29 |  | AJ22-0145 | Z7 Utility Infrastructure-Power Generation | 2219753 | FABRICATION | MANUAL TRANSFER SWITCH, MTS (OUTDOOR) 4Px2000A, W/ STAND | 45822 | 2022-09-29 | 2023-05-10 |  | 3 | EA | 1 | [6 empty] | LCVKW0637S | [11 empty] | AJ | Fab table | September | 2022 | AJ_Fabrication
16 | 2022-10-05 |  | AJ22-0156 | RMOs Motor Pool 19 | 2854733 | FABRICATION | FABRICATION, 8 WAY PANEL, MCB, IP54 APPROVED SUBMITTAL VIA TRANSMITTAL # AJ220156-LCV-ELE-MTL-0001 DATED 2022-09-15 | 38064 | 2022-10-05 | 2022-10-05 |  |  | AY | 1 | [6 empty] | PO KW1-6993 | [6 empty] | 2023-01-31 |  |  |  |  | AJ | Fab table | October | 2022 | AJ_Fabrication
17 | 2022-11-22 |  | AJ22-0248 | ZONE 1 B209 | 2969436 | FABRICATION | FABRICATION, DISTRIBUTION BOARD (DB-220/415V ), FABRICATION, DISTRIBUTION BOARD ( DB-120/230V ) | 39709 | 2022-11-22 | 2022-11-23 |  |  | AY | 1 | [18 empty] | AJ | Fab table | November | 2022 | AJ_Fabrication
18 | 2023-01-19 |  | AJ22-0135 | Replace 65 Street Light Heads | 238765 | FABRICATION | FABRICATION OF BRACKET ASPER THE DRAWING, ALUMINUM TAPERED ELLIPTICAL BRACKET (4 FEET LENGTH) (PATTON BLVD) ( INCLUDING ALL THE NUTS, BOLTS, SCREWS AND WASHER | 41504 | 2023-01-19 | 2023-01-21 |  | 1 | AY | 27 | [6 empty] | LCVKW0522S | [6 empty] | 2023-03-08 | COMP | 2023-04-04 | 1 |  | AJ | Fab table | January | 2023 | AJ_Fabrication
19 | 2023-03-12 |  | AJ22-0143, | Vectrus Tent 7 Relocation |  | FABRICATION | FABRICATION OF SOLID CORE WOOD DOORS AND METAL ,FRAMES, SARGENT PUSH BARS (CATALOG: 5340-60-V00-0169 ) SARGENT LEVER DOOR HANDLE | 44110 | 2023-03-12 | 2023-03-28 |  |  | AY | 2 | [18 empty] | AJ | Fab table | March | 2023 | AJ_Fabrication
20 | 2023-03-16 |  | AJ23-0089 | B314 Backup Power Connection |  | FABRICATION | FABRICATION, MSB-2 WAYS ( INCOMER 250A) , APPROVED SUBMITTAL VIA TRANSMITTAL # AJ230089-LCV-ELE-DSN-0001 | 43694 | 2023-03-16 | 2023-03-16 |  |  | AY | 1 | [6 empty] | LCVKW0574S | 1 | [10 empty] | AJ | Fab table | March | 2023 | AJ_Fabrication
21 | 2023-04-13 |  | AJ23-0122 | Z1 Pool Water Leak | 5434294 | FABRICATION | READY MADE CONCRETE MIX (4000 PSI) CONCRETE STRENGTH (TYPE-K-300-4000PSI) | 44816 | 2023-04-13 | 2023-04-17 |  | 1 | CUM | 5 | [18 empty] | AJ | Fab table | April | 2023 | AJ_Fabrication
23 | 2023-04-16 |  | AJ23-0413 | Z6 Patton Pipe Repair | 2874083 | FABRICATION | READY MADE CONCRETE MIX (4000 PSI) CONCRETE STRENGTH (TYPE-K-300-4000PSI) | 44798 | 2023-04-16 | 2023-04-16 |  | 1 | CUM | 6 | [18 empty] | AJ | Fab table | April | 2023 | AJ_Fabrication
26 | 2023-05-30 |  | AJ23-0467 | FSLIDs Container Power Connection | 4982395 | FABRICATION | FABRICATION PANEL, DISTRIBUTION BOARD IP-65, 120V,40A,60HZ 10ka | 46730 | 2023-05-30 | 2023-05-31 |  |  | AY | 1 | [18 empty] | AJ | Fab table | May | 2023 | AJ_Fabrication
26 | 2023-06-06 |  | AJ23-0467 | Warehouse 532 Power for Four Lift Storage Systems | 5967149 | FABRICATION | FABRICATION, PANEL (MAIN BREAKER-63A 3 POLE MCCB SUB BREAKERS 30MA 20A 3 POLE MCB (4EA) TWO SPACE INDOOR DB PANEL) | 48005 | 2023-06-06 | 2023-07-06 |  |  | AY | 2 | [6 empty] | LCVKW0681S | [11 empty] | AJ | Fab table | June | 2023 | AJ_Fabrication
26 | 2023-07-26 |  | AJ23-0467 | Electrical Outlets | 424782 | FABRICATION | FABRICATION, POWER OUTLETS STAND (METAL HOLLOW) (20"x12"x4") SEE ATTACHED DRAWING | 48795 | 2023-07-26 | 2023-07-26 |  |  | AY | 2 | [18 empty] | AJ | Fab table | July | 2023 | AJ_Fabrication
27 | 2023-09-10 |  | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | FABRICATION | FABRICATION, SERVICES METAL STAIR 1.5M WIDTH X 1.84M DEPTH AND 1M HEIGTH HANDRAIL, STEEL PLATE LANDING WITH DIAMOND GRATING FABRICATION SERVICES ALUMINUM SLIDING WINDOW WITH FRAME 100X120CM WITH SECONDARY SLIDING MESH PROCESSED BY (BUYER) PROMISED SHIPPING DATE Are these items ITAR controlled? METAL DOOR KNOCK OUT TYPE FRAME, JAMB LIP OPENING 12CM, DOOR LEAF PANEL 4.5 CM X 86CM X 202CM W/ HINGES,PUSH BAR MORTISE TYPE LEVER HANDLE, LEFT HAND REVERSE PRIMERED AND PAINTED TAN COLOR SMOOTH FINISH. (VENDOR SITE VISIT REQUIRED) FABRICATION SERVICE SIGN BOARDS T5802 (FABRICATION SERVICE) METAL STAND,CARRIER OUTDOOR SPLIT UNIT.SIZE:39.5" L X 19" W X 12" H (2"X2" ANGLE BAR THICKNESS 5MM) (SEE ATTACHED FABRICATION SOW AND DRAWINGS) | 50407 | 2023-09-10 |  |  | 1 | AY | 15 | [18 empty] | AJ | Fab table | September | 2023 | AJ_Fabrication
28 | 2023-09-13 |  | AJ23-0366 | TI Repairs | 7162722 | FABRICATION | FABRICATION ITEMS | 50407 | 2023-09-13 | 2023-09-13 |  |  | AY | 15 | [18 empty] | AJ | Fab table | September | 2023 | AJ_Fabrication
30 | 2023-10-22 |  | AJ23-0508 | Technical Inspection Repairs, T5802 | 7162722 | FABRICATION | FABRICATION PANEL, DB APPROVED SUBMITTAL VIA TRANSMITTAL# AJ230508-LCV-ELE-MTL- 0001 | 52073 | 2023-10-22 |  |  | 1 | AY | 1 | [18 empty] | AJ | Fab table | October | 2023 | AJ_Fabrication
31 | 2023-11-01 |  | AJ22-0135 | Install Smart Electric Meters | 8018616 | FABRICATION | FABRICATION, SCHNEIDER ELECTRIC (SE)FABRICATION, NEMA 4X CUSTOM ENCLOSURE, EACH WITH (1) INSTALLED PM5563 METER. THE ENCLOSURE TO INCLUDE THE FOLLOWING:PM5563 RD METER, FACTORY ASSEMBLED (WIRED) NEMA 4X ENCLOSURE, POWER SUPPLY,CONTROL POWER TRANSFORMER, FIBER MEDIA CONVERTER FUSE BLOCKS PROTECTION. (SEE ATTACHED APPROVED 4025) | 52595 | 2023-11-01 | 2023-11-08 |  |  | AY | 1 | [18 empty] | AJ | Fab table | November | 2023 | AJ_Fabrication
33 | 2023-11-02 |  | AJ22-0135 | Relocation of Building 370 from Z1 to Z7(IMD) | 7116535 | FABRICATION | FABRICATION PANEL, DB APPROVED SUBMITTAL VIA TRANSMITTAL# AJ230467-LCV-ELE-DSN- 0001 | 52514 | 2023-11-02 | 2023-11-06 |  |  | AY | 1 | [18 empty] | AJ | Fab table | November | 2023 | AJ_Fabrication
33 | 2023-11-02 |  | AJ22-0135 | Replacement of Isolator Panel and Suction Pumps B169 Z1 | 7641976 | FABRICATION | FABRICATION CONTROL PANEL, APPROVED SUBMITTAL VIA TRANSMITTAL# AJ230726-LCVGEN- MTL-0001 | 52516 | 2023-11-02 | 2023-11-06 |  |  | AY | 1 | [18 empty] | AJ | Fab table | November | 2023 | AJ_Fabrication
33 | 2023-11-02 |  | AJ22-0135 | CT Scanner Site Prep and Installation | 7922463 | FABRICATION | READY MADE CONCRETE MIX (4000 PSI) CONCRETE STRENGTH (TYPE-K-300-4000PSI) | 52448 | 2023-11-02 | 2023-11-02 |  |  | CUBIC | 8 | [18 empty] | AJ | Fab table | November | 2023 | AJ_Fabrication
34 | 2023-11-26 |  | AJ22-0551 | Provide electrical connection for CCTV installation for 17 buildings | 7249685 | FABRICATION | DB (DISTRIBUTION PANEL) APPROVED SUBMITTAL VIA TRANSMITTAL# AJ220551-LCV-ELEDSN- 0001 (SEE ATTCHED APPROVED SUBMITTAL) | 53320 | 2023-11-26 | 2023-12-01 |  |  | LT | 1 | [6 empty] | LCVKW0923S | 1 |  |  |  |  | AL NISF ELECTRICAL CO WLL | 2024-01-21 |  |  |  | CANCELLED | AJ | Fab table | November | 2023 | AJ_Fabrication
34 | 2023-11-26 |  | AJ22-0551 | Provide electrical connection for CCTV installation for 17 buildings | 7249685 | FABRICATION | FABRICATION, SPD BOX IP65 8 x 6 x 6in (HxWxD) (SEE ATTACHED DRAWING) | 53320 | 2023-11-26 | 2023-12-01 |  |  | LT | 1 | [6 empty] | LCVKW0923S | 2 |  |  |  |  | AL NISF ELECTRICAL CO WLL | 2024-01-21 |  |  |  | CANCELLED | AJ | Fab table | November | 2023 | AJ_Fabrication
34 | 2023-11-26 |  | AJ22-0551 | Provide electrical connection for CCTV installation for 17 buildings | 7249685 | FABRICATION | FABRICATION, STAND (SEE ATTACHED DRAWING) | 53320 | 2023-11-26 | 2023-12-01 |  |  | LT | 12 | [6 empty] | LCVKW0925S | 3 |  |  |  |  | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-01-21 |  |  |  | CANCELLED | AJ | Fab table | November | 2023 | AJ_Fabrication
35 | 2023-12-13 |  | AJ23-0512 | CLVB RLB Upgrade | 8139100 | FABRICATION | FABRICATION, PANEL (DB) , APPROVED SUBMITTAL VIA TRANSMITTAL# AJ230512-LCV-ELEDSN- 0001.01 | 54010 | 2023-12-13 | 2023-12-17 |  | 1 | LT | 1 | 1148 | 1148 |  |  |  |  | LCVKW0950S | 1 |  |  |  |  | AL NISF ELECTRICAL CO WLL |  | COMP | 2024-02-10 |  |  | AJ | Fab table | December | 2023 | AJ_Fabrication
36 | 2023-12-13 |  | AJ23-0536 | Electrical & Carpentry B1005 Z6, | 8379855 | FABRICATION | FABRICATION, PANEL MDB , APPROVED SUBMITTAL VIA TRANSMITTAL# AJ230536-LCV-ELEMTL- 0001 | 54009 | 2023-12-13 | 2023-12-17 |  | 1 | LT | 1 | 4430 | 4430 |  |  |  |  | LCVKW0949S | [5 empty] | AL NISF ELECTRICAL CO WLL | 2023-01-21 | COMP |  |  | Delivery completed | AJ | Fab table | December | 2023 | AJ_Fabrication
36 | 2023-12-13 |  | AJ23-0536 | Electrical & Carpentry B1005 Z6, | 8379855 | FABRICATION | FABRICATION, OUTDOOR OUTLET STAND (SEE ATTCHED DRAWING) | 54009 | 2023-12-13 | 2023-12-17 |  | 2 | LT | 6 | 179 | 1074 |  |  |  |  | LCVKW0949S | [5 empty] | AL NISF ELECTRICAL CO WLL | 2024-02-15 |  |  |  |  | AJ | Fab table | December | 2023 | AJ_Fabrication
40 | 2023-12-19 |  | AJ21-0011 | 43 Electrical Meter Installation, | 5171089 | FABRICATION | FABRICATION, SCHNEIDER ELECTRIC (SE)FABRICATION, SCHNEIDER ELECTRIC (SE) NEMA 4X CUSTOM ENCLOSURE, EACH | 54208 | 2023-12-19 | 2023-12-21 |  | 1 | LT | 33 | 221970.87 | 221970.87 |  |  |  |  | LCVKW0657S | 1 | 2024-02-05 |  |  |  | Schneider | 2024-05-02 |  |  |  | IFS PR COMPLETED | AJ | Fab table | December | 2023 | AJ_Fabrication
41 | 2023-12-19 |  | AJ21-0011 | 43 Electrical Meter Installation, | 5171089 | FABRICATION | CURRENT TRANSFORMER (CT) | 54208 | 2023-12-19 | 2023-12-21 |  | 2 | LT | 99 | 31747.47 | 31747.47 |  |  |  |  | LCVKW0657S | 2 | 2024-02-05 |  |  |  | Schneider | 2024-05-02 |  |  |  | IFS PR COMPLETED | AJ | Fab table | December | 2023 | AJ_Fabrication
44 | 2023-12-12 |  | AJ23-0788 | Replace electrical panel for TT7011 | 7996575 | FABRICATION | FABRICATION, PANEL MDB , APPROVED SUBMITTAL VIA TRANSMITTAL# AJ230788-LCV-ELEDSN- 0001 | 54414 | 2023-12-12 | 2023-12-31 |  | 1 | LT | 1 | 4317.1 | 4317.1 |  |  |  |  | LCVKW0983 | [5 empty] | AL NISF ELECTRICAL CO WLL | 2024-02-15 | COMP | 2024-02-10 |  | IFS PR COMPLETED | AJ | Fab table | December | 2023 | AJ_Fabrication
46 | 2023-11-01 |  | AJ23-0726 | Replacement of Isolator Panel and Suction Pumps | 7641976 | FABRICATION | FABRICATION CONTROL PANEL, APPROVED SUBMITTAL VIA TRANSMITTAL# AJ230726-LCVGEN- MTL-0001 | 52516 | 2023-11-02 | 2023-11-06 |  | 1 | LT | 1 | 4929 | 4929 |  |  |  |  | LCVKW0885S | [5 empty] | AL NISF ELECTRICAL CO WLL | 2024-01-21 | COMP |  |  | Delivery completed | AJ | Fab table | November | 2023 | AJ_Fabrication
47 | 2023-11-12 |  | AJ22-0465 | Zone 7 Fire Station 4 Refer Power Connection | 7116535 | FABRICATION | FDP (FINAL DISTRIBUTION PANEL) APPROVED SUBMITTAL VIA TRANSMITTAL# AJ220465-LCVELE- MTL-0001 (SEE ATTCHED APPROVED SUBMITTAL) | 52715 | 2023-11-12 | 2023-11-12 |  | 1 | LT | 1 | 2300.31 | 2300.31 |  |  |  |  | LCVKW0903S | [5 empty] | AL NISF ELECTRICAL CO WLL | 2024-01-21 | COMP | 2024-02-21 |  | IFS PR COMPLETED | AJ | Fab table | November | 2023 | AJ_Fabrication
48 | 2023-12-29 |  | AJ24-0065 | Zone 2 B505 ASG 511 Connection to Support ASG 014 | 8038045 | FABRICATION | MTS-2000A | 55085 | 2024-01-20 | 2024-01-22 |  | 1 | LT | 1 | 10437.9 | 10437.9 |  |  |  |  | LCVKW1014S | [5 empty] | AL NISF ELECTRICAL CO WLL | 2024-02-29 | COMP | 2024-02-10 |  | IFS PR COMPLETED | AJ | Fab table | December | 2023 | AJ_Fabrication
49 | 2024-01-03 |  | AJ23-0512 | CLVB RLB Upgrade | 8139100 | FABRICATION | MDB | 55228 | 2024-01-20 | 2024-01-24 |  | 1 | LT | 1 | 1750.85 | 1750.85 |  |  |  |  | LCVKW1029S | [5 empty] | AL NISF ELECTRICAL CO WLL | 2024-02-21 | COMP | 2024-02-21 |  | IFS PR COMPLETED | AJ | Fab table | January | 2024 | AJ_Fabrication
50 | 2024-01-31 |  | AJ24-0202 | Z7 CRSP Yard SS812 Elec Repairs |  | FABRICATION | LDB | [24 empty] | Vendor submittal received 1 Feb | AJ | Fab table | January | 2024 | AJ_Fabrication
51 | 2024-02-14 |  | AJ24-0203 | MAIN FEEDER CABLE DAMAGED NEED TO REPLACE |  | FABRICATION | MSB 100A , 4 WAYS 415/240V 100A 50H | PWD-ELEC-PANEL-PWO-AJ24-0203-4065.1 | 2024-03-05 |  |  | 1 | LT | 1 | 2211 | 2211 | [16 empty] | AJ | Fab table | February | 2024 | AJ_Fabrication
52 | 2024-02-29 |  | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | FABRICATION | DB-1, INDOOR IP 42, Main 63A |  |  |  |  | 1 | AY | [18 empty] | Vendor Suibmittal received 3Mar24 | AJ | Fab table | February | 2024 | AJ_Fabrication
52 | 2024-02-29 |  | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | FABRICATION | DB-2, INDOOR IP 42, Main 80A |  |  |  |  | 1 | AY | [19 empty] | AJ | Fab table | February | 2024 | AJ_Fabrication
52 | 2024-02-29 |  | AJ23-0789 | B572 New HVAC Install, Z7 | 9722230 | FABRICATION | BUS BAR FABRICATION (AJ MDP 1600A )https://www.bahra-electric.com/Products/Busbars.aspx |  |  |  |  | 1 | AY | [19 empty] | AJ | Fab table | February | 2024 | AJ_Fabrication
53 | 2024-02-14 |  | AJ23-0551 | SPOD T5 Refurbishment | 6443145 | FABRICATION | MDP PANEL 125A 6 WAYS |  |  |  |  | 1 | AY | [18 empty] | Vewndor submittal received 14 Feb | AJ | Fab table | February | 2024 | AJ_Fabrication
1 | 2023-12-16 |  | BU24-0095 | Install Vestibule Doors Z5 Pad21 TT14 | 8563372 | FABRICATION | FABRICATE METAL DOOR WITH METAL FRAME, CYPHER LOCK, PANIC BAR AND DOOR CLOSURE (SEE ATTCHED DRAWING AND SOW ) | 54270 | 2023-12-16 | 2023-12-24 | CLOSE | 1 | LT | 2 | 5224.66 | 10449.32 |  |  |  |  | LCVKW0995S | 1 | 2024-01-16 | APPR |  | SHIJO | EGYKUW | 2024-02-29 | COMP | 2024-03-05 | 1 | Rev-1 EDD March 10 | BU | Fab table | December | 2023 | BU_Fabrication
2 | 2023-12-16 |  | BU24-0096 | Install Vestibule Doors Z5 Pad21 TT09 | 8564095 | FABRICATION | FABRICATE METAL DOOR WITH METAL FRAME, CYPHER LOCK, PANIC BAR AND DOOR CLOSURE (SEE ATTCHED DRAWING AND SOW ) | 54279 | 2023-12-16 | 2023-12-24 | CLOSE | 1 | LT | 2 | 5224.66 | 10449.32 |  |  |  |  | LCVKW0995S | 1 | 2024-01-16 | APPR |  | SHIJO | EGYKUW | 2024-02-29 | COMP | 2024-03-05 | 1 | Rev-1 EDD March 10 | BU | Fab table | December | 2023 | BU_Fabrication
3 | 2023-12-19 |  | BU22-0007 | Install 50 Electrical Meters | 4103915 | FABRICATION | FABRICATION, SCHNEIDER ELECTRIC (SE)FABRICATION, SCHNEIDER ELECTRIC (SE) NEMA 4X CUSTOM ENCLOSURE, EACH | 54209 | 2023-12-19 | 2023-12-21 | APPR | 1 | LT | 40 | 269055.6 | 269055.6 |  |  |  |  | LCVKW0657S | 1 | 2024-02-05 | APPR |  | ROJAS | Schneider | 2024-05-02 |  |  |  | IFS PR COMPLETED | BU | Fab table | December | 2023 | BU_Fabrication
4 | 2023-12-19 |  | BU22-0007 | Install 50 Electrical Meters | 4103915 | FABRICATION | CURRENT TRANSFORMER (CT) | 54209 | 2023-12-19 | 2023-12-21 | APPR | 1 | LT | 120 | 17274.27 | 17274.27 |  |  |  |  | LCVKW0657S | 2 | 2024-02-05 | APPR |  | ROJAS | Schneider | 2024-05-02 |  |  |  | IFS PR COMPLETED | BU | Fab table | December | 2023 | BU_Fabrication
5 | 2023-12-24 |  | BU24-0093 | Change Door Z1 B100 RM127 | 8564196 | FABRICATION | FABRICATE METAL DOOR WITH CIPHER LOCK AS PER APPROVED DESIGN. INCLUDES PANICPUSH BAR, SARGENT HEAVY DUTY DOOR CLOSER AND CIPHER LOCK | 54415 | 2023-12-25 | 2023-12-31 | CLOSE | 1 | LT | 1 | 4052.91 | 4052.91 |  |  |  |  | LCVKW0995S | 1 | 2024-01-16 | APPR |  | SHIJO | EGYKUW | 2024-02-16 | COMP | 2024-03-05 | 1 | Rev-1 EDD March 10 | BU | Fab table | December | 2023 | BU_Fabrication
6 | 2024-01-07 |  | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | FABRICATION | Wooden door w/ 10cm frame x 90 x 210Cm pre painted w/ hinges,door locks lever type and thumblatch, sargeant locks, rigth hand (Lock set, mortise, 8205 series, office/entry, 2-3/4 inches ; manufacturer: sargent) | 54848 | 2024-01-14 | 2024-01-14 | APPR | 1 | AY | 2 | 2640 | 5280 |  |  |  |  | LCVKW1002S | 1 | 2024-01-18 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-18 | COMP | 2024-02-07 |  |  | BU | Fab table | January | 2024 | BU_Fabrication
7 | 2024-01-07 |  | BU24-0117 | Construct Dividing Walls Z5 TT523 | 8944832 | FABRICATION | Wooden door w/ 10cm frame x 100 x 210Cm pre- painted w/ hinges,door locks lever type and thumblatch, sargeant locks, rigth hand (Lock set, mortise, 8205 series, office/entry, 2-3/4 inches ; manufacturer: sargent) | 54848 | 2024-01-14 | 2024-01-14 | APPR | 2 | AY | 1 | 2640 | 2640 |  |  |  |  | LCVKW1002S | 2 | 2024-01-18 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-18 | COMP | 2024-02-07 |  |  | BU | Fab table | January | 2024 | BU_Fabrication
8 | 2024-01-08 |  | BU23-0193 | Z2 TT2071 Build Out | 6871039 | FABRICATION | DB (DISTRIBUTION PANEL) | 55258 | 2024-01-24 | 2024-01-25 | APPR | 1 | AY | 1 | 2333.1 | 2333.1 |  |  |  |  | LCVKW1029S | 1 | 2024-02-04 | APPR |  | SHIJO | AL NISF ELECTRICAL CO WLL | 2023-03-15 |  |  |  | IFS PR COMPLETED | BU | Fab table | January | 2024 | BU_Fabrication
9 | 2024-01-09 |  | BU24-0066 | Repair Sunshade Z3 SS3081 | 8293539 | FABRICATION | FABRICATION WITH MATERIALS OF FRAME AND CANVAS REPAIR (require vendor visit) | 55206 | 2024-01-23 | 2024-01-24 | APPR | 1 | AY | 1 | 15000 | 15000 |  |  |  |  | LCVKW1021S | 1 | 2024-01-29 | APPR |  | SHIJO | GULF PIONEER COMPANY LLC | 2024-02-28 | COMP |  |  |  | BU | Fab table | January | 2024 | BU_Fabrication
10 | 2024-01-09 |  | BU24-0064 | Rev1 Repair Sunshade Z3 SS3082 | 8687667 | FABRICATION | FABRICATION WITH MATERIALS OF FRAME AND CANVAS REPAIR (require vendor visit) | 55203 | 2024-01-23 | 2024-01-24 | APPR | 2 | AY | 1 | 16000 | 16000 |  |  |  |  | LCVKW1021S | 2 | 2024-01-29 | APPR |  | SHIJO | GULF PIONEER COMPANY LLC | 2024-02-28 | COMP |  |  |  | BU | Fab table | January | 2024 | BU_Fabrication
11 | 2024-01-16 |  | BU24-0048 | New Signs ASP Z8 T8000 | 8418200 | FABRICATION | Sign stand 2" x 2" squre tube 84" heigth, 6ft base frame 2" x 3" squre tube with 8 hole 4 hole each side, 1 1/4" diameter for anchor rod. Pls see attached file. (Primed and painted tan color) | 54993 | 2024-01-17 | 2024-01-18 | APPR | 1 | LT | 20 | 645 | 12900 |  |  |  |  | LCVKW1011S | 1 | 2024-01-24 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-24 | COMP | 2024-02-18 |  | IFS PR COMPLETED | BU | Fab table | January | 2024 | BU_Fabrication
13 | 2024-01-16 |  | BU24-0048 | New Signs ASP Z8 T8000 | 8418200 | FABRICATION | Steel rod pointed tip 1' diameter 24" length 2" x 2" square head. | 54993 | 2024-01-17 | 2024-01-18 | APPR | 2 | LT | 125 | 30 | 3750 |  |  |  |  | LCVKW1011S | 2 | 2024-01-24 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-02-24 | COMP | 2024-02-18 |  | IFS PR COMPLETED | BU | Fab table | January | 2024 | BU_Fabrication
12 | 2024-01-27 |  | BU24-0059 | Add T132 to TE | 8528915 | FABRICATION | consumer distribution panel indoor | 56192 | 2024-02-14 | 2024-02-17 | APPR | 2 | LT | 1 | 1914 | 3828 |  |  |  |  | LCVKW1098S | 1 | 2024-03-04 |  |  |  | AL NISF ELECTRICAL CO WLL | 2024-03-30 |  |  |  |  | BU | Fab table | January | 2024 | BU_Fabrication
13 | 2024-01-27 |  | BU24-0059 | Add T132 to TE | 8528915 | FABRICATION | Fabrication of single leaf wooden door with wooden frame, Door closer and Lock set cylindrical mortise (see attached drawing) | 56192 | 2024-02-14 | 2024-02-17 | APPR | 1 | EA | 2 | 541 | 541 |  |  |  |  | LCVKW1092S | 2 | 2024-03-04 |  |  |  | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | January | 2024 | BU_Fabrication
14 | 2024-01-31 |  | BU23-0366 | Connect to MDP Z5 Pad16 TT516 | 8528982 | FABRICATION | FABRICATION, PANEL (DB) DISTRIBUTION BOARD, APPROVED SUBMITTAL VIA TRANSMITTAL # BU230366-LCV-ELE-DSN-0001 (SEE ATTCHED SUBMITTAL | 55610 | 2024-01-31 | 2024-02-01 | APPR | 1 | LT | 1 | 2123.72 | 2123.72 |  |  |  |  | LCVKW1073S | 1 | 2024-02-13 | APPR |  | SHIJO | AL NISF ELECTRICAL CO WLL | 2024-03-13 | COMP | 2024-02-21 |  | IFS PR COMPLETED | BU | Fab table | January | 2024 | BU_Fabrication
15 | 2024-02-07 |  | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | FABRICATION | Wooden door 10cm frame, 90x210Cm, hinges, primed and painted smooth finish, LEFTT hand, (required vendor visit to match the exisitimg door design and color) | 55973 | 2024-02-10 | 2024-02-11 | APPR | 1 | LT | 5 | 1255 | 6275 |  |  |  |  | LCVKW1078S | 1 | 2024-02-17 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 | COMP | 2024-03-02 | 5 |  | BU | Fab table | February | 2024 | BU_Fabrication
15 | 2024-02-07 |  | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | FABRICATION | Wooden door 10cm frame, 90x210Cm, hinges, primed and painted smooth finish, RIGTH hand, (required vendor visit to match the exisitimg door design and color) | 55973 | 2024-02-10 | 2024-02-11 | APPR | 2 | LT | 5 | 1255 | 6275 |  |  |  |  | LCVKW1078S | 2 | 2024-02-17 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 | COMP | 2024-03-02 | 5 |  | BU | Fab table | February | 2024 | BU_Fabrication
15 | 2024-02-07 |  | BU23-241 | INSTALL WALL & CEILING IN ALL ROOM & SIPER ROOM & VISTIBULE REPLACE | 6185444 | FABRICATION | BAR, METAL, FLAT, GALVANIZE STEEL, 1/4 X 1-1/2 INCHES X 20 FEET WITH 18SQMM HOLE 1FT APART | 55973 | 2024-02-10 | 2024-02-11 | APPR | 3 | LT | 30 | 73 | 2190 |  |  |  |  | LCVKW1078S | 3 | 2024-02-17 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024 | BU_Fabrication
16 | 2024-02-07 |  | BU24-0050 | ARTC TT614 Vestibule | 9487106 | FABRICATION | PPGI ROOF SHEET BOX PROFILE,28 GAUGE- COLOR : BEIGE, SIZE 1.8 M X 1 M | 56189 | 2024-02-13 | 2024-02-17 | APPR | 1 | LT | 6 | 16 | 96 |  |  |  |  | LCVKW1089S | 1 | 2024-02-27 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024 | BU_Fabrication
16 | 2024-02-07 |  | BU24-0050 | ARTC TT614 Vestibule | 9487106 | FABRICATION | PPGI WALL SHEET BOX PROFILE,28 GAUGE- COLOR : BEIGE, SIZE 2.25 M X 1.15 M | 56189 | 2024-02-13 | 2024-02-17 | APPR | 2 | LT | 16 | 25 | 400 |  |  |  |  | LCVKW1089S | 2 | 2024-02-27 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024 | BU_Fabrication
16 | 2024-02-07 |  | BU24-0050 | ARTC TT614 Vestibule | 9487106 | FABRICATION | RIDGE - COLOR : BEIGE, SIZE 2.40 M X 0.035 MM | 56189 | 2024-02-13 | 2024-02-17 | APPR | 3 | LT | 4 | 122 | 488 |  |  |  |  | LCVKW1089S | 3 | 2024-02-27 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024 | BU_Fabrication
16 | 2024-02-07 |  | BU24-0050 | ARTC TT614 Vestibule | 9487106 | FABRICATION | FLASHING - COLOR : BEIGE, SIZE 2.40 M X 0.035 MM | 56189 | 2024-02-13 | 2024-02-17 | APPR | 4 | LT | 10 | 122 | 1220 |  |  |  |  | LCVKW1089S | 4 | 2024-02-27 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024 | BU_Fabrication
16 | 2024-02-07 |  | BU24-0050 | ARTC TT614 Vestibule | 9487106 | FABRICATION | METAL DOOR WITH FRAME INCLUDING ACCESSORIES (KABA CIPHER LOCK , SARGENT DOOR CLOSER ,SARGENT PUSH BAR LOCK , DOOR HINGES) | 56189 | 2024-02-13 | 2024-02-17 | APPR | 5 | LT | 2 | 6435 | 12870 |  |  |  |  | LCVKW1089S | 5 | 2024-02-27 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024 | BU_Fabrication
17 | 2024-02-07 |  | BU24-0051 | ARTC TT615 Vestibule | 9487373 | FABRICATION | PPGI ROOF SHEET BOX PROFILE,28 GAUGE- COLOR : BEIGE, SIZE 1.8 M X 1 M | 56190 | 2024-02-13 | 2024-02-17 | APPR | 1 | EA | 6 | 16 | 96 |  |  |  |  | LCVKW1090S | 1 | 2024-02-27 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024 | BU_Fabrication
17 | 2024-02-07 |  | BU24-0051 | ARTC TT615 Vestibule | 9487373 | FABRICATION | PPGI WALL SHEET BOX PROFILE,28 GAUGE- COLOR : BEIGE, SIZE 2.25 M X 1.15 M | 56190 | 2024-02-13 | 2024-02-17 | APPR | 2 | EA | 16 | 25 | 400 |  |  |  |  | LCVKW1090S | 2 | 2024-02-27 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024 | BU_Fabrication
17 | 2024-02-07 |  | BU24-0051 | ARTC TT615 Vestibule | 9487373 | FABRICATION | RIDGE - COLOR : BEIGE, SIZE 2.40 M X 0.035 MM | 56190 | 2024-02-13 | 2024-02-17 | APPR | 3 | EA | 4 | 122 | 488 |  |  |  |  | LCVKW1090S | 3 | 2024-02-27 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024 | BU_Fabrication
17 | 2024-02-07 |  | BU24-0051 | ARTC TT615 Vestibule | 9487373 | FABRICATION | FLASHING - COLOR : BEIGE, SIZE 2.40 M X 0.035 MM | 56190 | 2024-02-13 | 2024-02-17 | APPR | 4 | EA | 10 | 122 | 1220 |  |  |  |  | LCVKW1090S | 4 | 2024-02-27 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024 | BU_Fabrication
17 | 2024-02-07 |  | BU24-0051 | ARTC TT615 Vestibule | 9487373 | FABRICATION | METAL DOOR WITH FRAME INCLOODING ,ACCESSORIES (KABA CIPHER LOCK , SARGENT DOOR CLOSER ,SARGENT PUSH BAR LOCK , DOOR HINGES) | 56190 | 2024-02-13 | 2024-02-17 | APPR | 5 | LOT | 2 | 6435 | 12870 |  |  |  |  | LCVKW1090S | 5 | 2024-02-27 | APPR |  | SHIJO | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  |  | BU | Fab table | February | 2024 | BU_Fabrication
18 | 2024-02-18 |  | BU24-0167 | Install Security Bars Z2 Trailer2028 | 9653621 | FABRICATION | FABRICATED WINDOW GRILL WITH A HEIGHT OF 118 CM AND A WIDTH OF 98 CM USING A 4CM X 6MM FLAT BAR FRAME, WITH A DIMENSION OF | 56329 | 2024-02-21 | 2024-02-21 | APPR | 1 | LT | 2 | 280.5 | 280.5 | [10 empty] | UNITEC INTERNATIONAL GENERAL TRADING CO | 2024-03-30 |  |  |  | Verbal Award | BU | Fab table | February | 2024 | BU_Fabrication
19 | 2024-03-02 |  | BU24-0118 | REQUESTING A COVER ON TOP OF THE ONE ROOM, ACCORING TO AR 600-8-3 POSTAL OPERATIONS |  | Fabrication | BAR, METAL, FLAT, GALVANIZE STEEL, 1/4 X 1-1/2 INCHES X 20 FEET WITH 18SQMM HOLE 1FT APART) | 56856 | 2024-03-05 | 2024-03-05 | APPR | 1 | LT | 8 | 73 | 584 | [16 empty] | BU | Fab table | March | 2024 | BU_Fabrication
20 | 2024-02-24 |  | BU24-0174 | Correct TI deficiencies ECP1 Breakroom |  | Fabrication | FABRICATION OF WINDOW SCREEN ( height -95.5cm, width-79.5) | PRINPRG |  |  |  |  | EA | 2 | [18 empty] | BU | Fab table | February | 2024 | BU_Fabrication
21 | 2024-02-20 |  | BU24-0019 | ADN 4 GENERATOR REPLACEMENT | 9548324 | Fabrication | Testing and Commissioning by Supplier/SME | PRINPRG |  |  |  |  | LOT | 1 | [18 empty] | BU | BU table | December | 2023 | BU_Fabrication
22 | 2024-02-20 |  | BU24-0023 | ADN 2 GENERATOR REPLACEMENT | 9548113 | Fabrication | Testing and Commissioning by Supplier/SME | PRINPRG |  |  |  |  | LOT | 1 | [18 empty] | BU | Fab table | February | 2024 | BU_Fabrication
2 | 2022-10-02 |  | AJ22-0241 | Building 5723 TT PKAC Replacement | 2647953 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 38225 | 2022-10-02 | 2022-10-11 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
3 | 2022-10-03 |  | AJ22-0218 | Interlock Concrete Pavers for Walking Area at Camp Arifjan. | 2647953 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 38173 | 2022-10-03 | 2022-10-08 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
5 | 2022-10-10 |  | AJ22-0392 | ILU Repair Set 4 | 3326596 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 38641 | 2022-10-10 | 2022-10-26 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
6 | 2022-10-10 |  | AJ22-0234 | ILU Repair Set 1 | 3296566 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 38640 | 2022-10-10 | 2022-10-26 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
7 | 2022-10-11 |  | AJ22-0042 | B6075 MTS Replace | 2624592 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 38638 | 2022-10-11 | 2022-10-22 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
8 | 2022-10-15 |  | AJ22-0175 | Bldg. 224 Steam Generator 1 Replacement | 2873774 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39353 | 2022-10-15 | 2022-11-13 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
10 | 2022-10-17 |  | AJ21-0002 | APS-5 Medical Warehouse Bldg. 4009 | 195272 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39424 | 2022-10-17 | 2022-11-15 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
11 | 2022-10-17 |  | AJ22-0352 | Hazardous Waste Material Removal in Lot 59 | 3054100 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39621 | 2022-10-17 | 2022-11-21 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
12 | 2022-10-17 |  | AJ22-0335 | Bldg.205 Substation 5 Cleaning & Maintenance | 3055849 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39620 | 2022-10-17 | 2022-11-21 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
13 | 2022-10-17 |  | AJ22-0174 | B224 Chiller Water Pump Replacement | 2539650 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39259 | 2022-10-17 | 2022-11-09 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
14 | 2022-10-17 |  | AJ22-0336 | Z1 B165 Cleaning and Maintenance | 3055853 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39654 | 2022-10-17 | 2022-11-22 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
15 | 2022-10-17 |  | AJ22-0354 | Z7 Lot 32 Debris Removal | 3054121 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39264 | 2022-10-17 | 2022-11-09 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
16 | 2022-10-18 |  | AJ22-0353 | Z7 Clearing EOD Training Site | 2453547 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39352 | 2022-10-18 | 2022-11-13 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
18 | 2022-10-19 |  | AJ21-0038 | BLDG 1131 Office Buildout | 2504223 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39622 | 2022-10-19 | 2022-11-21 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
19 | 2022-10-20 |  | AJ22-0236 | ILU Repair Set 3 | 3326587 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39354 | 2022-10-20 | 2022-11-13 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
20 | 2022-10-22 |  | AJ22-0393 | ILU Repair Set 5 | 3326604 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39349 | 2022-10-22 | 2022-11-13 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
21 | 2022-10-22 |  | AJ22-0394 | ILU Repair Set 6 | 3326608 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39350 | 2022-10-22 | 2022-11-13 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
22 | 2022-10-23 |  | AJ22-0176 | BLDG 224 Steam Generator Replacement | 2873763 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39261 | 2022-10-23 | 2022-11-09 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
23 | 2022-10-26 |  | AJ22-0177 | Bldg. 224 Steam Generator 3 Replacement | 2873756 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39262 | 2022-10-26 | 2022-11-09 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
25 | 2022-10-27 |  | AJ22-0146 | B507 Fire Hardening | 2671555 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39050 | 2022-10-27 | 2022-11-03 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
26 | 2022-10-27 |  | AJ22-0147 | Utilities ASP500 Tie-in | 2147424 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39048 | 2022-10-27 | 2022-11-03 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
27 | 2022-10-29 |  | AJ22-0235 | ILU Repair Set 2 | 3296610 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 38960 | 2022-10-29 | 2022-11-01 | [22 empty] | AJ | Sub table | October | 2022 | AJ_Subcon_PR
29 | 2022-11-03 |  | AJ22-0534 | Care and Preservation Facility |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39049 | 2022-11-03 | 2022-11-03 | [22 empty] | AJ | Sub table | November | 2022 | AJ_Subcon_PR
30 | 2022-11-06 |  | AJ22-0407 | Z6 Senior Pods Shower Replacement | 3270986 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39265 | 2022-11-06 | 2022-11-09 | [22 empty] | AJ | Sub table | November | 2022 | AJ_Subcon_PR
31 | 2022-11-06 |  | AJ22-0409 | Z6 Senior Pods Female Shower | 3270589 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39256 | 2022-11-06 | 2022-11-09 | [22 empty] | AJ | Sub table | November | 2022 | AJ_Subcon_PR
32 | 2022-11-06 |  | AJ22-0407 | Z6 Senior Pods Shower Replacement | 3270986 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39265 | 2022-11-06 | 2022-11-09 | [22 empty] | AJ | Sub table | November | 2022 | AJ_Subcon_PR
33 | 2022-11-08 |  | AJ22-0333 | Substation 3 Cleaning & Maintenance Zone 1-Bldg 121 | 3137625 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39625 | 2022-11-08 | 2022-11-21 | [22 empty] | AJ | Sub table | November | 2022 | AJ_Subcon_PR
34 | 2022-11-09 |  | AJ22-0332 | Substation 2 Cleaning & Maintenance Zone 2-Bldg 463 | 3055876 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39624 | 2022-11-09 | 2022-11-21 | [22 empty] | AJ | Sub table | November | 2022 | AJ_Subcon_PR
35 | 2022-11-10 |  | AJ22-0334 | Z1 B145 Cleaning and Maintenance | 3055843 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39626 | 2022-11-10 | 2022-11-21 | [22 empty] | AJ | Sub table | November | 2022 | AJ_Subcon_PR
36 | 2022-11-14 |  | AJ22-0331 | Substation 1 Cleaning & Maintenance Zone 2-Bldg 513 | 3055868 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39646 | 2022-11-14 | 2022-11-22 | [22 empty] | AJ | Sub table | November | 2022 | AJ_Subcon_PR
37 | 2022-11-21 |  | AJ22-0046 | Replace HVAC System and Controls at B-306 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39903 | 2022-11-21 | 2022-11-29 | [22 empty] | AJ | Sub table | November | 2022 | AJ_Subcon_PR
38 | 2022-11-21 |  | AJ22-0106 | Pipe Leak Repair At Zone 2 APS 500 Warehouse 4 | 2539713 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | PWD-PROJECT-PWO-AJ22-0106- 2325 | 2022-11-21 | [22 empty] | As per Mark The Project has been cancelled | AJ | Sub table | November | 2022 | AJ_Subcon_PR
39 | 2022-11-22 |  | AJ22-0468 | Bldg.216 Chiller Efficiency Upgrade, Camp Arifjan | 3511691 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 40106 | 2022-11-22 | 2022-12-03 | [22 empty] | AJ | Sub table | November | 2022 | AJ_Subcon_PR
40 | 2022-12-11 |  | AJ22-0379 | Z5 Trailer T28 Tie In | 3133125 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 46334 | 2022-12-11 | 2023-05-23 | [22 empty] | AJ | Sub table | December | 2022 | AJ_Subcon_PR
41 | 2022-12-11 |  | AJ22-0232 | Z6 Repair Pipeline B544-1 | 3215439 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 48591 | 2022-12-11 | 2023-07-23 | [22 empty] | AJ | Sub table | December | 2022 | AJ_Subcon_PR
43 | 2022-12-18 |  | AJ22-0359 | Z7 Relocate Tents | 3145108 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 41641 | 2022-12-18 | 2023-01-24 | [22 empty] | AJ | Sub table | December | 2022 | AJ_Subcon_PR
44 | 2022-12-19 |  | AJ22-0325 | Z1 B145 Mini Splits | 3195847 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 40978 | 2022-12-19 | 2023-01-03 | [22 empty] | AJ | Sub table | December | 2022 | AJ_Subcon_PR
50 | 2023-01-17 |  | AJ22-0021 | Bldg 162 PSD Control Room Remodel | 4535846 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 41583 | 2023-01-17 | 2022-01-22 | [22 empty] | AJ | Sub table | January | 2023 | AJ_Subcon_PR
51 | 2023-01-21 |  | AJ22-0205 | Deconstruct RLB Pad-D, Camp Arifjan | 2035242 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 41729 | 2023-01-21 | 2023-01-25 | [22 empty] | AJ | Sub table | January | 2023 | AJ_Subcon_PR
52 | 2023-01-22 |  | AJ22-0233 | Bldg B6028 Replacement of Water Pipelines | 4246289 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 42739 | 2023-01-22 | 2023-01-19 | [22 empty] | AJ | Sub table | January | 2023 | AJ_Subcon_PR
54 | 2023-01-28 |  | AJ22-0534 | Care and Preservation Facility T | 3615548 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | PWD-PROJECT-PWO-AJ22-0534-3028 | 2023-01-28 | [22 empty] | PR Cancelled | AJ | Sub table | January | 2023 | AJ_Subcon_PR
57 | 2023-02-13 |  | AJ22-0297 | B131 Pool Pump Room HVAC and Handrail Install | 3604408 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44881 | 2023-02-13 | 2023-04-19 | [22 empty] | AJ | Sub table | February | 2023 | AJ_Subcon_PR
68 | 2023-03-14 |  | AJ22-0351 | Male Latrine Floor Tile Replacement B507 Zone 2 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 43635 | 2023-03-14 | 2023-03-15 | [22 empty] | AJ | Sub table | March | 2023 | AJ_Subcon_PR
69 | 2023-03-25 |  | AJ21-0038 | BUILDING 1131 OFFICE BUILDOUT |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45127 | 2023-03-25 | 2023-04-26 | [22 empty] | AJ | Sub table | March | 2023 | AJ_Subcon_PR
72 | 2023-03-29 |  | AJ22-0317 | Z6 T1022 SINK TIE IN | 3897909 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44237 | 2023-03-29 | 2023-03-30 | [22 empty] | AJ | Sub table | March | 2023 | AJ_Subcon_PR
74 | 2023-04-06 |  | AJ22-0322 | BLDG 513 HVAC AND FACILITY REPAIR | 3187334 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44605 | 2023-04-06 | 2023-04-11 | [22 empty] | AJ | Sub table | April | 2023 | AJ_Subcon_PR
75 | 2023-04-06 |  | AJ22-0326 | B 205 HVAC AND FACILITY REPAIR | 3196414 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44608 | 2023-04-06 | 2023-04-11 | [22 empty] | AJ | Sub table | April | 2023 | AJ_Subcon_PR
76 | 2023-04-06 |  | AJ22-0324 | BLDG 121 HVAC AND FACILITY REPAIR | 3193786 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44603 | 2023-04-06 | 2023-04-11 | [22 empty] | AJ | Sub table | April | 2023 | AJ_Subcon_PR
78 | 2023-04-10 |  | AJ22-0327 | B-165 HVAC AND FACILITY REPAIR | 3196067 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51577 | 2023-04-10 | 2023-10-10 | [22 empty] | AJ | Sub table | April | 2023 | AJ_Subcon_PR
82 | 2023-04-16 |  | AJ23-0045 | BACKUP CONNECTION TO HOSPITAL REEFER | 4304698 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 47185 | 2023-04-16 | 2023-06-13 | [22 empty] | AJ | Sub table | April | 2023 | AJ_Subcon_PR
83 | 2023-04-18 |  | AJ22-0321 | B-350 HVAC and Facility Repair at Camp Arifjan | 3196626 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45380 | 2023-04-18 | 2023-05-02 | [22 empty] | AJ | Sub table | April | 2023 | AJ_Subcon_PR
85 | 2023-04-18 |  | AJ23-0134 | CARE & PRESERVATION CENTER GENERATOR SERVICE | 5685817 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45465 | 2023-04-18 | 2023-05-03 | [22 empty] | AJ | Sub table | April | 2023 | AJ_Subcon_PR
87 | 2023-04-26 |  | AJ23-0090 | SPOD Fuel Generator Consolidation, Camp SPOD | 5770261 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45805 | 2023-04-26 | 2023-05-10 | [22 empty] | AJ | Sub table | April | 2023 | AJ_Subcon_PR
88 | 2023-04-30 |  | AJ22-0231 | BLDG 6029 REPLACEMENT OF WATER PIPELINES | 3216160 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45803 | 2023-04-30 | 2023-05-10 | [22 empty] | AJ | Sub table | April | 2023 | AJ_Subcon_PR
93 | 2023-05-06 |  | AJ23-0132 | TI FOR APS 500 WAREHOUSE |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45821 | 2023-05-06 | 2023-05-10 | [22 empty] | AJ | Sub table | May | 2023 | AJ_Subcon_PR
94 | 2023-05-06 |  | AJ23-0133 | TI FOR TIP C WAREHOUSE |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45957 | 2023-05-06 | 2023-05-13 | [22 empty] | AJ | Sub table | May | 2023 | AJ_Subcon_PR
96 | 2023-05-13 |  | AJ22-0222 | PAD HVAC PLACEMENT IN SENIOR PODS | 3344194 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 4623247068 | 2023-05-13 | 5/21/2023, 8Jun 23 | [22 empty] | AJ | Sub table | May | 2023 | AJ_Subcon_PR
97 | 2023-05-13 |  | AJ22-0400 | CONNECT 3100T TO GRID POWER ZONE 3 | 3682675 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 46055 | 2023-05-13 | 2023-05-17 | [22 empty] | AJ | Sub table | May | 2023 | AJ_Subcon_PR
100 | 2023-05-17 |  | AJ23-0006 | HVAC LIFECYCLE REPLACEMENT T-824D ZONE 7, |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 46250 | 2023-05-17 | 2023-05-21 | [22 empty] | AJ | Sub table | May | 2023 | AJ_Subcon_PR
102 | 2023-05-21 |  | AJ23-0005 | HVAC LIFECYCLE REPLACEMENT T-824C ZONE 7 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 46940 | 2023-05-21 | 2023-06-06 | [22 empty] | AJ | Sub table | May | 2023 | AJ_Subcon_PR
103 | 2023-05-22 |  | AJ22-0198 | Z6 TT6007 FLOOR REPAIR | 3812629 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 47193 | 2023-05-22 | 2023-06-14 | [22 empty] | AJ | Sub table | May | 2023 | AJ_Subcon_PR
104 | 2023-05-22 |  | AJ22-0322 | BLDG 513 HVAC FACILITY REPAIR | 3187334 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50607 | 2023-05-22 | 2023-09-19 | [22 empty] | AJ | Sub table | May | 2023 | AJ_Subcon_PR
105 | 2023-05-22 |  | AJ22-0324 | BLDG 121 HVAC FACILITY REPAIR | 3193786 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 47195 | 2023-05-22 | 2023-06-14 | [22 empty] | AJ | Sub table | May | 2023 | AJ_Subcon_PR
106 | 2023-05-22 |  | AJ22-0326 | B-205 HVAC AND FACILITY REPAIR | 3196414 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 47194 | 2023-05-22 | 2023-06-14 | [22 empty] | AJ | Sub table | May | 2023 | AJ_Subcon_PR
108 | 2023-05-24 |  | AJ22-0547 | UPS LIFE CYCLE REPLACEMENT BLDG 505 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 47344 | 2023-05-24 | 2023-06-19 | [22 empty] | AJ | Sub table | May | 2023 | AJ_Subcon_PR
109 | 2023-05-24 |  | AJ22-0507 | RADOME POWER UPGRADE |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 48309 | 2023-05-24 | 2023-07-13 | [22 empty] | AJ | Sub table | May | 2023 | AJ_Subcon_PR
112 | 2023-05-28 |  | AJ22-0497 | 5th Medical Brigade Warehouse Doors Replacement- Bldg.550 | 3682682 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 47340 | 2023-05-28 | 2023-06-19 | [22 empty] | AJ | Sub table | May | 2023 | AJ_Subcon_PR
114 | 2023-06-14 |  | AJ23-0004 | INSTALL SPLIT SYSTEM AND REPLACE THERMOSTAT | 3878081 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50914 | 2023-06-14 | 2023-09-23 | [22 empty] | AJ | Sub table | June | 2023 | AJ_Subcon_PR
115 | 2023-06-14 |  | AJ22-0149 | REPLACEMENT OF UDS4 CABLE | 1676813 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 48670 | 2023-06-14 | 2023-07-23 | [22 empty] | AJ | Sub table | June | 2023 | AJ_Subcon_PR
120 | 2023-07-12 |  | AJ23-0574 | Electrical Panel Replacement | 6653886 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | PWD-ELECT-PWO-AJ23-0574-3193 | 2023-07-12 | [22 empty] | Send ODC 12 July 23 | AJ | Sub table | July | 2023 | AJ_Subcon_PR
125 | 2023-08-28 |  | AJ22-0537 | Install 15 Smart Water Meters | 7178664 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50415 | 2023-08-28 | 2023-09-13 | [22 empty] | AJ | Sub table | August | 2023 | AJ_Subcon_PR
126 | 2023-09-02 |  | AJ22-0184 | ZONE 6 BASKET BALL COURT | 1975715 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52515 | 2023-09-02 | 2023-11-06 | [22 empty] | AJ | Sub table | September | 2023 | AJ_Subcon_PR
127 | 2023-09-03 |  | AJ23-0192 | KNB Wash Rack Tank Repair | 7297357 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50097 | 2023-09-03 | 2023-09-03 | [22 empty] | AJ | Sub table | September | 2023 | AJ_Subcon_PR
128 | 2023-09-03 |  | AJ23-0193 | KNB Wash Rack Sand Filter System Repair | 7312848 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50099 | 2023-09-03 | 2023-09-03 | [22 empty] | AJ | Sub table | September | 2023 | AJ_Subcon_PR
129 | 2023-09-03 |  | AJ22-0380 | TRAILER MOVE AND TIE-IN | 2624597 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51885 | 2023-09-03 | 2023-10-18 | [22 empty] | AJ | Sub table | September | 2023 | AJ_Subcon_PR
130 | 2023-09-07 |  | AJ22-0417 | TT752B HVAC REPLACEMEN | 3682803 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 3682803 | 2023-09-07 | 2023-09-07 | [22 empty] | AJ | Sub table | September | 2023 | AJ_Subcon_PR
131 | 2023-09-10 |  | AJ23-0167 | TI Deficiencies Correction | 4911390 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50414 | 2023-09-10 | 2023-09-13 | [22 empty] | AJ | Sub table | September | 2023 | AJ_Subcon_PR
132 | 2023-09-10 |  | AJ23-0179 | Lower Roof Replace Z4 Building 777, | 4970059 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50412 | 2023-09-10 | 2023-09-13 | [22 empty] | AJ | Sub table | September | 2023 | AJ_Subcon_PR
134 | 2023-09-17 |  | AJ23-0306 | Bldg.134 PX Roof Repair |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50927 | 2023-09-17 | 2023-09-25 | [22 empty] | AJ | Sub table | September | 2023 | AJ_Subcon_PR
135 | 2023-09-17 |  | AJ22-0123 | HVAC THERMOSTAT IN KDOC | 1567044 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50599 | 2023-09-17 | 2023-09-19 | [22 empty] | AJ | Sub table | September | 2023 | AJ_Subcon_PR
136 | 2023-09-17 |  | AJ22-0055 | REPLACE THE YARD RADIATION DETECTORS AT DLA | 7527758 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51355 | 2023-09-17 | 2023-10-04 | [22 empty] | AJ | Sub table | September | 2023 | AJ_Subcon_PR
137 | 2023-09-19 |  | AJ20-0135 | Military Working Dog |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52652 | 2023-09-19 | 2023-11-08 | [22 empty] | AJ | Sub table | September | 2023 | AJ_Subcon_PR
138 | 2023-09-19 |  | AJ22-0378 | Solar Light Set | 7584104 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52634 | 2023-09-19 | 2023-11-09 | [22 empty] | AJ | Sub table | September | 2023 | AJ_Subcon_PR
139 | 2023-09-19 |  | AJ22-0406 | RELOCATION OF POWER PANEL AND GENERATOR IN Z6 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52636 | 2023-09-19 | 2023-11-09 | [22 empty] | AJ | Sub table | September | 2023 | AJ_Subcon_PR
140 | 2023-09-20 |  | AJ22-0004 | ECP-1 Access Road Repair | 7584064 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52258 | 2023-09-20 | 26ODC23 | [22 empty] | AJ | Sub table | September | 2023 | AJ_Subcon_PR
141 | 2023-09-26 |  | AJ23-0007 | HVAC Lifecycle Replacement | 3898188 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52403 | 2023-09-26 | 2023-11-01 | [22 empty] | AJ | Sub table | September | 2023 | AJ_Subcon_PR
143 | 2023-09-27 |  | AJ22-0199 | Replacement of the Solid State Frequency Converte | 2024951 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51888 | 2023-09-27 | 2023-10-19 | [22 empty] | AJ | Sub table | September | 2023 | AJ_Subcon_PR
144 | 2023-09-28 |  | AJ23-0258 | RP6000 MARCENT New Trenching and Culverts |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52705 | 2023-09-28 | 2023-11-11 | [21 empty] | Resend to Contracts 6 Nov 23 | AJ | Sub table | September | 2023 | AJ_Subcon_PR
145 | 2023-10-02 |  | AJ21-0038 | Office Buildout1131 | 2504223 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52245 | 2023-10-02 | 2043-01-14 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
146 | 2023-10-03 |  | AJ23-0101 | DFAC Locker Rebuild | 4515922 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51361 | 2023-10-03 | 2023-10-04 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
147 | 2023-10-03 |  | AJ22-0323 | HVAC and Facility Light Fixture Repair, | 2324497 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51359 | 2023-10-03 | 2023-10-04 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
152 | 2023-10-09 |  | AJ23-0668 | Irrigation and Landscaping Zone 1 & 4 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52388 | 2023-10-09 | 2023-10-31 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
154 | 2023-10-11 |  | AJ22-0536 | Remove existing asphalt road to subbase to be repaired. | 3790651 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51868 | 2023-10-11 | 2023-10-18 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
157 | 2023-10-14 |  | AJ23-0268 | Walker Road Culvert Z2 | 7874945 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52495 | 2023-10-14 | 2023-11-04 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
159 | 2023-10-16 |  | AJ23-0437 | TFCF Training Trailer Electrical Upgrades Z4 | 7995997 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52416 | 2023-10-16 | 2023-11-01 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
161 | 2023-10-16 |  | AJ23-0079 | TT1004 Chapel Refurbishment Z6 | 7986313 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52413 | 2023-10-16 | 2023-11-01 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
162 | 2023-10-16 |  | AJ23-0532 | T6526 NEW DOOR AND CIPHER LOCKS Z6 | 7975040 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52414 | 2023-10-16 | 2023-11-01 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
163 | 2023-10-16 |  | AJ23-0598 | PAHP Flight Line Fence | 7973212 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52496 | 2023-10-16 | 2023-11-04 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
164 | 2023-10-17 |  | AJ22-0390 | Renovate room 115 of Building 300 Zone 1, | 3444456 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52334 | 2023-10-17 | 2023-10-30 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
165 | 2023-10-17 |  | AJ22-0546 | TT755 Grid Connection, | 8024236 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52134 | 2023-10-17 | 2023-10-24 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
167 | 2023-10-18 |  | AJ23-0245 | T1000 Structural Assessment Z2 | 8019766 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52378 | 2023-10-18 | 2023-10-31 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
169 | 2023-10-22 |  | AJ23-0481 | B505 HVAC Replacement | 7813302 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52316 | 2023-10-22 | 2023-10-28 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
170 | 2023-10-22 |  | AJ23-0482 | B506 HVAC Replacement | 7814 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52317 | 2023-10-22 | 2023-10-28 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
171 | 2023-10-22 |  | AJ23-0425 | B507 HVAC Replacement | 7815289 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52129 | 2023-10-22 | 2023-10-24 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
172 | 2023-10-23 |  | AJ22-0549 | Zone 1 Curb Construction Phase 2 | 7815713 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52160 | 2023-10-23 | 2023-10-24 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
173 | 2023-10-23 |  | AJ22-0073 | Lot 39 Perimeter Fence | 7815937 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52310 | 2023-10-23 | 2023-10-28 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
174 | 2023-10-23 |  | AJ23-0166 | Zone 1 Sidewalk Construction | 7817685 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52309 | 2023-10-23 | 2023-10-28 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
175 | 2023-10-24 |  | AJ23-0493 | Trailer LDN3 Floor Repairs Z6 | 3527965 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52358 | 2023-10-24 | 2023-10-30 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
176 | 2023-10-24 |  | AJ22-0240 | ZONE 6 SOFTBALL SCORE BOARD | 8084482 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52329 | 2023-10-24 | 2023-10-28 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
177 | 2023-10-24 |  | AJ23-0172 | MOTOR POOL 17 COMPOUND POWER CONSOLIDATION | 8013745 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52661 | 2023-10-24 | 2023-11-09 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
178 | 2023-10-24 |  | AJ23-0442 | ADA Generator Power Consolidation Z5 | 8017222 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52410 | 2023-10-24 | 2023-11-01 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
179 | 2023-10-24 |  | AJ23-0579 | PAT Entrance Gate and Fence Install Z5 | 8094857 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52714 | 2023-10-24 | 2023-11-13 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
180 | 2023-10-24 |  | AJ23-0300 | B148 Chapel Acoustic Z1 | 5233949 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52321 | 2023-10-24 | 2023-10-28 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
182 | 2023-10-25 |  | AJ23-0260 | Storm Water Drainage | 8110777 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52319 | 2023-10-25 | 2023-10-28 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
183 | 2023-10-29 |  | AJ23-0225 | CARE AND PRESERVATION STORM CHANNEL | 8095088 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52665 | 2023-10-29 | 2023-11-09 | [22 empty] | AJ | Sub table | October | 2023 | AJ_Subcon_PR
185 | 2023-11-01 |  | AJ23-0068 | B224 Fire Protection Assessment Z1 | 8111216 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52579 | 2023-11-01 | 2023-11-07 | [22 empty] | AJ | Sub table | November | 2023 | AJ_Subcon_PR
188 | 2023-11-06 |  | AJ22-0474 | Bldg 3029 PKCA Replacement | 5337653 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52656 | 2023-11-06 | [23 empty] | AJ | Sub table | November | 2023 | AJ_Subcon_PR
189 | 2023-11-07 |  | AJ22-0524 | B134 POST OFFICE PAINTING Z1 | 3527959 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 53321 | 2023-11-07 | 2023-12-01 | [22 empty] | AJ | Sub table | November | 2023 | AJ_Subcon_PR
190 | 2023-11-07 |  | AJ22-0505 | Replace the flooring for Building T438 | 3804265 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52752 | 2023-11-07 | 2023-11-15 | [22 empty] | AJ | Sub table | November | 2023 | AJ_Subcon_PR
191 | 2023-11-08 |  | AJ22-0399 | MOVE T2003 AND POWER TIE-IN | 7267384 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52751 | 2023-11-08 | 2023-11-15 | [22 empty] | AJ | Sub table | November | 2023 | AJ_Subcon_PR
194 | 2023-11-17 |  | AJ23-0260 | Zone 1 T115 Storm Water Drainage, | 8110777 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52319 | 2023-11-17 | 2023-10-28 | [18 empty] | COMP |  |  |  | AJ | Sub table | November | 2023 | AJ_Subcon_PR
195 | 2023-11-24 |  | AJ23-0645 | Z4 TT752D PKAC4481 Life Cycle Replacement | 6602085 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54372 | 2023-11-24 | 2023-12-28 |  | 1 | LT | 1 | 25000 | 25000 | [12 empty] | COMP |  |  |  | AJ | Sub table | November | 2023 | AJ_Subcon_PR
196 | 2023-11-24 |  | AJ22-0189 | Replace Feeder Cable, | 3878015 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54016 | 2023-11-24 | 2023-12-17 |  | 1 | LT | 1 | 46770 | 46770 | [12 empty] | COMP |  |  |  | AJ | Sub table | November | 2023 | AJ_Subcon_PR
197 | 2023-11-24 |  | AJ22-0190 | B450 Vent and Duct cleaning | 1850088 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54287 | 2023-11-24 | 2023-12-25 |  | 1 | LT | 1 | 11870 | 11870 | [12 empty] | COMP |  |  |  | AJ | Sub table | November | 2023 | AJ_Subcon_PR
198 | 2023-11-27 |  | AJ23-0502 | RP2002 Modifications Z2 | 8389198 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 53316 | 2023-11-27 | 2023-12-01 | [18 empty] | COMP |  |  |  | AJ | Sub table | November | 2023 | AJ_Subcon_PR
202 | 2023-12-06 |  | AJ22-0475 | TTHV5 PKAC Replacemen | 5337643 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54018 | 2023-12-06 | 2023-12-17 |  | 1 | LT | 1 | 29950 | 29950 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023 | AJ_Subcon_PR
203 | 2023-12-06 |  | AJ22-0371 | CHILLER REPAIR (SN 12A101231) | 2564193 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54344 | 2023-12-06 | 2023-12-27 |  | 1 | [16 empty] | COMP |  |  |  | AJ | Sub table | December | 2023 | AJ_Subcon_PR
204 | 2023-12-06 |  | AJ22-0530 | CFLCC Repair | 4515912 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54022 | 2023-12-06 | 2023-12-17 |  | 1 | LT | 1 | 52412 | 52412 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023 | AJ_Subcon_PR
205 | 2023-12-07 |  | AJ23-0450 | Zone 1 Pool Pump House | 5847348 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54023 | 2023-12-07 | 2023-12-17 |  | 1 | LT | 1 | 50338 | 50338 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023 | AJ_Subcon_PR
206 | 2023-12-07 |  | AJ23-0237 | Zone 2 Coalition Village Kitchen | 5424135 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54024 | 2023-12-07 | 2023-12-17 |  | 1 | LT | 1 | 49830 | 49830 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023 | AJ_Subcon_PR
207 | 2023-12-07 |  | AJ23-0040 | Rock or something for Welcome Sign_ Zone 4, | 4170764 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54375 | 2023-12-07 | 2023-12-28 |  | 1 | LT | 1 | 16600 | 16600 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023 | AJ_Subcon_PR
209 | 2023-12-10 |  | AJ23-0241 | Life Cycle Replacement | 5720168 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54011 | 2023-12-10 | 2023-12-17 |  | 1 | LT | 1 | 100000 | 10000 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023 | AJ_Subcon_PR
210 | 2023-12-10 |  | AJ23-0619 | Sink Booster Heater Installation | 6768439 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54021 | 2023-12-10 | 2023-12-17 |  | 1 | LT | 1 | 48589 | 48589 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023 | AJ_Subcon_PR
211 | 2023-12-11 |  | AJ23-0243 | Z6 Life Cycle Replacement 0609L | 5712915 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54369 | 2023-12-11 | 2023-12-28 |  | 1 | LT | 1 | 100000 | 100000 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023 | AJ_Subcon_PR
212 | 2023-12-11 |  | AJ23-0242 | Life Cycle Replacement | 5720130 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54370 | 2023-12-11 | 2023-12-28 |  | 1 | LT | 1 | 100000 | 100000 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023 | AJ_Subcon_PR
215 | 2023-12-17 |  | AJ23-0252 | Plumbing Correction | 5790685 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54378 | 2023-12-17 | 2023-12-28 |  | 1 | LT | 1 | 13703 | 13703 | [12 empty] | COMP |  |  |  | AJ | Sub table | December | 2023 | AJ_Subcon_PR
216 | 2023-12-20 |  | AJ22-0110 | Sunshade Relocate Z7 | 2642514 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54367 | 2023-12-20 | 2023-12-28 |  | 1 | LT | 1 | 25584 | 25584 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023 | AJ_Subcon_PR
217 | 2023-12-17 |  | AJ23-0606 | Z5 New Grounding Points on PAHP | 6679341 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54289 | 2023-12-17 | 2023-12-27 |  | 1 | LT | 1 | 27038 | 27038 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023 | AJ_Subcon_PR
218 | 2023-12-19 |  | AJ22-0267 | Zone 6 Post Office Truck Lift Repair | 2232451 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54502 | 2023-12-19 | 2023-01-06 | COMP | 1 | LT | 1 | 18412 | 18412 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023 | AJ_Subcon_PR
219 | 2023-12-19 |  | AJ23-0510 | CLM 1 Reskin | 6043651 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54603 | 2023-12-19 | 2024-01-06 | COMP | 1 | LT | 1 | 73100 | 73100 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023 | AJ_Subcon_PR
220 | 2023-12-19 |  | AJ23-0610 | SPOD T70 Female Latrine Renovations | 6417910 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54292 | 2023-12-19 | 2023-12-25 | COMP | 1 | LT | 1 | 38000 | 38000 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023 | AJ_Subcon_PR
221 | 2023-12-19 |  | AJ23-0676 | Sink Booster Heater Installation | 6768274 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54290 | 2023-12-19 | 2023-12-25 | COMP | 1 | LT | 1 | 27820 | 27820 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023 | AJ_Subcon_PR
223 | 2023-12-20 |  | AJ22-0168 | SS812 Sunshade Replace | 2635682 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54280 | 2023-12-19 | 2023-12-24 | COMP | 1 | LT | 1 | 41008 | 41008 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023 | AJ_Subcon_PR
225 | 2023-12-06 |  | AJ23-0593 | B777 ATS and Emergency Light, Zine 4 | 8675931 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54286 | 2023-12-24 | 2023-12-25 | COMP | 1 | LT | 1 | 39000 | 39000 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023 | AJ_Subcon_PR
226 | 2023-12-23 |  | AJ23-0492 | ARCENT CMD Group Foyer Work |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54615 | 2023-12-23 | 2024-01-08 | COMP | 1 | LT | 1 | 14553 | 14553 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023 | AJ_Subcon_PR
227 | 2023-12-23 |  | AJ23-0240 | Z6 Life Cycle Replacement 1404E and 1402W | 8084482 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54493 | 2023-12-23 | 2024-01-04 | COMP | 1 | LT | 1 | 100000 | 100000 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023 | AJ_Subcon_PR
228 | 2023-12-23 |  | AJ23-0611 | SPOD T73 Male Latrine Renovations |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54610 | 2023-12-23 | 2024-01-07 | COMP | 1 | LT | 1 | 52585 | 52585 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023 | AJ_Subcon_PR
229 | 2023-12-16 |  | AJ22-0120 | T1084 Outside Stairs Broken | 8810536 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54291 | 2023-12-24 | 2023-12-25 | COMP | 1 | LT | 1 | 10689.28 | 10689.28 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023 | AJ_Subcon_PR
230 | 2023-12-26 |  | AJ23-0496 | ECP2 RMU2-4A-4 Replacement | 6007449 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54497 | 2023-12-26 | 2024-01-04 | COMP | 1 | LT | 1 | 49000 | 49000 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023 | AJ_Subcon_PR
231 | 2023-12-26 |  | AJ23-0468 | T6207 Roof Replacement | 5903790 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54501 | 2023-12-26 | 2024-01-04 | COMP | 1 | LT | 1 | 34857 | 34857 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023 | AJ_Subcon_PR
232 | 2023-12-26 |  | AJ23-0469 | T6206 Roof Replacement | 5904257 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55069 | 2024-01-20 | 2024-01-04 | COMP | 1 | LT | 1 | 34857 | 34857 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | December | 2023 | AJ_Subcon_PR
234 | 2023-01-03 |  | AJ23-0666 | DFAC Lockers Rebuild, Zone 2, Camp Arifjan, Kuwait | 6653617 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54608 | 2023-01-04 | 2023-01-07 | COMP | 1 | LT | 1 | 24896 | 24896 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2023 | AJ_Subcon_PR
235 | 2024-01-03 |  | AJ23-0470 | Z6 T6208 Roof Replacement | 5904437 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54609 | 2023-01-04 | 2023-01-07 | COMP | 1 | LT | 1 | 32857 | 32857 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
238 | 2024-01-06 |  | AJ23-0723 | New Concrete Pad Zone 3 Camp Arifjan, Kuwait | 9069828, | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54843 | 2024-01-11 | 2024-01-14 | COMP | 1 | LT | 1 | 35462 | 35462 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
239 | 2024-01-07 |  | AJ23-0667 | DFAC Lockers Rebuild, Zone 6, Camp Arifjan, Kuwait | 6653596 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54844 | 2024-01-11 | 2024-01-14 | COMP | 1 | LT | 1 | 15601 | 15601 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
240 | 2024-01-09 |  | AJ23-0472 | T6204 Roof Replacement | 5904246 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54838 | 2024-01-11 | 2024-01-13 | COMP | 1 | LT | 1 | 32857.11 | 32857.11 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
241 | 2024-01-09 |  | AJ23-0750 | Repair HVAC in B216 Basement, S3 section | 7324760 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54839 | 2024-01-11 | 2024-01-13 | COMP | 1 | LT | 1 | 53817 | 53817 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
242 | 2024-01-09 |  | AJ23-0475 | T6201 Roof Replacement | 5904456 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54837 | 2024-01-11 | 2024-01-13 |  | 1 | LT | 1 | 32857.11 | 32857.11 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
243 | 2024-01-09 |  | AJ23-0420 | UDS 1-4A/1 Transformer Replacement Zone 2 Camp Arifjan, Kuwait | 5600909 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55083 | 2024-01-11 | 2024-01-22 | COMP | 1 | LT | 1 | 125780 | 125780 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
244 | 2024-01-09 |  | AJ23-0473 | T6203 Roof Replacement | 5904228 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54847 | 2024-01-11 | 2024-01-14 | COMP | 1 | LT | 1 | 32857.11 | 32857.11 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
245 | 2024-01-09 |  | AJ23-0474 | T6202 Roof Replacement | 5904297 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54841 | 2024-01-11 | 2024-01-13 | COMP | 1 | LT | 1 | 32857.11 | 32857.11 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
246 | 2024-01-09 |  | AJ23-0471 | T6205 Roof Replacement | 5904289 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54840 | 2024-01-11 | 2024-01-13 | COMP | 1 | LT | 1 | 32857 | 32857 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
247 | 2024-01-17 |  | AJ23-0699 | B224-BMS Preventive Maintenance Assessment, Camp Arifjan |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55070 | 2024-01-20 | 2024-01-20 | COMP | 1 | LT | 1 | 8620 | 8620 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
248 | 2024-01-17 |  | AJ23-0229 | Z6 Motor Pool 19 Power Consolidation |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55105 | 2024-01-20 | 2024-01-22 | COMP | 1 | LT | 1 | 69135 | 69135 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
249 | 2024-01-20 |  | AJ24-0170 | B229 Breaker and Breaker Frame Repair by Replacement, Camp Arifjan, Kuwait |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55084 | 2024-01-20 | 2024-01-22 | COMP | 1 | LT | 1 | 78500 | 78500 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
250 | 2024-01-20 |  | AJ22-0258 | B462 HVAC Replacement | 9117358 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55684 | 2024-01-22 | 2024-02-04 | COMP | 1 | LT | 1 | $ 1 03,492.00 | $ 1 03,492.00 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
251 | 2024-01-24 |  | AJ22-0179 | Z1 Repair LV Side at SS-6 | 9242132 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55790 | 2024-01-27 | 28jna24 | COMP | 1 | LT | 1 | 3800 | 3800 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
252 | 2024-01-27 |  | AJ23-0566 | Z3 ASP Magazine Concrete Remediations | 6669326 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55500 | 2024-01-29 | 2024-01-30 | COMP | 1 | LT | 1 | 114000 | 114000 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
253 | 2024-01-27 |  | AJ23-0423 | Zone 1-B229 HVAC Circuit on Backup Power, Camp Arifjan |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55680 | 2024-01-29 | 2024-02-03 | COMP | 1 | LT | 1 | 42140 | 42140 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
254 | 2024-01-27 |  | AJ23-0584 | Street Sign Refurbishment |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55547 | 2024-01-29 | 2024-01-31 | COMP | 1 | LT | 1 | 28170 | 28170 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
255 | 2024-01-27 |  | AJ23-0701 | Signal Radio Park Privacy Screen & Gate Removal |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55572 | 2024-01-29 | 2023-02-01 | COMP | 1 | LT | 1 | 34640 | 34640 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
256 | 2024-01-27 |  | AJ21-0097 | Recycling Fence Center Z7, Arifjan (PPR VEC-23-0400-KUW0 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55368 | 2024-01-27 |  |  | 1 | LT | 1 | 1 75,000.00 | 1 75,000.00 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
257 | 2024-01-28 |  | AJ22-0266 | B134 Post Office Truck Lift Repair, Zone 1, Camp Arifjan |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55967 | 2024-01-31 | 2024-02-10 | COMP | 1 | LT | 1 | 1 8,064.00 | 1 8,064.00 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | January | 2024 | AJ_Subcon_PR
258 | 2024-02-03 |  | AJ23-0093 | Z6 DFAC Prime Power Connection |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55682 | 2024-02-03 | 2024-02-04 |  | 1 | LT | 1 | 105,44 | 105,44 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | February | 2024 | AJ_Subcon_PR
259 | 2024-02-04 |  | AJ24-0022 | KNB Wash Rack Add Gravel, Compact and Grade |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55683 | 2024-02-04 | 2024-02-04 |  | 1 | LT | 1 | 28100 | 28100 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | February | 2024 | AJ_Subcon_PR
260 | 2024-02-04 |  | AJ22-0300 | Bldg.224 Tank Monitoring System Replacement, Camp Arifjan |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55966 | 2024-02-07 | 2024-02-10 | COMP | 1 | LT | 1 | 34802 | 34802 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | February | 2024 | AJ_Subcon_PR
261 | 2024-02-10 |  | AJ23-0250 | RP8002 Expansion |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55977 | 2024-02-10 | 2024-02-11 |  | 1 | LT | 1 | 1 34,235.00 | 1 34,235.00 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | February | 2024 | AJ_Subcon_PR
262 | 2024-02-10 |  | AJ23-0219 | Z2 B532 Door Frame Replacement |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55972 | 2024-02-10 | 2024-02-11 | COMP | 1 | LT | 1 | 1 0,750.00 | 1 0,750.00 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | February | 2024 | AJ_Subcon_PR
263 | 2024-02-10 |  | AJ23-0751 | Z1 B144 REPLACE HVAC UNITS |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55975 | 2024-02-10 | 2024-02-11 | COMP | 1 | LT | 1 | 120150 | 120150 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | February | 2024 | AJ_Subcon_PR
264 | 2024-02-10 |  | AJ23-0143 | Secure Exposed Overhead Electrical Cable |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55982 | 2024-02-10 | 2024-02-11 | COMP | 1 | LT | 1 | 1 4,220.00 | 1 4,220.00 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | February | 2024 | AJ_Subcon_PR
265 | 2024-02-10 |  | AJ24‐0009 | SPOD CHAIN‐LINK FENCE REPAIRS |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55974 | 2024-02-10 | 2024-02-11 | COMP | 1 | LT | 1 | 1 32,000.00 | 1 32,000.00 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | February | 2024 | AJ_Subcon_PR
266 | 2024-02-12 |  | AJ23-0238 | T758 Fence Inserts Zone 4, Camp Arifjan |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56193 | 2024-02-13 | 2024-02-18 | COMP | 1 | LT | 1 | 16969 | 16969 | [12 empty] | COMP |  |  | Sent signature Mark 13 Feb | AJ | Sub table | February | 2024 | AJ_Subcon_PR
267 | 2024-02-13 |  | AJ23-0740 | REPLACEMENT/INSTALLATION HVAC UNIT B179 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56061 | 2024-02-13 | 2024-02-13 | COMP | 1 | LT | 1 | 70000 | 70000 | [12 empty] | COMP |  |  | IFS PR COMPLETED | AJ | Sub table | February | 2024 | AJ_Subcon_PR
268 | 2024-02-17 |  | AJ23-0079 | TT1004 Chapel Refurb Z6 AJ23-0079 | 7986313 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56201 | 2024-02-18 | 2024-02-19 | COMP | [17 empty] | COMP |  |  |  | AJ | Sub table | February | 2024 | AJ_Subcon_PR
269 | 2024-02-17 |  | AJ23-0620 | T504D Cage Wall Installation |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56204 | 2024-02-18 | 2024-02-19 | COMP | 1 | LT | 1 | 7794 | 7794 | [12 empty] | COMP |  |  |  | AJ | Sub table | February | 2024 | AJ_Subcon_PR
270 | 2024-02-17 |  | AJ23-0247 | Z1 TT1700 Additional Exit Doors | 9705833 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56203 | 2024-02-18 | 2024-02-19 | COMP | 1 | LT | 1 | 23350 | 23350 | [12 empty] | COMP |  |  |  | AJ | Sub table | February | 2024 | AJ_Subcon_PR
271 | 2024-02-19 |  | AJ23-0376 | KNB T1 Repairs CT-14, KNB, Kuwait |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56304 | 2024-02-19 | 2024-02-21 | COMP | 1 | LT | 1 | 2 1,900.00 | [13 empty] | COMP |  |  |  | AJ | Sub table | February | 2024 | AJ_Subcon_PR
272 | 2024-02-24 |  | AJ23-0378 | KNB T1 Repairs T-411, KNB, Kuwait |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56655 | 2024-02-29 | 2024-02-29 | COMP | 1 | LT | 1 | 73930 | [13 empty] | COMP |  |  |  | AJ | Sub table | February | 2024 | AJ_Subcon_PR
273 | 2024-02-22 |  | AJ23-0494 | TT5000 Electrical Work |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56654 | 2024-02-29 | 2024-02-29 | COMP | 1 | LT | 1 | 135150 | [13 empty] | COMP |  |  |  | AJ | Sub table | February | 2024 | AJ_Subcon_PR
274 | 2024-02-24 |  | AJ21-0051 | Bldg. 222 Security Hardening_ Zone 1 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56660 | 2024-02-29 | 2024-02-29 |  | 1 | LT | 1 | 47000 | [13 empty] | COMP |  |  |  | AJ | Sub table | February | 2024 | AJ_Subcon_PR
275 | 2024-02-20 |  | AJ23-0254 | Off-Post Trench RP8002 CAKU |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56770 | 2024-02-29 | 2024-03-03 | COMP | 1 | LT | 1 | 91600 | [13 empty] | COMP |  |  |  | AJ | Sub table | February | 2024 | AJ_Subcon_PR
276 | 2024-02-13 |  | AJ23-0439 | Wash Rack Area Light Poles & Lighting KNB Camp Arifjan, Kuwait |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56768 | 2024-03-02 | 2024-03-03 | COMP | 1 | LT | 1 | [14 empty] | COMP |  |  |  | AJ | Sub table | February | 2024 | AJ_Subcon_PR
277 | 2024-03-02 |  | AJ24-0050 | TI Corrections - Fire Protection |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56899 | 2024-03-03 |  | COMP | 1 | LT | 1 | 98500 | [13 empty] | COMP |  |  |  | AJ | Sub table | March | 2024 | AJ_Subcon_PR
278 | 2024-03-02 |  | AJ23-0767 | B179 EDOC and Optometry Sun Shade |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56775 | 2024-03-03 | 2024-04-03 | COMP | 1 | LT | 1 | 31290 | [13 empty] | COMP |  |  |  | AJ | Sub table | March | 2024 | AJ_Subcon_PR
279 | 2024-03-02 |  | AJ23-0380 | KNB T1 Repairs T-413 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56777 | 2024-03-03 | 2024-03-03 |  | 1 | LT | 1 | 78950 | [13 empty] | COMP |  |  |  | AJ | Sub table | March | 2024 | AJ_Subcon_PR
280 | 2024-03-02 |  | AJ23-0382 | KNB T1 Repairs T-415 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56776 | 2024-03-03 | 2024-03-03 |  | 1 | LT | 1 | 110372 | [13 empty] | COMP |  |  |  | AJ | Sub table | March | 2024 | AJ_Subcon_PR
4 | 2022-10-06 |  | BU22-036 | Install HVAC in TT-526 | 1898690 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 38223 | 2022-10-06 | 2022-10-11 | [22 empty] | BU | Sub table | October | 2022 | BU_Subcon_PR
17 | 2022-10-19 |  | BU22-039 | installation of Bird Prevention Mesh for SS1070, | 3296468 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 38502 | 2022-10-19 | 2022-10-19 | [22 empty] | BU | Sub table | October | 2022 | BU_Subcon_PR
24 | 2022-10-27 |  | BU22-032 | TT-4053 Multi-Purpose Ctr. Renovation | 3812648 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 39110 | 2022-10-27 | 2022-11-05 | [22 empty] | BU | Sub table | October | 2022 | BU_Subcon_PR
42 | 2022-12-17 |  | BU22-027 | GS-3001 to Kcrossing | 2883768 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 40943 | 2022-12-17 | 2022-12-31 | [22 empty] | BU | Sub table | December | 2022 | BU_Subcon_PR
45 | 2022-12-20 |  | BU22-120 | Sanitary and Domestic Water Line Connection to New CAB HQ BLDG | 4322143 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 41068 | 2022-12-20 | 2023-01-05 | [22 empty] | BU | Sub table | December | 2022 | BU_Subcon_PR
46 | 2022-12-21 |  | BU22-069 | URC RANGE 6 MPMG, TOWER MOVEMENT AND PERMANENT POWER | 4369560 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 41835 | 2022-12-21 | 2023-01-28 | [22 empty] | BU | Sub table | December | 2022 | BU_Subcon_PR
47 | 2022-12-21 |  | BU22-045 | CAB HQ Roof Repairs | 4369511 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 40967 | 2022-12-21 | 2022-12-31 | [22 empty] | BU | Sub table | December | 2022 | BU_Subcon_PR
48 | 2022-12-24 |  | BU22-049 | Lightening Protection for ARTC RVTT Cover | 4369515 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 41366 | 2022-12-24 | 2023-01-14 | [22 empty] | BU | Sub table | December | 2022 | BU_Subcon_PR
49 | 2023-01-04 |  | BU22-048 | Dental Clinic Upgrades | 4369536 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 41267 | 2023-01-04 | 2022-12-12 | [22 empty] | BU | Sub table | January | 2023 | BU_Subcon_PR
53 | 2023-01-28 |  | BU22-039 | SS-1070 Bird Netting CO1 | 3296468 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 41996 | 2023-01-28 | 2023-02-02 | [22 empty] | BU | Sub table | January | 2023 | BU_Subcon_PR
55 | 2023-02-06 |  | BU23-0023 | FS-Lids Prep & Stair for Stacked Container | 4140138 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 42402 | 2023-02-06 | 2023-02-12 | [22 empty] | BU | Sub table | February | 2023 | BU_Subcon_PR
56 | 2023-02-09 |  | BU22-070 | ARF Control Tower Relocation | 2481790 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 42406 | 2023-02-09 | 2023-02-13 | [22 empty] | BU | Sub table | February | 2023 | BU_Subcon_PR
58 | 2023-02-15 |  | BU22-041 | PAD 9 ROOF REPAIR | 2238889 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 42586 | 2023-02-15 | 2023-02-16 | [22 empty] | BU | Sub table | February | 2023 | BU_Subcon_PR
63 | 2023-03-04 |  | BU22-064 | Bird Netting for MWD Small Exercise Yard Bldg. SS-110 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 43336 | 2023-03-04 | 2023-03-07 | [22 empty] | BU | Sub table | March | 2023 | BU_Subcon_PR
64 | 2023-03-12 |  | BU22-089 | Vet Clinic Sanitation Sink |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 43619 | 2023-03-12 | 2023-03-15 | [22 empty] | BU | Sub table | March | 2023 | BU_Subcon_PR
65 | 2023-03-12 |  | BU22-057 | BIRD NETTING FOR ARTC BLDG 606 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 43614 | 2023-03-12 | 2023-03-15 | [22 empty] | BU | Sub table | March | 2023 | BU_Subcon_PR
66 | 2023-03-12 |  | BU22-065 | BIRD NETTING FOR HAZMAT FACILITY SS2087 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 43615 | 2023-03-12 | 2023-03-15 | [22 empty] | BU | Sub table | March | 2023 | BU_Subcon_PR
67 | 2023-03-14 |  | BU22-0110 | WIDENING FOR NORTH AND SOUTH PERIMETER GATES |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 43673 | 2023-03-14 | 2023-03-16 | [22 empty] | BU | Sub table | March | 2023 | BU_Subcon_PR
70 | 2023-03-25 |  | BU22-047 | ULZ HANGAR 11 WATER SYSTEM |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44046 | 2023-03-25 | 2023-03-27 | [22 empty] | BU | Sub table | March | 2023 | BU_Subcon_PR
71 | 2023-03-28 |  | BU22-066 | Dual Containment, Concrete Pad for SS2087 | 2423847 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44156 | 2023-03-28 | 2023-03-29 | [22 empty] | BU | Sub table | March | 2023 | BU_Subcon_PR
73 | 2023-04-05 |  | BU22-0028 | REPLACE BREAKER PANEL OFF SUB STATION 6 | 5337607 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44416 | 2023-04-05 | 2023-04-05 | [22 empty] | BU | Sub table | April | 2023 | BU_Subcon_PR
77 | 2023-04-08 |  | BU22-069 | Range 6 MPMG Tower Relocation at Camp Buehring | 2481682 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44610 | 2023-04-08 | 2023-04-11 | [22 empty] | BU | Sub table | April | 2023 | BU_Subcon_PR
79 | 2023-04-10 |  | BU22-038 | B-503 INSTALLATION OF HVAC UNITS AND DUCT WORK | 1961070 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44590 | 2023-04-10 | 2023-04-11 | [22 empty] | BU | Sub table | April | 2023 | BU_Subcon_PR
80 | 2023-04-10 |  | BU22-031 | PAD 16 POWER CABLE REPLACEMENT | 1302592 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44611 | 2023-04-10 | 2023-04-11 | [22 empty] | BU | Sub table | April | 2023 | BU_Subcon_PR
81 | 2023-04-16 |  | BU22-0105 | GRIT BUILDING UTILIZATION PROJECT, T-4010 & TT-402 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44969 | 2023-04-16 | 2023-04-25 |  | 1 | RO | 4 | [18 empty] | BU | Sub table | April | 2023 | BU_Subcon_PR
84 | 2023-04-18 |  | BU22-066 | Dual Containment, Concrete Pad for SS2087 at Camp Buehring | 2423847 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 44156 | 2023-04-18 | 2023-04-29 | [22 empty] | BU | Sub table | April | 2023 | BU_Subcon_PR
89 | 2023-05-01 |  | BU22-062 | URC RANGE 4 SRGC MACHINE GUN POSITIONS | 5772162 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45466 | 2023-05-01 | 2023-05-03 | [22 empty] | BU | Sub table | May | 2023 | BU_Subcon_PR
90 | 2023-05-02 |  | BU23-030 | INSTALL SIDING TO RVTT SHELTER AREA | 5766601 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45382 | 2023-05-02 | 2023-05-03 | [22 empty] | BU | Sub table | May | 2023 | BU_Subcon_PR
91 | 2023-05-02 |  | BU23-032 | ARTC BLDG 605 PARKING COVER SIDING | 5768075 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45384 | 2023-05-02 | 2023-05-03 | [22 empty] | BU | Sub table | May | 2023 | BU_Subcon_PR
92 | 2023-05-02 |  | BU23-029 | PRIVACY FENCING FOR ARTC TRAINING AREA | 5767438 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45385 | 2023-05-02 | 2023-05-03 | [22 empty] | BU | Sub table | May | 2023 | BU_Subcon_PR
95 | 2023-05-11 |  | BU23-0102 | Provide Generator at IPBC Range at Camp Buehring |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 45958 | 2023-05-11 | 2023-05-13 | [22 empty] | BU | Sub table | May | 2023 | BU_Subcon_PR
98 | 2023-05-16 |  | BU23-0166 | ECP BIRD NETTING Z2, CAMP BUEHRING |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | PWD PROJECT-PWO-BU23-0166-3136 | 2023-05-16 | [22 empty] | Send ODC | BU | Sub table | May | 2023 | BU_Subcon_PR
99 | 2023-05-16 |  | BU23-0143 | K-CROSSING MOTORIZED GATE REPAIR |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | PWD PROJECT-PWO-BU23-0143-3136.1 | 2023-05-16 | [22 empty] | Send ODC | BU | Sub table | May | 2023 | BU_Subcon_PR
101 | 2023-05-20 |  | BU22-0066 |  |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 46251 | 2023-05-20 | [23 empty] | BU | Sub table | May | 2023 | BU_Subcon_PR
107 | 2023-05-23 |  | BU23-0111 | Remediation of flooding in the ARTC |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | PWD-PROJECT-PWO-BU23-0111-3143 | 2023-05-23 | [22 empty] | Send DPW 23 May 23 | BU | Sub table | May | 2023 | BU_Subcon_PR
110 | 2023-05-24 |  | BU23-0094 | Lockers and Sunshades at Camp Buehring |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | PWD-PROJECT-PWO-BU23-0094-3144.3 | 2023-05-24 | [22 empty] | Pending NTP | BU | Sub table | May | 2023 | BU_Subcon_PR
111 | 2023-05-24 |  | BU22-0055 | Range 6 MRF Tower Temperature Control Modification, Camp Buehring |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 48419 | 2023-05-24 | 2023-07-18 | [22 empty] | BU | Sub table | May | 2023 | BU_Subcon_PR
113 | 2023-06-03 |  | BU23-0077 | SHOOT HOUSE LEAD REMEDIATION |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 48233 | 2023-06-03 | 2023-07-12 | [22 empty] | BU | Sub table | June | 2023 | BU_Subcon_PR
116 | 2023-06-15 |  | BU23-0206 | Lease Generators for Weather Shelters A and B on ULZ, | 5616366 | SUBCON PR | LEASE OF GENSET 250KVA, 60 HZ WITH FUEL TANK AND CONTAINMENT TRAY INCLUDING INSTALLATION AND PERIODIC MAINTENANCE (POP 06 MONTHS) | 47347 | 2023-06-15 | 2023-06-19 | [22 empty] | BU | Sub table | June | 2023 | BU_Subcon_PR
117 | 2023-06-19 |  | BU22-0109 | Install Personnel Gate with Cipher lock into EOD Fence, |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 47378 | 2023-06-19 | 2023-06-21 | [22 empty] | BU | Sub table | June | 2023 | BU_Subcon_PR
118 | 2023-06-22 |  | BU23-0175 | REPLACE DAMAGED ROOF PANELS |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 47967 | 2023-06-22 | 2023-07-05 | [22 empty] | BU | Sub table | June | 2023 | BU_Subcon_PR
119 | 2023-06-24 |  | BU23-0166 | INSTALL BIRD NETTING IN ECP1 | 5286014 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 47968 | 2023-06-24 | 2023-07-05 | [22 empty] | BU | Sub table | June | 2023 | BU_Subcon_PR
121 | 2023-07-15 |  | BU23-0094 | LOCKERS AND SUNSHADE, |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | IFS PR 48687 | 2023-07-15 | 2023-08-01 | [22 empty] | BU | Sub table | July | 2023 | BU_Subcon_PR
122 | 2023-07-26 |  | BU23-0143 | MOTORIZED GATE REPAIR | 6767855 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 48927 | 2023-07-26 | 2023-07-31 | [22 empty] | BU | Sub table | July | 2023 | BU_Subcon_PR
123 | 2023-07-26 |  | BU23-0182 | GENERATORS WEATHER SHELTERS A AND B | 6871999 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 48926 | 2023-07-26 | 2023-07-31 | [22 empty] | BU | Sub table | July | 2023 | BU_Subcon_PR
124 | 2023-08-07 |  | BU23-0123 | Replace Manual Transfer Switch (MTS) for Substation | 6903875 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 49403 | 2023-08-07 | 2023-08-15 | [22 empty] | BU | Sub table | August | 2023 | BU_Subcon_PR
133 | 2023-09-11 |  | BU23-0029 | CO-01 Privacy Fencing for ARTC Training Area |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 50292 | 2023-09-11 | 2023-09-11 | [22 empty] | BU | Sub table | September | 2023 | BU_Subcon_PR
142 | 2023-09-26 |  | BU23-0232 | RUHQ Electrical Connection to SS-3 | 6328865 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51208 | 2023-09-26 | 2023-10-10 | [22 empty] | BU | Sub table | September | 2023 | BU_Subcon_PR
148 | 2023-10-03 |  | BU22-0031 | PAD 16 Power and MTS |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51357 | 2023-10-03 | 2023-10-10 | [22 empty] | BU | Sub table | October | 2023 | BU_Subcon_PR
149 | 2023-10-03 |  | BU23-0192 | Stair Access for Drone Defense Zone5 Tower13 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51574 | 2023-10-03 | 2023-10-11 | [22 empty] | BU | Sub table | October | 2023 | BU_Subcon_PR
150 | 2023-10-04 |  | BU23-0306 | Install Fire System Z4 TT4053 | 6589884 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51492 | 2023-10-04 | 2023-10-08 | [22 empty] | BU | Sub table | October | 2023 | BU_Subcon_PR
151 | 2023-10-09 |  | BU22-0045 | Car Ports |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51502 | 2023-10-09 | 2023-10-09 | [22 empty] | BU | Sub table | October | 2023 | BU_Subcon_PR
153 | 2023-10-11 |  | BU23-0372 | PROVIDE LEASED GENERATOR TO RUHQ | 7382193 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52529 | 2023-10-11 | 2023-11-06 | [22 empty] | BU | Sub table | October | 2023 | BU_Subcon_PR
155 | 2023-10-14 |  | BU23-0262 | NSTALLATION OF NEW ATS IN FS BLDG. 103 , C | 6231156 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51923 | 2023-10-14 | 2023-10-19 | [22 empty] | BU | Sub table | October | 2023 | BU_Subcon_PR
156 | 2023-10-14 |  | BU23-0281 | CAB HQ Emergency Power Generator, | 6408129 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51922 | 2023-10-14 | 2023-10-19 | [22 empty] | BU | Sub table | October | 2023 | BU_Subcon_PR
158 | 2023-10-14 |  | BU23-0183 | Asphalt Binder Capa Pads | 7874910 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51924 | 2023-10-14 | 2023-10-19 | [22 empty] | BU | Sub table | October | 2023 | BU_Subcon_PR
160 | 2023-10-16 |  | BU22-0105 | GRIT Building Utilization Project, |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 51891 | 2023-10-16 | 2023-10-19 | [22 empty] | BU | Sub table | October | 2023 | BU_Subcon_PR
166 | 2023-10-17 |  | BU23-0351 | Secondary Fence Installation Zone 6, | 7221399 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52063 | 2023-10-17 | 2023-10-21 | [22 empty] | BU | Sub table | October | 2023 | BU_Subcon_PR
168 | 2023-10-19 |  | BU23-0233 | ULZ Install Grounding Points at Aircraft Parking Pads, | 5876978 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52161 | 2023-10-19 | 2023-10-24 | [22 empty] | BU | Sub table | October | 2023 | BU_Subcon_PR
181 | 2023-10-25 |  | BU22-048 | CO#1 DENTAL CLINIC UPGRADES CAMP BUEHRING, KUWAIT | 4369536 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52247 | 2023-10-25 | 2023-10-26 | [22 empty] | BU | Sub table | October | 2023 | BU_Subcon_PR
184 | 2023-10-31 |  | BU23-0279 | BU23-0279 RUHQ Emergency Power Generation Installation, Camp Buehring $64,633.00 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52497 | 2023-10-31 | 2023-11-04 | [22 empty] | BU | Sub table | October | 2023 | BU_Subcon_PR
186 | 2023-11-05 |  | BU23-0350 | REPLACE DOORS Z6 B6016 | 7221392 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52750 | 2023-11-05 | 2023-11-15 | [22 empty] | BU | Sub table | November | 2023 | BU_Subcon_PR
187 | 2023-11-05 |  | BU23-0353 | 0353 Install Privacy Netting Z6 B6016 | 7221404 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52692 | 2023-11-05 | 2023-11-09 | [22 empty] | BU | Sub table | November | 2023 | BU_Subcon_PR
192 | 2023-11-08 |  | BU23-0124 | Engineer Village Power Consolidation | 5375966 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 53084 | 2023-11-08 | 2023-11-23 | [22 empty] | BU | Sub table | November | 2023 | BU_Subcon_PR
193 | 2023-11-08 |  | BU23-0353 | B6016 & B2017 PERIMETER FENCE PRIVACY NETTING | 8236743 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 52692 | 2023-11-08 | 2023-11-09 | [22 empty] | BU | Sub table | November | 2023 | BU_Subcon_PR
199 | 2023-12-02 |  | BU23-0193 | Build out Zone 2 TT 2071 into office space | 6871039 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 53561 | 2023-12-02 | 2023-12-06 | [18 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023 | BU_Subcon_PR
200 | 2023-12-04 |  | BU23-249 | DENTAL CLINIC CABINETS AND COUNTERTOP ZONE 2, | 8528611 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54008 | 2023-12-04 | 2023-12-17 |  | 1 | LT | 1 | 35000 | 35000 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023 | BU_Subcon_PR
201 | 2023-12-06 |  | BU23-0264 | Install Manual Transfer Switch Z2 TP2 | 8449225 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54017 | 2023-12-06 | 2023-12-17 |  | 1 | LT | 1 | 15000 | 15000 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023 | BU_Subcon_PR
208 | 2023-12-10 |  | BU23-0205 | Connect Sanitary Water Lines Z5 RUHQ B5999 | 8689493 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54014 | 2023-12-10 | 2023-12-24 |  | 1 | LT | 1 | 53314 | 53314 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023 | BU_Subcon_PR
213 | 2023-12-11 |  | BU23-0314 | Replacement of Water Filling Railing Zone 3, | 6665414 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54030 | 2023-12-11 | 2023-12-17 |  | 1 | LT | 1 | 27435 | 27435 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023 | BU_Subcon_PR
214 | 2023-12-17 |  | BU23-0375 | Deconstruct Facility Z6 TT7-3 TT7-9 | 8781713 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54377 | 2023-12-17 | 2023-12-28 |  | 1 | LT | 1 | 5688 | 5688 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023 | BU_Subcon_PR
222 | 2023-12-20 |  | BU23-0160 | Replace Manual Transfer Switch | 5203390 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54494 | 2023-12-19 | 2023-01-04 | COMP | 1 | LT | 1 | 75600 | 75600 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023 | BU_Subcon_PR
224 | 2023-12-19 |  | BU23-0208 | B6015 Relocation | 5616330 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54291 | 2023-12-19 | 2023-12-27 | COMP | 1 | LT | 1 | 47800 | 47800 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023 | BU_Subcon_PR
233 | 2023-12-27 |  | BU23-0357 | TT1051 Deconstruction Tent | 7249582 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54611 | 2023-12-27 | 2024-01-07 | COMP | 1 | LT | 1 | 9000 | 9000 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023 | BU_Subcon_PR
236 | 2023-12-31 |  | BU23-0373 | Deconstruct Z8 T2032 | 8948486 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54612 | 2023-01-06 | 2024-01-07 | COMP | 1 | LT | 1 | 6240 | 6240 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023 | BU_Subcon_PR
237 | 2023-12-31 |  | BU23-0338 | Emplace Furniture Z5 B5999 | 8944194 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 54725 | 2023-01-06 | 2024-01-11 | COMP | 1 | LT | 1 | 80500 | 80500 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | December | 2023 | BU_Subcon_PR
238 | 2024-01-28 |  | BU23-0368 | Connect Cable from Hangar 9 (TT9600) at ESS-14 | 7335344 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55549 | 2024-01-31 | 2024-01-31 | COMP | 1 | LT | 1 | 16150 | 16150 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | January | 2024 | BU_Subcon_PR
239 | 2024-02-07 |  | BU23-0275 | TT403 Sunshade Replacement Phase 1 | 6874479 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 55968 | 2024-02-07 | 2024-02-10 | COMP | 1 | LT | 1 | 87500 | 87500 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | February | 2024 | BU_Subcon_PR
240 | 2024-02-21 |  | BU23-0221 | Install Electrical Outlets FP-C to TDP | 9805359 | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 56589 | 2024-02-21 | 2024-02-28 | COMP | 1 | LT | 1 | 59530 | 59530 | [12 empty] | COMP |  |  | IFS PR COMPLETED | BU | Sub table | February | 2024 | BU_Subcon_PR
241 | 2024-03-03 |  | BU24-0060 | Install Fencing Gates Z3 TT307 |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 57046 | 2024-03-04 | 2024-03-09 | COMP | 1 | LT | 1 | 1 4,725.00 | [13 empty] | COMP |  |  |  | BU | Sub table | March | 2024 | BU_Subcon_PR
242 | 2024-03-02 |  | BU20-0026A | Automated Record Fire (ARF) Sunshade Range 4, Camp Buehring |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 57043 | 2024-03-05 | 2024-03-09 |  | 1 | LT | 1 | 101400 | [13 empty] | COMP |  |  |  | BU | Sub table | March | 2024 | BU_Subcon_PR
243 | 2024-03-02 |  | BU20-0026B | SRGC Sunshade Construction Range 4, Camp Buehring, Kuwait |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 57044 | 2024-03-05 | 2024-03-09 |  | 1 | LT | 1 | 154764 | [13 empty] | COMP |  |  |  | BU | Sub table | March | 2024 | BU_Subcon_PR
244 | 2024-03-05 |  | BU24-0012 | Fix Def Solar Lights |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | 57053 | 2024-03-05 |  |  | 1 | LT | 1 | 41500 | [13 empty] | comp |  |  |  | BU | Sub table | March | 2024 | BU_Subcon_PR
245 | 2024-03-09 |  | BU24-0006 | Connect HAZMAT and Pest Control Facilities to ESS-14 CAMP Buehring, Kuwait |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | PRINPRG |  |  |  | 1 | LT | 1 | 102000 | [17 empty] | BU | Sub table | March | 2024 | BU_Subcon_PR
246 | 2024-03-09 |  | BU23-0379 | Correct TI Deficiencies for ESS 14TO18 Zone -1,2 Camp Buehring |  | SUBCON PR | COST OF LABOR, MATERIALS AND EQUIPMENT | PRINPRG |  |  |  | 1 | LT | 1 | 32700 | [17 empty] | BU | Sub table | March | 2024 | BU_Subcon_PR
247 | [33 empty] | FALSE | January | 1900 | BU_Subcon_PR
248 | [33 empty] | FALSE | January | 1900 | BU_Subcon_PR
249 | [33 empty] | FALSE | January | 1900 | BU_Subcon_PR
250 | [33 empty] | FALSE | January | 1900 | BU_Subcon_PR
251 | [33 empty] | FALSE | January | 1900 | BU_Subcon_PR
252 | [33 empty] | FALSE | January | 1900 | BU_Subcon_PR